## Tasks
Task List | Task Name | Owner Type | Owner Name | Target Date | Days Overdue | Completed Date | NA | Protocol No | Institution
CTSU Pre-Award - 336-KHANNA | Feasibility w/Documents received | Role | CTSU Administrator | 2016-07-07 | 0 | 2016-07-07 | N | 00133684
Pre-Award Financial - 00123861 | Intake Form Completed | Role | CTSU Coordinator | 2017-01-17 | 0 | 2017-01-17 | N | 00123861
Pre-Award Financial - SLS-III | Intake Form Completed | Role | CTSU Coordinator | 2017-01-20 | 0 | 2017-01-20 | N | 00131953
Pre-Award Financial - SLS-III | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-01-22 | 0 | 2017-01-22 | N | 00131953
Pre-Award Financial - 00124920 | IRB Application Submitted | Role | CTSU Coordinator | 2017-01-23 | 0 | 2017-01-23 | N | 00124920
Pre-Award Financial - 305-PELOSI | UFA Completed | Role | CTSU Finance | 2017-01-23 | 0 | 2017-01-23 | N | 305-PELOSI
Pre-Award Financial - PLT-INF24-001 | Intake Form Completed | Role | CTSU Coordinator | 2017-01-24 | 0 | 2017-01-24 | N | 00135388
Pre-Award Financial - SLS-III | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-01-24 | 2 | 2017-01-26 | N | 00131953
Pre-Award Financial - 00125425 | IRB Application Submitted | Role | CTSU Coordinator | 2017-01-25 | 0 | 2017-01-25 | N | 00125425
Calendaring : Initial Calendar Build - SLS-III | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-01-27 | 138 | 2017-06-14 | N | 00131953
Calendaring : Initial Calendar Build - 00126707 | Feasibility Approval Notice Received |  |  | 2017-01-27 | 25 | 2017-02-21 | N | 00126707
Calendaring : Initial Calendar Build - SLS-III | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-01-29 | 143 | 2017-06-21 | N | 00131953
Calendaring : Initial Calendar Build - SLS-III | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-01-29 | 143 | 2017-06-21 | N | 00131953
Pre-Award Financial - 2-MARSH | Intake Form Completed | Role | CTSU Coordinator | 2017-01-30 | 0 | 2017-01-30 | N | 2-MARSH
Pre-Award Financial - MENEES-1 | Intake Form Completed | Role | CTSU Coordinator | 2017-01-30 | 0 | 2017-01-30 | N | MENEES-1
Pre-Award Financial - 2-MARSH | Feasibility w/Documents received | Role | CTSU Administrator | 2017-01-31 | 212 |  | N | 2-MARSH
Pre-Award Financial - 2-MARSH | Sponsor Reach out | Role | CTSU Coordinator | 2017-01-31 | 212 |  | N | 2-MARSH
Pre-Award Financial - PLT-INF24-001 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-02-01 | 0 | 2017-02-01 | N | 00135388
Pre-Award Financial - 00125786 | Intake Form Completed | Role | CTSU Coordinator | 2017-02-01 | 0 | 2017-02-01 | N | 00125786
Pre-Award Financial - SLS-III | Billing Calendar Received | Role | CTSU Finance | 2017-02-01 | 22 | 2017-02-23 | N | 00131953
Pre-Award Financial - 00124712 | Intake Form Completed | Role | CTSU Coordinator | 2017-02-02 | 0 | 2017-02-02 | N | 00124712
Pre-Award Financial - 00124920 | Intake Form Completed | Role | CTSU Coordinator | 2017-02-02 | 0 | 2017-02-02 | N | 00124920
Pre-Award Financial - 00127537 | Intake Form Completed | Role | CTSU Coordinator | 2017-02-03 | 0 | 2017-02-03 | N | 00127537
Pre-Award Financial - 10-JAYASUNDERA | Intake Form Completed | Role | CTSU Coordinator | 2017-02-03 | 0 | 2017-02-03 | N | 10-JAYASUNDERA
Pre-Award Financial - 11-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-02-03 | 0 | 2017-02-03 | N | 00134884
Pre-Award Financial - 12-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-02-03 | 0 | 2017-02-03 | N | 12-HIGGINS
Pre-Award Financial - 9-JAYASUNDERA | Intake Form Completed | Role | CTSU Coordinator | 2017-02-03 | 0 | 2017-02-03 | N | 9-JAYASUNDERA
Pre-Award Financial - PLT-INF24-001 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-02-03 | 4 | 2017-02-07 | N | 00135388
Pre-Award Financial - PLT-INF24-001 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-02-03 | 7 | 2017-02-10 | N | 00135388
Calendaring : Initial Calendar Build - SLS-III | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-02-05 | 134 | 2017-06-19 | N | 00131953
Pre-Award Financial - SLS-III | Planning Meeting Completed | Role | CTSU Finance | 2017-02-05 | 1 | 2017-02-06 | N | 00131953
Calendaring : Initial Calendar Build - SLS-III | Feasibility Approval Notice Received | Role | CRAO | 2017-02-06 | 0 | 2017-02-06 | N | 00131953
Pre-Award Financial - 00128531 | Intake Form Completed | Role | CTSU Coordinator | 2017-02-06 | 0 | 2017-02-03 | N | 00128531
Pre-Award Financial - 222-STEIGERWALT | UFA Completed | Role | CTSU Finance | 2017-02-06 | 0 | 2017-02-06 | N | 227-STEIGERWALT
Calendaring : Initial Calendar Build - SLS-III | Complete SVS & Pricing List ( Built & Coded ) | User | LaVasseur, Kristen | 2017-02-06 | 0 | 2017-02-06 | N | 00131953
Calendaring : Initial Calendar Build - SLS-III | Assign to Analyst | User | van Dijk, Tim | 2017-02-06 | 128 | 2017-06-14 | N | 00131953
Pre-Award Financial - 00123861 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-02-07 | 0 | 2017-01-19 | N | 00123861
Pre-Award Financial - 00124920 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-02-07 | 0 | 2017-02-07 | N | 00124920
Pre-Award Financial - 00125786 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-02-07 | 0 | 2017-02-07 | N | 00125786
Pre-Award Financial - 2-MARSH | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-02-07 | 205 |  | N | 2-MARSH
Pre-Award Financial - 00125425 | Intake Form Completed | Role | CTSU Coordinator | 2017-02-07 | 0 | 2017-02-07 | N | 00125425
Calendaring : Initial Calendar Build - SLS-III | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-02-07 | 150 | 2017-07-07 | N | 00131953
Calendaring : Initial Calendar Build - SLS-III | Make Updates | User | van Dijk, Tim | 2017-02-07 | 143 | 2017-06-30 | N | 00131953
Pre-Award Financial - 00125566 | Intake Form Completed | Role | CTSU Coordinator | 2017-02-08 | 0 | 2017-02-08 | N | 00125566
Pre-Award Financial - 00127136 | Intake Form Completed | Role | CTSU Coordinator | 2017-02-08 | 0 | 2017-02-08 | N | 00127136
Pre-Award Financial - SLS-III | Care Designations completed | User | Oliver, Amy | 2017-02-08 | 142 | 2017-06-30 | N | 00131953
Pre-Award Financial - 00128531 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-02-09 | 0 | 2017-02-09 | N | 00128531
Pre-Award Financial - 00124920 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-02-09 | 4 | 2017-02-13 | N | 00124920
Pre-Award Financial - 00125794 | Intake Form Completed | Role | CTSU Coordinator | 2017-02-09 | 0 | 2017-02-09 | N | 00125794
Pre-Award Financial - 00126215 | Intake Form Completed | Role | CTSU Coordinator | 2017-02-09 | 0 | 2017-02-09 | N | 00126215
Pre-Award Financial - 2-MARSH | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-02-09 | 203 |  | N | 2-MARSH
Pre-Award Financial - 00124920 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-02-09 | 1 | 2017-02-10 | N | 00124920
Pre-Award Financial - 00125786 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-02-09 | 0 | 2017-01-30 | N | 00125786
Pre-Award Financial - 2-MARSH | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-02-09 | 203 |  | N | 2-MARSH
Pre-Award Financial - 2-MARSH | Request MCRU Budget | Role | CTSU Finance | 2017-02-09 | 203 |  | N | 2-MARSH
Pre-Award Financial - 2-MARSH | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-02-09 | 203 |  | N | 2-MARSH
Calendaring : Initial Calendar Build - SLS-III | Acknowledge | User | Oliver, Amy | 2017-02-09 | 148 | 2017-07-07 | N | 00131953
BC : Initial Build - PLT-INF24-001 | Feasibility Approval Notice Received | Role | CRAO | 2017-02-10 | 0 | 2017-02-10 | N | 00135388
Calendaring : Initial Calendar Build - SLS-III | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO | 2017-02-10 | 0 | 2017-02-10 | N | 00131953
Pre-Award Financial - SLS-III | Feasibility w/Documents received | Role | CTSU Administrator | 2017-02-10 | 0 | 2017-01-22 | N | 00131953
Pre-Award Financial - 00125566 | IRB Application Submitted | Role | CTSU Coordinator | 2017-02-10 | 0 | 2017-02-10 | N | 00125566
Pre-Award Financial - 23-GUPTA | Intake Form Completed | Role | CTSU Coordinator | 2017-02-10 | 0 | 2017-02-10 | N | 00134236
Pre-Award Financial - SLS-III | Sponsor Reach out | Role | CTSU Coordinator | 2017-02-10 | 0 | 2017-01-22 | N | 00131953
Pre-Award Financial - SLS-III | UFA Completed | Role | CTSU Coordinator | 2017-02-10 | 34 | 2017-03-16 | N | 00131953
Pre-Award Financial - 00128531 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-02-11 | 34 | 2017-03-17 | N | 00128531
Pre-Award Financial - 00128531 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-02-11 | 25 | 2017-03-08 | N | 00128531
Pre-Award Financial - PLT-INF24-001 | Billing Calendar Received | Role | CTSU Finance | 2017-02-11 | 100 | 2017-05-22 | N | 00135388
BC : Initial Build - PLT-INF24-001 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO | 2017-02-12 | 0 | 2017-02-10 | N | 00135388
Pre-Award Financial - SLS-III | Internal Budget Finished | Role | CTSU Finance | 2017-02-12 | 36 | 2017-03-20 | N | 00131953
Pre-Award Financial - 00125786 | IRB Application Submitted | Role | CTSU Coordinator | 2017-02-13 | 0 | 2017-02-13 | N | 00125786
Pre-Award Financial - 00118070 | Intake Form Completed | Role | CTSU Finance | 2017-02-13 | 0 | 2017-02-13 | N | 00118070
Pre-Award Financial - 00123861 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-02-14 | 0 | 2017-01-19 | N | 00123861
Pre-Award Financial - 00125425 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-02-14 | 0 | 2017-02-14 | N | 00125425
Pre-Award Financial - 00127136 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-02-14 | 0 | 2017-02-14 | N | 00127136
Pre-Award Financial - PLT-INF24-001 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-02-14 | 0 | 2017-02-01 | N | 00135388
Pre-Award Financial - 00129851 | Intake Form Completed | Role | CTSU Coordinator | 2017-02-14 | 0 | 2017-02-14 | N | 00129851
Pre-Award Financial - 30-FLAHERTY | Intake Form Completed | Role | CTSU Coordinator | 2017-02-14 | 0 | 2017-02-14 | N | 30-FLAHERTY
BC : Initial Build - PLT-INF24-001 | Nimblify Build is Complete & Ready for Import | Role | CRAO | 2017-02-15 | 5 | 2017-02-20 | N | 00135388
Pre-Award Financial - PLT-INF24-001 | Planning Meeting Completed | Role | CTSU Finance | 2017-02-15 | 8 | 2017-02-23 | N | 00135388
Pre-Award Financial - SLS-III | PI approved Budget | Role | CTSU Finance | 2017-02-15 | 33 | 2017-03-20 | N | 00131953
Pre-Award Financial - 00123861 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-02-16 | 0 | 2017-01-26 | N | 00123861
Pre-Award Financial - 00125425 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-02-16 | 5 | 2017-02-21 | N | 00125425
Pre-Award Financial - 00127136 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-02-16 | 5 | 2017-02-21 | N | 00127136
Pre-Award Financial - 00123861 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-02-16 | 0 | 2017-01-27 | N | 00123861
Pre-Award Financial - 00125425 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-02-16 | 0 | 2017-01-24 | N | 00125425
Pre-Award Financial - 00127136 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-02-16 | 5 | 2017-02-21 | N | 00127136
BC : Initial Build - PLT-INF24-001 | Attach Build Notes ( as Protocol Doc ) | Role | CRAO | 2017-02-17 | 6 | 2017-02-23 | N | 00135388
Pre-Award Financial - 33-FLAHERTY | Intake Form Completed | Role | CTSU Coordinator | 2017-02-17 | 0 | 2017-02-17 | N | 00129716
Pre-Award Financial - 34-MARSH | Intake Form Completed | Role | CTSU Coordinator | 2017-02-17 | 0 | 2017-02-17 | N | 34-MARSH
Pre-Award Financial - 00124920 | Billing Calendar Received | Role | CTSU Finance | 2017-02-17 | 26 | 2017-03-15 | N | 00124920
Pre-Award Financial - 00125786 | Billing Calendar Received | Role | CTSU Finance | 2017-02-17 | 26 | 2017-03-15 | N | 00125786
Pre-Award Financial - 2-MARSH | Billing Calendar Received | Role | CTSU Finance | 2017-02-17 | 195 |  | N | 2-MARSH
Pre-Award Financial - SLS-III | Budget Negotiations | Role | CTSU Finance | 2017-02-17 | 37 | 2017-03-26 | N | 00131953
BC : Initial Build - PLT-INF24-001 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | LaVasseur, Kristen | 2017-02-17 | 6 | 2017-02-23 | N | 00135388
Pre-Award Financial - PLT-INF24-001 | Care Designations completed | Role | CTSU Finance | 2017-02-18 | 0 | 2017-02-01 | N | 00135388
Pre-Award Financial - 00128531 | Billing Calendar Received | Role | CTSU Finance | 2017-02-19 | 37 | 2017-03-28 | N | 00128531
Pre-Award Financial - MENEES-1 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-02-20 | 192 |  | N | MENEES-1
Pre-Award Financial - 2-MARSH | UFA Completed | Role | CTSU Coordinator | 2017-02-20 | 0 | 2017-01-30 | N | 2-MARSH
Pre-Award Financial - MENEES-1 | Sponsor Reach out | Role | CTSU Coordinator | 2017-02-20 | 192 |  | N | MENEES-1
Pre-Award Financial - MENEES-1 | UFA Completed | Role | CTSU Coordinator | 2017-02-20 | 192 |  | N | MENEES-1
Pre-Award Financial - 00125022 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-02-21 | 0 | 2017-02-21 | N | 00125022
Pre-Award Financial - 00125022 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-02-21 | 0 | 2017-02-21 | N | 00125022
Pre-Award Financial - 00130793 | Intake Form Completed | Role | CTSU Coordinator | 2017-02-21 | 0 | 2017-02-21 | N | 00130793
Pre-Award Financial - 00124920 | Planning Meeting Completed | Role | CTSU Finance | 2017-02-21 | 0 | 2017-02-14 | N | 00124920
Pre-Award Financial - 2-MARSH | Planning Meeting Completed | Role | CTSU Finance | 2017-02-21 | 191 |  | N | 2-MARSH
Pre-Award Financial - 00125786 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-02-22 | 0 | 2017-02-03 | N | 00125786
Pre-Award Financial - PLT-INF24-001 | Internal Budget Finished | Role | CTSU Finance | 2017-02-22 | 61 | 2017-04-24 | N | 00135388
Calendaring : Initial Calendar Build - 00126707 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO | 2017-02-23 | 0 | 2017-02-23 | N | 00126707
Pre-Award Financial - 00124712 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-02-23 | 0 | 2017-02-06 | N | 00124712
Pre-Award Financial - 00124920 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-02-23 | 0 | 2017-02-07 | N | 00124920
Pre-Award Financial - 00125566 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-02-23 | 0 | 2017-02-23 | N | 00125566
Pre-Award Financial - 00125794 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-02-23 | 0 | 2017-02-23 | N | 00125794
Pre-Award Financial - 00127537 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-02-23 | 0 | 2017-02-23 | N | 00127537
CTSU Pre-Award v2 - 37-SILVER | Intake Form Completed | Role | CTSU Coordinator | 2017-02-23 | 0 | 2017-02-23 | N | 37-SILVER
Pre-Award Financial - 00122254 | Intake Form Completed | Role | CTSU Coordinator | 2017-02-23 | 0 | 2017-02-23 | N | 00122254
Pre-Award Financial - 00125022 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-02-23 | 8 | 2017-03-03 | N | 00125022
Pre-Award Financial - 00125022 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-02-23 | 0 | 2017-02-23 | N | 00125022
Pre-Award Financial - 00128531 | Planning Meeting Completed | Role | CTSU Finance | 2017-02-23 | 39 | 2017-04-03 | N | 00128531
Pre-Award Financial - 241-SILVER | Intake Form Completed | Role | CTSU Finance | 2017-02-23 | 0 | 2017-02-23 | N | 00132956
Pre-Award Financial - 00127537 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-02-24 | 0 | 2017-02-23 | N | 00127537
Pre-Award Financial - 10-JAYASUNDERA | Feasibility w/Documents received | Role | CTSU Administrator | 2017-02-24 | 188 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 11-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-02-24 | 174 | 2017-08-17 | N | 00134884
Pre-Award Financial - 12-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-02-24 | 188 |  | N | 12-HIGGINS
Pre-Award Financial - 9-JAYASUNDERA | Feasibility w/Documents received | Role | CTSU Administrator | 2017-02-24 | 188 |  | N | 9-JAYASUNDERA
Pre-Award Financial - 00127505 | Intake Form Completed | Role | CTSU Coordinator | 2017-02-24 | 0 | 2017-02-24 | N | 00127505
Pre-Award Financial - 10-JAYASUNDERA | Sponsor Reach out | Role | CTSU Coordinator | 2017-02-24 | 188 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 11-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator | 2017-02-24 | 0 | 2017-02-07 | N | 00134884
Pre-Award Financial - 11-HIGGINS | UFA Completed | Role | CTSU Coordinator | 2017-02-24 | 60 | 2017-04-25 | N | 00134884
Pre-Award Financial - 12-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator | 2017-02-24 | 0 | 2017-02-07 | N | 12-HIGGINS
Pre-Award Financial - 12-HIGGINS | UFA Completed | Role | CTSU Coordinator | 2017-02-24 | 0 | 2017-02-03 | N | 12-HIGGINS
Pre-Award Financial - 9-JAYASUNDERA | Sponsor Reach out | Role | CTSU Coordinator | 2017-02-24 | 31 | 2017-03-27 | N | 9-JAYASUNDERA
Pre-Award Financial - 9-JAYASUNDERA | UFA Completed | Role | CTSU Coordinator | 2017-02-24 | 0 | 2017-01-20 | N | 9-JAYASUNDERA
Pre-Award Financial - 00123861 | Billing Calendar Received | Role | CTSU Finance | 2017-02-24 | 0 | 2017-02-23 | N | 00123861
Pre-Award Financial - 00124920 | Care Designations completed | Role | CTSU Finance | 2017-02-24 | 0 | 2017-02-01 | N | 00124920
Pre-Award Financial - 00125425 | Billing Calendar Received | Role | CTSU Finance | 2017-02-24 | 19 | 2017-03-15 | N | 00125425
Pre-Award Financial - 00125786 | Care Designations completed | Role | CTSU Finance | 2017-02-24 | 0 | 2017-02-01 | N | 00125786
Pre-Award Financial - 2-MARSH | Care Designations completed | Role | CTSU Finance | 2017-02-24 | 188 |  | N | 2-MARSH
Pre-Award Financial - 00125794 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-02-25 | 5 | 2017-03-02 | N | 00125794
Pre-Award Financial - 00127537 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-02-25 | 4 | 2017-03-01 | N | 00127537
Pre-Award Financial - 00125566 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-02-25 | 0 | 2016-12-19 | N | 00125566
Pre-Award Financial - 00125794 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-02-25 | 0 | 2017-01-26 | N | 00125794
Pre-Award Financial - 00127537 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-02-25 | 0 | 2017-02-23 | N | 00127537
Pre-Award Financial - PLT-INF24-001 | PI approved Budget | Role | CTSU Finance | 2017-02-25 | 81 | 2017-05-17 | N | 00135388
Calendaring : Initial Calendar Build - 00126707 | Nimblify Build is Complete & Ready for Import | Role | CRAO | 2017-02-26 | 1 | 2017-02-27 | N | 00126707
Pre-Award Financial - 12-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-02-26 | 186 |  | N | 12-HIGGINS
Calendaring : Initial Calendar Build - 00126707 | Complete SVS & Pricing List ( Built & Coded ) | User | LaVasseur, Kristen | 2017-02-26 | 68 | 2017-05-05 | N | 00126707
Pre-Award Financial - 00128531 | Care Designations completed | User | Oliver, Amy | 2017-02-26 | 95 | 2017-06-01 | N | 00128531
Pre-Award Financial - 00128531 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-02-27 | 0 | 2017-02-08 | N | 00128531
Pre-Award Financial - MENEES-1 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-02-27 | 185 |  | N | MENEES-1
Calendaring : Initial Calendar Build - 00123069 | Nimblify Build is Complete & Ready for Import | User | Greene, Paula | 2017-02-27 | 0 | 2017-02-27 | N | 00123069
Pre-Award Financial - PLT-INF24-001 | Budget Negotiations | User | Oliver, Amy | 2017-02-27 | 80 | 2017-05-18 | N | 00135388
Pre-Award Financial - 00125425 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-02-28 | 0 | 2017-02-14 | N | 00125425
Open to Accrual - 00125425 | IRB Approval | Role | CTSU Coordinator | 2017-02-28 | 0 | 2017-02-28 | N | 00125425
Pre-Award Financial - 12-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-02-28 | 184 |  | N | 12-HIGGINS
Pre-Award Financial - 44-MCUNE | Intake Form Completed | Role | CTSU Coordinator | 2017-02-28 | 0 | 2017-02-28 | N | 44-MCUNE
Pre-Award Financial - FONTANA-1 | Intake Form Completed | Role | CTSU Coordinator | 2017-02-28 | 0 | 2017-02-28 | N | 00133153
Pre-Award Financial - 00123861 | Planning Meeting Completed | Role | CTSU Finance | 2017-02-28 | 0 | 2017-02-23 | N | 00123861
Pre-Award Financial - 00124920 | Internal Budget Finished | Role | CTSU Finance | 2017-02-28 | 0 | 2017-02-17 | N | 00124920
Pre-Award Financial - 00125425 | Planning Meeting Completed | Role | CTSU Finance | 2017-02-28 | 8 | 2017-03-08 | N | 00125425
Pre-Award Financial - 00127136 | Planning Meeting Completed | Role | CTSU Finance | 2017-02-28 | 0 | 2017-02-24 | N | 00127136
Pre-Award Financial - 12-HIGGINS | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-02-28 | 184 |  | N | 12-HIGGINS
Pre-Award Financial - 12-HIGGINS | Request MCRU Budget | Role | CTSU Finance | 2017-02-28 | 184 |  | N | 12-HIGGINS
Pre-Award Financial - 2-MARSH | Internal Budget Finished | Role | CTSU Finance | 2017-02-28 | 184 |  | N | 2-MARSH
Calendaring : Initial Calendar Build - 00126707 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | LaVasseur, Kristen | 2017-02-28 | 66 | 2017-05-05 | N | 00126707
Calendaring : Initial Calendar Build - 147 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO | 2017-03-01 | 15 | 2017-03-16 | N | 00128322
Pre-Award Financial - 00125566 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-01 | 0 | 2017-02-23 | N | 00125566
Pre-Award Financial - 00127136 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-01 | 0 | 2017-02-13 | N | 00127136
Pre-Award Financial - FONTANA-3 | Intake Form Completed | Role | CTSU Coordinator | 2017-03-01 | 0 | 2017-03-01 | N | FONTANA-3
Pre-Award Financial - MENEES-1 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-03-01 | 183 |  | N | MENEES-1
Pre-Award Financial - MENEES-1 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-03-01 | 183 |  | N | MENEES-1
Pre-Award Financial - MENEES-1 | Request MCRU Budget | Role | CTSU Finance | 2017-03-01 | 183 |  | N | MENEES-1
Pre-Award Financial - MENEES-1 | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-03-01 | 183 |  | N | MENEES-1
Calendaring : Initial Calendar Build - 00126135 | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-03-01 | 113 | 2017-06-22 | N | 00126135
Pre-Award Financial - 00122254 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-03-02 | 0 | 2017-03-02 | N | 00122254
Pre-Award Financial - 00124712 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-03-02 | 0 | 2017-02-07 | N | 00124712
Pre-Award Financial - 00125794 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-02 | 0 | 2017-02-23 | N | 00125794
Pre-Award Financial - 00126215 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-02 | 0 | 2017-02-22 | N | 00126215
Pre-Award Financial - 00127505 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-03-02 | 0 | 2017-03-02 | N | 00127505
Pre-Award Financial - 00128531 | Internal Budget Finished | Role | CTSU Finance | 2017-03-02 | 30 | 2017-04-01 | N | 00128531
Calendaring : Migration - 00087702 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO | 2017-03-03 | 0 | 2017-03-03 | N | 00087702
Pre-Award Financial - 10-JAYASUNDERA | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-03-03 | 181 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 23-GUPTA | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-03 | 132 | 2017-07-13 | N | 00134236
Pre-Award Financial - 9-JAYASUNDERA | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-03-03 | 181 |  | N | 9-JAYASUNDERA
Pre-Award Financial - SCHIOPU-1 | Intake Form Completed | Role | CTSU Coordinator | 2017-03-03 | 0 | 2017-03-03 | N | SCHIOPU-1
Pre-Award Financial - 00123861 | Care Designations completed | Role | CTSU Finance | 2017-03-03 | 0 | 2017-02-01 | N | 00123861
Pre-Award Financial - 00124920 | PI approved Budget | Role | CTSU Finance | 2017-03-03 | 0 | 2017-02-21 | N | 00124920
Pre-Award Financial - 00125022 | Billing Calendar Received | Role | CTSU Finance | 2017-03-03 | 54 | 2017-04-26 | N | 00125022
Pre-Award Financial - 2-MARSH | PI approved Budget | Role | CTSU Finance | 2017-03-03 | 181 |  | N | 2-MARSH
Pre-Award Financial - SLS-III | Final Budget | Role | CTSU Finance | 2017-03-03 | 45 | 2017-04-17 | N | 00131953
Pre-Award Financial - 00125425 | Care Designations completed | User | VanderElzen, Liz | 2017-03-03 | 12 | 2017-03-15 | N | 00125425
Calendaring : Initial Calendar Build - 00126135 | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-03-03 | 112 | 2017-06-23 | N | 00126135
Calendaring : Initial Calendar Build - 00126135 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-03-03 | 112 | 2017-06-23 | N | 00126135
Pre-Award Financial - 00122254 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-03-04 | 0 | 2017-02-23 | N | 00122254
Pre-Award Financial - 00124712 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-03-04 | 0 | 2017-02-07 | N | 00124712
Pre-Award Financial - 00127505 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-03-04 | 13 | 2017-03-17 | N | 00127505
Pre-Award Financial - 00122254 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-03-04 | 4 | 2017-03-08 | N | 00122254
Pre-Award Financial - 00124712 | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-03-04 | 0 | 2017-02-07 | N | 00124712
Pre-Award Financial - 00127505 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-03-04 | 1 | 2017-03-05 | N | 00127505
Pre-Award Financial - 10-JAYASUNDERA | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-03-05 | 179 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 9-JAYASUNDERA | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-03-05 | 179 |  | N | 9-JAYASUNDERA
Pre-Award Financial - 00124920 | Budget Negotiations | Role | CTSU Finance | 2017-03-05 | 0 | 2017-02-21 | N | 00124920
Pre-Award Financial - 00125794 | Billing Calendar Received | Role | CTSU Finance | 2017-03-05 | 32 | 2017-04-06 | N | 00125794
Pre-Award Financial - 00127537 | Billing Calendar Received | Role | CTSU Finance | 2017-03-05 | 23 | 2017-03-28 | N | 00127537
Pre-Award Financial - 00128531 | PI approved Budget | Role | CTSU Finance | 2017-03-05 | 29 | 2017-04-03 | N | 00128531
Pre-Award Financial - 10-JAYASUNDERA | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-03-05 | 179 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 10-JAYASUNDERA | Request MCRU Budget | Role | CTSU Finance | 2017-03-05 | 179 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 10-JAYASUNDERA | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-03-05 | 179 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 12-HIGGINS | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-03-05 | 179 |  | N | 12-HIGGINS
Pre-Award Financial - 2-MARSH | Budget Negotiations | Role | CTSU Finance | 2017-03-05 | 179 |  | N | 2-MARSH
Pre-Award Financial - 9-JAYASUNDERA | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-03-05 | 179 |  | N | 9-JAYASUNDERA
Pre-Award Financial - 9-JAYASUNDERA | Request MCRU Budget | Role | CTSU Finance | 2017-03-05 | 179 |  | N | 9-JAYASUNDERA
Pre-Award Financial - 9-JAYASUNDERA | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-03-05 | 179 |  | N | 9-JAYASUNDERA
Pre-Award Financial - SLS-III | PAF routed | User | Oliver, Amy | 2017-03-05 | 129 | 2017-07-12 | N | 00131953
Pre-Award Financial - 46-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-03-06 | 0 | 2017-03-06 | N | 46-HIGGINS
Pre-Award Financial - 00129851 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-07 | 17 | 2017-03-24 | N | 00129851
Pre-Award Financial - 30-FLAHERTY | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-07 | 177 |  | N | 30-FLAHERTY
Pre-Award Financial - 00129851 | UFA Completed | Role | CTSU Coordinator | 2017-03-07 | 0 | 2017-03-07 | N | 00129851
Pre-Award Financial - 30-FLAHERTY | Sponsor Reach out | Role | CTSU Coordinator | 2017-03-07 | 0 | 2017-02-22 | N | 30-FLAHERTY
Pre-Award Financial - 30-FLAHERTY | UFA Completed | Role | CTSU Coordinator | 2017-03-07 | 0 | 2017-02-21 | N | 30-FLAHERTY
Pre-Award Financial - 00123861 | Internal Budget Finished | Role | CTSU Finance | 2017-03-07 | 0 | 2017-03-01 | N | 00123861
Pre-Award Financial - 00125022 | Planning Meeting Completed | Role | CTSU Finance | 2017-03-07 | 13 | 2017-03-20 | N | 00125022
Pre-Award Financial - 00125425 | Internal Budget Finished | Role | CTSU Finance | 2017-03-07 | 16 | 2017-03-23 | N | 00125425
Pre-Award Financial - 00127136 | Internal Budget Finished | Role | CTSU Finance | 2017-03-07 | 0 | 2017-02-21 | N | 00127136
Pre-Award Financial - 00128531 | Budget Negotiations | Role | CTSU Finance | 2017-03-07 | 28 | 2017-04-04 | N | 00128531
Pre-Award Financial - 00127356 | Intake Form Completed | Role | CTSU Coordinator | 2017-03-08 | 0 | 2017-03-08 | N | 00127356
Pre-Award Financial - 00130575 | Intake Form Completed | Role | CTSU Coordinator | 2017-03-08 | 0 | 2017-03-08 | N | 00130575
Pre-Award Financial - 12-HIGGINS | Billing Calendar Received | Role | CTSU Finance | 2017-03-08 | 176 |  | N | 12-HIGGINS
Pre-Award Financial - 00126215 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-03-09 | 0 | 2017-02-22 | N | 00126215
Pre-Award Financial - 00128157 | Intake Form Completed | Role | CTSU Coordinator | 2017-03-09 | 0 | 2017-03-09 | N | 00128157
Pre-Award Financial - 49-MARTINEZ | Intake Form Completed | Role | CTSU Coordinator | 2017-03-09 | 0 | 2017-03-09 | N | 00132020
Pre-Award Financial - 00125794 | Planning Meeting Completed | Role | CTSU Finance | 2017-03-09 | 18 | 2017-03-27 | N | 00125794
Pre-Award Financial - 00127537 | Planning Meeting Completed | Role | CTSU Finance | 2017-03-09 | 19 | 2017-03-28 | N | 00127537
Pre-Award Financial - MENEES-1 | Billing Calendar Received | Role | CTSU Finance | 2017-03-09 | 175 |  | N | MENEES-1
Pre-Award Financial - 33-FLAHERTY | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-10 | 10 | 2017-03-20 | N | 00129716
Pre-Award Financial - 34-MARSH | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-10 | 174 |  | N | 34-MARSH
Pre-Award Financial - 00125794 | IRB Application Submitted | Role | CTSU Coordinator | 2017-03-10 | 0 | 2017-03-10 | N | 00125794
Pre-Award Financial - 34-MARSH | Sponsor Reach out | Role | CTSU Coordinator | 2017-03-10 | 59 | 2017-05-08 | N | 34-MARSH
Pre-Award Financial - 34-MARSH | UFA Completed | Role | CTSU Coordinator | 2017-03-10 | 59 | 2017-05-08 | N | 34-MARSH
Calendaring : Initial Calendar Build - 00126135 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-03-10 | 143 | 2017-07-31 | N | 00126135
Pre-Award Financial - 00123861 | PI approved Budget | Role | CTSU Finance | 2017-03-10 | 0 | 2017-03-01 | N | 00123861
Pre-Award Financial - 00125425 | PI approved Budget | Role | CTSU Finance | 2017-03-10 | 19 | 2017-03-29 | N | 00125425
Pre-Award Financial - 00127136 | PI approved Budget | Role | CTSU Finance | 2017-03-10 | 0 | 2017-03-10 | N | 00127136
Pre-Award Financial - 00125022 | Care Designations completed | User | Oliver, Amy | 2017-03-10 | 89 | 2017-06-07 | N | 00125022
Pre-Award Financial - 00126215 | Planning Meeting Request Sent | Role | CTSU Administrator | 2017-03-11 | 0 | 2017-03-02 | N | 00126215
Pre-Award Financial - 00127136 | Billing Calendar Received | Role | CTSU Finance | 2017-03-11 | 0 | 2017-02-23 | N | 00127136
Pre-Award Financial - 00122254 | Billing Calendar Received | Role | CTSU Finance | 2017-03-12 | 32 | 2017-04-13 | N | 00122254
Pre-Award Financial - 00123861 | Budget Negotiations | Role | CTSU Finance | 2017-03-12 | 0 | 2017-03-02 | N | 00123861
Pre-Award Financial - 00125425 | Budget Negotiations | Role | CTSU Finance | 2017-03-12 | 18 | 2017-03-30 | N | 00125425
Pre-Award Financial - 00125794 | Care Designations completed | Role | CTSU Finance | 2017-03-12 | 61 | 2017-05-12 | N | 00125794
Pre-Award Financial - 00127136 | Budget Negotiations | Role | CTSU Finance | 2017-03-12 | 0 | 2017-03-10 | N | 00127136
Pre-Award Financial - 00127505 | Billing Calendar Received | Role | CTSU Finance | 2017-03-12 | 4 | 2017-03-16 | N | 00127505
Pre-Award Financial - 00127537 | Care Designations completed | Role | CTSU Finance | 2017-03-12 | 0 | 2017-02-01 | N | 00127537
Pre-Award Financial - 12-HIGGINS | Planning Meeting Completed | Role | CTSU Finance | 2017-03-12 | 172 |  | N | 12-HIGGINS
Calendaring : Initial Calendar Build - 00126135 | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-03-12 | 123 | 2017-07-13 | N | 00126135
Calendaring : Initial Calendar Build - 00126135 | Make Updates | User | van Dijk, Tim | 2017-03-12 | 123 | 2017-07-13 | N | 00126135
Pre-Award Financial - 00127356 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-03-13 | 0 | 2017-03-13 | N | 00127356
Pre-Award Financial - 00130575 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-03-13 | 0 | 2017-03-13 | N | 00130575
Pre-Award Financial - MENEES-1 | IRB Application Submitted | Role | CTSU Coordinator | 2017-03-13 | 171 |  | N | MENEES-1
Pre-Award Financial - 10-JAYASUNDERA | Billing Calendar Received | Role | CTSU Finance | 2017-03-13 | 171 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 9-JAYASUNDERA | Billing Calendar Received | Role | CTSU Finance | 2017-03-13 | 171 |  | N | 9-JAYASUNDERA
Pre-Award Financial - MENEES-1 | Planning Meeting Completed | Role | CTSU Finance | 2017-03-13 | 171 |  | N | MENEES-1
Pre-Award Financial - PLT-INF24-001 | Final Budget | User | Oliver, Amy | 2017-03-13 | 114 | 2017-07-05 | N | 00135388
Pre-Award Financial - 00129851 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-03-14 | 13 | 2017-03-27 | N | 00129851
Pre-Award Financial - 00130793 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-14 | 64 | 2017-05-17 | N | 00130793
Pre-Award Financial - 30-FLAHERTY | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-03-14 | 170 |  | N | 30-FLAHERTY
Pre-Award Financial - 00127537 | IRB Application Submitted | Role | CTSU Coordinator | 2017-03-14 | 0 | 2017-03-14 | N | 00127537
Pre-Award Financial - 00130793 | Sponsor Reach out | Role | CTSU Coordinator | 2017-03-14 | 62 | 2017-05-15 | N | 00130793
Pre-Award Financial - 00130793 | UFA Completed | Role | CTSU Coordinator | 2017-03-14 | 9 | 2017-03-23 | N | 00130793
Pre-Award Financial - 56-RAO | Intake Form Completed | Role | CTSU Coordinator | 2017-03-14 | 0 | 2017-03-14 | N | 00133286
Calendaring : Initial Calendar Build - 00126135 | Acknowledge | Role | CTSU Finance | 2017-03-14 | 119 | 2017-07-11 | N | 00126135
Pre-Award Financial - 00125022 | Internal Budget Finished | Role | CTSU Finance | 2017-03-14 | 15 | 2017-03-29 | N | 00125022
Pre-Award Financial - 00127356 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-03-15 | 14 | 2017-03-29 | N | 00127356
Pre-Award Financial - 00130575 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-03-15 | 5 | 2017-03-20 | N | 00130575
Pre-Award Financial - 00130575 | Planning Meeting Request Sent | Role | CTSU Finance | 2017-03-15 | 8 | 2017-03-23 | N | 00130575
Pre-Award Financial - 12-HIGGINS | Care Designations completed | Role | CTSU Finance | 2017-03-15 | 169 |  | N | 12-HIGGINS
Pre-Award Financial - PLT-INF24-001 | PAF routed | User | Oliver, Amy | 2017-03-15 | 127 | 2017-07-20 | N | 00135388
Pre-Award Financial - 00127356 | Planning Meeting Request Sent | User | VanderElzen, Liz | 2017-03-15 | 169 |  | N | 00127356
Calendaring : Migration - 00087702 | Nimblify Build is Complete & Ready for Import | Role | CRAO | 2017-03-16 | 0 | 2017-03-16 | N | 00087702
CTSU Pre-Award v2 - 37-SILVER | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-16 | 168 |  | N | 37-SILVER
Pre-Award Financial - 00122254 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-16 | 0 | 2017-03-01 | N | 00122254
Pre-Award Financial - 00129851 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-03-16 | 7 | 2017-03-23 | N | 00129851
Pre-Award Financial - 30-FLAHERTY | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-03-16 | 168 |  | N | 30-FLAHERTY
Pre-Award Financial - 00122254 | Planning Meeting Completed | Role | CTSU Finance | 2017-03-16 | 0 | 2017-03-16 | N | 00122254
Pre-Award Financial - 00124712 | Planning Meeting Completed | Role | CTSU Finance | 2017-03-16 | 0 | 2017-02-23 | N | 00124712
Pre-Award Financial - 00125794 | Internal Budget Finished | Role | CTSU Finance | 2017-03-16 | 26 | 2017-04-11 | N | 00125794
Pre-Award Financial - 00127505 | Planning Meeting Completed | Role | CTSU Finance | 2017-03-16 | 18 | 2017-04-03 | N | 00127505
Pre-Award Financial - 00127537 | Internal Budget Finished | Role | CTSU Finance | 2017-03-16 | 21 | 2017-04-06 | N | 00127537
Pre-Award Financial - 00129851 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-03-16 | 13 | 2017-03-29 | N | 00129851
Pre-Award Financial - 30-FLAHERTY | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-03-16 | 168 |  | N | 30-FLAHERTY
Pre-Award Financial - 30-FLAHERTY | Request MCRU Budget | Role | CTSU Finance | 2017-03-16 | 168 |  | N | 30-FLAHERTY
Pre-Award Financial - 30-FLAHERTY | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-03-16 | 168 |  | N | 30-FLAHERTY
Pre-Award Financial - MENEES-1 | Care Designations completed | Role | CTSU Finance | 2017-03-16 | 168 |  | N | MENEES-1
Pre-Award Financial - 00127505 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-17 | 0 | 2017-03-02 | N | 00127505
Pre-Award Financial - 34-MARSH | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-03-17 | 167 |  | N | 34-MARSH
Pre-Award Financial - 00125022 | PI approved Budget | Role | CTSU Finance | 2017-03-17 | 13 | 2017-03-30 | N | 00125022
Pre-Award Financial - 10-JAYASUNDERA | Planning Meeting Completed | Role | CTSU Finance | 2017-03-17 | 167 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 9-JAYASUNDERA | Planning Meeting Completed | Role | CTSU Finance | 2017-03-17 | 167 |  | N | 9-JAYASUNDERA
Pre-Award Financial - 00127136 | Care Designations completed | Role | CTSU Finance | 2017-03-18 | 10 | 2017-03-28 | N | 00127136
Pre-Award Financial - 34-MARSH | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-03-19 | 165 |  | N | 34-MARSH
Pre-Award Financial - 00122254 | Care Designations completed | Role | CTSU Finance | 2017-03-19 | 65 | 2017-05-23 | N | 00122254
Pre-Award Financial - 00124920 | Final Budget | Role | CTSU Finance | 2017-03-19 | 0 | 2017-02-21 | N | 00124920
Pre-Award Financial - 00125022 | Budget Negotiations | Role | CTSU Finance | 2017-03-19 | 17 | 2017-04-05 | N | 00125022
Pre-Award Financial - 00125794 | PI approved Budget | Role | CTSU Finance | 2017-03-19 | 24 | 2017-04-12 | N | 00125794
Pre-Award Financial - 00127505 | Care Designations completed | Role | CTSU Finance | 2017-03-19 | 59 | 2017-05-17 | N | 00127505
Pre-Award Financial - 00127537 | PI approved Budget | Role | CTSU Finance | 2017-03-19 | 26 | 2017-04-14 | N | 00127537
Pre-Award Financial - 12-HIGGINS | Internal Budget Finished | Role | CTSU Finance | 2017-03-19 | 165 |  | N | 12-HIGGINS
Pre-Award Financial - 2-MARSH | Final Budget | Role | CTSU Finance | 2017-03-19 | 165 |  | N | 2-MARSH
Pre-Award Financial - 34-MARSH | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-03-19 | 165 |  | N | 34-MARSH
Pre-Award Financial - 34-MARSH | Request MCRU Budget | Role | CTSU Finance | 2017-03-19 | 165 |  | N | 34-MARSH
Pre-Award Financial - 34-MARSH | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-03-19 | 165 |  | N | 34-MARSH
Pre-Award Financial - SLS-III | PAN Released | User | Oliver, Amy | 2017-03-19 | 165 |  | N | 00131953
Pre-Award Financial - 10-JAYASUNDERA | Care Designations completed | Role | CTSU Finance | 2017-03-20 | 164 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 9-JAYASUNDERA | Care Designations completed | Role | CTSU Finance | 2017-03-20 | 164 |  | N | 9-JAYASUNDERA
Pre-Award Financial - MENEES-1 | Internal Budget Finished | Role | CTSU Finance | 2017-03-20 | 164 |  | N | MENEES-1
Pre-Award Financial - 33-FLAHERTY | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-03-21 | 0 | 2017-03-21 | N | 00129716
Pre-Award Financial - 44-MCUNE | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-21 | 163 |  | N | 44-MCUNE
Pre-Award Financial - FONTANA-1 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-21 | 123 | 2017-07-22 | N | 00133153
Pre-Award Financial - 44-MCUNE | Sponsor Reach out | Role | CTSU Coordinator | 2017-03-21 | 114 | 2017-07-13 | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | UFA Completed | Role | CTSU Coordinator | 2017-03-21 | 0 | 2017-03-13 | N | 44-MCUNE
Pre-Award Financial - FONTANA-1 | Sponsor Reach out | Role | CTSU Coordinator | 2017-03-21 | 0 | 2017-02-28 | N | 00133153
Pre-Award Financial - FONTANA-1 | UFA Completed | Role | CTSU Coordinator | 2017-03-21 | 0 | 2017-02-28 | N | 00133153
Pre-Award Financial - 00124920 | PAF routed | Role | CTSU Finance | 2017-03-21 | 0 | 2017-02-27 | N | 00124920
Pre-Award Financial - 00125794 | Budget Negotiations | Role | CTSU Finance | 2017-03-21 | 22 | 2017-04-12 | N | 00125794
Pre-Award Financial - 00127537 | Budget Negotiations | Role | CTSU Finance | 2017-03-21 | 27 | 2017-04-17 | N | 00127537
Pre-Award Financial - 00128531 | Final Budget | Role | CTSU Finance | 2017-03-21 | 15 | 2017-04-05 | N | 00128531
Pre-Award Financial - 2-MARSH | PAF routed | Role | CTSU Finance | 2017-03-21 | 163 |  | N | 2-MARSH
Calendaring : Migration - 000127913 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO | 2017-03-22 | 0 | 2017-03-22 | N | 00127913
Pre-Award Financial - 00128743 | Intake Form Completed | Role | CTSU Coordinator | 2017-03-22 | 0 | 2017-03-22 | N | 00128743
Pre-Award Financial - 00125786 | Internal Budget Finished | Role | CTSU Finance | 2017-03-22 | 0 | 2017-02-17 | N | 00125786
Pre-Award Financial - 12-HIGGINS | PI approved Budget | Role | CTSU Finance | 2017-03-22 | 162 |  | N | 12-HIGGINS
CTSU Pre-Award v2 - 37-SILVER | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-03-23 | 161 |  | N | 37-SILVER
Pre-Award Financial - 69-KHANNA | Intake Form Completed | Role | CTSU Administrator | 2017-03-23 | 0 | 2017-03-23 | N | 69-KHANNA
Pre-Award Financial - 33-FLAHERTY | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-03-23 | 0 | 2017-03-22 | N | 00129716
Pre-Award Financial - 00122254 | Internal Budget Finished | Role | CTSU Finance | 2017-03-23 | 34 | 2017-04-26 | N | 00122254
Pre-Award Financial - 00124712 | Internal Budget Finished | Role | CTSU Finance | 2017-03-23 | 0 | 2017-02-22 | N | 00124712
Pre-Award Financial - 00126215 | Planning Meeting Completed | Role | CTSU Finance | 2017-03-23 | 4 | 2017-03-27 | N | 00126215
Pre-Award Financial - 00127356 | Billing Calendar Received | Role | CTSU Finance | 2017-03-23 | 33 | 2017-04-25 | N | 00127356
Pre-Award Financial - 00127505 | Internal Budget Finished | Role | CTSU Finance | 2017-03-23 | 9 | 2017-04-01 | N | 00127505
Pre-Award Financial - 00128531 | PAF routed | Role | CTSU Finance | 2017-03-23 | 19 | 2017-04-11 | N | 00128531
Pre-Award Financial - 00130575 | Billing Calendar Received | Role | CTSU Finance | 2017-03-23 | 25 | 2017-04-17 | N | 00130575
Pre-Award Financial - 33-FLAHERTY | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-03-23 | 4 | 2017-03-27 | N | 00129716
Pre-Award Financial - MENEES-1 | PI approved Budget | Role | CTSU Finance | 2017-03-23 | 161 |  | N | MENEES-1
Pre-Award Financial - SCHIOPU-1 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-24 | 160 |  | N | SCHIOPU-1
Pre-Award Financial - SCHIOPU-1 | Sponsor Reach out | Role | CTSU Coordinator | 2017-03-24 | 160 |  | N | SCHIOPU-1
Pre-Award Financial - SCHIOPU-1 | UFA Completed | Role | CTSU Coordinator | 2017-03-24 | 160 |  | N | SCHIOPU-1
Pre-Award Financial - 00118070 | Feasibility approved/CRAO Notified | Role | CTSU Finance | 2017-03-24 | 0 | 2017-03-24 | N | 00118070
Pre-Award Financial - 00129851 | Billing Calendar Received | Role | CTSU Finance | 2017-03-24 | 25 | 2017-04-18 | N | 00129851
Pre-Award Financial - 10-JAYASUNDERA | Internal Budget Finished | Role | CTSU Finance | 2017-03-24 | 160 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 12-HIGGINS | Budget Negotiations | Role | CTSU Finance | 2017-03-24 | 160 |  | N | 12-HIGGINS
Pre-Award Financial - 30-FLAHERTY | Billing Calendar Received | Role | CTSU Finance | 2017-03-24 | 160 |  | N | 30-FLAHERTY
Pre-Award Financial - 9-JAYASUNDERA | Internal Budget Finished | Role | CTSU Finance | 2017-03-24 | 160 |  | N | 9-JAYASUNDERA
Calendaring : Initial Calendar Build - 147 | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-03-24 | 0 | 2017-03-24 | N | 00128322
CTSU Pre-Award v2 - 37-SILVER | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-03-25 | 159 |  | N | 37-SILVER
CTSU Pre-Award v2 - 37-SILVER | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-03-25 | 159 |  | N | 37-SILVER
CTSU Pre-Award v2 - 37-SILVER | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-03-25 | 159 |  | N | 37-SILVER
Pre-Award Financial - 00125566 | Care Designations completed | Role | CTSU Finance | 2017-03-25 | 4 | 2017-03-29 | N | 00125566
Pre-Award Financial - 00125786 | PI approved Budget | Role | CTSU Finance | 2017-03-25 | 0 | 2017-02-21 | N | 00125786
Pre-Award Financial - MENEES-1 | Budget Negotiations | Role | CTSU Finance | 2017-03-25 | 159 |  | N | MENEES-1
Pre-Award Financial - 00122254 | PI approved Budget | Role | CTSU Finance | 2017-03-26 | 37 | 2017-05-02 | N | 00122254
Pre-Award Financial - 00123861 | Final Budget | Role | CTSU Finance | 2017-03-26 | 0 | 2017-03-13 | N | 00123861
Pre-Award Financial - 00125425 | Final Budget | Role | CTSU Finance | 2017-03-26 | 23 | 2017-04-18 | N | 00125425
Pre-Award Financial - 00127136 | Final Budget | Role | CTSU Finance | 2017-03-26 | 57 | 2017-05-22 | N | 00127136
Pre-Award Financial - 00127505 | PI approved Budget | Role | CTSU Finance | 2017-03-26 | 8 | 2017-04-03 | N | 00127505
Calendaring : Initial Calendar Build - 147 | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-03-26 | 25 | 2017-04-20 | N | 00128322
Calendaring : Initial Calendar Build - 147 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-03-26 | 26 | 2017-04-21 | N | 00128322
Pre-Award Financial - 46-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-27 | 74 | 2017-06-09 | N | 46-HIGGINS
Pre-Award Financial - 00128531 | IRB Application Submitted | Role | CTSU Coordinator | 2017-03-27 | 0 | 2017-03-27 | N | 00128531
Pre-Award Financial - 70-LUGOGO | Intake Form Completed | Role | CTSU Coordinator | 2017-03-27 | 0 | 2017-03-27 | N | 70-LUGOGO
Pre-Award Financial - 71-RICE | Intake Form Completed | Role | CTSU Coordinator | 2017-03-27 | 0 | 2017-03-27 | N | 00134857
Pre-Award Financial - 00125786 | Budget Negotiations | Role | CTSU Finance | 2017-03-27 | 3 | 2017-03-30 | N | 00125786
Pre-Award Financial - 00130575 | Planning Meeting Completed | Role | CTSU Finance | 2017-03-27 | 3 | 2017-03-30 | N | 00130575
Pre-Award Financial - 10-JAYASUNDERA | PI approved Budget | Role | CTSU Finance | 2017-03-27 | 157 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 34-MARSH | Billing Calendar Received | Role | CTSU Finance | 2017-03-27 | 157 |  | N | 34-MARSH
Pre-Award Financial - 9-JAYASUNDERA | PI approved Budget | Role | CTSU Finance | 2017-03-27 | 157 |  | N | 9-JAYASUNDERA
Pre-Award Financial - 00127356 | Planning Meeting Completed | User | VanderElzen, Liz | 2017-03-27 | 157 |  | N | 00127356
Calendaring : Initial Calendar Build - 00128531 | Feasibility Approval Notice Received | Role | CRAO | 2017-03-28 | 0 | 2017-03-28 | N | 00128531
Calendaring : Initial Calendar Build - 00128531 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO | 2017-03-28 | 16 | 2017-04-13 | N | 00128531
Pre-Award Financial - 44-MCUNE | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-03-28 | 156 |  | N | 44-MCUNE
Pre-Award Financial - 00122254 | Budget Negotiations | Role | CTSU Finance | 2017-03-28 | 43 | 2017-05-10 | N | 00122254
Pre-Award Financial - 00123861 | PAF routed | Role | CTSU Finance | 2017-03-28 | 0 | 2017-03-24 | N | 00123861
Pre-Award Financial - 00125425 | PAF routed | Role | CTSU Finance | 2017-03-28 | 36 | 2017-05-03 | N | 00125425
Pre-Award Financial - 00127505 | Budget Negotiations | Role | CTSU Finance | 2017-03-28 | 13 | 2017-04-10 | N | 00127505
Pre-Award Financial - 00129851 | Planning Meeting Completed | Role | CTSU Finance | 2017-03-28 | 6 | 2017-04-03 | N | 00129851
Pre-Award Financial - 30-FLAHERTY | Planning Meeting Completed | Role | CTSU Finance | 2017-03-28 | 156 |  | N | 30-FLAHERTY
Pre-Award Financial - 00127136 | PAF routed | User | Oliver, Amy | 2017-03-28 | 55 | 2017-05-22 | N | 00127136
Calendaring : Initial Calendar Build - 27-WALKOVICH | Assign to Analyst | User | Radenbaugh, Pauline | 2017-03-28 | 0 | 2017-03-28 | N | 00127988
Pre-Award Financial - 00127356 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-29 | 0 | 2017-03-13 | N | 00127356
Pre-Award Financial - 00130575 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-29 | 0 | 2017-03-13 | N | 00130575
Pre-Award Financial - 76-KHANNA | Intake Form Completed | Role | CTSU Coordinator | 2017-03-29 | 0 | 2017-03-29 | N | 00131837
Pre-Award Financial - 10-JAYASUNDERA | Budget Negotiations | Role | CTSU Finance | 2017-03-29 | 155 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 9-JAYASUNDERA | Budget Negotiations | Role | CTSU Finance | 2017-03-29 | 155 |  | N | 9-JAYASUNDERA
Pre-Award Financial - PLT-INF24-001 | PAN Released | User | Oliver, Amy | 2017-03-29 | 155 |  | N | 00135388
Pre-Award Financial - 00128157 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-03-30 | 19 | 2017-04-18 | N | 00128157
Open to Accrual - 00125566 | IRB Approval | Role | CTSU Coordinator | 2017-03-30 | 0 | 2017-03-30 | N | 00125566
Pre-Award Financial - 44-MCUNE | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-03-30 | 154 |  | N | 44-MCUNE
Pre-Award Financial - 49-MARTINEZ | UFA Completed | Role | CTSU Coordinator | 2017-03-30 | 0 | 2017-03-09 | N | 00132020
Pre-Award Financial - 77-CONJEEVARAM | Intake Form Completed | Role | CTSU Coordinator | 2017-03-30 | 0 | 2017-03-30 | N | 77-CONJEEVARAM
Pre-Award Financial - 00127356 | Care Designations completed | Role | CTSU Finance | 2017-03-30 | 0 | 2017-02-01 | N | 00127356
Pre-Award Financial - 00130575 | Care Designations completed | Role | CTSU Finance | 2017-03-30 | 26 | 2017-04-25 | N | 00130575
Pre-Award Financial - 44-MCUNE | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-03-30 | 154 |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Request MCRU Budget | Role | CTSU Finance | 2017-03-30 | 154 |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-03-30 | 154 |  | N | 44-MCUNE
Pre-Award Financial - SCHIOPU-1 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-03-31 | 153 |  | N | SCHIOPU-1
Amendment Checklist & Process - 113141 AME per Ginger | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-03-31 | 0 | 2017-03-31 | N | 00113141
Pre-Award Financial - 00129851 | Care Designations completed | Role | CTSU Finance | 2017-03-31 | 0 | 2017-02-01 | N | 00129851
Pre-Award Financial - 30-FLAHERTY | Care Designations completed | Role | CTSU Finance | 2017-03-31 | 153 |  | N | 30-FLAHERTY
Pre-Award Financial - 33-FLAHERTY | Billing Calendar Received | Role | CTSU Finance | 2017-03-31 | 10 | 2017-04-10 | N | 00129716
Pre-Award Financial - 34-MARSH | Planning Meeting Completed | Role | CTSU Finance | 2017-03-31 | 153 |  | N | 34-MARSH
Amendment Checklist & Process - 113141 AME per Ginger | Assign to Analyst | User | LaVasseur, Kristen | 2017-03-31 | 0 | 2017-03-31 | N | 00113141
Calendaring : Initial Calendar Build - 27-WALKOVICH | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-03-31 | 20 | 2017-04-20 | N | 00127988
Calendaring : Initial Calendar Build - 27-WALKOVICH | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-03-31 | 0 | 2017-03-22 | N | 00127988
Calendaring : Initial Calendar Build - 00128531 | Nimblify Build is Complete & Ready for Import | User | Zahs, Brian | 2017-03-31 | 28 | 2017-04-28 | N | 00128531
Pre-Award Financial - 00125566 | PI approved Budget | Role | CTSU Finance | 2017-04-01 | 0 | 2017-02-07 | N | 00125566
Amendment Checklist & Process - 113141 AME per Ginger | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | LaVasseur, Kristen | 2017-04-01 | 32 | 2017-05-03 | N | 00113141
Amendment Checklist & Process - 113141 AME per Ginger | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | LaVasseur, Kristen | 2017-04-01 | 0 | 2017-03-31 | N | 00113141
Calendar & Budget Retrofit - 00122254 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-04-01 | 131 | 2017-08-10 | N | 00122254
Calendar & Budget Retrofit - 00122254 | Review & Release Calendar | User | Oliver, Amy | 2017-04-01 | 131 | 2017-08-10 | N | 00122254
Pre-Award Financial - SCHIOPU-1 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-04-02 | 151 |  | N | SCHIOPU-1
CTSU Pre-Award v2 - 37-SILVER | Billing Calendar Received | Role | CTSU Finance | 2017-04-02 | 151 |  | N | 37-SILVER
Calendaring : Initial Calendar Build - 147 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-04-02 | 33 | 2017-05-05 | N | 00128322
Pre-Award Financial - SCHIOPU-1 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-04-02 | 151 |  | N | SCHIOPU-1
Pre-Award Financial - SCHIOPU-1 | Request MCRU Budget | Role | CTSU Finance | 2017-04-02 | 151 |  | N | SCHIOPU-1
Pre-Award Financial - SCHIOPU-1 | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-04-02 | 151 |  | N | SCHIOPU-1
Pre-Award Financial - 00125022 | Final Budget | User | Oliver, Amy | 2017-04-02 | 98 | 2017-07-09 | N | 00125022
Pre-Award Financial - SLS-III | OnCore Budget Build | User | Yunk, Jason | 2017-04-02 | 138 | 2017-08-18 | N | 00131953
Calendaring : Initial Calendar Build - 00128531 | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian | 2017-04-02 | 26 | 2017-04-28 | N | 00128531
Calendaring : Initial Calendar Build - 00128531 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian | 2017-04-02 | 31 | 2017-05-03 | N | 00128531
Pre-Award Financial - 81-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-04-03 | 0 | 2017-04-03 | N | 81-HIGGINS
Pre-Award Financial - 00125566 | Budget Negotiations | Role | CTSU Finance | 2017-04-03 | 0 | 2017-02-13 | N | 00125566
Pre-Award Financial - 34-MARSH | Care Designations completed | Role | CTSU Finance | 2017-04-03 | 150 |  | N | 34-MARSH
Calendar Build - 50-HUMMEL | Calendar Build Request sent to Nimblify | User | Hess, Aaron | 2017-04-03 | 0 | 2017-03-29 | N | 00129162
Pre-Award Financial - SLS-III | Calendar Released | User | Oliver, Amy | 2017-04-03 | 137 | 2017-08-18 | N | 00131953
Pre-Award Financial - 00127356 | Internal Budget Finished | User | VanderElzen, Liz | 2017-04-03 | 150 |  | N | 00127356
Pre-Award Financial - 00130575 | Internal Budget Finished | User | VanderElzen, Liz | 2017-04-03 | 7 | 2017-04-10 | N | 00130575
Pre-Award Financial - 56-RAO | Feasibility w/Documents received | Role | CTSU Administrator | 2017-04-04 | 66 | 2017-06-09 | N | 00133286
CTSU Pre-Award v2 - 82-BOLLING | Intake Form Completed | Role | CTSU Coordinator | 2017-04-04 | 0 | 2017-04-04 | N | 82-BOLLING
Pre-Award Financial - 56-RAO | UFA Completed | Role | CTSU Coordinator | 2017-04-04 | 0 | 2017-03-14 | N | 00133286
Pre-Award Financial - 00125794 | Final Budget | Role | CTSU Finance | 2017-04-04 | 31 | 2017-05-05 | N | 00125794
Pre-Award Financial - 00127537 | Final Budget | Role | CTSU Finance | 2017-04-04 | 31 | 2017-05-05 | N | 00127537
Pre-Award Financial - 00129851 | Internal Budget Finished | Role | CTSU Finance | 2017-04-04 | 1 | 2017-04-05 | N | 00129851
Pre-Award Financial - 2-MARSH | PAN Released | Role | CTSU Finance | 2017-04-04 | 149 |  | N | 2-MARSH
Pre-Award Financial - 30-FLAHERTY | Internal Budget Finished | Role | CTSU Finance | 2017-04-04 | 149 |  | N | 30-FLAHERTY
Pre-Award Financial - 33-FLAHERTY | Planning Meeting Completed | Role | CTSU Finance | 2017-04-04 | 0 | 2017-03-29 | N | 00129716
Pre-Award Financial - 00124920 | PAN Released | User | Oliver, Amy | 2017-04-04 | 119 | 2017-08-01 | N | 00124920
Pre-Award Financial - 00125022 | PAF routed | User | Oliver, Amy | 2017-04-04 | 149 |  | N | 00125022
Calendaring : Initial Calendar Build - 147 | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-04-04 | 33 | 2017-05-07 | N | 00128322
Calendaring : Initial Calendar Build - 147 | Make Updates | User | Radenbaugh, Pauline | 2017-04-04 | 33 | 2017-05-07 | N | 00128322
Pre-Award Financial - SLS-III | PI Signoff in OnCore | Role | CTSU Administrator | 2017-04-06 | 147 |  | N | 00131953
CTSU Pre-Award v2 - 37-SILVER | IRB Application Submitted | Role | CTSU Coordinator | 2017-04-06 | 147 |  | N | 37-SILVER
CTSU Pre-Award v2 - 37-SILVER | Planning Meeting Completed | Role | CTSU Finance | 2017-04-06 | 147 |  | N | 37-SILVER
Pre-Award Financial - 00125794 | PAF routed | Role | CTSU Finance | 2017-04-06 | 36 | 2017-05-12 | N | 00125794
Pre-Award Financial - 00127537 | PAF routed | Role | CTSU Finance | 2017-04-06 | 41 | 2017-05-17 | N | 00127537
Pre-Award Financial - 00130575 | PI approved Budget | Role | CTSU Finance | 2017-04-06 | 0 | 2017-03-30 | N | 00130575
Calendaring : Initial Calendar Build - 147 | Acknowledge | User | Cohan, Lynn | 2017-04-06 | 133 | 2017-08-17 | N | 00128322
Pre-Award Financial - 00128531 | PAN Released | User | Oliver, Amy | 2017-04-06 | 147 |  | N | 00128531
Pre-Award Financial - 00127356 | PI approved Budget | User | VanderElzen, Liz | 2017-04-06 | 147 |  | N | 00127356
Pre-Award Financial - 86-AUCHUS | Intake Form Completed | Role | CTSU Coordinator | 2017-04-07 | 0 | 2017-04-07 | N | 00132700
Pre-Award Financial - 87-ORAL | Intake Form Completed | Role | CTSU Coordinator | 2017-04-07 | 0 | 2017-04-07 | N | 00130757
Pre-Award Financial - 00129851 | PI approved Budget | Role | CTSU Finance | 2017-04-07 | 0 | 2017-04-05 | N | 00129851
Pre-Award Financial - 12-HIGGINS | Final Budget | Role | CTSU Finance | 2017-04-07 | 146 |  | N | 12-HIGGINS
Pre-Award Financial - 30-FLAHERTY | PI approved Budget | Role | CTSU Finance | 2017-04-07 | 146 |  | N | 30-FLAHERTY
Pre-Award Financial - 33-FLAHERTY | Care Designations completed | Role | CTSU Finance | 2017-04-07 | 6 | 2017-04-13 | N | 00129716
Pre-Award Financial - 34-MARSH | Internal Budget Finished | Role | CTSU Finance | 2017-04-07 | 146 |  | N | 34-MARSH
Pre-Award Financial - 44-MCUNE | Billing Calendar Received | Role | CTSU Finance | 2017-04-07 | 146 |  | N | 44-MCUNE
Calendaring : Initial Calendar Build - 00125022 | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-04-07 | 0 | 2017-04-07 | N | 00125022
Pre-Award Financial - SLS-III | Open to Accrual | Role | CTSU Administrator | 2017-04-08 | 145 |  | N | 00131953
Pre-Award Financial - 00130575 | Budget Negotiations | Role | CTSU Finance | 2017-04-08 | 2 | 2017-04-10 | N | 00130575
Pre-Award Financial - MENEES-1 | Final Budget | Role | CTSU Finance | 2017-04-08 | 145 |  | N | MENEES-1
Pre-Award Financial - 00127356 | Budget Negotiations | User | VanderElzen, Liz | 2017-04-08 | 145 |  | N | 00127356
CTSU Pre-Award v2 - 37-SILVER | Care Designations completed | Role | CTSU Finance | 2017-04-09 | 144 |  | N | 37-SILVER
Pre-Award Financial - 00129851 | Budget Negotiations | Role | CTSU Finance | 2017-04-09 | 2 | 2017-04-11 | N | 00129851
Pre-Award Financial - 12-HIGGINS | PAF routed | Role | CTSU Finance | 2017-04-09 | 144 |  | N | 12-HIGGINS
Pre-Award Financial - 30-FLAHERTY | Budget Negotiations | Role | CTSU Finance | 2017-04-09 | 144 |  | N | 30-FLAHERTY
Calendaring : Initial Calendar Build - 00128531 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Oliver, Amy | 2017-04-09 | 53 | 2017-06-01 | N | 00128531
Calendaring : Initial Calendar Build - 00125022 | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-04-09 | 17 | 2017-04-26 | N | 00125022
Calendaring : Initial Calendar Build - 00125022 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-04-09 | 17 | 2017-04-26 | N | 00125022
Pre-Award Financial - 00125786 | Final Budget | Role | CTSU Finance | 2017-04-10 | 10 | 2017-04-20 | N | 00125786
Pre-Award Financial - 34-MARSH | PI approved Budget | Role | CTSU Finance | 2017-04-10 | 143 |  | N | 34-MARSH
Pre-Award Financial - MENEES-1 | PAF routed | Role | CTSU Finance | 2017-04-10 | 143 |  | N | MENEES-1
Pre-Award Financial - SCHIOPU-1 | Billing Calendar Received | Role | CTSU Finance | 2017-04-10 | 143 |  | N | SCHIOPU-1
Pre-Award Financial - 44-MCUNE | IRB Application Submitted | Role | CTSU Coordinator | 2017-04-11 | 142 |  | N | 44-MCUNE
Pre-Award Financial - 91-ELSE | Intake Form Completed | Role | CTSU Coordinator | 2017-04-11 | 0 | 2017-04-11 | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | Intake Form Completed | Role | CTSU Coordinator | 2017-04-11 | 0 | 2017-04-11 | N | 92-AUCHUS
Pre-Award Financial - 00123861 | PAN Released | Role | CTSU Finance | 2017-04-11 | 0 | 2017-04-07 | N | 00123861
Pre-Award Financial - 33-FLAHERTY | Internal Budget Finished | Role | CTSU Finance | 2017-04-11 | 0 | 2017-04-06 | N | 00129716
Pre-Award Financial - 44-MCUNE | Planning Meeting Completed | Role | CTSU Finance | 2017-04-11 | 142 |  | N | 44-MCUNE
Pre-Award Financial - 00122254 | Final Budget | User | Oliver, Amy | 2017-04-11 | 86 | 2017-07-06 | N | 00122254
Pre-Award Financial - 00125425 | PAN Released | User | Oliver, Amy | 2017-04-11 | 63 | 2017-06-13 | N | 00125425
Pre-Award Financial - 00127136 | PAN Released | User | Oliver, Amy | 2017-04-11 | 142 |  | N | 00127136
Pre-Award Financial - 00127505 | Final Budget | User | VanderElzen, Liz | 2017-04-11 | 100 | 2017-07-20 | N | 00127505
Pre-Award Financial - MENEES-1 | OnCore Budget Build | User | Yunk, Jason | 2017-04-11 | 142 |  | N | MENEES-1
Calendaring : Initial Calendar Build - 00128531 | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-04-11 | 59 | 2017-06-09 | N | 00128531
Calendaring : Initial Calendar Build - 00128531 | Make Updates | User | Zahs, Brian | 2017-04-11 | 51 | 2017-06-01 | N | 00128531
Calendaring : Initial Calendar Build - 00128301 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO | 2017-04-12 | 0 | 2017-04-12 | N | 00128301
Calendaring : Migration - 00105810 | Assign to Analyst | Role | CRAO | 2017-04-12 | 0 | 2017-04-12 | N | 00105810
Pre-Award Financial - 00128743 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-04-12 | 1 | 2017-04-13 | N | 00128743
Pre-Award Financial - 00129652 | Intake Form Completed | Role | CTSU Coordinator | 2017-04-12 | 0 | 2017-04-12 | N | 00129652
Pre-Award Financial - 96-BESIRLI | Intake Form Completed | Role | CTSU Coordinator | 2017-04-12 | 0 | 2017-04-12 | N | 00129820
Pre-Award Financial - 00125786 | PAF routed | Role | CTSU Finance | 2017-04-12 | 16 | 2017-04-28 | N | 00125786
Pre-Award Financial - 10-JAYASUNDERA | Final Budget | Role | CTSU Finance | 2017-04-12 | 141 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 34-MARSH | Budget Negotiations | Role | CTSU Finance | 2017-04-12 | 141 |  | N | 34-MARSH
Pre-Award Financial - 9-JAYASUNDERA | Final Budget | Role | CTSU Finance | 2017-04-12 | 141 |  | N | 9-JAYASUNDERA
Pre-Award Financial - MENEES-1 | Calendar Released | User | Oliver, Amy | 2017-04-12 | 141 |  | N | MENEES-1
Calendaring : Initial Calendar Build - 00128301 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-04-12 | 0 | 2017-04-12 | N | 00128301
Calendaring : Migration - 00089664 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-04-12 | 1 | 2017-04-13 | N | 00089664
Pre-Award Financial - PLT-INF24-001 | OnCore Budget Build | User | Yunk, Jason | 2017-04-12 | 128 | 2017-08-18 | N | 00135388
Pre-Award Financial - 69-KHANNA | Feasibility w/Documents received | Role | CTSU Administrator | 2017-04-13 | 140 |  | N | 69-KHANNA
Pre-Award Financial - 69-KHANNA | Sponsor Reach out | Role | CTSU Administrator | 2017-04-13 | 140 |  | N | 69-KHANNA
CTSU Pre-Award v2 - 37-SILVER | Internal Budget Finished | Role | CTSU Finance | 2017-04-13 | 140 |  | N | 37-SILVER
Calendar Build - 50-HUMMEL | Specification has been Imported / Michiganized and is ready for Finance / Study team review, feedback and determination of care designations | User | Hess, Aaron | 2017-04-13 | 0 | 2017-04-04 | N | 00129162
Calendaring : Initial Calendar Build - 00128531 | Acknowledge | User | Oliver, Amy | 2017-04-13 | 60 | 2017-06-12 | N | 00128531
Pre-Award Financial - 00122254 | PAF routed | User | Oliver, Amy | 2017-04-13 | 88 | 2017-07-10 | N | 00122254
Pre-Award Financial - PLT-INF24-001 | Calendar Released | User | Oliver, Amy | 2017-04-13 | 127 | 2017-08-18 | N | 00135388
Pre-Award Financial - 00127505 | PAF routed | User | VanderElzen, Liz | 2017-04-13 | 103 | 2017-07-25 | N | 00127505
Pre-Award Financial - 00108880 | Intake Form Completed | Role | CTSU Coordinator | 2017-04-14 | 0 | 2017-04-14 | N | 00108880
Pre-Award Financial - 00128173 | Intake Form Completed | Role | CTSU Coordinator | 2017-04-14 | 0 | 2017-04-14 | N | 00128173
Pre-Award Financial - 10-JAYASUNDERA | PAF routed | Role | CTSU Finance | 2017-04-14 | 139 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 33-FLAHERTY | PI approved Budget | Role | CTSU Finance | 2017-04-14 | 5 | 2017-04-19 | N | 00129716
Pre-Award Financial - 44-MCUNE | Care Designations completed | Role | CTSU Finance | 2017-04-14 | 139 |  | N | 44-MCUNE
Pre-Award Financial - 9-JAYASUNDERA | PAF routed | Role | CTSU Finance | 2017-04-14 | 139 |  | N | 9-JAYASUNDERA
Pre-Award Financial - SCHIOPU-1 | Planning Meeting Completed | Role | CTSU Finance | 2017-04-14 | 139 |  | N | SCHIOPU-1
Pre-Award Financial - MENEES-1 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-04-15 | 138 |  | N | MENEES-1
Calendaring : Initial Calendar Build - 00128301 | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-04-15 | 16 | 2017-05-01 | N | 00128301
Calendaring : Initial Calendar Build - 00128301 | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-04-15 | 0 | 2017-04-13 | N | 00128301
Calendaring : Initial Calendar Build - 00128301 | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-04-15 | 13 | 2017-04-28 | N | 00128301
Calendaring : Migration - 00089664 | Attach Build Notes and MBECT Calendar Reference ( as Protocol Docs ) | User | Radenbaugh, Pauline | 2017-04-15 | 6 | 2017-04-21 | N | 00089664
Calendaring : Migration - 00089664 | Complete Calendar ( ie. Flag as Ready for Financials ) | User | Radenbaugh, Pauline | 2017-04-15 | 6 | 2017-04-21 | N | 00089664
Calendaring : Migration - 00089664 | Import + Michiganize, including Entry of Care Designations & Comments per Current Approved MBECT Calendar | User | Radenbaugh, Pauline | 2017-04-15 | 0 | 2017-04-13 | N | 00089664
Calendaring : Migration - 00105810 | Attach Build Notes and MBECT Calendar Reference ( as Protocol Docs ) | User | Radenbaugh, Pauline | 2017-04-15 | 6 | 2017-04-21 | N | 00105810
Calendaring : Migration - 00105810 | Complete Calendar ( ie. Flag as Ready for Financials ) | User | Radenbaugh, Pauline | 2017-04-15 | 6 | 2017-04-21 | N | 00105810
Calendaring : Migration - 00105810 | Import + Michiganize, including Entry of Care Designations & Comments per Current Approved MBECT Calendar | User | Radenbaugh, Pauline | 2017-04-15 | 6 | 2017-04-21 | N | 00105810
Pre-Award Financial - PLT-INF24-001 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-04-16 | 137 |  | N | 00135388
CTSU Pre-Award v2 - 37-SILVER | PI approved Budget | Role | CTSU Finance | 2017-04-16 | 137 |  | N | 37-SILVER
Pre-Award Financial - 33-FLAHERTY | Budget Negotiations | Role | CTSU Finance | 2017-04-16 | 5 | 2017-04-21 | N | 00129716
Pre-Award Financial - 00128743 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-04-17 | 0 | 2017-04-17 | N | 00128743
Pre-Award Financial - 70-LUGOGO | Feasibility w/Documents received | Role | CTSU Administrator | 2017-04-17 | 39 | 2017-05-26 | N | 70-LUGOGO
Pre-Award Financial - 71-RICE | Feasibility w/Documents received | Role | CTSU Administrator | 2017-04-17 | 23 | 2017-05-10 | N | 00134857
Pre-Award Financial - 96-BESIRLI | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-04-17 | 0 | 2017-04-17 | N | 00129820
Pre-Award Financial - MENEES-1 | Open to Accrual | Role | CTSU Administrator | 2017-04-17 | 136 |  | N | MENEES-1
Open to Accrual - 00127537 | IRB Approval | Role | CTSU Coordinator | 2017-04-17 | 0 | 2017-04-17 | N | 00127537
Pre-Award Financial - 70-LUGOGO | UFA Completed | Role | CTSU Coordinator | 2017-04-17 | 0 | 2017-03-27 | N | 70-LUGOGO
Calendaring : Migration - 00089664 | Acknowledge | Role | CTSU Finance | 2017-04-17 | 136 |  | N | 00089664
Calendaring : Migration - 00105810 | Acknowledge | Role | CTSU Finance | 2017-04-17 | 136 |  | N | 00105810
Pre-Award Financial - 00125566 | Final Budget | Role | CTSU Finance | 2017-04-17 | 0 | 2017-02-21 | N | 00125566
Pre-Award Financial - SCHIOPU-1 | Care Designations completed | Role | CTSU Finance | 2017-04-17 | 136 |  | N | SCHIOPU-1
Calendaring : Initial Calendar Build - 96-BESIRLI | Feasibility Approval Notice Received | User | Hess, Aaron | 2017-04-17 | 0 | 2017-04-17 | N | 00129820
Calendaring : Initial Calendar Build - 00128301 | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-04-17 | 14 | 2017-05-01 | N | 00128301
Calendaring : Initial Calendar Build - 00128301 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-04-17 | 14 | 2017-05-01 | N | 00128301
Pre-Award Financial - 00128157 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-04-18 | 0 | 2017-04-18 | N | 00128157
Pre-Award Financial - PLT-INF24-001 | Open to Accrual | Role | CTSU Administrator | 2017-04-18 | 135 |  | N | 00135388
CTSU Pre-Award v2 - 82-BOLLING | UFA Completed | Role | CTSU Coordinator | 2017-04-18 | 0 | 2017-04-18 | N | 82-BOLLING
CTSU Pre-Award v2 - 37-SILVER | Budget Negotiations | Role | CTSU Finance | 2017-04-18 | 135 |  | N | 37-SILVER
Pre-Award Financial - 2-MARSH | OnCore Budget Build | Role | CTSU Finance | 2017-04-18 | 135 |  | N | 2-MARSH
Pre-Award Financial - 44-MCUNE | Internal Budget Finished | Role | CTSU Finance | 2017-04-18 | 135 |  | N | 44-MCUNE
Calendaring : Migration - 00081004 | Assign to Analyst | User | Greene, Paula | 2017-04-18 | 63 | 2017-06-20 | N | 00081004
Calendaring : Initial Calendar Build - 00128157 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-04-18 | 1 | 2017-04-19 | N | 00128157
Calendaring : Initial Calendar Build - 00128743 | Submit Calendar Build Request and Docs to Nimblify 04/18/17 | User | Hess, Aaron | 2017-04-18 | 0 | 2017-04-18 | N | 00128743
Calendaring : Initial Calendar Build - FENNER-1 | Feasibility Approval Notice Received | User | Hess, Aaron | 2017-04-18 | 0 | 2017-04-18 | N | FENNER-1
Calendaring : Amendment Checklist & Process - 00119399 | Assign to Analyst | User | Hodges, Lynda | 2017-04-18 | 0 | 2017-04-18 | N | 00119399
Pre-Award Financial - 00125022 | PAN Released | User | Oliver, Amy | 2017-04-18 | 135 |  | N | 00125022
Calendaring : Initial Calendar Build - 00128157 | Feasibility Approval Notice Received | User | Radenbaugh, Pauline | 2017-04-18 | 1 | 2017-04-19 | N | 00128157
Pre-Award Financial - 00124920 | OnCore Budget Build | User | Yunk, Jason | 2017-04-18 | 44 | 2017-06-01 | N | 00124920
Pre-Award Financial - 76-KHANNA | Feasibility w/Documents received | Role | CTSU Administrator | 2017-04-19 | 43 | 2017-06-01 | N | 00131837
Pre-Award Financial - 00128743 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-04-19 | 5 | 2017-04-24 | N | 00128743
Pre-Award Financial - 00129427 | Intake Form Completed | Role | CTSU Coordinator | 2017-04-19 | 0 | 2017-04-19 | N | 00129427
Pre-Award Financial - 110-SCHIOPU | Intake Form Completed | Role | CTSU Coordinator | 2017-04-19 | 0 | 2017-04-19 | N | 00134444
Pre-Award Financial - 96-BESIRLI | IRB Application Submitted | Role | CTSU Coordinator | 2017-04-19 | 0 | 2017-04-19 | N | 00129820
CTSU Pre-Award - 314-PARK | UFA Completed | Role | CTSU Finance | 2017-04-19 | 0 | 2017-04-19 | N | 314-PARK
Pre-Award Financial - 00125566 | PAF routed | Role | CTSU Finance | 2017-04-19 | 0 | 2017-02-26 | N | 00125566
Pre-Award Financial - 00128743 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-04-19 | 0 | 2017-04-17 | N | 00128743
Pre-Award Financial - 2-MARSH | Calendar Released | Role | CTSU Finance | 2017-04-19 | 134 |  | N | 2-MARSH
Calendaring : Initial Calendar Build - 96-BESIRLI | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-04-19 | 0 | 2017-04-18 | N | 00129820
Calendaring : Initial Calendar Build - FENNER-1 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-04-19 | 0 | 2017-04-18 | N | FENNER-1
Calendaring : Amendment Checklist & Process - 00119399 | ** Footnote Edits | User | Hodges, Lynda | 2017-04-19 | 5 | 2017-04-24 | N | 00119399
Calendaring : Amendment Checklist & Process - 00119399 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Hodges, Lynda | 2017-04-19 | 0 | 2017-04-18 | N | 00119399
Pre-Award Financial - 00124920 | Calendar Released | User | Oliver, Amy | 2017-04-19 | 68 | 2017-06-26 | N | 00124920
Calendaring : Initial Calendar Build - 00128157 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-04-19 | 0 | 2017-04-19 | N | 00128157
Calendaring : Initial Calendar Build - 96-BESIRLI | Assign to Analyst | User | Radenbaugh, Pauline | 2017-04-19 | 0 | 2017-04-18 | N | 00129820
Pre-Award Financial - 69-KHANNA | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-04-20 | 133 |  | N | 69-KHANNA
Pre-Award Financial - 77-CONJEEVARAM | Feasibility w/Documents received | Role | CTSU Administrator | 2017-04-20 | 133 |  | N | 77-CONJEEVARAM
Pre-Award Financial - 00128157 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-04-20 | 11 | 2017-05-01 | N | 00128157
Pre-Award Financial - 111-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-04-20 | 0 | 2017-04-20 | N | 111-HIGGINS
Pre-Award Financial - 112-FLAHERTY | Intake Form Completed | Role | CTSU Coordinator | 2017-04-20 | 0 | 2017-04-20 | N | 112-FLAHERTY
Calendaring : Initial Calendar Build - 27-WALKOVICH | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-04-20 | 18 | 2017-05-08 | N | 00127988
Pre-Award Financial - 00128157 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-04-20 | 14 | 2017-05-04 | N | 00128157
Calendaring : Initial Calendar Build - FENNER-1 | Assign to Analyst | User | Hess, Aaron | 2017-04-20 | 0 | 2017-04-18 | N | FENNER-1
Pre-Award Financial - 00125794 | PAN Released | User | Oliver, Amy | 2017-04-20 | 68 | 2017-06-27 | N | 00125794
Pre-Award Financial - 00127537 | PAN Released | User | Oliver, Amy | 2017-04-20 | 54 | 2017-06-13 | N | 00127537
Pre-Award Financial - 00128531 | OnCore Budget Build | User | Yunk, Jason | 2017-04-20 | 95 | 2017-07-24 | N | 00128531
Calendaring : Initial Calendar Build - 00128743 | Nimblify Build is Complete & Ready for Import | Role | CRAO | 2017-04-21 | 4 | 2017-04-25 | N | 00128743
Calendaring : Migration - 00100501 | Nimblify Build is Complete & Ready for Import | Role | CRAO | 2017-04-21 | 0 | 2017-04-21 | N | 00100501
Pre-Award Financial - 110-SCHIOPU | Sponsor Reach out | Role | CTSU Coordinator | 2017-04-21 | 0 | 2017-04-21 | N | 00134444
Cal Update : h.121246 (add unsched) | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance | 2017-04-21 | 0 | 2017-04-21 | N | 00121246
Cal Update : h.121246 (add unsched) | Submit Update Request(s) | Role | CTSU Finance | 2017-04-21 | 0 | 2017-04-21 | N | 00121246
Calendaring : Updates ( per Archie, 4.21 ) // h. 122152 | Submit Update Request(s) | Role | CTSU Finance | 2017-04-21 | 0 | 2017-04-21 | N | 00122152
Calendaring : Updates ( per Archie, 4.21 ) // h. 122153 | ** Other Request(s) | Role | CTSU Finance | 2017-04-21 | 0 | 2017-04-21 | N | 00122153
Calendaring : Updates ( per Archie, 4.21 ) // h. 122153 | Submit Update Request(s) | Role | CTSU Finance | 2017-04-21 | 0 | 2017-04-21 | N | 00122153
Pre-Award Financial - 44-MCUNE | PI approved Budget | Role | CTSU Finance | 2017-04-21 | 132 |  | N | 44-MCUNE
Pre-Award Financial - SCHIOPU-1 | Internal Budget Finished | Role | CTSU Finance | 2017-04-21 | 132 |  | N | SCHIOPU-1
Calendaring : Amendment Checklist & Process - 00119399 | Update RSH Source in MBECT | User | Hodges, Lynda | 2017-04-21 | 0 | 2017-04-18 | N | 00119399
Pre-Award Financial - 00128531 | Calendar Released | User | Oliver, Amy | 2017-04-21 | 111 | 2017-08-10 | N | 00128531
Calendaring : Initial Calendar Build - 00128157 | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-04-21 | 5 | 2017-04-26 | N | 00128157
Calendaring : Initial Calendar Build - CIP-1403 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-04-21 | 0 | 2017-04-21 | N | 00128253
Calendaring : Migration - 00081004 | Attach Build Notes and MBECT Calendar Reference ( as Protocol Docs ) | User | van Dijk, Tim | 2017-04-21 | 61 | 2017-06-21 | N | 00081004
Calendaring : Migration - 00081004 | Complete Calendar ( ie. Flag as Ready for Financials ) | User | van Dijk, Tim | 2017-04-21 | 115 | 2017-08-14 | N | 00081004
Calendaring : Migration - 00081004 | Import + Michiganize, including Entry of Care Designations & Comments per Current Approved MBECT Calendar | User | van Dijk, Tim | 2017-04-21 | 61 | 2017-06-21 | N | 00081004
Pre-Award Financial - 00124920 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-04-22 | 131 |  | N | 00124920
Pre-Award Financial - 2-MARSH | PI Signoff in OnCore | Role | CTSU Administrator | 2017-04-22 | 131 |  | N | 2-MARSH
Calendaring : Initial Calendar Build - FENNER-1 | Nimblify Build is Complete & Ready for Import | User | Hess, Aaron | 2017-04-22 | 131 |  | N | FENNER-1
Calendaring : Initial Calendar Build - 00128157 | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-04-22 | 16 | 2017-05-08 | N | 00128157
Calendaring : Initial Calendar Build - 00128157 | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-04-22 | 0 | 2017-04-20 | N | 00128157
Calendaring : Initial Calendar Build - 27-WALKOVICH | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-04-22 | 19 | 2017-05-11 | N | 00127988
Calendaring : Initial Calendar Build - 27-WALKOVICH | Make Updates | User | Radenbaugh, Pauline | 2017-04-22 | 19 | 2017-05-11 | N | 00127988
Calendaring : Initial Calendar Build - 96-BESIRLI | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-04-22 | 0 | 2017-04-20 | N | 00129820
Calendaring : Initial Calendar Build - 96-BESIRLI | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-04-22 | 0 | 2017-04-19 | N | 00129820
Calendaring : Initial Calendar Build - 96-BESIRLI | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-04-22 | 3 | 2017-04-25 | N | 00129820
Pre-Award Financial - 00127356 | Final Budget | User | VanderElzen, Liz | 2017-04-22 | 131 |  | N | 00127356
Pre-Award Financial - 00130575 | Final Budget | User | VanderElzen, Liz | 2017-04-22 | 55 | 2017-06-16 | N | 00130575
Calendaring : Updates ( per Archie, 4.21 ) // h. 122152 | Assign to Analyst | Role | CRAO | 2017-04-23 | 3 | 2017-04-26 | N | 00122152
Calendaring : Migration - 00081004 | Acknowledge | Role | CTSU Finance | 2017-04-23 | 130 |  | N | 00081004
Pre-Award Financial - 00129851 | Final Budget | Role | CTSU Finance | 2017-04-23 | 0 | 2017-04-16 | N | 00129851
Pre-Award Financial - 12-HIGGINS | PAN Released | Role | CTSU Finance | 2017-04-23 | 130 |  | N | 12-HIGGINS
Pre-Award Financial - 30-FLAHERTY | Final Budget | Role | CTSU Finance | 2017-04-23 | 130 |  | N | 30-FLAHERTY
Pre-Award Financial - 44-MCUNE | Budget Negotiations | Role | CTSU Finance | 2017-04-23 | 130 |  | N | 44-MCUNE
Calendaring : Initial Calendar Build - FENNER-1 | Complete MCA / QCT | User | Hess, Aaron | 2017-04-23 | 130 |  | N | FENNER-1
Calendaring : Initial Calendar Build - FENNER-1 | Complete SVS & Pricing List ( Built & Coded ) | User | Hess, Aaron | 2017-04-23 | 130 |  | N | FENNER-1
Calendaring : Initial Calendar Build - 00128157 | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-04-23 | 10 | 2017-05-03 | N | 00128157
Calendaring : Initial Calendar Build - 00128157 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-04-23 | 10 | 2017-05-03 | N | 00128157
Calendaring : Initial Calendar Build - 00128743 | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-04-23 | 4 | 2017-04-27 | N | 00128743
Calendaring : Initial Calendar Build - 00128743 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-04-23 | 4 | 2017-04-27 | N | 00128743
Calendaring : Updates ( per Archie, 4.21 ) // h. 122153 | Assign to Analyst |  |  | 2017-04-23 | 3 | 2017-04-26 | N | 00122153
Pre-Award Financial - 00124920 | Open to Accrual | Role | CTSU Administrator | 2017-04-24 | 129 |  | N | 00124920
Pre-Award Financial - 00128531 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-04-24 | 129 |  | N | 00128531
Pre-Award Financial - 2-MARSH | Open to Accrual | Role | CTSU Administrator | 2017-04-24 | 129 |  | N | 2-MARSH
Pre-Award Financial - 81-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-04-24 | 129 |  | N | 81-HIGGINS
Pre-Award Financial - 81-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator | 2017-04-24 | 129 |  | N | 81-HIGGINS
Pre-Award Financial - 81-HIGGINS | UFA Completed | Role | CTSU Coordinator | 2017-04-24 | 129 |  | N | 81-HIGGINS
Calendaring : Initial Calendar Build - 00128301 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-04-24 | 21 | 2017-05-15 | N | 00128301
Calendaring : Initial Calendar Build - 27-WALKOVICH | Acknowledge | Role | CTSU Finance | 2017-04-24 | 21 | 2017-05-15 | N | 00127988
Pre-Award Financial - MENEES-1 | Initiate Post-Award Task List | Role | CTSU Finance | 2017-04-24 | 129 |  | N | MENEES-1
Pre-Award Financial - SCHIOPU-1 | PI approved Budget | Role | CTSU Finance | 2017-04-24 | 129 |  | N | SCHIOPU-1
Calendaring : Initial Calendar Build - FENNER-1 | Attach Build Notes ( as Protocol Doc ) | User | Hess, Aaron | 2017-04-24 | 129 |  | N | FENNER-1
Calendaring : Initial Calendar Build - FENNER-1 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hess, Aaron | 2017-04-24 | 129 |  | N | FENNER-1
Pre-Award Financial - MENEES-1 | PAN Released | User | Oliver, Amy | 2017-04-24 | 129 |  | N | MENEES-1
Calendaring : Initial Calendar Build - 00127356 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-04-24 | 1 | 2017-04-25 | N | 00127356
Calendaring : Initial Calendar Build - 96-BESIRLI | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-04-24 | 1 | 2017-04-25 | N | 00129820
Calendaring : Initial Calendar Build - 96-BESIRLI | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-04-24 | 1 | 2017-04-25 | N | 00129820
Calendaring : Initial Calendar Build - CIP-1403 | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-04-24 | 0 | 2017-04-21 | N | 00128253
Calendaring : Initial Calendar Build - CIP-1403 | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-04-24 | 0 | 2017-04-24 | N | 00128253
Pre-Award Financial - 00127356 | PAF routed | User | VanderElzen, Liz | 2017-04-24 | 129 |  | N | 00127356
Pre-Award Financial - 00130575 | PAF routed | User | VanderElzen, Liz | 2017-04-24 | 64 | 2017-06-27 | N | 00130575
Calendaring : Initial Calendar Build - 00109407 | Feasibility Approval Notice Received | Role | CRAO | 2017-04-25 | 0 | 2017-04-25 | N | 00109407
Calendaring : Initial Calendar Build - 00113042 | Feasibility Approval Notice Received | Role | CRAO | 2017-04-25 | 0 | 2017-04-25 | N | 00113042
Pre-Award Financial - 00123861 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-04-25 | 24 | 2017-05-19 | N | 00123861
Pre-Award Financial - 00129427 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-04-25 | 0 | 2017-04-25 | N | 00129427
Calendaring : Initial Calendar Build - 00127505 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-04-25 | 22 | 2017-05-17 | N | 00127505
Pre-Award Financial - 00123861 | OnCore Budget Build | Role | CTSU Finance | 2017-04-25 | 0 | 2017-04-25 | N | 00123861
Pre-Award Financial - 00129851 | PAF routed | Role | CTSU Finance | 2017-04-25 | 0 | 2017-04-17 | N | 00129851
Pre-Award Financial - 30-FLAHERTY | PAF routed | Role | CTSU Finance | 2017-04-25 | 128 |  | N | 30-FLAHERTY
Calendaring : Initial Calendar Build - 00109407 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-04-25 | 0 | 2017-04-25 | N | 00109407
Calendaring : Initial Calendar Build - 00113042 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-04-25 | 0 | 2017-04-25 | N | 00113042
Calendaring : Initial Calendar Build - 00120786 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-04-25 | 0 | 2017-04-25 | N | 00120786
Calendaring : Initial Calendar Build - 00127505 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-04-25 | 0 | 2017-04-25 | N | 00127505
Calendaring : Initial Calendar Build - 00129427 2 | Feasibility Approval Notice Received | User | Radenbaugh, Pauline | 2017-04-25 | 0 | 2017-04-25 | N | 00129427
Pre-Award Financial - 00125425 | OnCore Budget Build | User | Yunk, Jason | 2017-04-25 | 41 | 2017-06-05 | N | 00125425
Pre-Award Financial - 00127136 | OnCore Budget Build | User | Yunk, Jason | 2017-04-25 | 48 | 2017-06-12 | N | 00127136
Calendaring : Updates ( per Archie, 4.21 ) // h. 122152 | ** Request for Clarification | User | Benton, Archie | 2017-04-26 | 8 | 2017-05-04 | N | 00122152
Calendaring : Updates ( per Archie, 4.21 ) // h. 122153 | ** Request for Clarification | User | Benton, Archie | 2017-04-26 | 8 | 2017-05-04 | N | 00122153
Pre-Award Financial - 00128531 | Open to Accrual | Role | CTSU Administrator | 2017-04-26 | 127 |  | N | 00128531
Pre-Award Financial - 00123861 | Calendar Released | Role | CTSU Finance | 2017-04-26 | 0 | 2017-04-25 | N | 00123861
Pre-Award Financial - 34-MARSH | Final Budget | Role | CTSU Finance | 2017-04-26 | 127 |  | N | 34-MARSH
Pre-Award Financial - SCHIOPU-1 | Budget Negotiations | Role | CTSU Finance | 2017-04-26 | 127 |  | N | SCHIOPU-1
Calendaring : Initial Calendar Build - KCHOU001 | Feasibility Approval Notice Received | User | Greene, Paula | 2017-04-26 | 0 | 2017-04-26 | N | 00130004
Calendaring : Updates ( per Archie, 4.21 ) // h. 122152 | ** Other Request(s) | User | LaVasseur, Kristen | 2017-04-26 | 0 | 2017-04-26 | N | 00122152
Calendaring : Initial Calendar Build - 00125022 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Oliver, Amy | 2017-04-26 | 42 | 2017-06-07 | N | 00125022
Pre-Award Financial - 00125425 | Calendar Released | User | Oliver, Amy | 2017-04-26 | 48 | 2017-06-13 | N | 00125425
Pre-Award Financial - 00125786 | PAN Released | User | Oliver, Amy | 2017-04-26 | 71 | 2017-07-06 | N | 00125786
Pre-Award Financial - 00127136 | Calendar Released | User | Oliver, Amy | 2017-04-26 | 61 | 2017-06-26 | N | 00127136
Calendaring : Initial Calendar Build - 00125022 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-04-26 | 0 | 2017-04-25 | N | 00125022
Calendaring : Initial Calendar Build - 00128301 | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-04-26 | 19 | 2017-05-15 | N | 00128301
Calendaring : Initial Calendar Build - 00128301 | Make Updates | User | Radenbaugh, Pauline | 2017-04-26 | 19 | 2017-05-15 | N | 00128301
Calendaring : Initial Calendar Build - 00118461 | Feasibility Approval Notice Received | Role | CRAO | 2017-04-27 | 0 | 2017-04-27 | N | 00118461
Calendaring : Initial Calendar Build - 00127356 | Complete SVS & Pricing List ( Built & Coded ) | Role | CRAO | 2017-04-27 | 0 | 2017-04-07 | N | 00127356
Pre-Award Financial - 00123861 | Open to Accrual | Role | CTSU Administrator | 2017-04-27 | 22 | 2017-05-19 | N | 00123861
Pre-Award Financial - 77-CONJEEVARAM | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-04-27 | 126 |  | N | 77-CONJEEVARAM
Pre-Award Financial - 00129427 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-04-27 | 5 | 2017-05-02 | N | 00129427
Pre-Award Financial - 00128743 | Billing Calendar Received | Role | CTSU Finance | 2017-04-27 | 0 | 2017-04-27 | N | 00128743
Pre-Award Financial - 00129427 | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-04-27 | 13 | 2017-05-10 | N | 00129427
Calendaring : Initial Calendar Build - 00124839 | Feasibility Approval Notice Received | User | Greene, Paula | 2017-04-27 | 0 | 2017-04-27 | N | 00124839
Calendaring : Initial Calendar Build - 00124839 | Assign to Analyst | User | Hess, Aaron | 2017-04-27 | 0 | 2017-04-27 | N | 00124839
Calendaring : Initial Calendar Build - 00124839 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-04-27 | 0 | 2017-04-27 | N | 00124839
Pre-Award Financial - 00122254 | PAN Released | User | Oliver, Amy | 2017-04-27 | 126 |  | N | 00122254
Pre-Award Financial - 00127505 | PAN Released | User | Oliver, Amy | 2017-04-27 | 105 | 2017-08-10 | N | 00127505
Pre-Award Financial - 00129427 | Request MCRU Budget | User | Oliver, Amy | 2017-04-27 | 13 | 2017-05-10 | N | 00129427
Calendaring : Initial Calendar Build - 00127356 | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-04-27 | 0 | 2017-04-25 | N | 00127356
Calendaring : Initial Calendar Build - 00127356 | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-04-27 | 0 | 2017-04-25 | N | 00127356
Calendaring : Initial Calendar Build - 00127505 | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-04-27 | 26 | 2017-05-23 | N | 00127505
Calendaring : Initial Calendar Build - 00127505 | Make Updates | User | Radenbaugh, Pauline | 2017-04-27 | 26 | 2017-05-23 | N | 00127505
Calendaring : Initial Calendar Build - 00129427 2 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-04-27 | 0 | 2017-04-25 | N | 00129427
Calendaring : Initial Calendar Build - 00129427 2 | Submit Calendar Build Request and Docs to Nimblify | User | Radenbaugh, Pauline | 2017-04-27 | 0 | 2017-04-25 | N | 00129427
Calendaring : Initial Calendar Build - 00128531 | Assign to Analyst | User | Zahs, Brian | 2017-04-27 | 54 | 2017-06-20 | N | 00128531
Calendaring : Initial Calendar Build - 00108880 | Feasibility Approval Notice Received | Role | CRAO | 2017-04-28 | 2 | 2017-04-30 | N | 00108880
Calendaring : Initial Calendar Build - 00109407 | Nimblify Build is Complete & Ready for Import | Role | CRAO | 2017-04-28 | 3 | 2017-05-01 | N | 00109407
Calendaring : Initial Calendar Build - 00113042 | Nimblify Build is Complete & Ready for Import | Role | CRAO | 2017-04-28 | 0 | 2017-04-28 | N | 00113042
Calendaring : Initial Calendar Build - 00120786 | Feasibility Approval Notice Received | Role | CRAO | 2017-04-28 | 0 | 2017-04-28 | N | 00120786
Calendaring : Initial Calendar Build - 00120786 | Nimblify Build is Complete & Ready for Import | Role | CRAO | 2017-04-28 | 0 | 2017-04-28 | N | 00120786
Calendaring : Initial Calendar Build - 00128173 | Feasibility Approval Notice Received | Role | CRAO | 2017-04-28 | 2 | 2017-04-30 | N | 00128173
Calendaring : Initial Calendar Build - 97-KALES | Feasibility Approval Notice Received | Role | CRAO | 2017-04-28 | 0 | 2017-04-28 | N | 97-KALES
Pre-Award Financial - 00108880 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-04-28 | 0 | 2017-04-28 | N | 00108880
Pre-Award Financial - 00128173 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-04-28 | 0 | 2017-04-28 | N | 00128173
Pre-Award Financial - 86-AUCHUS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-04-28 | 77 | 2017-07-14 | N | 00132700
Pre-Award Financial - 87-ORAL | Feasibility w/Documents received | Role | CTSU Administrator | 2017-04-28 | 21 | 2017-05-19 | N | 00130757
Pre-Award Financial - 131-LUGOGO | Intake Form Completed | Role | CTSU Coordinator | 2017-04-28 | 0 | 2017-04-28 | N | 131-LUGOGO
Pre-Award Financial - 179-LUGOGO | Intake Form Completed | Role | CTSU Coordinator | 2017-04-28 | 0 | 2017-04-28 | N | 179-LUGOGO
Pre-Award Financial - 86-AUCHUS | UFA Completed | Role | CTSU Coordinator | 2017-04-28 | 0 | 2017-04-07 | N | 00132700
Pre-Award Financial - 87-ORAL | Sponsor Reach out | Role | CTSU Coordinator | 2017-04-28 | 0 | 2017-04-28 | N | 00130757
Pre-Award Financial - 87-ORAL | UFA Completed | Role | CTSU Coordinator | 2017-04-28 | 0 | 2017-04-08 | N | 00130757
Calendaring : Amendment Checklist & Process - 00089260 2 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-04-28 | 0 | 2017-04-28 | N | 00089260
Calendaring : Amendment Checklist & Process - 00110881 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-04-28 | 17 | 2017-05-15 | N | 00110881
Calendaring : Initial Calendar Build - 00128301 | Acknowledge | Role | CTSU Finance | 2017-04-28 | 17 | 2017-05-15 | N | 00128301
Pre-Award Financial - 00128157 | Billing Calendar Received | Role | CTSU Finance | 2017-04-28 | 5 | 2017-05-03 | N | 00128157
Pre-Award Financial - 10-JAYASUNDERA | PAN Released | Role | CTSU Finance | 2017-04-28 | 125 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 34-MARSH | PAF routed | Role | CTSU Finance | 2017-04-28 | 125 |  | N | 34-MARSH
Pre-Award Financial - 9-JAYASUNDERA | PAN Released | Role | CTSU Finance | 2017-04-28 | 125 |  | N | 9-JAYASUNDERA
Calendaring : Initial Calendar Build - 00109407 | Assign to Analyst | User | Hess, Aaron | 2017-04-28 | 0 | 2017-04-25 | N | 00109407
Calendaring : Initial Calendar Build - 00113042 | Assign to Analyst | User | Hess, Aaron | 2017-04-28 | 0 | 2017-04-28 | N | 00113042
Calendaring : Initial Calendar Build - KCHOU001 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-04-28 | 0 | 2017-04-26 | N | 00130004
Calendaring : Amendment Checklist & Process - 00119399 | Complete Calendar and Document Approval | User | Hodges, Lynda | 2017-04-28 | 0 | 2017-04-25 | N | 00119399
Calendaring : Initial Calendar Build - 00127505 | Complete SVS & Pricing List ( Built & Coded ) | User | Hodges, Lynda | 2017-04-28 | 0 | 2017-03-16 | N | 00127505
Calendaring : Updates ( per Archie, 4.21 ) // h. 122152 | Make Update(s) | User | LaVasseur, Kristen | 2017-04-28 | 6 | 2017-05-04 | N | 00122152
Calendaring : Updates ( per Archie, 4.21 ) // h. 122152 | Re-Complete Calendar | User | LaVasseur, Kristen | 2017-04-28 | 6 | 2017-05-04 | N | 00122152
Calendaring : Updates ( per Archie, 4.21 ) // h. 122153 | Make Update(s) | User | LaVasseur, Kristen | 2017-04-28 | 6 | 2017-05-04 | N | 00122153
Calendaring : Initial Calendar Build - 00125022 | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-04-28 | 46 | 2017-06-13 | N | 00125022
Calendaring : Initial Calendar Build - 00125022 | Make Updates | User | Radenbaugh, Pauline | 2017-04-28 | 46 | 2017-06-13 | N | 00125022
Calendaring : Initial Calendar Build - 00127505 | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-04-28 | 0 | 2017-04-25 | N | 00127505
Calendaring : Initial Calendar Build - KCHOU001 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-04-28 | 0 | 2017-04-26 | N | 00130004
Calendaring : Initial Calendar Build - 00120786 | Assign to Analyst | User | Zahs, Brian | 2017-04-28 | 0 | 2017-04-28 | N | 00120786
Calendaring : Updates ( per Archie, 4.21 ) // h. 122153 | Re-Complete Calendar |  |  | 2017-04-28 | 6 | 2017-05-04 | N | 00122153
Pre-Award Financial - 00125425 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-04-29 | 76 | 2017-07-14 | N | 00125425
Pre-Award Financial - 00127136 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-04-29 | 124 |  | N | 00127136
Pre-Award Financial - 77-CONJEEVARAM | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-04-29 | 0 | 2017-04-18 | N | 77-CONJEEVARAM
Calendaring : Initial Calendar Build - 00127505 | Acknowledge | Role | CTSU Finance | 2017-04-29 | 39 | 2017-06-07 | N | 00127505
Pre-Award Financial - 77-CONJEEVARAM | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-04-29 | 124 |  | N | 77-CONJEEVARAM
Pre-Award Financial - 77-CONJEEVARAM | Request MCRU Budget | Role | CTSU Finance | 2017-04-29 | 124 |  | N | 77-CONJEEVARAM
Pre-Award Financial - 77-CONJEEVARAM | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-04-29 | 124 |  | N | 77-CONJEEVARAM
Calendaring : Initial Calendar Build - 00125022 | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-04-29 | 0 | 2017-04-29 | N | 00125022
Calendaring : Initial Calendar Build - 00125022 | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-04-29 | 0 | 2017-04-26 | N | 00125022
Calendaring : Initial Calendar Build - 00127356 | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-04-29 | 0 | 2017-04-25 | N | 00127356
Calendaring : Initial Calendar Build - 00127356 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-04-29 | 0 | 2017-04-25 | N | 00127356
Calendaring : Updates ( per Archie, 4.21 ) // h. 122152 | Acknowledge | User | Benton, Archie | 2017-04-30 | 0 | 2017-04-26 | N | 00122152
Calendaring : Initial Calendar Build - 00120786 | Import + Michiganize & Export Billing Grid for Determining Care Designations | Role | CRAO | 2017-04-30 | 0 | 2017-04-30 | N | 00120786
Calendaring : Initial Calendar Build - 00124839 | Nimblify Build is Complete & Ready for Import | Role | CRAO | 2017-04-30 | 1 | 2017-05-01 | N | 00124839
Calendaring : Updates ( per Archie, 4.21 ) // h. 122153 | Acknowledge | Role | CRAO | 2017-04-30 | 0 | 2017-04-26 | N | 00122153
Pre-Award Financial - 00108880 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-04-30 | 5 | 2017-05-05 | N | 00108880
Pre-Award Financial - 00128173 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-04-30 | 5 | 2017-05-05 | N | 00128173
Calendaring : Amendment Checklist & Process - 00119399 | Acknowledge | Role | CTSU Finance | 2017-04-30 | 0 | 2017-04-30 | N | 00119399
Calendaring : Initial Calendar Build - 00128743 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-04-30 | 46 | 2017-06-15 | N | 00128743
Calendaring : Initial Calendar Build - 00109407 | Attach Build Notes ( as Protocol Doc ) | User | Hess, Aaron | 2017-04-30 | 5 | 2017-05-05 | N | 00109407
Calendaring : Initial Calendar Build - 00109407 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hess, Aaron | 2017-04-30 | 2 | 2017-05-02 | N | 00109407
Calendaring : Initial Calendar Build - 00113042 | Attach Build Notes ( as Protocol Doc ) | User | Hess, Aaron | 2017-04-30 | 4 | 2017-05-04 | N | 00113042
Calendaring : Initial Calendar Build - 00113042 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hess, Aaron | 2017-04-30 | 9 | 2017-05-09 | N | 00113042
Calendaring : Initial Calendar Build - 00124839 | Complete MCA / QCT | User | Hess, Aaron | 2017-04-30 | 123 |  | N | 00124839
Calendaring : Initial Calendar Build - 00125022 | Acknowledge | User | Oliver, Amy | 2017-04-30 | 50 | 2017-06-19 | N | 00125022
Pre-Award Financial - 33-FLAHERTY | Final Budget | User | Oliver, Amy | 2017-04-30 | 32 | 2017-06-01 | N | 00129716
Pre-Award Financial - 69-KHANNA | Billing Calendar Received | User | Oliver, Amy | 2017-04-30 | 123 |  | N | 69-KHANNA
Calendaring : Amendment Checklist & Process - 00089260 2 | Assign to Analyst | User | Przykucki, Anne | 2017-04-30 | 1 | 2017-05-01 | N | 00089260
Calendaring : Initial Calendar Build - 00108880 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-04-30 | 0 | 2017-04-30 | N | 00108880
Calendaring : Initial Calendar Build - 00118461 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-04-30 | 0 | 2017-04-30 | N | 00118461
Calendaring : Initial Calendar Build - 00128173 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-04-30 | 0 | 2017-04-30 | N | 00128173
Calendaring : Initial Calendar Build - 00129427 2 | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-04-30 | 1 | 2017-05-01 | N | 00129427
Calendaring : Initial Calendar Build - 00129427 2 | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-04-30 | 0 | 2017-04-26 | N | 00129427
Calendaring : Initial Calendar Build - 00129427 2 | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-04-30 | 0 | 2017-04-28 | N | 00129427
Calendaring : Initial Calendar Build - 97-KALES | Assign to Analyst | User | Radenbaugh, Pauline | 2017-04-30 | 2 | 2017-05-02 | N | 97-KALES
Calendaring : Initial Calendar Build - 00128157 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-04-30 | 117 | 2017-08-25 | N | 00128157
Pre-Award Financial - 00108880 | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-04-30 | 61 | 2017-06-30 | N | 00108880
Pre-Award Financial - 00128173 | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-04-30 | 123 |  | N | 00128173
Calendaring : Initial Calendar Build - 00120786 | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian | 2017-04-30 | 123 |  | N | 00120786
Calendaring : Initial Calendar Build - 00128531 | Complete MCA / QCT | User | Zahs, Brian | 2017-04-30 | 0 | 2017-04-28 | N | 00128531
Calendaring : Initial Calendar Build - 00128531 | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian | 2017-04-30 | 0 | 2017-03-31 | N | 00128531
Pre-Award Financial - 00125425 | Open to Accrual | Role | CTSU Administrator | 2017-05-01 | 74 | 2017-07-14 | N | 00125425
Pre-Award Financial - 00127136 | Open to Accrual | Role | CTSU Administrator | 2017-05-01 | 122 |  | N | 00127136
Pre-Award Financial - 81-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-05-01 | 122 |  | N | 81-HIGGINS
Open to Accrual - 00125786 | IRB Approval | Role | CTSU Coordinator | 2017-05-01 | 0 | 2017-05-01 | N | 00125786
Calendaring : Initial Calendar Build - 96-BESIRLI | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-05-01 | 1 | 2017-05-02 | N | 00129820
Calendaring : Initial Calendar Build - FENNER-1 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-05-01 | 122 |  | N | FENNER-1
Pre-Award Financial - 00128743 | Planning Meeting Completed | Role | CTSU Finance | 2017-05-01 | 0 | 2017-05-01 | N | 00128743
Calendaring : Initial Calendar Build - 00108880 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-01 | 4 | 2017-05-05 | N | 00108880
Calendaring : Initial Calendar Build - 00113042 | Complete MCA / QCT | User | Hess, Aaron | 2017-05-01 | 8 | 2017-05-09 | N | 00113042
Calendaring : Initial Calendar Build - 00118461 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-01 | 4 | 2017-05-05 | N | 00118461
Calendaring : Initial Calendar Build - 00128173 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-01 | 4 | 2017-05-05 | N | 00128173
Calendaring : Initial Calendar Build - 97-KALES | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-01 | 4 | 2017-05-05 | N | 97-KALES
Calendaring : Amendment Checklist & Process - 00089260 2 | ** Footnote Edits | User | Przykucki, Anne | 2017-05-01 | 31 | 2017-06-01 | N | 00089260
Calendaring : Amendment Checklist & Process - 00089260 2 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Przykucki, Anne | 2017-05-01 | 31 | 2017-06-01 | N | 00089260
Calendaring : Amendment Checklist & Process - 00089260 2 | ** Visit Tolerance Edits | User | Przykucki, Anne | 2017-05-01 | 31 | 2017-06-01 | N | 00089260
Calendaring : Amendment Checklist & Process - 00089260 2 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Przykucki, Anne | 2017-05-01 | 25 | 2017-05-26 | N | 00089260
Calendaring : Initial Calendar Build - KCHOU001 | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-05-01 | 0 | 2017-04-26 | N | 00130004
Calendaring : Initial Calendar Build - KCHOU001 | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-05-01 | 0 | 2017-04-28 | N | 00130004
Calendaring : Initial Calendar Build - KCHOU001 | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-05-01 | 0 | 2017-05-01 | N | 00130004
Calendaring : Initial Calendar Build - 116-BRUMMETT | Feasibility Approval Notice Received | Role | CRAO | 2017-05-02 | 0 | 2017-05-02 | N | 00129418
Pre-Award Financial - 91-ELSE | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-02 | 121 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-02 | 121 |  | N | 92-AUCHUS
CTSU Pre-Award v2 - 140-CHUNG | Intake Form Completed | Role | CTSU Coordinator | 2017-05-02 | 0 | 2017-05-02 | N | 00133613
Pre-Award Financial - 91-ELSE | UFA Completed | Role | CTSU Coordinator | 2017-05-02 | 55 | 2017-06-26 | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | Sponsor Reach out | Role | CTSU Coordinator | 2017-05-02 | 121 |  | N | 92-AUCHUS
Pre-Award Financial - 92-AUCHUS | UFA Completed | Role | CTSU Coordinator | 2017-05-02 | 0 | 2017-04-16 | N | 92-AUCHUS
CTSU Pre-Award v2 - 37-SILVER | Final Budget | Role | CTSU Finance | 2017-05-02 | 121 |  | N | 37-SILVER
Calendaring : Specification Update Request(s) - 00128322 | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance | 2017-05-02 | 0 | 2017-05-02 | N | 00128322
Pre-Award Financial - 00128157 | Planning Meeting Completed | Role | CTSU Finance | 2017-05-02 | 34 | 2017-06-05 | N | 00128157
Calendaring : Initial Calendar Build - 00124839 | Attach Build Notes ( as Protocol Doc ) | User | Hess, Aaron | 2017-05-02 | 121 |  | N | 00124839
Calendaring : Initial Calendar Build - 00124839 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hess, Aaron | 2017-05-02 | 1 | 2017-05-03 | N | 00124839
Calendaring : Initial Calendar Build - 116-BRUMMETT | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-02 | 3 | 2017-05-05 | N | 00129418
Cal Update : h.121246 (add unsched) | Make Update(s) | User | LaVasseur, Kristen | 2017-05-02 | 0 | 2017-04-26 | N | 00121246
Cal Update : h.121246 (add unsched) | Re-Complete Calendar | User | LaVasseur, Kristen | 2017-05-02 | 0 | 2017-04-26 | N | 00121246
Calendaring : Initial Calendar Build - 116-BRUMMETT | Assign to Analyst | User | Munasinghe, Sadeepa | 2017-05-02 | 10 | 2017-05-12 | N | 00129418
Pre-Award Financial - 33-FLAHERTY | PAF routed | User | Oliver, Amy | 2017-05-02 | 34 | 2017-06-05 | N | 00129716
Calendaring : Amendment Checklist & Process - 00089260 2 | ** Items/Services : Addition or Removal of Procedures / Events | User | Przykucki, Anne | 2017-05-02 | 30 | 2017-06-01 | N | 00089260
Calendaring : Initial Calendar Build - 00128157 | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-05-02 | 121 |  | N | 00128157
Calendaring : Initial Calendar Build - 00128157 | Make Updates | User | Radenbaugh, Pauline | 2017-05-02 | 121 |  | N | 00128157
Calendaring : Initial Calendar Build - 00128743 | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-05-02 | 48 | 2017-06-19 | N | 00128743
Calendaring : Initial Calendar Build - 00129427 2 | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-05-02 | 0 | 2017-05-01 | N | 00129427
Calendaring : Initial Calendar Build - 00129427 2 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-05-02 | 0 | 2017-05-01 | N | 00129427
Pre-Award Financial - 00125022 | OnCore Budget Build | User | Yunk, Jason | 2017-05-02 | 113 | 2017-08-23 | N | 00125022
Pre-Award Financial - 00129652 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-03 | 23 | 2017-05-26 | N | 00129652
Pre-Award Financial - 96-BESIRLI | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-03 | 0 | 2017-04-17 | N | 00129820
Pre-Award Financial - 00129652 | Sponsor Reach out | Role | CTSU Coordinator | 2017-05-03 | 15 | 2017-05-18 | N | 00129652
Pre-Award Financial - 00129652 | UFA Completed | Role | CTSU Coordinator | 2017-05-03 | 0 | 2017-04-12 | N | 00129652
Pre-Award Financial - 142-FLAHERTY | Intake Form Completed | Role | CTSU Coordinator | 2017-05-03 | 0 | 2017-05-03 | N | 142-FLAHERTY
Pre-Award Financial - 147-SCHIOPU | Intake Form Completed | Role | CTSU Coordinator | 2017-05-03 | 0 | 2017-05-03 | N | 00131329
Pre-Award Financial - 81-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-05-03 | 120 |  | N | 81-HIGGINS
Pre-Award Financial - 81-HIGGINS | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-05-03 | 120 |  | N | 81-HIGGINS
Pre-Award Financial - 81-HIGGINS | Request MCRU Budget | Role | CTSU Finance | 2017-05-03 | 120 |  | N | 81-HIGGINS
Pre-Award Financial - 81-HIGGINS | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-05-03 | 120 |  | N | 81-HIGGINS
Calendaring : Initial Calendar Build - FENNER-1 | Complete Calendar ( ie. Ready for Financials ) | User | Hess, Aaron | 2017-05-03 | 120 |  | N | FENNER-1
Calendaring : Initial Calendar Build - FENNER-1 | Make Updates | User | Hess, Aaron | 2017-05-03 | 120 |  | N | FENNER-1
Amendment Checklist & Process - 113141 AME per Ginger | Request Care Designations | User | LaVasseur, Kristen | 2017-05-03 | 0 | 2017-05-03 | N | 00113141
Calendaring : Initial Calendar Build - 00108880 | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-05-03 | 13 | 2017-05-16 | N | 00108880
Pre-Award Financial - 00125022 | Calendar Released | User | Oliver, Amy | 2017-05-03 | 112 | 2017-08-23 | N | 00125022
Pre-Award Financial - 00125566 | PAN Released | User | Oliver, Amy | 2017-05-03 | 57 | 2017-06-29 | N | 00125566
Calendaring : Amendment Checklist & Process - 00089260 2 | ** Other | User | Przykucki, Anne | 2017-05-03 | 29 | 2017-06-01 | N | 00089260
Calendaring : Amendment Checklist & Process - 00089260 2 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Przykucki, Anne | 2017-05-03 | 29 | 2017-06-01 | N | 00089260
Calendaring : Amendment Checklist & Process - 00089260 2 | ** Visits : Addition or Removal of Time Points | User | Przykucki, Anne | 2017-05-03 | 29 | 2017-06-01 | N | 00089260
Calendaring : Amendment Checklist & Process - 00089260 2 | Request Care Designations | User | Przykucki, Anne | 2017-05-03 | 30 | 2017-06-02 | N | 00089260
Calendaring : Amendment Checklist & Process - 00089260 2 | Update RSH Source in MBECT | User | Przykucki, Anne | 2017-05-03 | 30 | 2017-06-02 | N | 00089260
Calendaring : Initial Calendar Build - 00108880 | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-05-03 | 5 | 2017-05-08 | N | 00108880
Calendaring : Initial Calendar Build - 00118461 | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-05-03 | 5 | 2017-05-08 | N | 00118461
Calendaring : Initial Calendar Build - 00128173 | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-05-03 | 5 | 2017-05-08 | N | 00128173
Calendaring : Initial Calendar Build - 00128173 | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-05-03 | 0 | 2017-05-03 | N | 00128173
Calendaring : Initial Calendar Build - 96-BESIRLI | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-05-03 | 0 | 2017-05-03 | N | 00129820
Calendaring : Initial Calendar Build - 96-BESIRLI | Make Updates | User | Radenbaugh, Pauline | 2017-05-03 | 0 | 2017-05-03 | N | 00129820
Calendaring : Initial Calendar Build - 97-KALES | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-05-03 | 9 | 2017-05-12 | N | 97-KALES
Calendaring : Initial Calendar Build - 97-KALES | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-05-03 | 0 | 2017-05-02 | N | 97-KALES
Calendaring : Initial Calendar Build - KCHOU001 | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-05-03 | 0 | 2017-05-01 | N | 00130004
Calendaring : Initial Calendar Build - KCHOU001 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-05-03 | 0 | 2017-05-01 | N | 00130004
Cal Update : h.121246 (add unsched) | Acknowledge | User | Benton, Archie | 2017-05-04 | 0 | 2017-04-26 | N | 00121246
Calendaring : Updates ( per Archie, 4.21 ) // h. 122152 | Care Designation | Role | CRAO | 2017-05-04 | 0 | 2017-05-04 | N | 00122152
Pre-Award Financial - 155-ORAL | Intake Form Completed | Role | CTSU Coordinator | 2017-05-04 | 0 | 2017-05-04 | N | 00130803
CTSU Pre-Award v2 - 37-SILVER | PAF routed | Role | CTSU Finance | 2017-05-04 | 119 |  | N | 37-SILVER
Calendaring : Updates ( per Archie, 4.21 ) // h. 122153 | Care Designation | User | LaVasseur, Kristen | 2017-05-04 | 0 | 2017-05-04 | N | 00122153
Calendaring : Initial Calendar Build - 00108880 | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-05-04 | 8 | 2017-05-12 | N | 00108880
Calendaring : Initial Calendar Build - 00118461 | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-05-04 | 7 | 2017-05-11 | N | 00118461
Calendaring : Initial Calendar Build - 00128173 | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-05-04 | 6 | 2017-05-10 | N | 00128173
Calendaring : Initial Calendar Build - 97-KALES | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-05-04 | 6 | 2017-05-10 | N | 97-KALES
Calendaring : Initial Calendar Build - 00128157 | Acknowledge | User | VanderElzen, Liz | 2017-05-04 | 119 |  | N | 00128157
Calendaring : Initial Calendar Build - 00128743 | Acknowledge | User | VanderElzen, Liz | 2017-05-04 | 48 | 2017-06-21 | N | 00128743
Pre-Award Financial - 00128743 | Care Designations completed | User | VanderElzen, Liz | 2017-05-04 | 40 | 2017-06-13 | N | 00128743
Pre-Award Financial - 00125794 | OnCore Budget Build | User | Yunk, Jason | 2017-05-04 | 33 | 2017-06-06 | N | 00125794
Pre-Award Financial - 00127537 | OnCore Budget Build | User | Yunk, Jason | 2017-05-04 | 32 | 2017-06-05 | N | 00127537
BC : Initial Build - PLT-INF24-001 | Complete Calendar ( ie. Ready for Financials ) | Role | CRAO | 2017-05-05 | 0 | 2017-05-05 | N | 00135388
Calendaring : Initial Calendar Build - HUM00091711 | Feasibility Approval Notice Received | Role | CRAO | 2017-05-05 | 0 | 2017-05-05 | N | 00091711
Calendaring : Initial Calendar Build - HUM00091711 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO | 2017-05-05 | 0 | 2017-05-05 | N | 00091711
Pre-Award Financial - 00108880 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-05 | 0 | 2017-04-28 | N | 00108880
Pre-Award Financial - 00128173 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-05 | 0 | 2017-04-28 | N | 00128173
CTSU Pre-Award v2 - 37-SILVER | OnCore Budget Build | Role | CTSU Finance | 2017-05-05 | 118 |  | N | 37-SILVER
Calendaring : Initial Calendar Build - 96-BESIRLI | Acknowledge | Role | CTSU Finance | 2017-05-05 | 0 | 2017-05-04 | N | 00129820
Calendaring : Initial Calendar Build - FENNER-1 | Acknowledge | Role | CTSU Finance | 2017-05-05 | 118 |  | N | FENNER-1
Calendaring : Specification Update Request(s) - 00117851 | ** Structural Edits | Role | CTSU Finance | 2017-05-05 | 0 | 2017-05-05 | N | 00117851
Calendaring : Specification Update Request(s) - 00117851 | Submit Update Request(s) | Role | CTSU Finance | 2017-05-05 | 0 | 2017-05-05 | N | 00117851
Calendaring : Specification Update Request(s) - 00122815 | ** Structural Edits | Role | CTSU Finance | 2017-05-05 | 0 | 2017-05-05 | N | 00122815
Calendaring : Specification Update Request(s) - 00122815 | Submit Update Request(s) | Role | CTSU Finance | 2017-05-05 | 0 | 2017-05-05 | N | 00122815
Calendaring : Specification Update Request(s) - 00128322 | Submit Update Request(s) | Role | CTSU Finance | 2017-05-05 | 0 | 2017-05-05 | N | 00128322
Calendaring : Initial Calendar Build - 00126707 | Attach Build Notes ( as Protocol Doc ) | User | LaVasseur, Kristen | 2017-05-05 | 0 | 2017-05-05 | N | 00126707
Calendaring : Initial Calendar Build - 00126707 | Complete MCA / QCT | User | LaVasseur, Kristen | 2017-05-05 | 0 | 2017-05-05 | N | 00126707
Calendaring : Initial Calendar Build - 116-BRUMMETT | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-05-05 | 118 |  | N | 00129418
Calendaring : Initial Calendar Build - 116-BRUMMETT | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-05-05 | 7 | 2017-05-12 | N | 00129418
Calendaring : Initial Calendar Build - 116-BRUMMETT | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-05-05 | 7 | 2017-05-12 | N | 00129418
Pre-Award Financial - 00125794 | Calendar Released | User | Oliver, Amy | 2017-05-05 | 52 | 2017-06-26 | N | 00125794
Pre-Award Financial - 00127537 | Calendar Released | User | Oliver, Amy | 2017-05-05 | 41 | 2017-06-15 | N | 00127537
Pre-Award Financial - 00129427 | Billing Calendar Received | User | Oliver, Amy | 2017-05-05 | 0 | 2017-05-01 | N | 00129427
Pre-Award Financial - 00128157 | Care Designations completed | User | VanderElzen, Liz | 2017-05-05 | 112 | 2017-08-25 | N | 00128157
Calendaring : Initial Calendar Build - 96-BESIRLI | CRAO Approval Issue & Documented | Role | CRAO | 2017-05-06 | 1 | 2017-05-07 | N | 00129820
Pre-Award Financial - 00125022 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-06 | 117 |  | N | 00125022
CTSU Pre-Award v2 - 37-SILVER | Calendar Released | Role | CTSU Finance | 2017-05-06 | 117 |  | N | 37-SILVER
Calendaring : Initial Calendar Build - 00108880 | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-05-06 | 10 | 2017-05-16 | N | 00108880
Calendaring : Initial Calendar Build - 00108880 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-05-06 | 10 | 2017-05-16 | N | 00108880
Calendaring : Initial Calendar Build - 00118461 | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-05-06 | 6 | 2017-05-12 | N | 00118461
Calendaring : Initial Calendar Build - 00118461 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-05-06 | 6 | 2017-05-12 | N | 00118461
Calendaring : Initial Calendar Build - 00128173 | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-05-06 | 6 | 2017-05-12 | N | 00128173
Calendaring : Initial Calendar Build - 00128173 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-05-06 | 6 | 2017-05-12 | N | 00128173
Calendaring : Initial Calendar Build - 97-KALES | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-05-06 | 6 | 2017-05-12 | N | 97-KALES
Calendaring : Initial Calendar Build - 97-KALES | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-05-06 | 6 | 2017-05-12 | N | 97-KALES
Calendaring : Initial Calendar Build - 00127356 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-05-06 | 117 |  | N | 00127356
Calendaring : Initial Calendar Build - 00120786 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Boyd, Collin | 2017-05-07 | 39 | 2017-06-15 | N | 00120786
Pre-Award Financial - 12-HIGGINS | OnCore Budget Build | Role | CTSU Finance | 2017-05-07 | 116 |  | N | 12-HIGGINS
Pre-Award Financial - 44-MCUNE | Final Budget | Role | CTSU Finance | 2017-05-07 | 116 |  | N | 44-MCUNE
Pre-Award Financial - 77-CONJEEVARAM | Billing Calendar Received | Role | CTSU Finance | 2017-05-07 | 116 |  | N | 77-CONJEEVARAM
Calendaring : Initial Calendar Build - 00109407 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Frasier, Lora | 2017-05-07 | 2 | 2017-05-09 | N | 00109407
Calendaring : Initial Calendar Build - 116-BRUMMETT | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-05-07 | 5 | 2017-05-12 | N | 00129418
Calendaring : Initial Calendar Build - 116-BRUMMETT | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-05-07 | 5 | 2017-05-12 | N | 00129418
Pre-Award Financial - 69-KHANNA | Care Designations completed | User | Oliver, Amy | 2017-05-07 | 116 |  | N | 69-KHANNA
Calendaring : Specification Update Request(s) - 00117851 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-05-07 | 60 | 2017-07-06 | N | 00117851
Calendaring : Specification Update Request(s) - 00122815 | Assign to Analyst | User | Zahs, Brian | 2017-05-07 | 116 |  | N | 00122815
Calendaring : Initial Calendar Build - 00122957 | Feasibility Approval Notice Received | Role | CRAO | 2017-05-08 | 0 | 2017-05-08 | N | 00124722
Calendaring : Initial Calendar Build - HUM00129276 | Feasibility Approval Notice Received | Role | CRAO | 2017-05-08 | 0 | 2017-05-08 | N | 00129276
Pre-Award Financial - 00125022 | Open to Accrual | Role | CTSU Administrator | 2017-05-08 | 115 |  | N | 00125022
Pre-Award Financial - 00125794 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-08 | 49 | 2017-06-26 | N | 00125794
Pre-Award Financial - 00127537 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-08 | 0 | 2016-07-07 | N | 00127537
Core Sponsor Documents for Study Feasibility & Start Up - General - 111-HIGGINS | Initial contact with sponsor | Role | CTSU Coordinator | 2017-05-08 | 0 | 2017-05-08 | N | 111-HIGGINS
Calendaring : Amendment Checklist & Process - 00089260 2 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance | 2017-05-08 | 25 | 2017-06-02 | N | 00089260
Calendaring : Initial Calendar Build - 00126707 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-05-08 | 3 | 2017-05-11 | N | 00126707
Pre-Award Financial - 12-HIGGINS | Calendar Released | Role | CTSU Finance | 2017-05-08 | 115 |  | N | 12-HIGGINS
Amendment Checklist & Process - 113141 AME per Ginger | Provide PI-Determined Care Designations ( +/- Feedback ) | User | Gladkowski, Ginger | 2017-05-08 | 0 | 2017-05-08 | N | 00113141
Calendaring : Initial Calendar Build - 00122957 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-08 | 0 | 2017-05-08 | N | 00124722
Calendaring : Initial Calendar Build - HUM00129276 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-08 | 0 | 2017-05-08 | N | 00129276
Pre-Award Financial - 00127356 | PAN Released | User | Oliver, Amy | 2017-05-08 | 115 |  | N | 00127356
Pre-Award Financial - 00130575 | PAN Released | User | Oliver, Amy | 2017-05-08 | 115 |  | N | 00130575
Calendaring : Initial Calendar Build - 00122957 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-05-08 | 0 | 2017-05-08 | N | 00124722
Calendaring : Initial Calendar Build - 00127356 | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-05-08 | 115 |  | N | 00127356
Calendaring : Initial Calendar Build - 00127356 | Make Updates | User | Radenbaugh, Pauline | 2017-05-08 | 115 |  | N | 00127356
Calendaring : Initial Calendar Build - HUM00091711 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-05-08 | 0 | 2017-05-08 | N | 00091711
Calendaring : Initial Calendar Build - HUM00091711 | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-05-08 | 4 | 2017-05-12 | N | 00091711
Pre-Award Financial - 00108880 | Billing Calendar Received | User | VanderElzen, Liz | 2017-05-08 | 8 | 2017-05-16 | N | 00108880
Pre-Award Financial - 00128173 | Billing Calendar Received | User | VanderElzen, Liz | 2017-05-08 | 12 | 2017-05-20 | N | 00128173
Pre-Award Financial - 00128743 | Internal Budget Finished | User | VanderElzen, Liz | 2017-05-08 | 39 | 2017-06-16 | N | 00128743
Calendaring : Initial Calendar Build - P-3058HELFRICH | Feasibility Approval Notice Received | Role | CRAO | 2017-05-09 | 0 | 2017-05-09 | N | 00129897
Calendaring : Initial Calendar Build - P-3073HELFRICH | Feasibility Approval Notice Received | Role | CRAO | 2017-05-09 | 0 | 2017-05-09 | N | 00128488
CTSU Pre-Award v2 - 37-SILVER | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-09 | 114 |  | N | 37-SILVER
Pre-Award Financial - 91-ELSE | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-05-09 | 114 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-05-09 | 114 |  | N | 92-AUCHUS
Pre-Award Financial - 170-SCHIOPU | Intake Form Completed | Role | CTSU Coordinator | 2017-05-09 | 0 | 2017-05-09 | N | 00134035
Calendaring : Initial Calendar Build - 00124839 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-05-09 | 0 | 2017-05-08 | N | 00124839
Pre-Award Financial - 00129851 | PAN Released | Role | CTSU Finance | 2017-05-09 | 28 | 2017-06-06 | N | 00129851
Pre-Award Financial - 30-FLAHERTY | PAN Released | Role | CTSU Finance | 2017-05-09 | 114 |  | N | 30-FLAHERTY
Pre-Award Financial - 44-MCUNE | PAF routed | Role | CTSU Finance | 2017-05-09 | 114 |  | N | 44-MCUNE
Calendaring : Initial Calendar Build - 00109407 | Complete Calendar ( ie. Ready for Financials ) | User | Hess, Aaron | 2017-05-09 | 21 | 2017-05-30 | N | 00109407
Calendaring : Initial Calendar Build - 00109407 | Make Updates | User | Hess, Aaron | 2017-05-09 | 21 | 2017-05-30 | N | 00109407
Calendaring : Initial Calendar Build - 00113042 | Complete Calendar ( ie. Ready for Financials ) | User | Hess, Aaron | 2017-05-09 | 0 | 2017-05-09 | N | 00113042
Calendaring : Initial Calendar Build - P-3058HELFRICH | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-09 | 114 |  | N | 00129897
Calendaring : Initial Calendar Build - P-3073HELFRICH | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-09 | 114 |  | N | 00128488
Calendaring : Initial Calendar Build - 00129427 2 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Oliver, Amy | 2017-05-09 | 22 | 2017-05-31 | N | 00129427
Pre-Award Financial - 00129427 | Planning Meeting Completed | User | Oliver, Amy | 2017-05-09 | 6 | 2017-05-15 | N | 00129427
Pre-Award Financial - 00128157 | Internal Budget Finished | User | VanderElzen, Liz | 2017-05-09 | 13 | 2017-05-22 | N | 00128157
Calendaring : Initial Calendar Build - 00120786 | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-05-09 | 45 | 2017-06-23 | N | 00120786
Calendaring : Initial Calendar Build - 00120786 | Make Updates | User | Zahs, Brian | 2017-05-09 | 45 | 2017-06-23 | N | 00120786
Calendaring : Initial Calendar Build - 71-RICE | Feasibility Approval Notice Received | Role | CRAO | 2017-05-10 | 0 | 2017-05-10 | N | 00134857
Pre-Award Financial - 00125794 | Open to Accrual | Role | CTSU Administrator | 2017-05-10 | 48 | 2017-06-27 | N | 00125794
Pre-Award Financial - 00127537 | Open to Accrual | Role | CTSU Administrator | 2017-05-10 | 61 | 2017-07-10 | N | 00127537
Pre-Award Financial - 00129427 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-10 | 0 | 2017-04-25 | N | 00129427
Pre-Award Financial - 110-SCHIOPU | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-10 | 75 | 2017-07-24 | N | 00134444
Pre-Award Financial - 71-RICE | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-05-10 | 0 | 2017-05-10 | N | 00134857
Open to Accrual - 00129820 | IRB Approval | Role | CTSU Coordinator | 2017-05-10 | 0 | 2017-05-10 | N | 00129820
Pre-Award Financial - SCHIOPU-1 | Final Budget | Role | CTSU Finance | 2017-05-10 | 113 |  | N | SCHIOPU-1
Calendaring : Initial Calendar Build - 00125798 | Feasibility Approval Notice Received | User | Greene, Paula | 2017-05-10 | 0 | 2017-05-10 | N | 00125798
Calendaring : Initial Calendar Build - P-3058HELFRICH | Assign to Analyst | User | Hess, Aaron | 2017-05-10 | 8 | 2017-05-18 | N | 00129897
Amendment Checklist & Process - 113141 AME per Ginger | Complete Calendar and Document Approval | User | LaVasseur, Kristen | 2017-05-10 | 12 | 2017-05-22 | N | 00113141
Calendaring : Initial Calendar Build - 00126707 | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-05-10 | 51 | 2017-06-30 | N | 00126707
Calendaring : Initial Calendar Build - P-3073HELFRICH | Assign to Analyst | User | Munasinghe, Sadeepa | 2017-05-10 | 0 | 2017-05-10 | N | 00128488
Calendaring : Amendment Checklist & Process - 00089260 2 | Complete Calendar and Document Approval | User | Przykucki, Anne | 2017-05-10 | 23 | 2017-06-02 | N | 00089260
Calendaring : Initial Calendar Build - HUM00091711 | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-05-10 | 5 | 2017-05-15 | N | 00091711
Calendaring : Initial Calendar Build - HUM00091711 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-05-10 | 5 | 2017-05-15 | N | 00091711
Calendaring : Initial Calendar Build - KCHOU001 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Stovall, Angela | 2017-05-10 | 20 | 2017-05-30 | N | 00130004
Calendaring : Initial Calendar Build - 00127356 | Acknowledge | User | VanderElzen, Liz | 2017-05-10 | 113 |  | N | 00127356
Pre-Award Financial - 00125786 | OnCore Budget Build | User | Yunk, Jason | 2017-05-10 | 26 | 2017-06-05 | N | 00125786
Pre-Award Financial - 44-MCUNE | OnCore Budget Build | User | Yunk, Jason | 2017-05-10 | 113 |  | N | 44-MCUNE
Calendaring : Initial Calendar Build - HUM00129276 | Assign to Analyst | User | van Dijk, Tim | 2017-05-10 | 0 | 2017-05-10 | N | 00129276
CTSU Pre-Award v2 - 37-SILVER | Open to Accrual | Role | CTSU Administrator | 2017-05-11 | 112 |  | N | 37-SILVER
Pre-Award Financial - 112-FLAHERTY | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-11 | 57 | 2017-07-07 | N | 112-FLAHERTY
Pre-Award Financial - 12-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-11 | 112 |  | N | 12-HIGGINS
Pre-Award Financial - 111-HIGGINS | UFA Completed | Role | CTSU Coordinator | 2017-05-11 | 0 | 2017-04-20 | N | 111-HIGGINS
Pre-Award Financial - 112-FLAHERTY | Sponsor Reach out | Role | CTSU Coordinator | 2017-05-11 | 56 | 2017-07-06 | N | 112-FLAHERTY
Pre-Award Financial - 112-FLAHERTY | UFA Completed | Role | CTSU Coordinator | 2017-05-11 | 50 | 2017-06-30 | N | 112-FLAHERTY
Pre-Award Financial - 180-HOFF | Intake Form Completed | Role | CTSU Coordinator | 2017-05-11 | 0 | 2017-05-11 | N | 00129450
Pre-Award Financial - 91-ELSE | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-05-11 | 112 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-05-11 | 112 |  | N | 92-AUCHUS
Pre-Award Financial - 00127988 | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-05-11 | 0 | 2017-05-11 | N | 00127988
Pre-Award Financial - 77-CONJEEVARAM | Planning Meeting Completed | Role | CTSU Finance | 2017-05-11 | 112 |  | N | 77-CONJEEVARAM
Pre-Award Financial - 81-HIGGINS | Billing Calendar Received | Role | CTSU Finance | 2017-05-11 | 112 |  | N | 81-HIGGINS
Pre-Award Financial - 91-ELSE | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-05-11 | 112 |  | N | 91-ELSE
Pre-Award Financial - 91-ELSE | Request MCRU Budget | Role | CTSU Finance | 2017-05-11 | 112 |  | N | 91-ELSE
Pre-Award Financial - 91-ELSE | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-05-11 | 112 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-05-11 | 112 |  | N | 92-AUCHUS
Pre-Award Financial - 92-AUCHUS | Request MCRU Budget | Role | CTSU Finance | 2017-05-11 | 112 |  | N | 92-AUCHUS
Pre-Award Financial - 92-AUCHUS | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-05-11 | 112 |  | N | 92-AUCHUS
Pre-Award Financial - HUM00129276 | Planning Meeting Completed | Role | CTSU Finance | 2017-05-11 | 0 | 2017-05-11 | N | 00129276
Calendaring : Initial Calendar Build - 00120786 | Acknowledge | User | Fitzpatrick, Patti | 2017-05-11 | 60 | 2017-07-10 | N | 00120786
Calendaring : Initial Calendar Build - 00109407 | Acknowledge | User | Frasier, Lora | 2017-05-11 | 112 |  | N | 00109407
Calendaring : Initial Calendar Build - 00125798 | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-05-11 | 0 | 2017-05-11 | N | 00125798
Calendaring : Initial Calendar Build - 71-RICE | Assign to Analyst | User | Greene, Paula | 2017-05-11 | 0 | 2017-05-11 | N | 00134857
Calendaring : Initial Calendar Build - 71-RICE | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-05-11 | 0 | 2017-05-11 | N | 00134857
Calendaring : Initial Calendar Build - 00124839 | Complete Calendar ( ie. Ready for Financials ) | User | Hess, Aaron | 2017-05-11 | 12 | 2017-05-23 | N | 00124839
Calendaring : Initial Calendar Build - 00124839 | Make Updates | User | Hess, Aaron | 2017-05-11 | 12 | 2017-05-23 | N | 00124839
Pre-Award Financial - 00125786 | Calendar Released | User | Oliver, Amy | 2017-05-11 | 33 | 2017-06-13 | N | 00125786
Pre-Award Financial - 44-MCUNE | Calendar Released | User | Oliver, Amy | 2017-05-11 | 112 |  | N | 44-MCUNE
Calendaring : Initial Calendar Build - 00122957 | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-05-11 | 6 | 2017-05-17 | N | 00124722
Calendaring : Initial Calendar Build - 00122957 | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-05-11 | 6 | 2017-05-17 | N | 00124722
Calendaring : Initial Calendar Build - 00129427 2 | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-05-11 | 25 | 2017-06-05 | N | 00129427
Calendaring : Initial Calendar Build - 00129427 2 | Make Updates | User | Radenbaugh, Pauline | 2017-05-11 | 21 | 2017-06-01 | N | 00129427
Calendaring : Initial Calendar Build - HUM00091711 | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-05-11 | 4 | 2017-05-15 | N | 00091711
Calendaring : Initial Calendar Build - HUM00091711 | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-05-11 | 0 | 2017-05-08 | N | 00091711
Pre-Award Financial - 00128743 | PI approved Budget | User | VanderElzen, Liz | 2017-05-11 | 36 | 2017-06-16 | N | 00128743
Calendaring : Initial Calendar Build - 00113042 | Acknowledge | User | Watson, Donna | 2017-05-11 | 8 | 2017-05-19 | N | 00113042
Pre-Award Financial - 00122254 | OnCore Budget Build | User | Yunk, Jason | 2017-05-11 | 68 | 2017-07-18 | N | 00122254
Pre-Award Financial - 00127505 | OnCore Budget Build | User | Yunk, Jason | 2017-05-11 | 91 | 2017-08-10 | N | 00127505
Calendaring : Initial Build - 00126224 | CRAO Approval Issue & Documented | User | Zahs, Brian | 2017-05-11 | 13 | 2017-05-24 | N | 00126224
Calendaring : Initial Calendar Build - 58-BONIFANT | Feasibility Approval Notice Received | User | Zahs, Brian | 2017-05-11 | 0 | 2017-05-11 | N | 00132916
Calendaring : Initial Calendar Build - 00122957 | Complete MCA / QCT | User | van Dijk, Tim | 2017-05-11 | 6 | 2017-05-17 | N | 00124722
Calendaring : Initial Calendar Build - HUM00129276 | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-05-11 | 6 | 2017-05-17 | N | 00129276
Pre-Award Financial - 180-HOFF | UFA Completed | Role | CTSU Coordinator | 2017-05-12 | 0 | 2017-05-12 | N | 00129450
Pre-Award Financial - 71-RICE | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-05-12 | 0 | 2017-05-07 | N | 00134857
Calendaring : Initial Calendar Build - 00125836 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-05-12 | 25 | 2017-06-06 | N | 00125836
Calendaring : Initial Calendar Build - 00126707 | Acknowledge | Role | CTSU Finance | 2017-05-12 | 61 | 2017-07-12 | N | 00126707
Pre-Award Financial - 10-JAYASUNDERA | OnCore Budget Build | Role | CTSU Finance | 2017-05-12 | 111 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 34-MARSH | PAN Released | Role | CTSU Finance | 2017-05-12 | 111 |  | N | 34-MARSH
Pre-Award Financial - 71-RICE | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-05-12 | 0 | 2017-03-31 | N | 00134857
Pre-Award Financial - 9-JAYASUNDERA | OnCore Budget Build | Role | CTSU Finance | 2017-05-12 | 111 |  | N | 9-JAYASUNDERA
Pre-Award Financial - SCHIOPU-1 | PAF routed | Role | CTSU Finance | 2017-05-12 | 111 |  | N | SCHIOPU-1
Calendaring : Initial Calendar Build - 58-BONIFANT | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-05-12 | 0 | 2017-05-12 | N | 00132916
Calendaring : Initial Calendar Build - P-3058HELFRICH | Nimblify Build is Complete & Ready for Import | User | Hess, Aaron | 2017-05-12 | 111 |  | N | 00129897
Calendaring : Initial Calendar Build - P-3073HELFRICH | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-05-12 | 0 | 2017-05-12 | N | 00128488
Pre-Award Financial - 00122254 | Calendar Released | User | Oliver, Amy | 2017-05-12 | 75 | 2017-07-26 | N | 00122254
Pre-Award Financial - 00127505 | Calendar Released | User | Oliver, Amy | 2017-05-12 | 90 | 2017-08-10 | N | 00127505
Pre-Award Financial - 00129427 | Care Designations completed | User | Oliver, Amy | 2017-05-12 | 32 | 2017-06-13 | N | 00129427
Calendaring : Amendment Checklist & Process - 00080998 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-05-12 | 0 | 2017-05-12 | N | 00080998
Calendaring : Specification Update Request(s) - 00117851 | Make Update(s) | User | Radenbaugh, Pauline | 2017-05-12 | 55 | 2017-07-06 | N | 00117851
Calendaring : Specification Update Request(s) - 00117851 | Re-Complete Calendar | User | Radenbaugh, Pauline | 2017-05-12 | 55 | 2017-07-06 | N | 00117851
Pre-Award Financial - 00108880 | Planning Meeting Completed | User | VanderElzen, Liz | 2017-05-12 | 0 | 2017-05-11 | N | 00108880
Pre-Award Financial - 00128157 | PI approved Budget | User | VanderElzen, Liz | 2017-05-12 | 48 | 2017-06-29 | N | 00128157
Pre-Award Financial - 00128173 | Planning Meeting Completed | User | VanderElzen, Liz | 2017-05-12 | 0 | 2017-05-11 | N | 00128173
Calendaring : Amendment Checklist & Process - 00089260 2 | Acknowledge | User | Yunk, Jason | 2017-05-12 | 80 | 2017-07-31 | N | 00089260
Calendaring : Initial Calendar Build - 58-BONIFANT | Assign to Analyst | User | Zahs, Brian | 2017-05-12 | 3 | 2017-05-15 | N | 00132916
Calendaring : Specification Update Request(s) - 00122815 | Make Update(s) | User | Zahs, Brian | 2017-05-12 | 111 |  | N | 00122815
Calendaring : Specification Update Request(s) - 00122815 | Re-Complete Calendar | User | Zahs, Brian | 2017-05-12 | 111 |  | N | 00122815
Calendaring : Initial Calendar Build - 00125798 | Assign to Analyst |  |  | 2017-05-12 | 111 |  | N | 00125798
Pre-Award Financial - 12-HIGGINS | Open to Accrual | Role | CTSU Administrator | 2017-05-13 | 110 |  | N | 12-HIGGINS
Core Sponsor Documents for Study Feasibility & Start Up - General - 111-HIGGINS | Informed Consent | Role | CTSU Coordinator | 2017-05-13 | 110 |  | N | 111-HIGGINS
Core Sponsor Documents for Study Feasibility & Start Up - General - 111-HIGGINS | Investigational Drug Brochure / Investigator's Brochure | Role | CTSU Coordinator | 2017-05-13 | 110 |  | N | 111-HIGGINS
Core Sponsor Documents for Study Feasibility & Start Up - General - 111-HIGGINS | Protocol (and any approved Amendments) | Role | CTSU Coordinator | 2017-05-13 | 110 |  | N | 111-HIGGINS
Core Sponsor Documents for Study Feasibility & Start Up - General - 111-HIGGINS | Sponsor Budget | Role | CTSU Coordinator | 2017-05-13 | 110 |  | N | 111-HIGGINS
Core Sponsor Documents for Study Feasibility & Start Up - General - 111-HIGGINS | Sponsor Contract | Role | CTSU Coordinator | 2017-05-13 | 110 |  | N | 111-HIGGINS
Core Sponsor Documents for Study Feasibility & Start Up - General - 111-HIGGINS | U-M Planning Questionnaire | Role | CTSU Coordinator | 2017-05-13 | 110 |  | N | 111-HIGGINS
Calendaring : Initial Calendar Build - 97-KALES | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-05-13 | 11 | 2017-05-24 | N | 97-KALES
Pre-Award Financial - 10-JAYASUNDERA | Calendar Released | Role | CTSU Finance | 2017-05-13 | 110 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 9-JAYASUNDERA | Calendar Released | Role | CTSU Finance | 2017-05-13 | 110 |  | N | 9-JAYASUNDERA
Calendaring : Initial Calendar Build - 00124839 | Acknowledge | User | Dahlgren, Molly | 2017-05-13 | 25 | 2017-06-07 | N | 00124839
Calendaring : Initial Calendar Build - P-3058HELFRICH | Complete MCA / QCT | User | Hess, Aaron | 2017-05-13 | 110 |  | N | 00129897
Calendaring : Initial Calendar Build - P-3058HELFRICH | Complete SVS & Pricing List ( Built & Coded ) | User | Hess, Aaron | 2017-05-13 | 17 | 2017-05-30 | N | 00129897
Calendaring : Initial Calendar Build - P-3073HELFRICH | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-05-13 | 4 | 2017-05-17 | N | 00128488
Calendaring : Initial Calendar Build - P-3073HELFRICH | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-05-13 | 0 | 2017-05-12 | N | 00128488
Calendaring : Initial Calendar Build - 00129427 2 | Acknowledge | User | Oliver, Amy | 2017-05-13 | 31 | 2017-06-13 | N | 00129427
Calendaring : Amendment Checklist & Process - 00080998 | ** Footnote Edits | User | Radenbaugh, Pauline | 2017-05-13 | 0 | 2017-05-13 | N | 00080998
Calendaring : Amendment Checklist & Process - 00080998 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Radenbaugh, Pauline | 2017-05-13 | 0 | 2017-05-13 | N | 00080998
Calendaring : Initial Calendar Build - 00122957 | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-05-13 | 4 | 2017-05-17 | N | 00124722
Calendaring : Initial Calendar Build - 00108880 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-05-13 | 88 | 2017-08-09 | N | 00108880
Calendaring : Initial Calendar Build - 00128173 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-05-13 | 88 | 2017-08-09 | N | 00128173
Pre-Award Financial - 00128743 | Budget Negotiations | User | VanderElzen, Liz | 2017-05-13 | 34 | 2017-06-16 | N | 00128743
Calendaring : Initial Calendar Build - 00122957 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-05-13 | 4 | 2017-05-17 | N | 00124722
Calendaring : Initial Calendar Build - HUM00129276 | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-05-13 | 5 | 2017-05-18 | N | 00129276
Calendaring : Initial Calendar Build - HUM00129276 | Complete MCA / QCT | User | van Dijk, Tim | 2017-05-13 | 0 | 2017-05-12 | N | 00129276
Calendaring : Initial Calendar Build - HUM00129276 | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-05-13 | 0 | 2017-05-11 | N | 00129276
Calendaring : Initial Calendar Build - HUM00129276 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-05-13 | 5 | 2017-05-18 | N | 00129276
Pre-Award Financial - 00125786 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-14 | 30 | 2017-06-13 | N | 00125786
Pre-Award Financial - 44-MCUNE | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-14 | 109 |  | N | 44-MCUNE
Calendaring : Specification Update Request(s) - 00117851 | Acknowledge | Role | CTSU Finance | 2017-05-14 | 80 | 2017-08-02 | N | 00117851
Calendaring : Specification Update Request(s) - 00122815 | Acknowledge | Role | CTSU Finance | 2017-05-14 | 58 | 2017-07-11 | N | 00122815
Pre-Award Financial - 77-CONJEEVARAM | Care Designations completed | Role | CTSU Finance | 2017-05-14 | 109 |  | N | 77-CONJEEVARAM
Pre-Award Financial - 96-BESIRLI | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-05-14 | 0 | 2017-04-17 | N | 00129820
Calendaring : Initial Calendar Build - 116-BRUMMETT | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Earwood, Rebecca | 2017-05-14 | 30 | 2017-06-13 | N | 00129418
Calendaring : Initial Calendar Build - P-3058HELFRICH | Attach Build Notes ( as Protocol Doc ) | User | Hess, Aaron | 2017-05-14 | 109 |  | N | 00129897
Calendaring : Initial Calendar Build - P-3058HELFRICH | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hess, Aaron | 2017-05-14 | 109 |  | N | 00129897
Calendaring : Initial Calendar Build - P-3073HELFRICH | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-05-14 | 3 | 2017-05-17 | N | 00128488
Calendaring : Initial Calendar Build - P-3073HELFRICH | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-05-14 | 11 | 2017-05-25 | N | 00128488
Pre-Award Financial - 00128157 | Budget Negotiations | User | VanderElzen, Liz | 2017-05-14 | 57 | 2017-07-10 | N | 00128157
Calendaring : Initial Calendar Build - 00125836 | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-05-14 | 45 | 2017-06-28 | N | 00125836
Calendaring : Initial Calendar Build - 00125836 | Make Updates | User | Zahs, Brian | 2017-05-14 | 11 | 2017-05-25 | N | 00125836
Calendaring : Initial Calendar Build - 71-RICE | Complete MCA / QCT | User | Zahs, Brian | 2017-05-14 | 51 | 2017-07-04 | N | 00134857
Calendaring : Initial Calendar Build - 71-RICE | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian | 2017-05-14 | 5 | 2017-05-19 | N | 00134857
Calendaring : Initial Calendar Build - 71-RICE | Nimblify Build is Complete & Ready for Import | User | Zahs, Brian | 2017-05-14 | 0 | 2017-05-14 | N | 00134857
Calendaring : Initial Calendar Build - 00125798 | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-05-14 | 23 | 2017-06-06 | N | 00125798
Pre-Award Financial - 00122254 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-15 | 108 |  | N | 00122254
Pre-Award Financial - 00127505 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-15 | 108 |  | N | 00127505
Pre-Award Financial - 170-SCHIOPU | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-15 | 17 | 2017-06-01 | N | 00134035
Core Sponsor Documents for Study Feasibility & Start Up - General - 192-ALAM | Initial contact with sponsor | Role | CTSU Coordinator | 2017-05-15 | 0 | 2017-05-15 | N | 192-ALAM
Core Sponsor Documents for Study Feasibility & Start Up - General - 192-ALAM | Protocol (and any approved Amendments) | Role | CTSU Coordinator | 2017-05-15 | 0 | 2017-05-15 | N | 192-ALAM
Pre-Award Financial - 00129427 | IRB Application Submitted | Role | CTSU Coordinator | 2017-05-15 | 0 | 2017-05-15 | N | 00129427
Pre-Award Financial - 188-RUBENSTEIN | Intake Form Completed | Role | CTSU Coordinator | 2017-05-15 | 0 | 2017-05-15 | N | 188-RUBENSTEIN
Calendaring : Amendment Checklist & Process - 00068856 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-05-15 | 0 | 2017-05-15 | N | 00068856
Pre-Award Financial - 192-ALAM | Intake Form Completed | Role | CTSU Finance | 2017-05-15 | 0 | 2017-05-15 | N | 192-ALAM
Pre-Award Financial - 81-HIGGINS | Planning Meeting Completed | Role | CTSU Finance | 2017-05-15 | 108 |  | N | 81-HIGGINS
Update Requests : 120231 (5.15.17) | Submit Update Request(s) | Role | CTSU Finance | 2017-05-15 | 0 | 2017-05-15 | N | 00120231
Calendaring : Amendment Checklist & Process - 00110881 | Assign to Analyst | User | Hodges, Lynda | 2017-05-15 | 1 | 2017-05-16 | N | 00110881
Update Requests : 120231 (5.15.17) | Assign to Analyst | User | LaVasseur, Kristen | 2017-05-15 | 0 | 2017-05-15 | N | 00120231
Calendaring : Initial Calendar Build - 00108880 | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-05-15 | 108 |  | N | 00108880
Calendaring : Initial Calendar Build - 00108880 | Make Updates | User | Munasinghe, Sadeepa | 2017-05-15 | 108 |  | N | 00108880
Calendaring : Amendment Checklist & Process - 00068856 | Complete Calendar and Document Approval | User | Przykucki, Anne | 2017-05-15 | 0 | 2017-05-15 | N | 00068856
Calendaring : Initial Calendar Build - 00128173 | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-05-15 | 91 | 2017-08-14 | N | 00128173
Calendaring : Initial Calendar Build - 00128173 | Make Updates | User | Radenbaugh, Pauline | 2017-05-15 | 91 | 2017-08-14 | N | 00128173
Calendaring : Initial Calendar Build - 97-KALES | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-05-15 | 16 | 2017-05-31 | N | 97-KALES
Calendaring : Initial Calendar Build - 97-KALES | Make Updates | User | Radenbaugh, Pauline | 2017-05-15 | 16 | 2017-05-31 | N | 97-KALES
Pre-Award Financial - 00108880 | Care Designations completed | User | VanderElzen, Liz | 2017-05-15 | 86 | 2017-08-09 | N | 00108880
Pre-Award Financial - 00128173 | Care Designations completed | User | VanderElzen, Liz | 2017-05-15 | 91 | 2017-08-14 | N | 00128173
Calendaring : Initial Calendar Build - 58-BONIFANT | Complete MCA / QCT | User | Zahs, Brian | 2017-05-15 | 108 |  | N | 00132916
Calendaring : Initial Calendar Build - 58-BONIFANT | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian | 2017-05-15 | 23 | 2017-06-07 | N | 00132916
Calendaring : Initial Calendar Build - 58-BONIFANT | Nimblify Build is Complete & Ready for Import | User | Zahs, Brian | 2017-05-15 | 108 |  | N | 00132916
Calendaring : Initial Calendar Build - 00125798 | Complete MCA / QCT | User | van Dijk, Tim | 2017-05-15 | 22 | 2017-06-06 | N | 00125798
Calendaring : Initial Calendar Build - 00125798 | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-05-15 | 22 | 2017-06-06 | N | 00125798
Update Requests : 120231 (5.15.17) | ** Other Request(s) |  |  | 2017-05-15 | 0 | 2017-05-15 | N | 00120231
Pre-Award Financial - 00125786 | Open to Accrual | Role | CTSU Administrator | 2017-05-16 | 54 | 2017-07-09 | N | 00125786
Pre-Award Financial - 10-JAYASUNDERA | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-16 | 107 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 44-MCUNE | Open to Accrual | Role | CTSU Administrator | 2017-05-16 | 107 |  | N | 44-MCUNE
Pre-Award Financial - 9-JAYASUNDERA | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-16 | 107 |  | N | 9-JAYASUNDERA
Pre-Award Financial - 190-SCHIOPU | Intake Form Completed | Role | CTSU Coordinator | 2017-05-16 | 0 | 2017-05-16 | N | 00134443
Pre-Award Financial - 96-BESIRLI | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-05-16 | 0 | 2017-04-24 | N | 00129820
Calendaring : Amendment Checklist & Process - 00101092 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-05-16 | 0 | 2017-05-16 | N | 00101092
Calendaring : Initial Calendar Build - 00125836 | Acknowledge | Role | CTSU Finance | 2017-05-16 | 65 | 2017-07-20 | N | 00125836
Calendaring : Amendment Checklist & Process - 00110881 | ** Footnote Edits | User | Hodges, Lynda | 2017-05-16 | 1 | 2017-05-17 | N | 00110881
Calendaring : Amendment Checklist & Process - 00110881 | ** Items/Services : Addition or Removal of Procedures / Events | User | Hodges, Lynda | 2017-05-16 | 1 | 2017-05-17 | N | 00110881
Calendaring : Amendment Checklist & Process - 00110881 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Hodges, Lynda | 2017-05-16 | 1 | 2017-05-17 | N | 00110881
Calendaring : Amendment Checklist & Process - 00110881 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Hodges, Lynda | 2017-05-16 | 0 | 2017-05-16 | N | 00110881
Calendaring : Amendment Checklist & Process - 00110881 | Update RSH Source in MBECT | User | Hodges, Lynda | 2017-05-16 | 1 | 2017-05-17 | N | 00110881
Calendaring : Initial Calendar Build - 116-BRUMMETT | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-05-16 | 31 | 2017-06-16 | N | 00129418
Pre-Award Financial - 00129427 | Internal Budget Finished | User | Oliver, Amy | 2017-05-16 | 0 | 2017-05-14 | N | 00129427
Pre-Award Financial - 33-FLAHERTY | Initiate Post-Award Task List | User | Oliver, Amy | 2017-05-16 | 77 | 2017-08-01 | N | 00129716
Pre-Award Financial - 33-FLAHERTY | PAN Released | User | Oliver, Amy | 2017-05-16 | 77 | 2017-08-01 | N | 00129716
Calendaring : Initial Calendar Build - 71-RICE | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian | 2017-05-16 | 0 | 2017-05-16 | N | 00134857
Calendaring : Initial Calendar Build - 71-RICE | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian | 2017-05-16 | 3 | 2017-05-19 | N | 00134857
Calendaring : Initial Calendar Build - 00125798 | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-05-16 | 21 | 2017-06-06 | N | 00125798
Calendaring : Initial Calendar Build - 00125798 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-05-16 | 21 | 2017-06-06 | N | 00125798
Pre-Award Financial - 00122254 | Open to Accrual | Role | CTSU Administrator | 2017-05-17 | 106 |  | N | 00122254
Pre-Award Financial - 00127505 | Open to Accrual | Role | CTSU Administrator | 2017-05-17 | 106 |  | N | 00127505
Pre-Award Financial - 00127505 | IRB Application Submitted | Role | CTSU Coordinator | 2017-05-17 | 0 | 2017-04-24 | N | 00127505
Calendaring : Amendment Checklist & Process - 00068856 | Acknowledge | Role | CTSU Finance | 2017-05-17 | 1 | 2017-05-18 | N | 00068856
Calendaring : Initial Calendar Build - 97-KALES | Acknowledge | Role | CTSU Finance | 2017-05-17 | 14 | 2017-05-31 | N | 97-KALES
Calendaring : Initial Calendar Build - HUM00091711 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-05-17 | 8 | 2017-05-25 | N | 00091711
Pre-Award Financial - 76-KHANNA | Internal Budget Finished | Role | CTSU Finance | 2017-05-17 | 2 | 2017-05-19 | N | 00131837
Pre-Award Financial - HUM00129276 | Billing Calendar Received | Role | CTSU Finance | 2017-05-17 | 1 | 2017-05-18 | N | 00129276
Calendaring : Amendment Checklist & Process - 00068856 | Assign to Analyst | User | Przykucki, Anne | 2017-05-17 | 0 | 2017-05-15 | N | 00068856
Calendaring : Initial Calendar Build - 00108880 | Acknowledge | User | VanderElzen, Liz | 2017-05-17 | 106 |  | N | 00108880
Calendaring : Initial Calendar Build - 00128173 | Acknowledge | User | VanderElzen, Liz | 2017-05-17 | 90 | 2017-08-15 | N | 00128173
Pre-Award Financial - 00125566 | OnCore Budget Build | User | Yunk, Jason | 2017-05-17 | 21 | 2017-06-07 | N | 00125566
Calendaring : Initial Calendar Build - 58-BONIFANT | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian | 2017-05-17 | 106 |  | N | 00132916
Calendaring : Initial Calendar Build - 58-BONIFANT | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian | 2017-05-17 | 26 | 2017-06-12 | N | 00132916
Calendaring : Initial Calendar Build - 93-FREEHILL | Feasibility Approval Notice Received | Role | CRAO | 2017-05-18 | 0 | 2017-05-18 | N | 00129863
Pre-Award Financial - 10-JAYASUNDERA | Open to Accrual | Role | CTSU Administrator | 2017-05-18 | 105 |  | N | 10-JAYASUNDERA
Pre-Award Financial - 9-JAYASUNDERA | Open to Accrual | Role | CTSU Administrator | 2017-05-18 | 105 |  | N | 9-JAYASUNDERA
Pre-Award Financial - 201-MCCUNE | Intake Form Completed | Role | CTSU Coordinator | 2017-05-18 | 0 | 2017-05-18 | N | 201-MCCUNE
Pre-Award Financial - 203-ELSE | Intake Form Completed | Role | CTSU Coordinator | 2017-05-18 | 0 | 2017-05-18 | N | 00132173
CTSU Pre-Award v2 - 37-SILVER | Initiate Post-Award Task List | Role | CTSU Finance | 2017-05-18 | 105 |  | N | 37-SILVER
CTSU Pre-Award v2 - 37-SILVER | PAN Released | Role | CTSU Finance | 2017-05-18 | 105 |  | N | 37-SILVER
Calendaring : Initial Calendar Build - 116-BRUMMETT | Acknowledge | Role | CTSU Finance | 2017-05-18 | 32 | 2017-06-19 | N | 00129418
Pre-Award Financial - 194-MCLAUGHLIN | Intake Form Completed | Role | CTSU Finance | 2017-05-18 | 0 | 2017-05-18 | N | 194-MCLAUGHLIN
Pre-Award Financial - 77-CONJEEVARAM | Internal Budget Finished | Role | CTSU Finance | 2017-05-18 | 105 |  | N | 77-CONJEEVARAM
Pre-Award Financial - 81-HIGGINS | Care Designations completed | Role | CTSU Finance | 2017-05-18 | 105 |  | N | 81-HIGGINS
Pre-Award Financial - 198-LUCKRITZ | Intake Form Completed | User | Naylor, Tracey | 2017-05-18 | 0 | 2017-05-18 | N | 198-LUCKRITZ
Pre-Award Financial - 00125566 | Calendar Released | User | Oliver, Amy | 2017-05-18 | 34 | 2017-06-21 | N | 00125566
Calendaring : Amendment Checklist & Process - 00068856 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Przykucki, Anne | 2017-05-18 | 0 | 2017-05-15 | N | 00068856
Calendaring : Amendment Checklist & Process - 00101092 | Assign to Analyst | User | Przykucki, Anne | 2017-05-18 | 7 | 2017-05-25 | N | 00101092
Calendaring : Amendment Checklist & Process - 00101092 | ** Footnote Edits | Role | CRAO | 2017-05-19 | 17 | 2017-06-05 | N | 00101092
Calendaring : Amendment Checklist & Process - 00101092 | ** Items/Services : Updates to Activity for Existing Procedures / Events | Role | CRAO | 2017-05-19 | 17 | 2017-06-05 | N | 00101092
Calendaring : Amendment Checklist & Process - 00101092 | ** Visit Tolerance Edits | Role | CRAO | 2017-05-19 | 17 | 2017-06-05 | N | 00101092
Calendaring : Initial Calendar Build - | Feasibility Approval Notice Received | Role | CRAO | 2017-05-19 | 0 | 2017-05-19 | N | 103-GAGNIER
Calendaring : Initial Calendar Build - 00130757 | Feasibility Approval Notice Received | Role | CRAO | 2017-05-19 | 0 | 2017-05-19 | N | 00130757
Calendaring : Initial Calendar Build - 00130793 | Feasibility Approval Notice Received | Role | CRAO | 2017-05-19 | 31 | 2017-06-19 | N | 00130793
Pre-Award Financial - 00130793 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-05-19 | 0 | 2017-05-19 | N | 00130793
Pre-Award Financial - 179-LUGOGO | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-19 | 59 | 2017-07-17 | N | 179-LUGOGO
Pre-Award Financial - 87-ORAL | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-05-19 | 0 | 2017-05-19 | N | 00130757
Pre-Award Financial - 00126010 | Intake Form Completed | Role | CTSU Coordinator | 2017-05-19 | 0 | 2017-05-19 | N | 00126010
Pre-Award Financial - 131-LUGOGO | Sponsor Reach out | Role | CTSU Coordinator | 2017-05-19 | 11 | 2017-05-30 | N | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | UFA Completed | Role | CTSU Coordinator | 2017-05-19 | 0 | 2017-05-01 | N | 131-LUGOGO
Pre-Award Financial - 179-LUGOGO | UFA Completed | Role | CTSU Coordinator | 2017-05-19 | 0 | 2017-05-03 | N | 179-LUGOGO
Pre-Award Financial - 205-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-05-19 | 0 | 2017-05-19 | N | 205-HIGGINS
Calendaring : Amendment Checklist & Process - 00113560 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-05-19 | 0 | 2017-04-19 | N | 00113560
Pre-Award Financial - 91-ELSE | Billing Calendar Received | Role | CTSU Finance | 2017-05-19 | 104 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | Billing Calendar Received | Role | CTSU Finance | 2017-05-19 | 104 |  | N | 92-AUCHUS
Pre-Award Financial - HUM00129276 | Care Designations completed | Role | CTSU Finance | 2017-05-19 | 3 | 2017-05-22 | N | 00129276
Pre-Award Financial - 198-LUCKRITZ | UFA Completed | User | Earwood, Rebecca | 2017-05-19 | 0 | 2017-05-19 | N | 198-LUCKRITZ
Calendaring : Initial Calendar Build - | Assign to Analyst | User | Hess, Aaron | 2017-05-19 | 0 | 2017-05-19 | N | 103-GAGNIER
Calendaring : Initial Calendar Build - | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-19 | 0 | 2017-05-19 | N | 103-GAGNIER
Calendaring : Initial Calendar Build - 00130757 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-19 | 0 | 2017-05-19 | N | 00130757
Calendaring : Initial Calendar Build - 00130793 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-19 | 0 | 2017-05-19 | N | 00130793
Calendaring : Initial Calendar Build - 4033CYTOKINETICS-GOUTMAN | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-19 | 0 | 2017-05-19 | N | 00130639
Calendaring : Initial Calendar Build - 93-FREEHILL | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-19 | 0 | 2017-05-19 | N | 00129863
Calendaring : Initial Calendar Build - 4033CYTOKINETICS-GOUTMAN | Feasibility Approval Notice Received | User | Munasinghe, Sadeepa | 2017-05-19 | 3 | 2017-05-22 | N | 00130639
Pre-Award Financial - 00129427 | PI approved Budget | User | Oliver, Amy | 2017-05-19 | 104 |  | N | 00129427
Calendaring : Amendment Checklist & Process - 00101092 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Przykucki, Anne | 2017-05-19 | 17 | 2017-06-05 | N | 00101092
Calendaring : Initial Calendar Build - HUM00091711 | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-05-19 | 13 | 2017-06-01 | N | 00091711
Calendaring : Initial Calendar Build - HUM00091711 | Make Updates | User | Radenbaugh, Pauline | 2017-05-19 | 13 | 2017-06-01 | N | 00091711
Calendaring : Initial Calendar Build - 93-FREEHILL | Assign to Analyst | User | Zahs, Brian | 2017-05-19 | 0 | 2017-05-19 | N | 00129863
Calendaring : Initial Calendar Build - 00130793 | Assign to Analyst | User | van Dijk, Tim | 2017-05-19 | 0 | 2017-05-19 | N | 00130793
Calendaring : Amendment Checklist & Process - 00101092 | ** Items/Services : Addition or Removal of Procedures / Events | Role | CRAO | 2017-05-20 | 16 | 2017-06-05 | N | 00101092
Calendaring : Initial Calendar Build - 00122957 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-05-20 | 3 | 2017-05-23 | N | 00124722
Calendaring : Initial Calendar Build - HUM00129276 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-05-20 | 2 | 2017-05-22 | N | 00129276
Pre-Award Financial - 76-KHANNA | PI approved Budget | Role | CTSU Finance | 2017-05-20 | 0 | 2017-05-19 | N | 00131837
Update Requests : 120231 (5.15.17) | Make Update(s) | User | LaVasseur, Kristen | 2017-05-20 | 0 | 2017-05-20 | N | 00120231
Update Requests : 120231 (5.15.17) | Re-Complete Calendar | User | LaVasseur, Kristen | 2017-05-20 | 0 | 2017-05-20 | N | 00120231
Pre-Award Financial - 71-RICE | Billing Calendar Received | User | Oliver, Amy | 2017-05-20 | 0 | 2017-05-19 | N | 00134857
Calendaring : Initial Calendar Build - P-3058HELFRICH | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Bell, Jennifer | 2017-05-21 | 9 | 2017-05-30 | N | 00129897
Calendaring : Initial Calendar Build - P-3073HELFRICH | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Bell, Jennifer | 2017-05-21 | 4 | 2017-05-25 | N | 00128488
Calendaring : Amendment Checklist & Process - 00101092 | ** Other | Role | CRAO | 2017-05-21 | 15 | 2017-06-05 | N | 00101092
Calendaring : Amendment Checklist & Process - 00101092 | Update RSH Source in MBECT | Role | CRAO | 2017-05-21 | 15 | 2017-06-05 | N | 00101092
Pre-Award Financial - 00125566 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-21 | 43 | 2017-07-03 | N | 00125566
Pre-Award Financial - 00130793 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-05-21 | 5 | 2017-05-26 | N | 00130793
Pre-Award Financial - 87-ORAL | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-05-21 | 1 | 2017-05-22 | N | 00130757
Calendaring : Initial Calendar Build - HUM00091711 | Acknowledge | Role | CTSU Finance | 2017-05-21 | 102 |  | N | 00091711
Pre-Award Financial - 00130793 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-05-21 | 12 | 2017-06-02 | N | 00130793
Pre-Award Financial - 77-CONJEEVARAM | PI approved Budget | Role | CTSU Finance | 2017-05-21 | 102 |  | N | 77-CONJEEVARAM
Pre-Award Financial - 87-ORAL | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-05-21 | 12 | 2017-06-02 | N | 00130757
Pre-Award Financial - 87-ORAL | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-05-21 | 1 | 2017-05-22 | N | 00130757
Pre-Award Financial - 00130793 | Request Research Pharmacy Budget | User | Henry, Robin | 2017-05-21 | 15 | 2017-06-05 | N | 00130793
Calendaring : Amendment Checklist & Process - 00113560 | Assign to Analyst | User | Hodges, Lynda | 2017-05-21 | 0 | 2017-05-17 | N | 00113560
Pre-Award Financial - 00129427 | Budget Negotiations | User | Oliver, Amy | 2017-05-21 | 102 |  | N | 00129427
Calendaring : Initial Calendar Build - | Nimblify Build is Complete & Ready for Import | Role | CRAO | 2017-05-22 | 4 | 2017-05-26 | N | 103-GAGNIER
Pre-Award Financial - 211-HIGGINS | IRB Application Submitted | Role | CTSU Coordinator | 2017-05-22 | 46 | 2017-07-07 | N | 00128325
Pre-Award Financial - 211-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-05-22 | 0 | 2017-05-22 | N | 00128325
Amendment Checklist & Process - 113141 AME per Ginger | Acknowledge | Role | CTSU Finance | 2017-05-22 | 0 | 2017-05-22 | N | 00113141
Calendaring : Amendment Checklist & Process - 00113560 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | Role | CTSU Finance | 2017-05-22 | 76 | 2017-08-06 | N | 00113560
Pre-Award Financial - 76-KHANNA | Budget Negotiations | Role | CTSU Finance | 2017-05-22 | 2 | 2017-05-24 | N | 00131837
Pre-Award Financial - 81-HIGGINS | Internal Budget Finished | Role | CTSU Finance | 2017-05-22 | 101 |  | N | 81-HIGGINS
Update Requests : 120231 (5.15.17) | Acknowledge | Role | CTSU Finance | 2017-05-22 | 50 | 2017-07-11 | N | 00120231
Calendaring : Initial Calendar Build - | Complete MCA / QCT | User | Hess, Aaron | 2017-05-22 | 0 | 2017-05-22 | N | 103-GAGNIER
BC : Initial Build - PLT-INF24-001 | Complete MCA / QCT | User | LaVasseur, Kristen | 2017-05-22 | 0 | 2017-05-22 | N | 00135388
Calendaring : Initial Calendar Build - 4033CYTOKINETICS-GOUTMAN | Assign to Analyst | User | Munasinghe, Sadeepa | 2017-05-22 | 0 | 2017-05-22 | N | 00130639
Calendaring : Initial Calendar Build - 4033CYTOKINETICS-GOUTMAN | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-05-22 | 1 | 2017-05-23 | N | 00130639
Calendaring : Amendment Checklist & Process - 00080998 | Complete Calendar and Document Approval | User | Radenbaugh, Pauline | 2017-05-22 | 0 | 2017-05-16 | N | 00080998
Pre-Award Financial - 00126010 | PI approved Budget | User | VanderElzen, Liz | 2017-05-22 | 17 | 2017-06-08 | N | 00126010
Pre-Award Financial - 00127356 | OnCore Budget Build | User | Yunk, Jason | 2017-05-22 | 101 |  | N | 00127356
Pre-Award Financial - 00130575 | OnCore Budget Build | User | Yunk, Jason | 2017-05-22 | 66 | 2017-07-27 | N | 00130575
Calendaring : Initial Calendar Build - 93-FREEHILL | Complete MCA / QCT | User | Zahs, Brian | 2017-05-22 | 30 | 2017-06-21 | N | 00129863
Calendaring : Initial Calendar Build - 93-FREEHILL | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian | 2017-05-22 | 18 | 2017-06-09 | N | 00129863
Calendaring : Initial Calendar Build - 93-FREEHILL | Nimblify Build is Complete & Ready for Import | User | Zahs, Brian | 2017-05-22 | 0 | 2017-05-22 | N | 00129863
Calendaring : Initial Calendar Build - 00122957 | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-05-22 | 1 | 2017-05-23 | N | 00124722
Calendaring : Initial Calendar Build - 00122957 | Make Updates | User | van Dijk, Tim | 2017-05-22 | 1 | 2017-05-23 | N | 00124722
Calendaring : Initial Calendar Build - 00130793 | Complete MCA / QCT | User | van Dijk, Tim | 2017-05-22 | 0 | 2017-05-22 | N | 00130793
Calendaring : Initial Calendar Build - 00130793 | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-05-22 | 1 | 2017-05-23 | N | 00130793
Calendaring : Initial Calendar Build - 00130793 | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-05-22 | 18 | 2017-06-09 | N | 00130793
Calendaring : Initial Calendar Build - HUM00129276 | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-05-22 | 2 | 2017-05-24 | N | 00129276
Calendaring : Initial Calendar Build - HUM00129276 | Make Updates | User | van Dijk, Tim | 2017-05-22 | 2 | 2017-05-24 | N | 00129276
Calendaring : Initial Calendar Build - 00129943 | Feasibility Approval Notice Received | Role | CRAO | 2017-05-23 | 0 | 2017-05-23 | N | 00129943
Calendaring : Initial Calendar Build - 162-PIPE | Feasibility Approval Notice Received | Role | CRAO | 2017-05-23 | 0 | 2017-05-23 | N | 00131320
CTSU Pre-Award v2 - 140-CHUNG | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-23 | 86 | 2017-08-17 | N | 00133613
CTSU Pre-Award v2 - 82-BOLLING | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-23 | 100 |  | N | 82-BOLLING
Pre-Award Financial - 00125566 | Open to Accrual | Role | CTSU Administrator | 2017-05-23 | 66 | 2017-07-28 | N | 00125566
CTSU Pre-Award v2 - 82-BOLLING | Sponsor Reach out | Role | CTSU Coordinator | 2017-05-23 | 0 | 2017-05-23 | N | 82-BOLLING
Calendaring : Initial Calendar Build - 00125798 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-05-23 | 15 | 2017-06-07 | N | 00125798
Pre-Award Financial - 30-FLAHERTY | OnCore Budget Build | Role | CTSU Finance | 2017-05-23 | 100 |  | N | 30-FLAHERTY
Pre-Award Financial - 44-MCUNE | Initiate Post-Award Task List | Role | CTSU Finance | 2017-05-23 | 100 |  | N | 44-MCUNE
Pre-Award Financial - 77-CONJEEVARAM | Budget Negotiations | Role | CTSU Finance | 2017-05-23 | 100 |  | N | 77-CONJEEVARAM
Pre-Award Financial - 91-ELSE | Planning Meeting Completed | Role | CTSU Finance | 2017-05-23 | 100 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | Planning Meeting Completed | Role | CTSU Finance | 2017-05-23 | 100 |  | N | 92-AUCHUS
Calendaring : Initial Calendar Build - P-3058HELFRICH | Complete Calendar ( ie. Ready for Financials ) | User | Hess, Aaron | 2017-05-23 | 100 |  | N | 00129897
Calendaring : Initial Calendar Build - P-3058HELFRICH | Make Updates | User | Hess, Aaron | 2017-05-23 | 100 |  | N | 00129897
Calendaring : Initial Calendar Build - P-3073HELFRICH | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-05-23 | 21 | 2017-06-13 | N | 00128488
Calendaring : Initial Calendar Build - 71-RICE | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Oliver, Amy | 2017-05-23 | 57 | 2017-07-19 | N | 00134857
Pre-Award Financial - 00127356 | Calendar Released | User | Oliver, Amy | 2017-05-23 | 100 |  | N | 00127356
Pre-Award Financial - 00130575 | Calendar Released | User | Oliver, Amy | 2017-05-23 | 87 | 2017-08-18 | N | 00130575
Pre-Award Financial - 44-MCUNE | PAN Released | User | Oliver, Amy | 2017-05-23 | 100 |  | N | 44-MCUNE
Pre-Award Financial - 00129851 | OnCore Budget Build | User | Yunk, Jason | 2017-05-23 | 9 | 2017-06-01 | N | 00129851
Pre-Award Financial - 00126010 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-24 | 0 | 2017-05-24 | N | 00126010
Pre-Award Financial - 142-FLAHERTY | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-24 | 99 |  | N | 142-FLAHERTY
Pre-Award Financial - 147-SCHIOPU | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-24 | 2 | 2017-05-26 | N | 00131329
Pre-Award Financial - 211-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-05-24 | 0 | 2017-05-24 | N | 00128325
Pre-Award Financial - 142-FLAHERTY | Sponsor Reach out | Role | CTSU Coordinator | 2017-05-24 | 99 |  | N | 142-FLAHERTY
Pre-Award Financial - 142-FLAHERTY | UFA Completed | Role | CTSU Coordinator | 2017-05-24 | 0 | 2017-05-09 | N | 142-FLAHERTY
BC : Initial Build - PLT-INF24-001 | Acknowledge | Role | CTSU Finance | 2017-05-24 | 0 | 2017-05-22 | N | 00135388
Calendaring : Initial Calendar Build - 00122957 | Acknowledge | Role | CTSU Finance | 2017-05-24 | 0 | 2017-05-24 | N | 00124722
Calendaring : Initial Calendar Build - 58-BONIFANT | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-05-24 | 47 | 2017-07-10 | N | 00132916
Calendaring : Initial Calendar Build - HUM00129276 | Acknowledge | Role | CTSU Finance | 2017-05-24 | 6 | 2017-05-30 | N | 00129276
Pre-Award Financial - 00129851 | Calendar Released | Role | CTSU Finance | 2017-05-24 | 8 | 2017-06-01 | N | 00129851
Pre-Award Financial - 30-FLAHERTY | Calendar Released | Role | CTSU Finance | 2017-05-24 | 99 |  | N | 30-FLAHERTY
Calendaring : Initial Calendar Build - | Attach Build Notes ( as Protocol Doc ) | User | Hess, Aaron | 2017-05-24 | 8 | 2017-06-01 | N | 103-GAGNIER
Calendaring : Initial Calendar Build - 00129943 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-24 | 99 |  | N | 00129943
Calendaring : Initial Calendar Build - 162-PIPE | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-24 | 99 |  | N | 00131320
Calendaring : Initial Calendar Build - 4033CYTOKINETICS-GOUTMAN | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-05-24 | 0 | 2017-05-23 | N | 00130639
Calendaring : Initial Calendar Build - 4033CYTOKINETICS-GOUTMAN | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-05-24 | 6 | 2017-05-30 | N | 00130639
Pre-Award Financial - 71-RICE | Planning Meeting Completed | User | Oliver, Amy | 2017-05-24 | 19 | 2017-06-12 | N | 00134857
Pre-Award Financial - 00126010 | Budget Negotiations | User | VanderElzen, Liz | 2017-05-24 | 15 | 2017-06-08 | N | 00126010
Calendaring : Initial Calendar Build - 00130757 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian | 2017-05-24 | 15 | 2017-06-08 | N | 00130757
Calendaring : Initial Calendar Build - 93-FREEHILL | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian | 2017-05-24 | 34 | 2017-06-27 | N | 00129863
Calendaring : Initial Calendar Build - 93-FREEHILL | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian | 2017-05-24 | 28 | 2017-06-21 | N | 00129863
Calendaring : Initial Calendar Build - 00129943 | Assign to Analyst | User | van Dijk, Tim | 2017-05-24 | 0 | 2017-05-24 | N | 00129943
Calendaring : Initial Calendar Build - 00130793 | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-05-24 | 16 | 2017-06-09 | N | 00130793
Calendaring : Initial Calendar Build - 00130793 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-05-24 | 16 | 2017-06-09 | N | 00130793
Calendaring : Initial Calendar Build - 162-PIPE | Assign to Analyst | User | van Dijk, Tim | 2017-05-24 | 0 | 2017-05-24 | N | 00131320
Calendaring : Initial Calendar Build - P-3058HELFRICH | Acknowledge | User | Bell, Jennifer | 2017-05-25 | 21 | 2017-06-15 | N | 00129897
Calendaring : Initial Calendar Build - P-3073HELFRICH | Acknowledge | User | Bell, Jennifer | 2017-05-25 | 22 | 2017-06-16 | N | 00128488
CTSU Pre-Award v2 - 00111295 | Intake Form Completed | Role | CTSU Coordinator | 2017-05-25 | 0 | 2017-05-25 | N | 00111295
Pre-Award Financial - 234-MCLAUGHLIN | Intake Form Completed | Role | CTSU Finance | 2017-05-25 | 0 | 2017-05-25 | N | 234-MCLAUGHLIN
Pre-Award Financial - 81-HIGGINS | PI approved Budget | Role | CTSU Finance | 2017-05-25 | 98 |  | N | 81-HIGGINS
Calendar Build - 50-HUMMEL | Add more SVS MBect Items per Study Team | User | Cohan, Lynn | 2017-05-25 | 0 | 2017-05-25 | N | 00129162
Calendaring : Initial Calendar Build - 4033CYTOKINETICS-GOUTMAN | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-05-25 | 8 | 2017-06-02 | N | 00130639
Calendaring : Initial Calendar Build - 4033CYTOKINETICS-GOUTMAN | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-05-25 | 5 | 2017-05-30 | N | 00130639
Calendaring : Initial Calendar Build - 71-RICE | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-05-25 | 67 | 2017-07-31 | N | 00134857
Calendaring : Initial Calendar Build - 71-RICE | Make Updates | User | Zahs, Brian | 2017-05-25 | 67 | 2017-07-31 | N | 00134857
Calendaring : Initial Calendar Build - 175-ORAL | Feasibility Approval Notice Received | Role | CRAO | 2017-05-26 | 0 | 2017-05-26 | N | 175-ORAL
Pre-Award Financial - 00127356 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-26 | 97 |  | N | 00127356
Pre-Award Financial - 00129652 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-05-26 | 0 | 2017-05-26 | N | 00129652
Pre-Award Financial - 00130575 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-26 | 97 |  | N | 00130575
CTSU Pre-Award v2 - 00111295 | UFA Completed | Role | CTSU Coordinator | 2017-05-26 | 0 | 2017-05-26 | N | 00111295
Open to Accrual - 00129851 | IRB Approval | Role | CTSU Coordinator | 2017-05-26 | 0 | 2017-05-26 | N | 00129851
Pre-Award Financial - 235-SUGAR | Intake Form Completed | Role | CTSU Coordinator | 2017-05-26 | 0 | 2017-05-26 | N | 235-SUGAR
Pre-Award Financial - 34-MARSH | OnCore Budget Build | Role | CTSU Finance | 2017-05-26 | 97 |  | N | 34-MARSH
Pre-Award Financial - 91-ELSE | Care Designations completed | Role | CTSU Finance | 2017-05-26 | 97 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | Care Designations completed | Role | CTSU Finance | 2017-05-26 | 97 |  | N | 92-AUCHUS
Pre-Award Financial - SCHIOPU-1 | PAN Released | Role | CTSU Finance | 2017-05-26 | 97 |  | N | SCHIOPU-1
Calendar Build - 50-HUMMEL | Update List in MBect | User | Hess, Aaron | 2017-05-26 | 4 | 2017-05-30 | N | 00129162
Calendaring : Initial Calendar Build - 175-ORAL | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-26 | 0 | 2017-05-26 | N | 175-ORAL
Calendaring : Initial Calendar Build - 94-AUCHUS | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-26 | 0 | 2017-05-26 | N | 00129652
Calendaring : Initial Calendar Build - 94-AUCHUS | Feasibility Approval Notice Received | User | Munasinghe, Sadeepa | 2017-05-26 | 0 | 2017-05-26 | N | 00129652
Calendaring : Initial Calendar Build - 58-BONIFANT | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-05-26 | 45 | 2017-07-10 | N | 00132916
Calendaring : Initial Calendar Build - 58-BONIFANT | Make Updates | User | Zahs, Brian | 2017-05-26 | 45 | 2017-07-10 | N | 00132916
Pre-Award Financial - 00129851 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-27 | 5 | 2017-06-01 | N | 00129851
Pre-Award Financial - 30-FLAHERTY | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-27 | 96 |  | N | 30-FLAHERTY
Pre-Award Financial - 34-MARSH | Calendar Released | Role | CTSU Finance | 2017-05-27 | 96 |  | N | 34-MARSH
Pre-Award Financial - 81-HIGGINS | Budget Negotiations | Role | CTSU Finance | 2017-05-27 | 96 |  | N | 81-HIGGINS
Calendaring : Initial Calendar Build - 71-RICE | Acknowledge | User | Oliver, Amy | 2017-05-27 | 79 | 2017-08-14 | N | 00134857
Pre-Award Financial - 71-RICE | Care Designations completed | User | Oliver, Amy | 2017-05-27 | 53 | 2017-07-19 | N | 00134857
Pre-Award Financial - 00128743 | Final Budget | User | VanderElzen, Liz | 2017-05-27 | 20 | 2017-06-16 | N | 00128743
Calendaring : Initial Calendar Build - 00129943 | Complete MCA / QCT | User | van Dijk, Tim | 2017-05-27 | 5 | 2017-06-01 | N | 00129943
Calendaring : Initial Calendar Build - 00129943 | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-05-27 | 5 | 2017-06-01 | N | 00129943
Calendaring : Initial Calendar Build - 00129943 | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-05-27 | 5 | 2017-06-01 | N | 00129943
Calendaring : Initial Calendar Build - 162-PIPE | Complete MCA / QCT | User | van Dijk, Tim | 2017-05-27 | 5 | 2017-06-01 | N | 00131320
Calendaring : Initial Calendar Build - 162-PIPE | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-05-27 | 0 | 2017-05-25 | N | 00131320
Calendaring : Initial Calendar Build - 162-PIPE | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-05-27 | 5 | 2017-06-01 | N | 00131320
Calendaring : Amendment Checklist & Process - 00101092 | Complete Calendar and Document Approval | Role | CRAO | 2017-05-28 | 8 | 2017-06-05 | N | 00101092
Pre-Award Financial - 00127356 | Open to Accrual | Role | CTSU Administrator | 2017-05-28 | 95 |  | N | 00127356
Pre-Award Financial - 00130575 | Open to Accrual | Role | CTSU Administrator | 2017-05-28 | 95 |  | N | 00130575
Calendaring : Initial Calendar Build - 58-BONIFANT | Acknowledge | Role | CTSU Finance | 2017-05-28 | 43 | 2017-07-10 | N | 00132916
Pre-Award Financial - 00129652 | Planning Meeting Request Sent | User | Huffman, Kate | 2017-05-28 | 2 | 2017-05-30 | N | 00129652
Pre-Award Financial - 00128157 | Final Budget | User | VanderElzen, Liz | 2017-05-28 | 88 | 2017-08-24 | N | 00128157
Pre-Award Financial - 00129652 | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-05-28 | 3 | 2017-05-31 | N | 00129652
Pre-Award Financial - 00129652 | Request MCRU Budget | User | VanderElzen, Liz | 2017-05-28 | 33 | 2017-06-30 | N | 00129652
Pre-Award Financial - 00129652 | Request Research Pharmacy Budget | User | VanderElzen, Liz | 2017-05-28 | 3 | 2017-05-31 | N | 00129652
Pre-Award Financial - 00129851 | Open to Accrual | Role | CTSU Administrator | 2017-05-29 | 8 | 2017-06-06 | N | 00129851
Pre-Award Financial - 30-FLAHERTY | Open to Accrual | Role | CTSU Administrator | 2017-05-29 | 94 |  | N | 30-FLAHERTY
Pre-Award Financial - 00130793 | Billing Calendar Received | User | Henry, Robin | 2017-05-29 | 11 | 2017-06-09 | N | 00130793
Pre-Award Financial - 87-ORAL | Billing Calendar Received | User | Henry, Robin | 2017-05-29 | 4 | 2017-06-02 | N | 00130757
Calendaring : Initial Calendar Build - 94-AUCHUS | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-05-29 | 2 | 2017-05-31 | N | 00129652
Pre-Award Financial - 00128743 | PAF routed | User | VanderElzen, Liz | 2017-05-29 | 32 | 2017-06-30 | N | 00128743
Calendaring : Initial Calendar Build - 00129943 | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-05-29 | 3 | 2017-06-01 | N | 00129943
Calendaring : Initial Calendar Build - 00129943 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-05-29 | 3 | 2017-06-01 | N | 00129943
Calendaring : Initial Calendar Build - 162-PIPE | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-05-29 | 9 | 2017-06-07 | N | 00131320
Calendaring : Initial Calendar Build - 162-PIPE | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-05-29 | 4 | 2017-06-02 | N | 00131320
Calendaring : Initial Calendar Build - 175-ORAL | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-05-29 | 9 | 2017-06-07 | N | 175-ORAL
Calendaring : Initial Calendar Build - 158-PIPE | Feasibility Approval Notice Received | Role | CRAO | 2017-05-30 | 0 | 2017-05-30 | N | 00131463
CTSU Pre-Award v2 - 82-BOLLING | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-05-30 | 93 |  | N | 82-BOLLING
Pre-Award Financial - 34-MARSH | PI Signoff in OnCore | Role | CTSU Administrator | 2017-05-30 | 93 |  | N | 34-MARSH
Pre-Award Financial - 170-SCHIOPU | Sponsor Reach out | Role | CTSU Coordinator | 2017-05-30 | 0 | 2017-05-18 | N | 00134035
Pre-Award Financial - 170-SCHIOPU | UFA Completed | Role | CTSU Coordinator | 2017-05-30 | 0 | 2017-05-09 | N | 00134035
Calendaring : Amendment Checklist & Process - 00115982 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-05-30 | 9 | 2017-06-08 | N | 00115982
Pre-Award Financial - 155-ORAL | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-05-30 | 0 | 2017-05-30 | N | 00130803
Pre-Award Financial - 91-ELSE | Internal Budget Finished | Role | CTSU Finance | 2017-05-30 | 93 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | Internal Budget Finished | Role | CTSU Finance | 2017-05-30 | 93 |  | N | 92-AUCHUS
Pre-Award Financial - 96-BESIRLI | Planning Meeting Completed | Role | CTSU Finance | 2017-05-30 | 0 | 2017-05-02 | N | 00129820
Calendaring : Initial Calendar Build - 00118461 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Dahlgren, Molly | 2017-05-30 | 0 | 2017-05-30 | N | 00118461
Calendaring : Initial Calendar Build - 158-PIPE | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-05-30 | 0 | 2017-05-30 | N | 00131463
Calendaring : Initial Calendar Build - 158-PIPE | Assign to Analyst | User | Munasinghe, Sadeepa | 2017-05-30 | 0 | 2017-05-30 | N | 00131463
Calendaring : Initial Calendar Build - 94-AUCHUS | Assign to Analyst | User | Munasinghe, Sadeepa | 2017-05-30 | 1 | 2017-05-31 | N | 00129652
Pre-Award Financial - 239-KORLEY | Intake Form Completed | User | Munsey, Barbara | 2017-05-30 | 0 | 2017-05-30 | N | 00129045
Pre-Award Financial - 00128157 | PAF routed | User | VanderElzen, Liz | 2017-05-30 | 87 | 2017-08-25 | N | 00128157
Calendaring : Amendment Checklist & Process - 00101092 | Acknowledge | User | Yunk, Jason | 2017-05-30 | 62 | 2017-07-31 | N | 00101092
Pre-Award Financial - 33-FLAHERTY | OnCore Budget Build | User | Yunk, Jason | 2017-05-30 | 27 | 2017-06-26 | N | 00129716
Calendaring : Initial Calendar Build - 175-ORAL | Assign to Analyst | User | van Dijk, Tim | 2017-05-30 | 0 | 2017-05-30 | N | 175-ORAL
Calendaring : Initial Calendar Build - 4033CYTOKINETICS-GOUTMAN | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Boyd, Collin | 2017-05-31 | 5 | 2017-06-05 | N | 00130639
Pre-Award Financial - 142-FLAHERTY | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-05-31 | 92 |  | N | 142-FLAHERTY
Pre-Award Financial - 242-AS-SANIE | Intake Form Completed | Role | CTSU Coordinator | 2017-05-31 | 0 | 2017-05-31 | N | 242-AS-SANIE
CTSU Post-Award - 00107755 | Date Reconciled | Role | CTSU Finance | 2017-05-31 | 0 | 2017-05-31 | N | 00107755
CTSU Post-Award - 00113391 | Date Reconciled | Role | CTSU Finance | 2017-05-31 | 0 | 2017-05-31 | N | 00113391
CTSU Post-Award - 00119175 | Date Reconciled | Role | CTSU Finance | 2017-05-31 | 0 | 2017-05-31 | N | 00119175
Calendaring : Initial Calendar Build - 00130757 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-05-31 | 14 | 2017-06-14 | N | 00130757
Calendaring : Initial Calendar Build - 93-FREEHILL | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-05-31 | 69 | 2017-08-08 | N | 00129863
Calendaring : Initial Calendar Build - 94-AUCHUS | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-05-31 | 2 | 2017-06-02 | N | 00129652
Calendaring : Initial Calendar Build - 94-AUCHUS | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-05-31 | 7 | 2017-06-07 | N | 00129652
Calendaring : Initial Calendar Build - 00130793 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Oliver, Amy | 2017-05-31 | 47 | 2017-07-17 | N | 00130793
Pre-Award Financial - 33-FLAHERTY | Calendar Released | User | Oliver, Amy | 2017-05-31 | 27 | 2017-06-27 | N | 00129716
Pre-Award Financial - 71-RICE | Internal Budget Finished | User | Oliver, Amy | 2017-05-31 | 75 | 2017-08-14 | N | 00134857
Calendaring : Amendment Checklist & Process - 00113560 | Complete Calendar and Document Approval | User | Przykucki, Anne | 2017-05-31 | 70 | 2017-08-09 | N | 00113560
CTSU Post-Award - 00066077 | Date Reconciled | User | Yunk, Jason | 2017-05-31 | 0 | 2017-05-31 | N | 00066077
CTSU Post-Award - 00101092 | Date Reconciled | User | Yunk, Jason | 2017-05-31 | 0 | 2017-05-31 | N | 00101092
CTSU Post-Award - 00101426 | Date Reconciled | User | Yunk, Jason | 2017-05-31 | 0 | 2017-05-31 | N | 00101426
CTSU Post-Award - 00107927 | Date Reconciled | User | Yunk, Jason | 2017-05-31 | 0 | 2017-05-31 | N | 00107927
CTSU Post-Award - 00107954 | Date Reconciled | User | Yunk, Jason | 2017-05-31 | 0 | 2017-05-31 | N | 00107954
CTSU Post-Award - 00113496 | Date Reconciled | User | Yunk, Jason | 2017-05-31 | 0 | 2017-05-31 | N | 00113496
CTSU Post-Award - 00114593 | Date Reconciled | User | Yunk, Jason | 2017-05-31 | 0 | 2017-05-31 | N | 00114593
CTSU Post-Award - 00118570 | Date Reconciled | User | Yunk, Jason | 2017-05-31 | 0 | 2017-05-31 | N | 00118570
CTSU Post-Award - 00119399 | Date Reconciled | User | Yunk, Jason | 2017-05-31 | 0 | 2017-05-31 | N | 00119399
CTSU Post-Award - 00123231 | Date Reconciled | User | Yunk, Jason | 2017-05-31 | 0 | 2017-05-31 | N | 00123231
CTSU Post-Award - 00123861 | Date Reconciled | User | Yunk, Jason | 2017-05-31 | 0 | 2017-05-31 | N | 00123861
Calendaring : Initial Calendar Build - 175-ORAL | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-05-31 | 7 | 2017-06-07 | N | 175-ORAL
Calendaring : Initial Calendar Build - 175-ORAL | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-05-31 | 7 | 2017-06-07 | N | 175-ORAL
Calendaring : Initial Calendar Build - 00125599 | Feasibility Approval Notice Received | Role | CRAO | 2017-06-01 | 1 | 2017-06-02 | N | 00125599
CTSU Pre-Award v2 - 00111295 | Feasibility w/Documents received | Role | CTSU Administrator | 2017-06-01 | 91 |  | N | 00111295
Open to Accrual - 00129716 | Budget Finalized | Role | CTSU Administrator | 2017-06-01 | 0 | 2017-06-01 | N | 00129716
Open to Accrual - 00129716 | Contract Executed | Role | CTSU Administrator | 2017-06-01 | 39 | 2017-07-10 | N | 00129716
Pre-Award Financial - 34-MARSH | Open to Accrual | Role | CTSU Administrator | 2017-06-01 | 91 |  | N | 34-MARSH
CTSU Pre-Award v2 - 00111295 | Sponsor Reach out | Role | CTSU Coordinator | 2017-06-01 | 0 | 2017-06-01 | N | 00111295
CTSU Pre-Award v2 - 82-BOLLING | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-06-01 | 91 |  | N | 82-BOLLING
CTSU Pre-Award v2 - 82-BOLLING | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-06-01 | 91 |  | N | 82-BOLLING
CTSU Pre-Award v2 - 82-BOLLING | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-06-01 | 91 |  | N | 82-BOLLING
Calendaring : Amendment Checklist & Process - 00115982 | Assign to Analyst | User | Hodges, Lynda | 2017-06-01 | 0 | 2017-05-30 | N | 00115982
Pre-Award Financial - 69-KHANNA | PAF routed | User | Oliver, Amy | 2017-06-01 | 0 | 2017-02-13 | N | 69-KHANNA
Calendaring : Initial Calendar Build - 00118461 | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-06-01 | 0 | 2017-06-01 | N | 00118461
Calendaring : Initial Calendar Build - 00118461 | Make Updates | User | Radenbaugh, Pauline | 2017-06-01 | 0 | 2017-06-01 | N | 00118461
Calendaring : Specification Update Request(s) - 00127136 | Submit Update Request(s) | User | Yunk, Jason | 2017-06-01 | 4 | 2017-06-05 | N | 00127136
Calendaring : Initial Calendar Build - 147-SCHIOPU | Feasibility Approval Notice Received | Role | CRAO | 2017-06-02 | 0 | 2017-06-02 | N | 00131329
Calendaring : Initial Calendar Build - 170-SCHIOPU | Feasibility Approval Notice Received | Role | CRAO | 2017-06-02 | 0 | 2017-06-02 | N | 00134035
Calendaring : Initial Calendar Build - 70-LUGOGO | Feasibility Approval Notice Received | Role | CRAO | 2017-06-02 | 0 | 2017-06-02 | N | 70-LUGOGO
Pre-Award Financial - 147-SCHIOPU | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-02 | 0 | 2017-06-02 | N | 00131329
Pre-Award Financial - 170-SCHIOPU | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-02 | 0 | 2017-06-02 | N | 00134035
Pre-Award Financial - 142-FLAHERTY | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-06-02 | 90 |  | N | 142-FLAHERTY
Pre-Award Financial - 00130793 | Planning Meeting Completed | Role | CTSU Finance | 2017-06-02 | 11 | 2017-06-13 | N | 00130793
Pre-Award Financial - 142-FLAHERTY | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-06-02 | 90 |  | N | 142-FLAHERTY
Pre-Award Financial - 142-FLAHERTY | Request MCRU Budget | Role | CTSU Finance | 2017-06-02 | 90 |  | N | 142-FLAHERTY
Pre-Award Financial - 142-FLAHERTY | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-06-02 | 90 |  | N | 142-FLAHERTY
Pre-Award Financial - 246-AS-SANIE | Intake Form Completed | Role | CTSU Finance | 2017-06-02 | 0 | 2017-06-02 | N | 246-AS-SANIE
Pre-Award Financial - 87-ORAL | Planning Meeting Completed | Role | CTSU Finance | 2017-06-02 | 0 | 2017-05-30 | N | 00130757
Pre-Award Financial - 91-ELSE | PI approved Budget | Role | CTSU Finance | 2017-06-02 | 90 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | PI approved Budget | Role | CTSU Finance | 2017-06-02 | 90 |  | N | 92-AUCHUS
Calendaring : Initial Calendar Build - 00125599 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-02 | 0 | 2017-06-02 | N | 00125599
Calendaring : Initial Calendar Build - 147-SCHIOPU | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-02 | 0 | 2017-06-02 | N | 00131329
Calendaring : Initial Calendar Build - 170-SCHIOPU | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-02 | 0 | 2017-06-02 | N | 00134035
Calendaring : Initial Calendar Build - 70-LUGOGO | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-02 | 4 | 2017-06-06 | N | 70-LUGOGO
Calendaring : Amendment Checklist & Process - 00115982 | ** Footnote Edits | User | Hodges, Lynda | 2017-06-02 | 6 | 2017-06-08 | N | 00115982
Calendaring : Amendment Checklist & Process - 00115982 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Hodges, Lynda | 2017-06-02 | 6 | 2017-06-08 | N | 00115982
Calendaring : Amendment Checklist & Process - 00115982 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Hodges, Lynda | 2017-06-02 | 6 | 2017-06-08 | N | 00115982
Calendaring : Initial Calendar Build - 00125599 | Assign to Analyst | User | Hodges, Lynda | 2017-06-02 | 3 | 2017-06-05 | N | 00125599
Calendaring : Amendment Checklist & Process - 00110881 | Provide PI-Determined Care Designations ( +/- Feedback ) | User | Kim, Sangri | 2017-06-02 | 0 | 2017-05-30 | N | 00110881
Calendaring : Initial Calendar Build - 147-SCHIOPU | Assign to Analyst | User | Munasinghe, Sadeepa | 2017-06-02 | 0 | 2017-06-02 | N | 00131329
Calendaring : Initial Calendar Build - 158-PIPE | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-06-02 | 21 | 2017-06-23 | N | 00131463
Calendaring : Initial Calendar Build - 158-PIPE | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-06-02 | 7 | 2017-06-09 | N | 00131463
Calendaring : Initial Calendar Build - 158-PIPE | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-06-02 | 9 | 2017-06-11 | N | 00131463
Calendaring : Initial Calendar Build - 4033CYTOKINETICS-GOUTMAN | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-06-02 | 7 | 2017-06-09 | N | 00130639
Calendaring : Initial Calendar Build - 4033CYTOKINETICS-GOUTMAN | Make Updates | User | Munasinghe, Sadeepa | 2017-06-02 | 3 | 2017-06-05 | N | 00130639
Calendaring : Initial Calendar Build - 94-AUCHUS | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-06-02 | 28 | 2017-06-30 | N | 00129652
Calendaring : Initial Calendar Build - 94-AUCHUS | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-06-02 | 0 | 2017-06-02 | N | 00129652
Calendaring : Initial Calendar Build - KCHOU001 | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-06-02 | 0 | 2017-05-31 | N | 00130004
Calendaring : Initial Calendar Build - 00130757 | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-06-02 | 21 | 2017-06-23 | N | 00130757
Calendaring : Initial Calendar Build - 00130757 | Make Updates | User | Zahs, Brian | 2017-06-02 | 21 | 2017-06-23 | N | 00130757
Calendaring : Initial Calendar Build - 93-FREEHILL | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-06-02 | 69 | 2017-08-10 | N | 00129863
Calendaring : Initial Calendar Build - 93-FREEHILL | Make Updates | User | Zahs, Brian | 2017-06-02 | 20 | 2017-06-22 | N | 00129863
Calendaring : Initial Calendar Build - 00130793 | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-06-02 | 48 | 2017-07-20 | N | 00130793
Calendaring : Initial Calendar Build - 00130793 | Make Updates | User | van Dijk, Tim | 2017-06-02 | 48 | 2017-07-20 | N | 00130793
Calendaring : Initial Calendar Build - 170-SCHIOPU | Assign to Analyst | User | van Dijk, Tim | 2017-06-02 | 0 | 2017-06-02 | N | 00134035
Calendaring : Initial Calendar Build - 175-ORAL | Complete MCA / QCT | User | van Dijk, Tim | 2017-06-02 | 0 | 2017-06-02 | N | 175-ORAL
Calendaring : Initial Calendar Build - 175-ORAL | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-06-02 | 0 | 2017-06-01 | N | 175-ORAL
Pre-Award Financial - 180-HOFF | Feasibility w/Documents received | Role | CTSU Administrator | 2017-06-03 | 89 |  | N | 00129450
Pre-Award Financial - 33-FLAHERTY | PI Signoff in OnCore | Role | CTSU Administrator | 2017-06-03 | 44 | 2017-07-17 | N | 00129716
Calendaring : Initial Calendar Build - 00118461 | Acknowledge | User | Dahlgren, Molly | 2017-06-03 | 0 | 2017-06-01 | N | 00118461
Calendaring : Specification Update Request(s) - 00127136 | Assign to Analyst | User | LaVasseur, Kristen | 2017-06-03 | 6 | 2017-06-09 | N | 00127136
Pre-Award Financial - 71-RICE | PI approved Budget | User | Oliver, Amy | 2017-06-03 | 89 |  | N | 00134857
Pre-Award Financial - 147-SCHIOPU | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-06-04 | 0 | 2017-06-02 | N | 00131329
Pre-Award Financial - 170-SCHIOPU | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-06-04 | 0 | 2017-06-02 | N | 00134035
Pre-Award Financial - 205-KHANNA | Intake Form Completed | Role | CTSU Coordinator | 2017-06-04 | 0 | 2017-06-04 | N | 00132200
Calendaring : Initial Calendar Build - | Acknowledge | Role | CTSU Finance | 2017-06-04 | 88 |  | N | 103-GAGNIER
Calendaring : Initial Calendar Build - 93-FREEHILL | Acknowledge | Role | CTSU Finance | 2017-06-04 | 88 |  | N | 00129863
Pre-Award Financial - 147-SCHIOPU | Request MCRU Budget | Role | CTSU Finance | 2017-06-04 | 33 | 2017-07-07 | N | 00131329
Pre-Award Financial - 170-SCHIOPU | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-06-04 | 3 | 2017-06-07 | N | 00134035
Pre-Award Financial - 91-ELSE | Budget Negotiations | Role | CTSU Finance | 2017-06-04 | 88 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | Budget Negotiations | Role | CTSU Finance | 2017-06-04 | 88 |  | N | 92-AUCHUS
Calendaring : Initial Calendar Build - KCHOU001 | Acknowledge | User | Frasier, Lora | 2017-06-04 | 0 | 2017-06-01 | N | 00130004
Pre-Award Financial - 147-SCHIOPU | Created CTRF & "Notify ORSP" | User | Henry, Robin | 2017-06-04 | 64 | 2017-08-07 | N | 00131329
Pre-Award Financial - 147-SCHIOPU | Request Research Pharmacy Budget | User | Henry, Robin | 2017-06-04 | 1 | 2017-06-05 | N | 00131329
Pre-Award Financial - 170-SCHIOPU | Request Research Pharmacy Budget | User | Henry, Robin | 2017-06-04 | 1 | 2017-06-05 | N | 00134035
Calendaring : Amendment Checklist & Process - 00110881 | Complete Calendar and Document Approval | User | Hodges, Lynda | 2017-06-04 | 0 | 2017-06-01 | N | 00110881
Calendaring : Initial Calendar Build - 158-PIPE | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-06-04 | 8 | 2017-06-12 | N | 00131463
Calendaring : Initial Calendar Build - 158-PIPE | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-06-04 | 19 | 2017-06-23 | N | 00131463
Calendaring : Initial Calendar Build - 00130757 | Acknowledge | User | Oliver, Amy | 2017-06-04 | 32 | 2017-07-06 | N | 00130757
Calendaring : Initial Calendar Build - 00130793 | Acknowledge | User | Oliver, Amy | 2017-06-04 | 50 | 2017-07-24 | N | 00130793
Pre-Award Financial - 00129427 | Final Budget | User | Oliver, Amy | 2017-06-04 | 88 |  | N | 00129427
Calendaring : Initial Calendar Build - 00125599 | Nimblify Build is Complete & Ready for Import | Role | CRAO | 2017-06-05 | 7 | 2017-06-12 | N | 00125599
Calendaring : Initial Calendar Build - 00131837 | Feasibility Approval Notice Received | Role | CRAO | 2017-06-05 | 2 | 2017-06-07 | N | 00131837
Calendaring : Initial Calendar Build - 230-ROGERS | Feasibility Approval Notice Received | Role | CRAO | 2017-06-05 | 2 | 2017-06-07 | N | 00130272
Pre-Award Financial - 188-RUBENSTEIN | Feasibility w/Documents received | Role | CTSU Administrator | 2017-06-05 | 87 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 33-FLAHERTY | Open to Accrual | Role | CTSU Administrator | 2017-06-05 | 87 |  | N | 00129716
Pre-Award Financial - 49-MARTINEZ | Feasibility w/Documents received | Role | CTSU Administrator | 2017-06-05 | 0 | 2017-06-05 | N | 00132020
Pre-Award Financial - 70-LUGOGO | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-05 | 0 | 2017-06-05 | N | 70-LUGOGO
Pre-Award Financial - 76-KHANNA | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-05 | 0 | 2017-06-05 | N | 00131837
Pre-Award Financial - 00126010 | IRB Application Submitted | Role | CTSU Coordinator | 2017-06-05 | 0 | 2017-06-05 | N | 00126010
Pre-Award Financial - 188-RUBENSTEIN | Sponsor Reach out | Role | CTSU Coordinator | 2017-06-05 | 0 | 2017-06-01 | N | 188-RUBENSTEIN
Pre-Award Financial - 188-RUBENSTEIN | UFA Completed | Role | CTSU Coordinator | 2017-06-05 | 0 | 2017-05-15 | N | 188-RUBENSTEIN
Pre-Award Financial - 251-COMER | Intake Form Completed | Role | CTSU Coordinator | 2017-06-05 | 0 | 2017-06-05 | N | 00134232
Pre-Award Financial - 49-MARTINEZ | Sponsor Reach out | Role | CTSU Coordinator | 2017-06-05 | 0 | 2017-03-30 | N | 00132020
Calendaring : Initial Calendar Build - 00129943 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-06-05 | 8 | 2017-06-13 | N | 00129943
Calendaring : Initial Calendar Build - 162-PIPE | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-06-05 | 8 | 2017-06-13 | N | 00131320
Calendaring : Specification Update Request(s) - 00113560 | ** Structural Edits | Role | CTSU Finance | 2017-06-05 | 0 | 2017-06-05 | N | 00113560
Calendaring : Specification Update Request(s) - 00113560 | Submit Update Request(s) | Role | CTSU Finance | 2017-06-05 | 0 | 2017-06-05 | N | 00113560
Pre-Award Financial - 76-KHANNA | Final Budget | Role | CTSU Finance | 2017-06-05 | 7 | 2017-06-12 | N | 00131837
Calendaring : Initial Calendar Build - 230-ROGERS | Assign to Analyst | User | Greene, Paula | 2017-06-05 | 2 | 2017-06-07 | N | 00130272
Pre-Award Financial - 00130793 | Care Designations completed | User | Henry, Robin | 2017-06-05 | 42 | 2017-07-17 | N | 00130793
Pre-Award Financial - 87-ORAL | Care Designations completed | User | Henry, Robin | 2017-06-05 | 9 | 2017-06-14 | N | 00130757
Calendaring : Initial Calendar Build - 230-ROGERS | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-05 | 0 | 2017-06-05 | N | 00130272
Calendaring : Initial Calendar Build - 00125599 | Complete MCA / QCT | User | Hodges, Lynda | 2017-06-05 | 7 | 2017-06-12 | N | 00125599
Calendaring : Initial Calendar Build - 147-SCHIOPU | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-06-05 | 11 | 2017-06-16 | N | 00131329
Calendaring : Initial Calendar Build - 147-SCHIOPU | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-06-05 | 11 | 2017-06-16 | N | 00131329
Calendaring : Initial Calendar Build - 147-SCHIOPU | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-06-05 | 15 | 2017-06-20 | N | 00131329
Pre-Award Financial - 71-RICE | Budget Negotiations | User | Oliver, Amy | 2017-06-05 | 87 |  | N | 00134857
Calendaring : Initial Calendar Build - 70-LUGOGO | Assign to Analyst | User | Radenbaugh, Pauline | 2017-06-05 | 0 | 2017-06-05 | N | 70-LUGOGO
Calendaring : Initial Calendar Build - 70-LUGOGO | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-06-05 | 11 | 2017-06-16 | N | 70-LUGOGO
Pre-Award Financial - 00129652 | Billing Calendar Received | User | VanderElzen, Liz | 2017-06-05 | 15 | 2017-06-20 | N | 00129652
Calendaring : Initial Calendar Build - 170-SCHIOPU | Complete MCA / QCT | User | van Dijk, Tim | 2017-06-05 | 1 | 2017-06-06 | N | 00134035
Calendaring : Initial Calendar Build - 170-SCHIOPU | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-06-05 | 1 | 2017-06-06 | N | 00134035
Calendaring : Initial Calendar Build - 170-SCHIOPU | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-06-05 | 4 | 2017-06-09 | N | 00134035
Calendaring : Initial Calendar Build - 00126010 | Feasibility Approval Notice Received | Role | CRAO | 2017-06-06 | 1 | 2017-06-07 | N | 00126010
Calendaring : Initial Calendar Build - 236-NASR | Feasibility Approval Notice Received | Role | CRAO | 2017-06-06 | 0 | 2017-06-06 | N | 00131580
Calendaring : Initial Calendar Build - 49-MARTINEZ | Feasibility Approval Notice Received | Role | CRAO | 2017-06-06 | 1 | 2017-06-07 | N | 00132020
Pre-Award Financial - 00126010 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-06 | 0 | 2017-06-06 | N | 00126010
Pre-Award Financial - 190-SCHIOPU | Feasibility w/Documents received | Role | CTSU Administrator | 2017-06-06 | 23 | 2017-06-29 | N | 00134443
Pre-Award Financial - 49-MARTINEZ | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-06 | 0 | 2017-06-06 | N | 00132020
Pre-Award Financial - 190-SCHIOPU | Sponsor Reach out | Role | CTSU Coordinator | 2017-06-06 | 0 | 2017-05-26 | N | 00134443
Pre-Award Financial - 190-SCHIOPU | UFA Completed | Role | CTSU Coordinator | 2017-06-06 | 0 | 2017-05-16 | N | 00134443
Pre-Award Financial - 194-MCLAUGHLIN | UFA Completed | Role | CTSU Finance | 2017-06-06 | 0 | 2017-06-06 | N | 194-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | UFA Completed | Role | CTSU Finance | 2017-06-06 | 0 | 2017-06-06 | N | 234-MCLAUGHLIN
Pre-Award Financial - 77-CONJEEVARAM | Final Budget | Role | CTSU Finance | 2017-06-06 | 86 |  | N | 77-CONJEEVARAM
Calendaring : Amendment Checklist & Process - 00108921 | AME Calendaring Process Initiated | User | Gladkowski, Ginger | 2017-06-06 | 0 | 2017-06-06 | N | 00108921
Calendaring : Initial Calendar Build - 00131837 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-06 | 0 | 2017-06-06 | N | 00131837
Pre-Award Financial - 00129427 | PAF routed | User | Oliver, Amy | 2017-06-06 | 86 |  | N | 00129427
Calendaring : Amendment Checklist & Process - 00110881 | Acknowledge | User | Rollins, Matthew | 2017-06-06 | 0 | 2017-06-01 | N | 00110881
Pre-Award Financial - 255-LOK | Intake Form Completed | Role | CTSU Coordinator | 2017-06-07 | 0 | 2017-06-07 | N | 255-LOK
Pre-Award Financial - 70-LUGOGO | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-06-07 | 0 | 2017-06-05 | N | 70-LUGOGO
Pre-Award Financial - 76-KHANNA | IRB Application Submitted | Role | CTSU Coordinator | 2017-06-07 | 0 | 2017-06-07 | N | 00131837
Calendaring : Specification Update Request(s) - 00128253 | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance | 2017-06-07 | 0 | 2017-06-07 | N | 00128253
Calendaring : Specification Update Request(s) - 00128253 | Submit Update Request(s) | Role | CTSU Finance | 2017-06-07 | 0 | 2017-06-07 | N | 00128253
Pre-Award Financial - 234-MCLAUGHLIN | Sponsor Reach out | Role | CTSU Finance | 2017-06-07 | 0 | 2017-06-07 | N | 234-MCLAUGHLIN
Pre-Award Financial - 76-KHANNA | PAF routed | Role | CTSU Finance | 2017-06-07 | 5 | 2017-06-12 | N | 00131837
Calendaring : Initial Calendar Build - 00126010 | Assign to Analyst | User | Greene, Paula | 2017-06-07 | 0 | 2017-06-07 | N | 00126010
Calendaring : Initial Calendar Build - 49-MARTINEZ | Assign to Analyst | User | Greene, Paula | 2017-06-07 | 0 | 2017-06-07 | N | 00132020
Calendaring : Initial Calendar Build - 00126010 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-07 | 0 | 2017-06-07 | N | 00126010
Calendaring : Initial Calendar Build - 00131837 | Assign to Analyst | User | Hess, Aaron | 2017-06-07 | 0 | 2017-06-07 | N | 00131837
Calendaring : Initial Calendar Build - 49-MARTINEZ | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-07 | 0 | 2017-06-07 | N | 00132020
Calendaring : Initial Calendar Build - 00125599 | Attach Build Notes ( as Protocol Doc ) | User | Hodges, Lynda | 2017-06-07 | 7 | 2017-06-14 | N | 00125599
Calendaring : Initial Calendar Build - 00125599 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hodges, Lynda | 2017-06-07 | 7 | 2017-06-14 | N | 00125599
Calendaring : Initial Calendar Build - 147-SCHIOPU | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-06-07 | 13 | 2017-06-20 | N | 00131329
Calendaring : Initial Calendar Build - 147-SCHIOPU | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-06-07 | 15 | 2017-06-22 | N | 00131329
Calendaring : Specification Update Request(s) - 00113560 | Assign to Analyst | User | Przykucki, Anne | 2017-06-07 | 28 | 2017-07-05 | N | 00113560
Calendaring : Initial Calendar Build - 70-LUGOGO | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-06-07 | 13 | 2017-06-20 | N | 70-LUGOGO
Calendaring : Initial Calendar Build - 70-LUGOGO | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-06-07 | 13 | 2017-06-20 | N | 70-LUGOGO
Calendaring : Initial Calendar Build - 94-AUCHUS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-06-07 | 16 | 2017-06-23 | N | 00129652
Pre-Award Financial - 00108880 | Final Budget | User | VanderElzen, Liz | 2017-06-07 | 85 |  | N | 00108880
Pre-Award Financial - 00126010 | Final Budget | User | VanderElzen, Liz | 2017-06-07 | 1 | 2017-06-08 | N | 00126010
Pre-Award Financial - 00126010 | Planning Meeting Completed | User | VanderElzen, Liz | 2017-06-07 | 0 | 2017-06-07 | N | 00126010
Pre-Award Financial - 00128173 | Final Budget | User | VanderElzen, Liz | 2017-06-07 | 85 |  | N | 00128173
Pre-Award Financial - 70-LUGOGO | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-06-07 | 0 | 2017-06-07 | N | 70-LUGOGO
Pre-Award Financial - 70-LUGOGO | Request Research Pharmacy Budget | User | VanderElzen, Liz | 2017-06-07 | 2 | 2017-06-09 | N | 70-LUGOGO
Calendaring : Specification Update Request(s) - 00127136 | ** Request(s) to Add Unscheduled Procedure(s) | User | Yunk, Jason | 2017-06-07 | 0 | 2017-06-07 | N | 00127136
Calendaring : Initial Calendar Build - 00125798 | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-06-07 | 9 | 2017-06-16 | N | 00125798
Calendaring : Initial Calendar Build - 00125798 | Make Updates | User | van Dijk, Tim | 2017-06-07 | 9 | 2017-06-16 | N | 00125798
Calendaring : Initial Calendar Build - 00129943 | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-06-07 | 7 | 2017-06-14 | N | 00129943
Calendaring : Initial Calendar Build - 00129943 | Make Updates | User | van Dijk, Tim | 2017-06-07 | 7 | 2017-06-14 | N | 00129943
Calendaring : Initial Calendar Build - 162-PIPE | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-06-07 | 7 | 2017-06-14 | N | 00131320
Calendaring : Initial Calendar Build - 162-PIPE | Make Updates | User | van Dijk, Tim | 2017-06-07 | 7 | 2017-06-14 | N | 00131320
Calendaring : Initial Calendar Build - 170-SCHIOPU | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-06-07 | 2 | 2017-06-09 | N | 00134035
Calendaring : Initial Calendar Build - 170-SCHIOPU | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-06-07 | 2 | 2017-06-09 | N | 00134035
Calendaring : Initial Calendar Build - 211-HIGGINS | Feasibility Approval Notice Received | Role | CRAO | 2017-06-08 | 0 | 2017-06-08 | N | 00128325
CTSU Pre-Award v2 - 00111295 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-08 | 84 |  | N | 00111295
Open to Accrual - 00129716 | Project Award Notice (PAN) Received | Role | CTSU Administrator | 2017-06-08 | 84 |  | N | 00129716
Pre-Award Financial - 211-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-08 | 0 | 2017-06-08 | N | 00128325
Pre-Award Financial - 00126010 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-06-08 | 0 | 2017-06-06 | N | 00126010
Pre-Award Financial - 201-MCCUNE | Sponsor Reach out | Role | CTSU Coordinator | 2017-06-08 | 7 | 2017-06-15 | N | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | UFA Completed | Role | CTSU Coordinator | 2017-06-08 | 7 | 2017-06-15 | N | 201-MCCUNE
Pre-Award Financial - 203-ELSE | Sponsor Reach out | Role | CTSU Coordinator | 2017-06-08 | 0 | 2017-06-08 | N | 00132173
Pre-Award Financial - 203-ELSE | UFA Completed | Role | CTSU Coordinator | 2017-06-08 | 0 | 2017-06-07 | N | 00132173
Pre-Award Financial - 261-LUGOGO | Intake Form Completed | Role | CTSU Coordinator | 2017-06-08 | 0 | 2017-06-08 | N | 261-LUGOGO
Pre-Award Financial - 49-MARTINEZ | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-06-08 | 0 | 2017-06-06 | N | 00132020
Calendaring : Amendment Checklist & Process - 00066077 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-06-08 | 0 | 2017-06-08 | N | 00066077
Calendaring : Specification Update Request(s) - 00125798 | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance | 2017-06-08 | 0 | 2017-06-08 | N | 00125798
Calendaring : Specification Update Request(s) - 00125798 | Submit Update Request(s) | Role | CTSU Finance | 2017-06-08 | 0 | 2017-06-08 | N | 00125798
Calendaring : Specification Update Request(s) - 00128322 2 | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance | 2017-06-08 | 0 | 2017-06-08 | N | 00128322
Calendaring : Specification Update Request(s) - 00128322 2 | Submit Update Request(s) | Role | CTSU Finance | 2017-06-08 | 0 | 2017-06-08 | N | 00128322
Pre-Award Financial - 77-CONJEEVARAM | PAF routed | Role | CTSU Finance | 2017-06-08 | 84 |  | N | 77-CONJEEVARAM
Calendaring : Initial Calendar Build - 236-NASR | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-08 | 0 | 2017-06-06 | N | 00131580
Calendaring : Specification Update Request(s) - 00127136 | Make Update(s) | User | LaVasseur, Kristen | 2017-06-08 | 1 | 2017-06-09 | N | 00127136
Calendaring : Specification Update Request(s) - 00127136 | Re-Complete Calendar | User | LaVasseur, Kristen | 2017-06-08 | 1 | 2017-06-09 | N | 00127136
Calendaring : Amendment Checklist & Process - 00108921 | Assign to Analyst | User | Przykucki, Anne | 2017-06-08 | 0 | 2017-06-06 | N | 00108921
Calendaring : Initial Calendar Build - 236-NASR | Assign to Analyst | User | Radenbaugh, Pauline | 2017-06-08 | 0 | 2017-06-06 | N | 00131580
Calendaring : Initial Calendar Build - 70-LUGOGO | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-06-08 | 0 | 2017-06-06 | N | 70-LUGOGO
Calendaring : Initial Calendar Build - 70-LUGOGO | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-06-08 | 0 | 2017-06-06 | N | 70-LUGOGO
Pre-Award Financial - 00126010 | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-06-08 | 0 | 2017-06-08 | N | 00126010
Pre-Award Financial - 00129652 | Planning Meeting Completed | User | VanderElzen, Liz | 2017-06-08 | 0 | 2017-06-08 | N | 00129652
Pre-Award Financial - 49-MARTINEZ | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-06-08 | 0 | 2017-06-06 | N | 00132020
Pre-Award Financial - 49-MARTINEZ | Request Research Pharmacy Budget | User | VanderElzen, Liz | 2017-06-08 | 0 | 2017-06-06 | N | 00132020
Calendaring : Initial Calendar Build - 230-ROGERS | Nimblify Build is Complete & Ready for Import | User | Zahs, Brian | 2017-06-08 | 0 | 2007-06-09 | N | 00130272
Calendaring : Initial Calendar Build - 235-SUGAR | Feasibility Approval Notice Received | Role | CRAO | 2017-06-09 | 0 | 2017-06-09 | N | 235-SUGAR
Calendaring : Initial Calendar Build - 268-NEUMAR | Feasibility Approval Notice Received | Role | CRAO | 2017-06-09 | 0 | 2017-06-09 | N | 268-NEUMAR
Open to Accrual - 00129716 | Study Team Roles/Responsibilities Finalized | Role | CTSU Administrator | 2017-06-09 | 42 | 2017-07-21 | N | 00129716
Pre-Award Financial - 205-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-06-09 | 73 | 2017-08-21 | N | 205-HIGGINS
Pre-Award Financial - 235-SUGAR | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-09 | 0 | 2017-06-09 | N | 235-SUGAR
Pre-Award Financial - 00129652 | IRB Application Submitted | Role | CTSU Coordinator | 2017-06-09 | 0 | 2017-06-09 | N | 00129652
Pre-Award Financial - 147-SCHIOPU | IRB Application Submitted | Role | CTSU Coordinator | 2017-06-09 | 0 | 2017-06-09 | N | 00131329
Pre-Award Financial - 205-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator | 2017-06-09 | 5 | 2017-06-14 | N | 205-HIGGINS
Pre-Award Financial - 205-HIGGINS | UFA Completed | Role | CTSU Coordinator | 2017-06-09 | 4 | 2017-06-13 | N | 205-HIGGINS
Pre-Award Financial - 263-DELMONTE | Intake Form Completed | Role | CTSU Coordinator | 2017-06-09 | 0 | 2017-06-09 | N | 263-DELMONTE
CTSU Post-Award - 00129851 | Date Reconciled | Role | CTSU Finance | 2017-06-09 | 0 | 2017-06-09 | N | 00129851
CTSU Pre-Award v2 - 82-BOLLING | Billing Calendar Received | Role | CTSU Finance | 2017-06-09 | 83 |  | N | 82-BOLLING
Calendaring : Amendment Checklist & Process - 00091897 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-06-09 | 0 | 2017-06-09 | N | 00091897
Calendaring : Amendment Checklist & Process - 00115982 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance | 2017-06-09 | 0 | 2017-06-08 | N | 00115982
Calendaring : Initial Calendar Build - 00125798 | Acknowledge | Role | CTSU Finance | 2017-06-09 | 7 | 2017-06-16 | N | 00125798
Calendaring : Initial Calendar Build - 00129943 | Acknowledge | Role | CTSU Finance | 2017-06-09 | 5 | 2017-06-14 | N | 00129943
Calendaring : Initial Calendar Build - 162-PIPE | Acknowledge | Role | CTSU Finance | 2017-06-09 | 5 | 2017-06-14 | N | 00131320
Pre-Award Financial - SCHIOPU-1 | OnCore Budget Build | Role | CTSU Finance | 2017-06-09 | 83 |  | N | SCHIOPU-1
Calendaring : Amendment Checklist & Process - 00108139 | AME Calendaring Process Initiated | User | Frisch, Karen | 2017-06-09 | 32 | 2017-07-11 | N | 00108139
Calendaring : Amendment Checklist & Process - 00108921 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Gladkowski, Ginger | 2017-06-09 | 83 |  | N | 00108921
Pre-Award Financial - 00130793 | Internal Budget Finished | User | Henry, Robin | 2017-06-09 | 45 | 2017-07-24 | N | 00130793
Pre-Award Financial - 87-ORAL | Internal Budget Finished | User | Henry, Robin | 2017-06-09 | 20 | 2017-06-29 | N | 00130757
Calendaring : Initial Calendar Build - 00131837 | Nimblify Build is Complete & Ready for Import | User | Hess, Aaron | 2017-06-09 | 11 | 2017-06-20 | N | 00131837
Open to Accrual - 00129709 | Contract Executed | User | Miller, Diana | 2017-06-09 | 0 | 2017-06-09 | N | 00129709
Calendaring : Initial Calendar Build - 94-AUCHUS | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-06-09 | 21 | 2017-06-30 | N | 00129652
Calendaring : Amendment Checklist & Process - 00108921 | ** Footnote Edits | User | Przykucki, Anne | 2017-06-09 | 83 |  | N | 00108921
Calendaring : Amendment Checklist & Process - 00108921 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Przykucki, Anne | 2017-06-09 | 83 |  | N | 00108921
Calendaring : Amendment Checklist & Process - 00108921 | ** Visit Tolerance Edits | User | Przykucki, Anne | 2017-06-09 | 83 |  | N | 00108921
Calendaring : Specification Update Request(s) - 00128253 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-06-09 | 11 | 2017-06-20 | N | 00128253
Pre-Award Financial - 00108880 | PAF routed | User | VanderElzen, Liz | 2017-06-09 | 83 |  | N | 00108880
Pre-Award Financial - 00126010 | PAF routed | User | VanderElzen, Liz | 2017-06-09 | 0 | 2017-06-08 | N | 00126010
Pre-Award Financial - 00128173 | PAF routed | User | VanderElzen, Liz | 2017-06-09 | 83 |  | N | 00128173
Open to Accrual - 00129716 | Adequate Equipment and Supplies Available | Role | CTSU Administrator | 2017-06-10 | 82 |  | N | 00129716
Open to Accrual - 00129716 | Investigational Drug/Device Supplies Available | Role | CTSU Administrator | 2017-06-10 | 82 |  | N | 00129716
Open to Accrual - 00129716 | MiChart Verifications | Role | CTSU Administrator | 2017-06-10 | 82 |  | N | 00129716
Open to Accrual - 00129716 | Provisions for Support and Services Finalized | Role | CTSU Administrator | 2017-06-10 | 41 | 2017-07-21 | N | 00129716
Open to Accrual - 00129716 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Administrator | 2017-06-10 | 82 |  | N | 00129716
Open to Accrual - 00129716 | Study Files Established | Role | CTSU Administrator | 2017-06-10 | 41 | 2017-07-21 | N | 00129716
Pre-Award Financial - 180-HOFF | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-10 | 82 |  | N | 00129450
CTSU Pre-Award v2 - 00111295 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-06-10 | 82 |  | N | 00111295
Open to Accrual - 00129716 | Other Personnel Notified | Role | CTSU Coordinator | 2017-06-10 | 41 | 2017-07-21 | N | 00129716
Pre-Award Financial - 211-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-06-10 | 0 | 2017-06-09 | N | 00128325
CTSU Pre-Award v2 - 00111295 | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-06-10 | 82 |  | N | 00111295
CTSU Pre-Award v2 - 00111295 | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-06-10 | 82 |  | N | 00111295
Calendaring : Initial Calendar Build - 00126010 | Complete SVS & Pricing List ( Built & Coded ) | Role | CTSU Finance | 2017-06-10 | 0 | 2017-06-09 | N | 00126010
Pre-Award Financial - 142-FLAHERTY | Billing Calendar Received | Role | CTSU Finance | 2017-06-10 | 82 |  | N | 142-FLAHERTY
Pre-Award Financial - 81-HIGGINS | Final Budget | Role | CTSU Finance | 2017-06-10 | 82 |  | N | 81-HIGGINS
Pre-Award Financial - SCHIOPU-1 | Calendar Released | Role | CTSU Finance | 2017-06-10 | 82 |  | N | SCHIOPU-1
Calendaring : Initial Calendar Build - 211-HIGGINS | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-06-10 | 2 | 2017-06-12 | N | 00128325
Calendaring : Initial Calendar Build - 00131837 | Complete SVS & Pricing List ( Built & Coded ) | User | Hess, Aaron | 2017-06-10 | 11 | 2017-06-21 | N | 00131837
Calendaring : Amendment Checklist & Process - 00066077 | Assign to Analyst | User | Przykucki, Anne | 2017-06-10 | 0 | 2017-06-08 | N | 00066077
Calendaring : Amendment Checklist & Process - 00108921 | ** Items/Services : Addition or Removal of Procedures / Events | User | Przykucki, Anne | 2017-06-10 | 82 |  | N | 00108921
Calendaring : Initial Calendar Build - 00126010 | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-06-10 | 0 | 2017-06-09 | N | 00126010
Calendaring : Initial Calendar Build - 00126010 | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-06-10 | 4 | 2017-06-14 | N | 00126010
Calendaring : Initial Calendar Build - 211-HIGGINS | Assign to Analyst | User | Radenbaugh, Pauline | 2017-06-10 | 0 | 2017-06-09 | N | 00128325
Calendaring : Specification Update Request(s) - 00125798 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-06-10 | 10 | 2017-06-20 | N | 00125798
Calendaring : Specification Update Request(s) - 00128322 2 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-06-10 | 0 | 2017-06-09 | N | 00128322
Calendaring : Specification Update Request(s) - 00127136 | Acknowledge | User | Yunk, Jason | 2017-06-10 | 2 | 2017-06-12 | N | 00127136
Calendaring : Initial Calendar Build - 230-ROGERS | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian | 2017-06-10 | 34 | 2017-07-14 | N | 00130272
Calendaring : Initial Calendar Build - 230-ROGERS | Complete MCA / QCT | User | Zahs, Brian | 2017-06-10 | 82 |  | N | 00130272
Calendaring : Initial Calendar Build - 49-MARTINEZ | Complete MCA / QCT | User | van Dijk, Tim | 2017-06-10 | 0 | 2017-06-09 | N | 00132020
Calendaring : Initial Calendar Build - 49-MARTINEZ | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-06-10 | 0 | 2017-06-08 | N | 00132020
Calendaring : Initial Calendar Build - 49-MARTINEZ | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-06-10 | 6 | 2017-06-16 | N | 00132020
Pre-Award Financial - 235-SUGAR | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-06-11 | 5 | 2017-06-16 | N | 235-SUGAR
Calendaring : Initial Calendar Build - 158-PIPE | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-06-11 | 44 | 2017-07-25 | N | 00131463
Pre-Award Financial - 96-BESIRLI | Billing Calendar Received | Role | CTSU Finance | 2017-06-11 | 0 | 2017-04-25 | N | 00129820
Calendaring : Initial Calendar Build - 235-SUGAR | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-06-11 | 1 | 2017-06-12 | N | 235-SUGAR
Calendaring : Initial Calendar Build - 00131837 | Attach Build Notes ( as Protocol Doc ) | User | Hess, Aaron | 2017-06-11 | 9 | 2017-06-20 | N | 00131837
Calendaring : Initial Calendar Build - 00131837 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hess, Aaron | 2017-06-11 | 10 | 2017-06-21 | N | 00131837
Calendaring : Amendment Checklist & Process - 00108139 | Assign to Analyst | User | Hodges, Lynda | 2017-06-11 | 8 | 2017-06-19 | N | 00108139
Calendaring : Amendment Checklist & Process - 00115982 | Complete Calendar and Document Approval | User | Hodges, Lynda | 2017-06-11 | 8 | 2017-06-19 | N | 00115982
Calendaring : Amendment Checklist & Process - 00066077 | ** Footnote Edits | User | Przykucki, Anne | 2017-06-11 | 0 | 2017-06-09 | N | 00066077
Calendaring : Amendment Checklist & Process - 00066077 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Przykucki, Anne | 2017-06-11 | 0 | 2017-06-09 | N | 00066077
Calendaring : Amendment Checklist & Process - 00108921 | ** Other | User | Przykucki, Anne | 2017-06-11 | 81 |  | N | 00108921
Calendaring : Amendment Checklist & Process - 00108921 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Przykucki, Anne | 2017-06-11 | 81 |  | N | 00108921
Calendaring : Amendment Checklist & Process - 00108921 | ** Visits : Addition or Removal of Time Points | User | Przykucki, Anne | 2017-06-11 | 81 |  | N | 00108921
Calendaring : Amendment Checklist & Process - 00108921 | Request Care Designations | User | Przykucki, Anne | 2017-06-11 | 81 |  | N | 00108921
Calendaring : Amendment Checklist & Process - 00108921 | Update RSH Source in MBECT | User | Przykucki, Anne | 2017-06-11 | 81 |  | N | 00108921
Calendaring : Initial Calendar Build - 235-SUGAR | Assign to Analyst | User | Radenbaugh, Pauline | 2017-06-11 | 0 | 2017-06-09 | N | 235-SUGAR
Calendaring : Initial Calendar Build - 236-NASR | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-06-11 | 0 | 2017-06-06 | N | 00131580
Calendaring : Initial Calendar Build - 236-NASR | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-06-11 | 0 | 2017-06-07 | N | 00131580
Calendaring : Initial Calendar Build - 236-NASR | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-06-11 | 5 | 2017-06-16 | N | 00131580
Calendaring : Initial Calendar Build - 94-AUCHUS | Acknowledge | User | VanderElzen, Liz | 2017-06-11 | 25 | 2017-07-06 | N | 00129652
Pre-Award Financial - 235-SUGAR | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-06-11 | 81 |  | N | 235-SUGAR
Calendaring : Amendment Checklist & Process - 00091897 | Assign to Analyst | User | van Dijk, Tim | 2017-06-11 | 4 | 2017-06-15 | N | 00091897
Calendaring : Initial Calendar Build - 46-HIGGINS | Feasibility Approval Notice Received | Role | CRAO | 2017-06-12 | 0 | 2017-06-12 | N | 46-HIGGINS
Calendaring : Initial Calendar Build - 56-RAO | Feasibility Approval Notice Received | Role | CRAO | 2017-06-12 | 0 | 2017-06-12 | N | 00133286
Pre-Award Financial - 188-RUBENSTEIN | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-12 | 80 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 46-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-12 | 0 | 2017-06-12 | N | 46-HIGGINS
Pre-Award Financial - 56-RAO | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-12 | 0 | 2017-06-12 | N | 00133286
Pre-Award Financial - 180-HOFF | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-06-12 | 0 | 2017-05-12 | N | 00129450
Pre-Award Financial - 33-FLAHERTY | IRB Application Submitted | Role | CTSU Coordinator | 2017-06-12 | 0 | 2017-06-12 | N | 00129716
Pre-Award Financial - 81-HIGGINS | PAF routed | Role | CTSU Finance | 2017-06-12 | 80 |  | N | 81-HIGGINS
Calendaring : Initial Calendar Build - 268-NEUMAR | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-06-12 | 0 | 2017-06-12 | N | 268-NEUMAR
Calendaring : Initial Calendar Build - 46-HIGGINS | Assign to Analyst | User | Greene, Paula | 2017-06-12 | 0 | 2017-06-12 | N | 46-HIGGINS
Calendaring : Initial Calendar Build - 46-HIGGINS | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-06-12 | 0 | 2017-06-12 | N | 46-HIGGINS
Calendaring : Initial Calendar Build - 56-RAO | Assign to Analyst | User | Greene, Paula | 2017-06-12 | 0 | 2017-06-12 | N | 00133286
Calendaring : Initial Calendar Build - 56-RAO | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-06-12 | 0 | 2017-06-12 | N | 00133286
Pre-Award Financial - 00130793 | PI approved Budget | User | Henry, Robin | 2017-06-12 | 74 | 2017-08-25 | N | 00130793
Pre-Award Financial - 147-SCHIOPU | Billing Calendar Received | User | Henry, Robin | 2017-06-12 | 10 | 2017-06-22 | N | 00131329
Pre-Award Financial - 170-SCHIOPU | Billing Calendar Received | User | Henry, Robin | 2017-06-12 | 0 | 2017-06-09 | N | 00134035
Pre-Award Financial - 87-ORAL | PI approved Budget | User | Henry, Robin | 2017-06-12 | 17 | 2017-06-29 | N | 00130757
Calendaring : Amendment Checklist & Process - 00108139 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Hodges, Lynda | 2017-06-12 | 29 | 2017-07-11 | N | 00108139
Pre-Award Financial - 00128743 | PAN Released | User | Oliver, Amy | 2017-06-12 | 80 |  | N | 00128743
Calendaring : Amendment Checklist & Process - 00066077 | ** Items/Services : Addition or Removal of Procedures / Events | User | Przykucki, Anne | 2017-06-12 | 0 | 2017-06-09 | N | 00066077
Calendaring : Specification Update Request(s) - 00113560 | Make Update(s) | User | Przykucki, Anne | 2017-06-12 | 58 | 2017-08-09 | N | 00113560
Calendaring : Initial Calendar Build - 00126010 | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-06-12 | 2 | 2017-06-14 | N | 00126010
Calendaring : Initial Calendar Build - 00126010 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-06-12 | 2 | 2017-06-14 | N | 00126010
Pre-Award Financial - 00129652 | Care Designations completed | User | VanderElzen, Liz | 2017-06-12 | 18 | 2017-06-30 | N | 00129652
Calendaring : Amendment Checklist & Process - 00091897 | ** Footnote Edits | User | van Dijk, Tim | 2017-06-12 | 3 | 2017-06-15 | N | 00091897
Calendaring : Amendment Checklist & Process - 00091897 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | van Dijk, Tim | 2017-06-12 | 3 | 2017-06-15 | N | 00091897
Calendaring : Amendment Checklist & Process - 00091897 | ** Visit Tolerance Edits | User | van Dijk, Tim | 2017-06-12 | 3 | 2017-06-15 | N | 00091897
Calendaring : Amendment Checklist & Process - 00091897 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | van Dijk, Tim | 2017-06-12 | 3 | 2017-06-15 | N | 00091897
Calendaring : Initial Calendar Build - 268-NEUMAR | Assign to Analyst | User | van Dijk, Tim | 2017-06-12 | 0 | 2017-06-12 | N | 268-NEUMAR
Calendaring : Initial Calendar Build - 49-MARTINEZ | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-06-12 | 4 | 2017-06-16 | N | 00132020
Calendaring : Initial Calendar Build - 49-MARTINEZ | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-06-12 | 4 | 2017-06-16 | N | 00132020
Pre-Award Financial - SCHIOPU-1 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-06-13 | 79 |  | N | SCHIOPU-1
CTSU Pre-Award v2 - 82-BOLLING | IRB Application Submitted | Role | CTSU Coordinator | 2017-06-13 | 79 |  | N | 82-BOLLING
CTSU Pre-Award v2 - 82-BOLLING | Planning Meeting Completed | Role | CTSU Finance | 2017-06-13 | 79 |  | N | 82-BOLLING
Calendaring : Initial Calendar Build - 211-HIGGINS | Nimblify Build is Complete & Ready for Import | User | Hodges, Lynda | 2017-06-13 | 9 | 2017-06-22 | N | 00128325
Calendaring : Initial Calendar Build - 158-PIPE | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-06-13 | 44 | 2017-07-27 | N | 00131463
Pre-Award Financial - 00128157 | PAN Released | User | Oliver, Amy | 2017-06-13 | 79 |  | N | 00128157
Calendaring : Amendment Checklist & Process - 00066077 | ** Other | User | Przykucki, Anne | 2017-06-13 | 0 | 2017-06-09 | N | 00066077
Calendaring : Amendment Checklist & Process - 00066077 | Update RSH Source in MBECT | User | Przykucki, Anne | 2017-06-13 | 0 | 2017-06-09 | N | 00066077
Calendaring : Initial Calendar Build - 211-HIGGINS | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-06-13 | 0 | 2017-06-13 | N | 00128325
Calendaring : Initial Calendar Build - 211-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-06-13 | 0 | 2017-06-13 | N | 00128325
Calendaring : Initial Calendar Build - 236-NASR | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-06-13 | 7 | 2017-06-20 | N | 00131580
Calendaring : Initial Calendar Build - 236-NASR | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-06-13 | 7 | 2017-06-20 | N | 00131580
CTSU Post-Award - 00125425 | Date Reconciled | User | Yunk, Jason | 2017-06-13 | 0 | 2017-06-13 | N | 00125425
CTSU Post-Award - 00127537 | Date Reconciled | User | Yunk, Jason | 2017-06-13 | 0 | 2017-06-13 | N | 00127537
Calendaring : Amendment Checklist & Process - 00091897 | ** Items/Services : Addition or Removal of Procedures / Events | User | van Dijk, Tim | 2017-06-13 | 2 | 2017-06-15 | N | 00091897
Calendaring : Initial Calendar Build - 00121569 2 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Boyd, Collin | 2017-06-14 | 0 | 2017-06-14 | N | 00121569
Calendaring : Initial Calendar Build - 216-MODY | Feasibility Approval Notice Received | Role | CRAO | 2017-06-14 | 0 | 2017-06-14 | N | 00134866
Calendaring : Initial Calendar Build - 223-MODY | Feasibility Approval Notice Received | Role | CRAO | 2017-06-14 | 0 | 2017-06-14 | N | 00131377
Calendaring : Initial Calendar Build - 243-MODY | Feasibility Approval Notice Received | Role | CRAO | 2017-06-14 | 1 | 2017-06-15 | N | 00130968
Calendaring : Initial Calendar Build - 244-MODY | Feasibility Approval Notice Received | Role | CRAO | 2017-06-14 | 0 | 2017-06-14 | N | 244-MODY
Pre-Award Financial - 188-RUBENSTEIN | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-06-14 | 78 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 56-RAO | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-06-14 | 26 | 2017-07-10 | N | 00133286
Calendaring : Initial Calendar Build - 235-SUGAR | Complete SVS & Pricing List ( Built & Coded ) | Role | CTSU Finance | 2017-06-14 | 0 | 2017-06-14 | N | 235-SUGAR
Pre-Award Financial - 142-FLAHERTY | Planning Meeting Completed | Role | CTSU Finance | 2017-06-14 | 78 |  | N | 142-FLAHERTY
Pre-Award Financial - 188-RUBENSTEIN | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-06-14 | 78 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 188-RUBENSTEIN | Request MCRU Budget | Role | CTSU Finance | 2017-06-14 | 78 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 188-RUBENSTEIN | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-06-14 | 78 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 46-HIGGINS | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-06-14 | 16 | 2017-06-30 | N | 46-HIGGINS
Pre-Award Financial - 56-RAO | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-06-14 | 5 | 2017-06-19 | N | 00133286
Pre-Award Financial - 56-RAO | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-06-14 | 1 | 2017-06-15 | N | 00133286
Calendaring : Initial Calendar Build - 216-MODY | Assign to Analyst | User | Greene, Paula | 2017-06-14 | 1 | 2017-06-15 | N | 00134866
Calendaring : Initial Calendar Build - 223-MODY | Assign to Analyst | User | Greene, Paula | 2017-06-14 | 1 | 2017-06-15 | N | 00131377
Calendaring : Initial Calendar Build - 243-MODY | Assign to Analyst | User | Greene, Paula | 2017-06-14 | 1 | 2017-06-15 | N | 00130968
Calendaring : Initial Calendar Build - 244-MODY | Assign to Analyst | User | Greene, Paula | 2017-06-14 | 1 | 2017-06-15 | N | 244-MODY
Calendaring : Initial Calendar Build - 147-SCHIOPU | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Henry, Robin | 2017-06-14 | 23 | 2017-07-07 | N | 00131329
Pre-Award Financial - 00130793 | Budget Negotiations | User | Henry, Robin | 2017-06-14 | 75 | 2017-08-28 | N | 00130793
Pre-Award Financial - 87-ORAL | Budget Negotiations | User | Henry, Robin | 2017-06-14 | 15 | 2017-06-29 | N | 00130757
Calendaring : Initial Calendar Build - 216-MODY | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-14 | 0 | 2017-06-14 | N | 00134866
Calendaring : Initial Calendar Build - 223-MODY | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-14 | 0 | 2017-06-14 | N | 00131377
Calendaring : Initial Calendar Build - 243-MODY | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-14 | 0 | 2017-06-14 | N | 00130968
Calendaring : Initial Calendar Build - 244-MODY | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-14 | 0 | 2017-06-14 | N | 244-MODY
Calendaring : Initial Calendar Build - 00125599 | Complete Calendar ( ie. Ready for Financials ) | User | Hodges, Lynda | 2017-06-14 | 0 | 2017-06-14 | N | 00125599
Calendaring : Initial Calendar Build - 235-SUGAR | Nimblify Build is Complete & Ready for Import | User | Hodges, Lynda | 2017-06-14 | 8 | 2017-06-22 | N | 235-SUGAR
Calendaring : Initial Calendar Build - 170-SCHIOPU | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Oliver, Amy | 2017-06-14 | 37 | 2017-07-21 | N | 00134035
Calendaring : Initial Calendar Build - 235-SUGAR | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-06-14 | 0 | 2017-06-13 | N | 235-SUGAR
Calendaring : Specification Update Request(s) - 00128253 | Make Update(s) | User | Radenbaugh, Pauline | 2017-06-14 | 6 | 2017-06-20 | N | 00128253
Calendaring : Specification Update Request(s) - 00128253 | Re-Complete Calendar | User | Radenbaugh, Pauline | 2017-06-14 | 6 | 2017-06-20 | N | 00128253
Open to Accrual - 00130004 | FDA Approval | User | Stovall, Angela | 2017-06-14 | 0 | 2017-06-14 | N | 00130004
Open to Accrual - 00130004 | IRB Approval | User | Stovall, Angela | 2017-06-14 | 0 | 2017-06-14 | N | 00130004
Calendaring : Initial Calendar Build - 70-LUGOGO | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-06-14 | 37 | 2017-07-21 | N | 70-LUGOGO
Pre-Award Financial - 00126010 | Internal Budget Finished | User | VanderElzen, Liz | 2017-06-14 | 0 | 2017-06-08 | N | 00126010
Pre-Award Financial - 46-HIGGINS | Request Research Pharmacy Budget | User | VanderElzen, Liz | 2017-06-14 | 29 | 2017-07-13 | N | 46-HIGGINS
CTSU Post-Award - 00125566 | Date Reconciled | User | Yunk, Jason | 2017-06-14 | 0 | 2017-06-14 | N | 00125566
Calendaring : Amendment Checklist & Process - 00113391 | AME Calendaring Process Initiated | User | Yunk, Jason | 2017-06-14 | 0 | 2017-06-14 | N | 00113391
Calendaring : Amendment Checklist & Process - 00119399 2 | AME Calendaring Process Initiated | User | Yunk, Jason | 2017-06-14 | 0 | 2017-06-14 | N | 00119399
Calendaring : Amendment Checklist & Process - 00091897 | ** Other | User | van Dijk, Tim | 2017-06-14 | 1 | 2017-06-15 | N | 00091897
Calendaring : Amendment Checklist & Process - 00091897 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | van Dijk, Tim | 2017-06-14 | 1 | 2017-06-15 | N | 00091897
Calendaring : Amendment Checklist & Process - 00091897 | ** Visits : Addition or Removal of Time Points | User | van Dijk, Tim | 2017-06-14 | 1 | 2017-06-15 | N | 00091897
Calendaring : Amendment Checklist & Process - 00091897 | Request Care Designations | User | van Dijk, Tim | 2017-06-14 | 1 | 2017-06-15 | N | 00091897
Calendaring : Amendment Checklist & Process - 00091897 | Update RSH Source in MBECT | User | van Dijk, Tim | 2017-06-14 | 1 | 2017-06-15 | N | 00091897
Calendaring : Initial Calendar Build - SLS-III | Complete MCA / QCT | User | van Dijk, Tim | 2017-06-14 | 8 | 2017-06-22 | N | 00131953
Calendaring : Initial Calendar Build - 173-WICKMAN | Feasibility Approval Notice Received | Role | CRAO | 2017-06-15 | 6 | 2017-06-21 | N | 00133542
Pre-Award Financial - SCHIOPU-1 | Open to Accrual | Role | CTSU Administrator | 2017-06-15 | 77 |  | N | SCHIOPU-1
Open to Accrual - 00125599 | FDA Approval | Role | CTSU Coordinator | 2017-06-15 | 0 | 2017-06-15 | N | 00125599
Open to Accrual - 00125599 | IRB Approval | Role | CTSU Coordinator | 2017-06-15 | 0 | 2017-06-15 | N | 00125599
Pre-Award Financial - 278-CONJEEVARAM | Intake Form Completed | Role | CTSU Coordinator | 2017-06-15 | 0 | 2017-06-15 | N | 00133341
Calendaring : Initial Calendar Build - 158-PIPE | Acknowledge | Role | CTSU Finance | 2017-06-15 | 42 | 2017-07-27 | N | 00131463
Pre-Award Financial - 76-KHANNA | Billing Calendar Received | Role | CTSU Finance | 2017-06-15 | 6 | 2017-06-21 | N | 00131837
Calendaring : Initial Calendar Build - 211-HIGGINS | Attach Build Notes ( as Protocol Doc ) | User | Hodges, Lynda | 2017-06-15 | 11 | 2017-06-26 | N | 00128325
Calendaring : Initial Calendar Build - 211-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hodges, Lynda | 2017-06-15 | 11 | 2017-06-26 | N | 00128325
Calendaring : Initial Calendar Build - 00121569 2 | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-06-15 | 0 | 2017-06-02 | N | 00121569
Pre-Award Financial - 69-KHANNA | PAN Released | User | Oliver, Amy | 2017-06-15 | 77 |  | N | 69-KHANNA
Calendaring : Initial Calendar Build - 56-RAO | Complete MCA / QCT | User | Przykucki, Anne | 2017-06-15 | 0 | 2017-06-14 | N | 00133286
Calendaring : Initial Calendar Build - 56-RAO | Complete SVS & Pricing List ( Built & Coded ) | User | Przykucki, Anne | 2017-06-15 | 0 | 2017-06-14 | N | 00133286
Calendaring : Initial Calendar Build - 56-RAO | Nimblify Build is Complete & Ready for Import | User | Przykucki, Anne | 2017-06-15 | 15 | 2017-06-30 | N | 00133286
Calendaring : Specification Update Request(s) - 00125798 | Make Update(s) | User | Radenbaugh, Pauline | 2017-06-15 | 5 | 2017-06-20 | N | 00125798
Calendaring : Specification Update Request(s) - 00125798 | Re-Complete Calendar | User | Radenbaugh, Pauline | 2017-06-15 | 5 | 2017-06-20 | N | 00125798
Calendaring : Specification Update Request(s) - 00128322 2 | Make Update(s) | User | Radenbaugh, Pauline | 2017-06-15 | 0 | 2017-06-09 | N | 00128322
Calendaring : Specification Update Request(s) - 00128322 2 | Re-Complete Calendar | User | Radenbaugh, Pauline | 2017-06-15 | 0 | 2017-06-09 | N | 00128322
Pre-Award Financial - 00129652 | Internal Budget Finished | User | VanderElzen, Liz | 2017-06-15 | 1 | 2017-06-16 | N | 00129652
Pre-Award Financial - 70-LUGOGO | Billing Calendar Received | User | VanderElzen, Liz | 2017-06-15 | 6 | 2017-06-21 | N | 70-LUGOGO
Calendaring : Initial Calendar Build - 46-HIGGINS | Complete MCA / QCT | User | Zahs, Brian | 2017-06-15 | 77 |  | N | 46-HIGGINS
Calendaring : Initial Calendar Build - 46-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian | 2017-06-15 | 39 | 2017-07-24 | N | 46-HIGGINS
Calendaring : Initial Calendar Build - 46-HIGGINS | Nimblify Build is Complete & Ready for Import | User | Zahs, Brian | 2017-06-15 | 33 | 2017-07-18 | N | 46-HIGGINS
Calendaring : Initial Calendar Build - 268-NEUMAR | Complete MCA / QCT | User | van Dijk, Tim | 2017-06-15 | 12 | 2017-06-27 | N | 268-NEUMAR
Calendaring : Initial Calendar Build - 268-NEUMAR | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-06-15 | 0 | 2017-06-15 | N | 268-NEUMAR
Calendaring : Initial Calendar Build - 268-NEUMAR | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-06-15 | 12 | 2017-06-27 | N | 268-NEUMAR
Open to Accrual - 00130004 | Budget Finalized | User | Boyd, Collin | 2017-06-16 | 0 | 2017-06-14 | N | 00130004
Calendaring : Initial Calendar Build - 221-MODY | Feasibility Approval Notice Received | Role | CRAO | 2017-06-16 | 0 | 2017-06-16 | N | 00129412
Calendaring : Initial Calendar Build - 260-MODY | Feasibility Approval Notice Received | Role | CRAO | 2017-06-16 | 4 | 2017-06-20 | N | 00134979
Pre-Award Financial - 235-SUGAR | Feasibility w/Documents received | Role | CTSU Administrator | 2017-06-16 | 0 | 2017-06-09 | N | 235-SUGAR
Open to Accrual - 00118461 | FDA Approval | Role | CTSU Coordinator | 2017-06-16 | 0 | 2017-06-16 | N | 00118461
Open to Accrual - 00118461 | IRB Approval | Role | CTSU Coordinator | 2017-06-16 | 0 | 2017-06-16 | N | 00118461
Open to Accrual - 00125566 | Contract Executed | Role | CTSU Coordinator | 2017-06-16 | 0 | 2017-06-16 | N | 00125566
Pre-Award Financial - 282-POP-BUSUI | Intake Form Completed | Role | CTSU Coordinator | 2017-06-16 | 0 | 2017-06-16 | N | 00133290
CTSU Pre-Award v2 - 82-BOLLING | Care Designations completed | Role | CTSU Finance | 2017-06-16 | 76 |  | N | 82-BOLLING
Calendar Build - 1-THOMAS | Care Designations +/- finance / study-team feedback submitted to CRAO for OnCore entry | Role | CTSU Finance | 2017-06-16 | 0 | 2017-06-16 | N | 00125306
Calendaring : Amendment Checklist & Process - 00108921 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance | 2017-06-16 | 76 |  | N | 00108921
Calendaring : Specification Update Request(s) - 00128253 | Acknowledge | Role | CTSU Finance | 2017-06-16 | 11 | 2017-06-27 | N | 00128253
Pre-Award Financial - 147-SCHIOPU | Planning Meeting Completed | Role | CTSU Finance | 2017-06-16 | 0 | 2017-06-15 | N | 00131329
Pre-Award Financial - 170-SCHIOPU | Planning Meeting Completed | Role | CTSU Finance | 2017-06-16 | 0 | 2017-06-15 | N | 00134035
Calendaring : Initial Calendar Build - 173-WICKMAN | Assign to Analyst | User | Greene, Paula | 2017-06-16 | 5 | 2017-06-21 | N | 00133542
Calendaring : Initial Calendar Build - 205-KHANNA | Assign to Analyst | User | Greene, Paula | 2017-06-16 | 4 | 2017-06-20 | N | 00132200
Calendaring : Initial Calendar Build - 221-MODY | Assign to Analyst | User | Greene, Paula | 2017-06-16 | 4 | 2017-06-20 | N | 00129412
Calendaring : Initial Calendar Build - 260-MODY | Assign to Analyst | User | Greene, Paula | 2017-06-16 | 4 | 2017-06-20 | N | 00134979
Calendaring : Initial Calendar Build - 173-WICKMAN | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-16 | 0 | 2017-06-16 | N | 00133542
Calendaring : Amendment Checklist & Process - 00119399 2 | Assign to Analyst | User | Hodges, Lynda | 2017-06-16 | 12 | 2017-06-28 | N | 00119399
Calendaring : Initial Calendar Build - 235-SUGAR | Attach Build Notes ( as Protocol Doc ) | User | Hodges, Lynda | 2017-06-16 | 11 | 2017-06-27 | N | 235-SUGAR
Calendaring : Initial Calendar Build - 235-SUGAR | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hodges, Lynda | 2017-06-16 | 13 | 2017-06-29 | N | 235-SUGAR
Calendaring : Initial Calendar Build - 00121569 2 | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-06-16 | 27 | 2017-07-13 | N | 00121569
Calendaring : Initial Calendar Build - 147-SCHIOPU | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-06-16 | 33 | 2017-07-19 | N | 00131329
Calendaring : Amendment Checklist & Process - 00113391 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-06-16 | 19 | 2017-07-05 | N | 00113391
Calendaring : Initial Calendar Build - 70-LUGOGO | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-06-16 | 54 | 2017-08-09 | N | 70-LUGOGO
Calendaring : Initial Calendar Build - 70-LUGOGO | Make Updates | User | Radenbaugh, Pauline | 2017-06-16 | 54 | 2017-08-09 | N | 70-LUGOGO
Pre-Award Financial - 00126010 | Billing Calendar Received | User | VanderElzen, Liz | 2017-06-16 | 0 | 2017-06-14 | N | 00126010
Pre-Award Financial - 49-MARTINEZ | Billing Calendar Received | User | VanderElzen, Liz | 2017-06-16 | 4 | 2017-06-20 | N | 00132020
Calendaring : Initial Calendar Build - 00125798 | CRAO Approval Issue & Documented | User | van Dijk, Tim | 2017-06-16 | 0 | 2017-06-16 | N | 00125798
Calendaring : Initial Calendar Build - 170-SCHIOPU | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-06-16 | 40 | 2017-07-26 | N | 00134035
Calendaring : Initial Calendar Build - 170-SCHIOPU | Make Updates | User | van Dijk, Tim | 2017-06-16 | 40 | 2017-07-26 | N | 00134035
Calendaring : Specification Update Request(s) - 00125798 | Acknowledge | User | Benton, Archie | 2017-06-17 | 3 | 2017-06-20 | N | 00125798
Calendaring : Specification Update Request(s) - 00128322 2 | Acknowledge | Role | CTSU Finance | 2017-06-17 | 0 | 2017-06-09 | N | 00128322
Pre-Award Financial - 142-FLAHERTY | Care Designations completed | Role | CTSU Finance | 2017-06-17 | 75 |  | N | 142-FLAHERTY
Calendaring : Initial Calendar Build - 223-MODY | Complete MCA / QCT | User | Hodges, Lynda | 2017-06-17 | 5 | 2017-06-22 | N | 00131377
Calendaring : Initial Calendar Build - 223-MODY | Complete SVS & Pricing List ( Built & Coded ) | User | Hodges, Lynda | 2017-06-17 | 5 | 2017-06-22 | N | 00131377
Calendaring : Initial Calendar Build - 223-MODY | Nimblify Build is Complete & Ready for Import | User | Hodges, Lynda | 2017-06-17 | 9 | 2017-06-26 | N | 00131377
Calendaring : Initial Calendar Build - 243-MODY | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-06-17 | 10 | 2017-06-27 | N | 00130968
Calendaring : Initial Calendar Build - 56-RAO | Attach Build Notes ( as Protocol Doc ) | User | Przykucki, Anne | 2017-06-17 | 13 | 2017-06-30 | N | 00133286
Calendaring : Initial Calendar Build - 56-RAO | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Przykucki, Anne | 2017-06-17 | 46 | 2017-08-02 | N | 00133286
Calendaring : Amendment Checklist & Process - 00113391 | ** Footnote Edits | User | Radenbaugh, Pauline | 2017-06-17 | 18 | 2017-07-05 | N | 00113391
Calendaring : Amendment Checklist & Process - 00113391 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Radenbaugh, Pauline | 2017-06-17 | 18 | 2017-07-05 | N | 00113391
Calendaring : Amendment Checklist & Process - 00113391 | ** Visit Tolerance Edits | User | Radenbaugh, Pauline | 2017-06-17 | 18 | 2017-07-05 | N | 00113391
Calendaring : Amendment Checklist & Process - 00113391 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Radenbaugh, Pauline | 2017-06-17 | 18 | 2017-07-05 | N | 00113391
Calendaring : Initial Calendar Build - 243-MODY | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-06-17 | 19 | 2017-07-06 | N | 00130968
Calendaring : Initial Calendar Build - 243-MODY | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-06-17 | 24 | 2017-07-11 | N | 00130968
Calendaring : Initial Calendar Build - 244-MODY | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-06-17 | 27 | 2017-07-14 | N | 244-MODY
Calendaring : Initial Calendar Build - 244-MODY | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-06-17 | 27 | 2017-07-14 | N | 244-MODY
Calendaring : Initial Calendar Build - 244-MODY | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-06-17 | 18 | 2017-07-05 | N | 244-MODY
Calendaring : Initial Calendar Build - 46-HIGGINS | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian | 2017-06-17 | 38 | 2017-07-25 | N | 46-HIGGINS
Calendaring : Initial Calendar Build - 46-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian | 2017-06-17 | 37 | 2017-07-24 | N | 46-HIGGINS
Calendaring : Initial Calendar Build - 216-MODY | Complete MCA / QCT | User | van Dijk, Tim | 2017-06-17 | 10 | 2017-06-27 | N | 00134866
Calendaring : Initial Calendar Build - 216-MODY | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-06-17 | 9 | 2017-06-26 | N | 00134866
Calendaring : Initial Calendar Build - 216-MODY | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-06-17 | 19 | 2017-07-06 | N | 00134866
Calendaring : Initial Calendar Build - 268-NEUMAR | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-06-17 | 10 | 2017-06-27 | N | 268-NEUMAR
Calendaring : Initial Calendar Build - 268-NEUMAR | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-06-17 | 10 | 2017-06-27 | N | 268-NEUMAR
CTSU Pre-Award v2 - 00111295 | Billing Calendar Received | Role | CTSU Finance | 2017-06-18 | 74 |  | N | 00111295
Pre-Award Financial - 91-ELSE | Final Budget | Role | CTSU Finance | 2017-06-18 | 74 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | Final Budget | Role | CTSU Finance | 2017-06-18 | 74 |  | N | 92-AUCHUS
Pre-Award Financial - 96-BESIRLI | Care Designations completed | Role | CTSU Finance | 2017-06-18 | 0 | 2017-05-02 | N | 00129820
Calendaring : Initial Calendar Build - 00125599 | Acknowledge | User | Drogs, Stacey | 2017-06-18 | 0 | 2017-06-16 | N | 00125599
Calendaring : Initial Calendar Build - 147-SCHIOPU | Acknowledge | User | Henry, Robin | 2017-06-18 | 33 | 2017-07-21 | N | 00131329
Pre-Award Financial - 211-HIGGINS | Billing Calendar Received | User | Henry, Robin | 2017-06-18 | 8 | 2017-06-26 | N | 00128325
Calendar Build - 1-THOMAS | Feedback incorporated / resolved | User | Hess, Aaron | 2017-06-18 | 3 | 2017-06-21 | N | 00125306
Calendaring : Initial Calendar Build - 00131837 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Oliver, Amy | 2017-06-18 | 31 | 2017-07-19 | N | 00131837
Calendaring : Initial Calendar Build - 170-SCHIOPU | Acknowledge | User | Oliver, Amy | 2017-06-18 | 51 | 2017-08-08 | N | 00134035
Calendaring : Amendment Checklist & Process - 00108921 | Complete Calendar and Document Approval | User | Przykucki, Anne | 2017-06-18 | 74 |  | N | 00108921
Calendaring : Amendment Checklist & Process - 00113391 | ** Items/Services : Addition or Removal of Procedures / Events | User | Radenbaugh, Pauline | 2017-06-18 | 17 | 2017-07-05 | N | 00113391
Calendaring : Initial Calendar Build - 70-LUGOGO | Acknowledge | User | VanderElzen, Liz | 2017-06-18 | 59 | 2017-08-16 | N | 70-LUGOGO
Pre-Award Financial - 00129652 | PI approved Budget | User | VanderElzen, Liz | 2017-06-18 | 3 | 2017-06-21 | N | 00129652
Calendaring : Initial Calendar Build - 00121569 2 | Acknowledge | User | Watson, Donna | 2017-06-18 | 65 | 2017-08-22 | N | 00121569
Open to Accrual - 00125599 | Adequate Equipment and Supplies Available | User | Bell, Jennifer | 2017-06-19 | 0 | 2017-06-19 | N | 00125599
Open to Accrual - 00125599 | Investigational Drug/Device Supplies Available | User | Bell, Jennifer | 2017-06-19 | 0 | 2017-06-16 | N | 00125599
Open to Accrual - 00125599 | Other Personnel Notified | User | Bell, Jennifer | 2017-06-19 | 0 | 2017-06-19 | N | 00125599
Open to Accrual - 00125599 | Provisions for Support and Services Finalized | User | Bell, Jennifer | 2017-06-19 | 0 | 2017-06-19 | N | 00125599
Open to Accrual - 00125599 | Sponsor/Organizing Group Approval Granted for Initiation of Study | User | Bell, Jennifer | 2017-06-19 | 0 | 2017-06-14 | N | 00125599
Open to Accrual - 00125599 | Study Files Established | User | Bell, Jennifer | 2017-06-19 | 0 | 2017-06-19 | N | 00125599
Open to Accrual - 00125599 | Study Team Roles/Responsibilities Finalized | User | Bell, Jennifer | 2017-06-19 | 0 | 2017-06-19 | N | 00125599
Calendaring : Initial Calendar Build - 00132363 | Feasibility Approval Notice Received | Role | CRAO | 2017-06-19 | 1 | 2017-06-20 | N | 00132363
Calendaring : Initial Calendar Build - 287-HUTCHINSON | Feasibility Approval Notice Received | Role | CRAO | 2017-06-19 | 1 | 2017-06-20 | N | 00119926
Pre-Award Financial - 00127136 | IRB Application Submitted | Role | CTSU Coordinator | 2017-06-19 | 0 | 2017-06-19 | N | 00127136
Calendaring : Amendment Checklist & Process - 00091897 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance | 2017-06-19 | 2 | 2017-06-21 | N | 00091897
Open to Accrual - 00118461 | Budget Finalized | User | Dahlgren, Molly | 2017-06-19 | 3 | 2017-06-22 | N | 00118461
Open to Accrual - 00125599 | Budget Finalized | User | Drogs, Stacey | 2017-06-19 | 2 | 2017-06-21 | N | 00125599
Calendaring : Initial Calendar Build - 00132363 | Assign to Analyst | User | Greene, Paula | 2017-06-19 | 1 | 2017-06-20 | N | 00132363
Calendaring : Initial Calendar Build - 287-HUTCHINSON | Assign to Analyst | User | Greene, Paula | 2017-06-19 | 1 | 2017-06-20 | N | 00119926
Pre-Award Financial - 147-SCHIOPU | Care Designations completed | User | Henry, Robin | 2017-06-19 | 16 | 2017-07-05 | N | 00131329
Pre-Award Financial - 170-SCHIOPU | Care Designations completed | User | Henry, Robin | 2017-06-19 | 7 | 2017-06-26 | N | 00134035
Calendar Build - 1-THOMAS | Care designations entered ( per PI determinations) | User | Hess, Aaron | 2017-06-19 | 2 | 2017-06-21 | N | 00125306
Calendaring : Initial Calendar Build - 00132363 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-19 | 1 | 2017-06-20 | N | 00132363
Calendaring : Initial Calendar Build - 205-KHANNA | Complete MCA / QCT | User | Hess, Aaron | 2017-06-19 | 73 |  | N | 00132200
Calendaring : Initial Calendar Build - 205-KHANNA | Complete SVS & Pricing List ( Built & Coded ) | User | Hess, Aaron | 2017-06-19 | 73 |  | N | 00132200
Calendaring : Initial Calendar Build - 287-HUTCHINSON | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-19 | 1 | 2017-06-20 | N | 00119926
Calendaring : Initial Calendar Build - 221-MODY | Complete MCA / QCT | User | Hodges, Lynda | 2017-06-19 | 1 | 2017-06-20 | N | 00129412
Calendaring : Initial Calendar Build - 221-MODY | Complete SVS & Pricing List ( Built & Coded ) | User | Hodges, Lynda | 2017-06-19 | 1 | 2017-06-20 | N | 00129412
Calendaring : Initial Calendar Build - 223-MODY | Attach Build Notes ( as Protocol Doc ) | User | Hodges, Lynda | 2017-06-19 | 8 | 2017-06-27 | N | 00131377
Calendaring : Initial Calendar Build - 223-MODY | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hodges, Lynda | 2017-06-19 | 8 | 2017-06-27 | N | 00131377
Open to Accrual - 00125599 | Project Award Notice (PAN) Received | User | Keeley, Kathryn | 2017-06-19 | 2 | 2017-06-21 | N | 00125599
Open to Accrual - 00125599 | MiChart Verifications | User | Miller, Diana | 2017-06-19 | 0 | 2017-06-19 | N | 00125599
Calendaring : Initial Calendar Build - 00126010 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Oliver, Amy | 2017-06-19 | 43 | 2017-08-01 | N | 00126010
Pre-Award Financial - 71-RICE | Final Budget | User | Oliver, Amy | 2017-06-19 | 73 |  | N | 00134857
Calendaring : Amendment Checklist & Process - 00113391 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Radenbaugh, Pauline | 2017-06-19 | 16 | 2017-07-05 | N | 00113391
Calendaring : Amendment Checklist & Process - 00113391 | ** Visits : Addition or Removal of Time Points | User | Radenbaugh, Pauline | 2017-06-19 | 16 | 2017-07-05 | N | 00113391
Calendaring : Amendment Checklist & Process - 00113391 | Request Care Designations | User | Radenbaugh, Pauline | 2017-06-19 | 16 | 2017-07-05 | N | 00113391
Calendaring : Initial Calendar Build - 243-MODY | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-06-19 | 22 | 2017-07-11 | N | 00130968
Calendaring : Initial Calendar Build - 243-MODY | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-06-19 | 24 | 2017-07-13 | N | 00130968
Calendaring : Initial Calendar Build - 244-MODY | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-06-19 | 25 | 2017-07-14 | N | 244-MODY
Calendaring : Initial Calendar Build - 244-MODY | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-06-19 | 25 | 2017-07-14 | N | 244-MODY
Calendaring : Initial Calendar Build - 49-MARTINEZ | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-06-19 | 45 | 2017-08-03 | N | 00132020
Pre-Award Financial - 235-SUGAR | Billing Calendar Received | User | VanderElzen, Liz | 2017-06-19 | 4 | 2017-06-23 | N | 235-SUGAR
Pre-Award Financial - 70-LUGOGO | Planning Meeting Completed | User | VanderElzen, Liz | 2017-06-19 | 0 | 2017-06-13 | N | 70-LUGOGO
Calendaring : Initial Calendar Build - 230-ROGERS | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-06-19 | 25 | 2017-07-14 | N | 00130272
Calendaring : Amendment Checklist & Process - 00121569 2 | AME Calendaring Process Initiated | User | Ziolkowski, Jaimie | 2017-06-19 | 0 | 2017-06-19 | N | 00121569
Calendaring : Initial Calendar Build - 173-WICKMAN | Complete MCA / QCT | User | van Dijk, Tim | 2017-06-19 | 8 | 2017-06-27 | N | 00133542
Calendaring : Initial Calendar Build - 173-WICKMAN | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-06-19 | 8 | 2017-06-27 | N | 00133542
Calendaring : Initial Calendar Build - 173-WICKMAN | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-06-19 | 8 | 2017-06-27 | N | 00133542
Calendaring : Initial Calendar Build - 216-MODY | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-06-19 | 17 | 2017-07-06 | N | 00134866
Calendaring : Initial Calendar Build - 216-MODY | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-06-19 | 17 | 2017-07-06 | N | 00134866
Calendaring : Initial Calendar Build - 260-MODY | Complete MCA / QCT | User | van Dijk, Tim | 2017-06-19 | 11 | 2017-06-30 | N | 00134979
Calendaring : Initial Calendar Build - 260-MODY | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-06-19 | 10 | 2017-06-29 | N | 00134979
CTSU Pre-Award v2 - 82-BOLLING | Internal Budget Finished | Role | CTSU Finance | 2017-06-20 | 72 |  | N | 82-BOLLING
Calendaring : Amendment Checklist & Process - 00108921 | Acknowledge | Role | CTSU Finance | 2017-06-20 | 72 |  | N | 00108921
Calendaring : Initial Calendar Build - 236-NASR | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-06-20 | 21 | 2017-07-11 | N | 00131580
Pre-Award Financial - 91-ELSE | PAF routed | Role | CTSU Finance | 2017-06-20 | 72 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | PAF routed | Role | CTSU Finance | 2017-06-20 | 72 |  | N | 92-AUCHUS
Calendaring : Initial Calendar Build - 00129709 | Assign to Analyst | User | Greene, Paula | 2017-06-20 | 1 | 2017-06-21 | N | 00129709
Calendar Build - 1-THOMAS | ‘Build Notes’ documentation ( w. CRAO comments, as needed ) attached ( as protocol doc ) +/- other supplemental documentation | User | Hess, Aaron | 2017-06-20 | 1 | 2017-06-21 | N | 00125306
Calendaring : Initial Calendar Build - 221-MODY | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-20 | 0 | 2017-06-20 | N | 00129412
Calendaring : Initial Calendar Build - 260-MODY | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-20 | 0 | 2017-06-20 | N | 00134979
Calendaring : Amendment Checklist & Process - 00115982 | Acknowledge | User | Hilfinger, Diane | 2017-06-20 | 8 | 2017-06-28 | N | 00115982
Calendaring : Initial Calendar Build - 00131837 | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-06-20 | 55 | 2017-08-14 | N | 00131837
Calendaring : Initial Calendar Build - 00131837 | Make Updates | User | Munasinghe, Sadeepa | 2017-06-20 | 55 | 2017-08-14 | N | 00131837
Pre-Award Financial - 00129427 | PAN Released | User | Oliver, Amy | 2017-06-20 | 72 |  | N | 00129427
Pre-Award Financial - 180-HOFF | Billing Calendar Received | User | Oliver, Amy | 2017-06-20 | 72 |  | N | 00129450
Calendaring : Amendment Checklist & Process - 00066077 | Complete Calendar and Document Approval | User | Przykucki, Anne | 2017-06-20 | 0 | 2017-06-09 | N | 00066077
Pre-Award Financial - 00129652 | Budget Negotiations | User | VanderElzen, Liz | 2017-06-20 | 1 | 2017-06-21 | N | 00129652
Pre-Award Financial - 49-MARTINEZ | Planning Meeting Completed | User | VanderElzen, Liz | 2017-06-20 | 6 | 2017-06-26 | N | 00132020
Pre-Award Financial - 242-AS-SANIE | Feasibility w/Documents received | Role | CTSU Administrator | 2017-06-21 | 71 |  | N | 242-AS-SANIE
Pre-Award Financial - 242-AS-SANIE | Sponsor Reach out | Role | CTSU Coordinator | 2017-06-21 | 27 | 2017-07-18 | N | 242-AS-SANIE
Pre-Award Financial - 242-AS-SANIE | UFA Completed | Role | CTSU Coordinator | 2017-06-21 | 27 | 2017-07-18 | N | 242-AS-SANIE
Pre-Award Financial - 298-SCHIOPU | Intake Form Completed | Role | CTSU Coordinator | 2017-06-21 | 0 | 2017-06-21 | N | 298-SCHIOPU
Calendaring : Initial Calendar Build - 230-ROGERS | Acknowledge | Role | CTSU Finance | 2017-06-21 | 71 |  | N | 00130272
Open to Accrual - 00125566 | Budget Finalized | Role | CTSU Finance | 2017-06-21 | 0 | 2017-06-21 | N | 00125566
Pre-Award Financial - 142-FLAHERTY | Internal Budget Finished | Role | CTSU Finance | 2017-06-21 | 71 |  | N | 142-FLAHERTY
Calendaring : Initial Calendar Build - 00126135 | Assign to Analyst | User | Greene, Paula | 2017-06-21 | 1 | 2017-06-22 | N | 00126135
Calendaring : Initial Calendar Build - 00126707 | Assign to Analyst | User | Greene, Paula | 2017-06-21 | 19 | 2017-07-10 | N | 00126707
Open to Accrual - 00125599 | Contract Executed | User | Keeley, Kathryn | 2017-06-21 | 0 | 2017-06-21 | N | 00125599
Calendaring : Amendment Checklist & Process - 00121569 2 | Assign to Analyst | User | Munasinghe, Sadeepa | 2017-06-21 | 0 | 2017-06-21 | N | 00121569
Pre-Award Financial - 71-RICE | PAF routed | User | Oliver, Amy | 2017-06-21 | 71 |  | N | 00134857
Pre-Award Financial - 76-KHANNA | Initiate Post-Award Task List | User | Oliver, Amy | 2017-06-21 | 71 |  | N | 00131837
Pre-Award Financial - 76-KHANNA | PAN Released | User | Oliver, Amy | 2017-06-21 | 71 |  | N | 00131837
Calendaring : Initial Calendar Build - 00126010 | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-06-21 | 41 | 2017-08-01 | N | 00126010
Calendaring : Initial Calendar Build - 00126010 | Make Updates | User | Radenbaugh, Pauline | 2017-06-21 | 41 | 2017-08-01 | N | 00126010
CTSU Post-Award - 00125794 | Date Reconciled | User | Yunk, Jason | 2017-06-21 | 0 | 2017-06-21 | N | 00125794
Calendaring : Amendment Checklist & Process - 00091897 | Complete Calendar and Document Approval | User | van Dijk, Tim | 2017-06-21 | 1 | 2017-06-22 | N | 00091897
Calendaring : Initial Calendar Build - 173-WICKMAN | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-06-21 | 6 | 2017-06-27 | N | 00133542
Calendaring : Initial Calendar Build - 173-WICKMAN | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-06-21 | 7 | 2017-06-28 | N | 00133542
Calendaring : Initial Calendar Build - 49-MARTINEZ | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-06-21 | 47 | 2017-08-07 | N | 00132020
Calendaring : Initial Calendar Build - 49-MARTINEZ | Make Updates | User | van Dijk, Tim | 2017-06-21 | 47 | 2017-08-07 | N | 00132020
Calendar Build - 1-THOMAS | CRAO Approval issued / documented |  |  | 2017-06-21 | 71 |  | N | 00125306
Calendaring : Initial Calendar Build - 205-KHANNA | Feasibility Approval Notice Received | Role | CRAO | 2017-06-22 | 0 | 2017-06-22 | N | 00132200
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Feasibility Approval Notice Received | Role | CRAO | 2017-06-22 | 0 | 2017-06-22 | N | 00133290
Pre-Award Financial - 155-ORAL | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-22 | 0 | 2017-06-22 | N | 00130803
Pre-Award Financial - 205-KHANNA | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-22 | 0 | 2017-06-22 | N | 00132200
Pre-Award Financial - 282-POP-BUSUI | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-22 | 0 | 2017-06-22 | N | 00133290
CTSU Pre-Award v2 - 00111295 | IRB Application Submitted | Role | CTSU Coordinator | 2017-06-22 | 70 |  | N | 00111295
Pre-Award Financial - 205-KHANNA | IRB Application Submitted | Role | CTSU Coordinator | 2017-06-22 | 0 | 2017-06-16 | N | 00132200
CTSU Pre-Award v2 - 00111295 | Planning Meeting Completed | Role | CTSU Finance | 2017-06-22 | 70 |  | N | 00111295
Calendar Build - 1-THOMAS | Calendar Completed and Ready for CTSU Finance to Build Budget | Role | CTSU Finance | 2017-06-22 | 19 | 2017-07-11 | N | 00125306
Calendaring : Initial Calendar Build - 211-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-06-22 | 21 | 2017-07-13 | N | 00128325
Pre-Award Financial - 188-RUBENSTEIN | Billing Calendar Received | Role | CTSU Finance | 2017-06-22 | 70 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 222-STEIGERWALT | Feasibility w/Documents received | Role | CTSU Finance | 2017-06-22 | 0 | 2017-06-22 | N | 227-STEIGERWALT
Pre-Award Financial - 305-PELOSI | Intake Form Completed | Role | CTSU Finance | 2017-06-22 | 0 | 2017-06-22 | N | 305-PELOSI
Pre-Award Financial - 77-CONJEEVARAM | PAN Released | Role | CTSU Finance | 2017-06-22 | 70 |  | N | 77-CONJEEVARAM
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Assign to Analyst | User | Greene, Paula | 2017-06-22 | 0 | 2017-06-22 | N | 00133290
Pre-Award Financial - 211-HIGGINS | Planning Meeting Completed | User | Henry, Robin | 2017-06-22 | 0 | 2017-06-20 | N | 00128325
Pre-Award Financial - 56-RAO | Billing Calendar Received | User | Henry, Robin | 2017-06-22 | 13 | 2017-07-05 | N | 00133286
Calendaring : Initial Calendar Build - 155-ORAL | Assign to Analyst | User | Hess, Aaron | 2017-06-22 | 0 | 2017-06-22 | N | 00130803
Calendaring : Initial Calendar Build - 155-ORAL | Feasibility Approval Notice Received | User | Hess, Aaron | 2017-06-22 | 0 | 2017-06-22 | N | 00130803
Calendaring : Initial Calendar Build - 155-ORAL | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-22 | 0 | 2017-06-22 | N | 00130803
Calendaring : Initial Calendar Build - 205-KHANNA | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-22 | 0 | 2017-06-22 | N | 00132200
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-22 | 0 | 2017-06-22 | N | 00133290
Calendaring : Amendment Checklist & Process - 00121569 2 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Munasinghe, Sadeepa | 2017-06-22 | 20 | 2017-07-12 | N | 00121569
Calendaring : Amendment Checklist & Process - 00121569 2 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Munasinghe, Sadeepa | 2017-06-22 | 20 | 2017-07-12 | N | 00121569
Calendaring : Initial Calendar Build - 00132363 | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-06-22 | 70 |  | N | 00132363
Calendaring : Initial Calendar Build - 00132363 | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-06-22 | 7 | 2017-06-29 | N | 00132363
Calendaring : Initial Calendar Build - 00132363 | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-06-22 | 32 | 2017-07-24 | N | 00132363
Calendaring : Amendment Checklist & Process - 00066077 | Acknowledge | User | Oliver, Amy | 2017-06-22 | 70 |  | N | 00066077
Calendaring : Initial Calendar Build - 00131837 | Acknowledge | User | Oliver, Amy | 2017-06-22 | 53 | 2017-08-14 | N | 00131837
Pre-Award Financial - 76-KHANNA | Care Designations completed | User | Oliver, Amy | 2017-06-22 | 53 | 2017-08-14 | N | 00131837
Calendaring : Initial Calendar Build - 00128743 | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline | 2017-06-22 | 21 | 2017-07-13 | N | 00128743
Calendaring : Initial Calendar Build - 236-NASR | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-06-22 | 19 | 2017-07-11 | N | 00131580
Calendaring : Initial Calendar Build - 236-NASR | Make Updates | User | Radenbaugh, Pauline | 2017-06-22 | 19 | 2017-07-11 | N | 00131580
Calendaring : Initial Calendar Build - 287-HUTCHINSON | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-06-22 | 27 | 2017-07-19 | N | 00119926
Pre-Award Financial - 46-HIGGINS | Billing Calendar Received | User | VanderElzen, Liz | 2017-06-22 | 32 | 2017-07-24 | N | 46-HIGGINS
Pre-Award Financial - 70-LUGOGO | Care Designations completed | User | VanderElzen, Liz | 2017-06-22 | 42 | 2017-08-03 | N | 70-LUGOGO
Open to Accrual - 00118461 | Adequate Equipment and Supplies Available | User | Ball, Ron | 2017-06-23 | 0 | 2017-06-16 | N | 00118461
Open to Accrual - 00118461 | Investigational Drug/Device Supplies Available | User | Ball, Ron | 2017-06-23 | 0 | 2017-06-16 | N | 00118461
Open to Accrual - 00118461 | Other Personnel Notified | User | Ball, Ron | 2017-06-23 | 0 | 2017-06-16 | N | 00118461
Open to Accrual - 00118461 | Provisions for Support and Services Finalized | User | Ball, Ron | 2017-06-23 | 0 | 2017-06-16 | N | 00118461
Open to Accrual - 00118461 | Study Files Established | User | Ball, Ron | 2017-06-23 | 69 |  | N | 00118461
Open to Accrual - 00118461 | Study Team Roles/Responsibilities Finalized | User | Ball, Ron | 2017-06-23 | 0 | 2017-06-16 | N | 00118461
Pre-Award Financial - 246-AS-SANIE | Feasibility w/Documents received | Role | CTSU Administrator | 2017-06-23 | 69 |  | N | 246-AS-SANIE
CTSU Pre-Award - 309-MOROI | Intake Form Completed | Role | CTSU Coordinator | 2017-06-23 | 0 | 2017-06-23 | N | 309-MOROI
Pre-Award Financial - 246-AS-SANIE | Sponsor Reach out | Role | CTSU Coordinator | 2017-06-23 | 69 |  | N | 246-AS-SANIE
Pre-Award Financial - 246-AS-SANIE | UFA Completed | Role | CTSU Coordinator | 2017-06-23 | 69 |  | N | 246-AS-SANIE
Pre-Award Financial - 87-ORAL | IRB Application Submitted | Role | CTSU Coordinator | 2017-06-23 | 0 | 2017-06-21 | N | 00130757
CTSU Pre-Award v2 - 82-BOLLING | PI approved Budget | Role | CTSU Finance | 2017-06-23 | 69 |  | N | 82-BOLLING
Calendaring : Amendment Checklist & Process - 00091897 | Acknowledge | Role | CTSU Finance | 2017-06-23 | 69 |  | N | 00091897
Calendaring : Amendment Checklist & Process - 00105691 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-06-23 | 12 | 2017-07-05 | N | 00105691
Open to Accrual - 00130004 | Contract Executed | User | Frasier, Lora | 2017-06-23 | 31 | 2017-07-24 | N | 00130004
Open to Accrual - 00130004 | Project Award Notice (PAN) Received | User | Frasier, Lora | 2017-06-23 | 38 | 2017-07-31 | N | 00130004
Pre-Award Financial - 147-SCHIOPU | Internal Budget Finished | User | Henry, Robin | 2017-06-23 | 14 | 2017-07-07 | N | 00131329
Pre-Award Financial - 170-SCHIOPU | Internal Budget Finished | User | Henry, Robin | 2017-06-23 | 19 | 2017-07-12 | N | 00134035
Calendaring : Initial Calendar Build - 294-ARNEDT | Feasibility Approval Notice Received | User | Hess, Aaron | 2017-06-23 | 0 | 2017-06-23 | N | 00124702
Calendaring : Initial Calendar Build - 294-ARNEDT | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-06-23 | 0 | 2017-06-23 | N | 00124702
Calendaring : Initial Calendar Build - 221-MODY | Nimblify Build is Complete & Ready for Import | User | Hodges, Lynda | 2017-06-23 | 19 | 2017-07-12 | N | 00129412
Open to Accrual - 00130004 | MiChart Verifications | User | Miller, Diana | 2017-06-23 | 0 | 2017-06-20 | N | 00130004
Calendaring : Initial Calendar Build - 00126010 | Acknowledge | User | Oliver, Amy | 2017-06-23 | 39 | 2017-08-01 | N | 00126010
Pre-Award Financial - 00126010 | PAN Released | User | Oliver, Amy | 2017-06-23 | 69 |  | N | 00126010
Pre-Award Financial - 00128173 | PAN Released | User | Oliver, Amy | 2017-06-23 | 69 |  | N | 00128173
Open to Accrual - 00130004 | Adequate Equipment and Supplies Available | User | Stovall, Angela | 2017-06-23 | 69 |  | N | 00130004
Open to Accrual - 00130004 | Investigational Drug/Device Supplies Available | User | Stovall, Angela | 2017-06-23 | 69 |  | N | 00130004
Open to Accrual - 00130004 | Other Personnel Notified | User | Stovall, Angela | 2017-06-23 | 0 | 2017-06-20 | N | 00130004
Open to Accrual - 00130004 | Provisions for Support and Services Finalized | User | Stovall, Angela | 2017-06-23 | 69 |  | N | 00130004
Open to Accrual - 00130004 | Sponsor/Organizing Group Approval Granted for Initiation of Study | User | Stovall, Angela | 2017-06-23 | 69 |  | N | 00130004
Open to Accrual - 00130004 | Study Files Established | User | Stovall, Angela | 2017-06-23 | 0 | 2017-06-20 | N | 00130004
Open to Accrual - 00130004 | Study Team Roles/Responsibilities Finalized | User | Stovall, Angela | 2017-06-23 | 0 | 2017-06-20 | N | 00130004
Calendaring : Initial Calendar Build - 235-SUGAR | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-06-23 | 55 | 2017-08-17 | N | 235-SUGAR
Calendaring : Initial Calendar Build - 49-MARTINEZ | Acknowledge | User | VanderElzen, Liz | 2017-06-23 | 54 | 2017-08-16 | N | 00132020
Pre-Award Financial - 00108880 | PAN Released | User | VanderElzen, Liz | 2017-06-23 | 69 |  | N | 00108880
Pre-Award Financial - 00126010 | Care Designations completed | User | VanderElzen, Liz | 2017-06-23 | 39 | 2017-08-01 | N | 00126010
Pre-Award Financial - 49-MARTINEZ | Care Designations completed | User | VanderElzen, Liz | 2017-06-23 | 41 | 2017-08-03 | N | 00132020
Calendaring : Initial Calendar Build - 00129709 | Complete MCA / QCT | User | van Dijk, Tim | 2017-06-23 | 13 | 2017-07-06 | N | 00129709
Calendaring : Initial Calendar Build - 00129709 | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-06-23 | 13 | 2017-07-06 | N | 00129709
Calendaring : Initial Calendar Build - 260-MODY | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-06-23 | 38 | 2017-07-31 | N | 00134979
Pre-Award Financial - 282-POP-BUSUI | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-06-24 | 0 | 2017-06-19 | N | 00133290
Calendaring : Initial Calendar Build - 236-NASR | Acknowledge | Role | CTSU Finance | 2017-06-24 | 26 | 2017-07-20 | N | 00131580
Calendaring : Initial Calendar Build - 268-NEUMAR | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-06-24 | 60 | 2017-08-23 | N | 268-NEUMAR
Pre-Award Financial - 142-FLAHERTY | PI approved Budget | Role | CTSU Finance | 2017-06-24 | 68 |  | N | 142-FLAHERTY
Pre-Award Financial - 205-KHANNA | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-06-24 | 6 | 2017-06-30 | N | 00132200
Calendaring : Amendment Checklist & Process - 00121569 2 | ** Visits : Addition or Removal of Time Points | User | Munasinghe, Sadeepa | 2017-06-24 | 18 | 2017-07-12 | N | 00121569
Calendaring : Initial Calendar Build - 00132363 | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-06-24 | 31 | 2017-07-25 | N | 00132363
Calendaring : Initial Calendar Build - 00132363 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-06-24 | 31 | 2017-07-25 | N | 00132363
Calendaring : Initial Calendar Build - 56-RAO | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Oliver, Amy | 2017-06-24 | 45 | 2017-08-08 | N | 00133286
Pre-Award Financial - 180-HOFF | Planning Meeting Completed | User | Oliver, Amy | 2017-06-24 | 0 | 2017-05-31 | N | 00129450
Calendaring : Initial Calendar Build - 211-HIGGINS | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-06-24 | 23 | 2017-07-17 | N | 00128325
Calendaring : Initial Calendar Build - 211-HIGGINS | Make Updates | User | Radenbaugh, Pauline | 2017-06-24 | 23 | 2017-07-17 | N | 00128325
Calendaring : Initial Calendar Build - 287-HUTCHINSON | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-06-24 | 31 | 2017-07-25 | N | 00119926
Calendaring : Initial Calendar Build - 287-HUTCHINSON | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-06-24 | 31 | 2017-07-25 | N | 00119926
Calendaring : Initial Calendar Build - 46-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-06-24 | 62 | 2017-08-25 | N | 46-HIGGINS
Pre-Award Financial - 282-POP-BUSUI | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-06-24 | 4 | 2017-06-28 | N | 00133290
Calendaring : Amendment Checklist & Process - 00113391 | Provide PI-Determined Care Designations ( +/- Feedback ) | User | Yunk, Jason | 2017-06-24 | 37 | 2017-07-31 | N | 00113391
Calendaring : Initial Calendar Build - 00126135 | Complete MCA / QCT | User | van Dijk, Tim | 2017-06-24 | 0 | 2017-06-23 | N | 00126135
Pre-Award Financial - 205-KHANNA | Feasibility w/Documents received | Role | CTSU Administrator | 2017-06-25 | 0 | 2017-06-20 | N | 00132200
CTSU Pre-Award v2 - 00111295 | Care Designations completed | Role | CTSU Finance | 2017-06-25 | 67 |  | N | 00111295
CTSU Pre-Award v2 - 82-BOLLING | Budget Negotiations | Role | CTSU Finance | 2017-06-25 | 67 |  | N | 82-BOLLING
Pre-Award Financial - 96-BESIRLI | Internal Budget Finished | Role | CTSU Finance | 2017-06-25 | 0 | 2017-05-02 | N | 00129820
Pre-Award Financial - 211-HIGGINS | Care Designations completed | User | Henry, Robin | 2017-06-25 | 17 | 2017-07-12 | N | 00128325
Calendaring : Initial Calendar Build - 205-KHANNA | Nimblify Build is Complete & Ready for Import | User | Hess, Aaron | 2017-06-25 | 5 | 2017-06-30 | N | 00132200
Calendaring : Amendment Checklist & Process - 00105691 | Assign to Analyst | User | Hodges, Lynda | 2017-06-25 | 11 | 2017-07-06 | N | 00105691
Calendaring : Initial Calendar Build - 155-ORAL | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-06-25 | 11 | 2017-07-06 | N | 00130803
Calendaring : Initial Calendar Build - 155-ORAL | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-06-25 | 11 | 2017-07-06 | N | 00130803
Calendaring : Initial Calendar Build - 155-ORAL | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-06-25 | 22 | 2017-07-17 | N | 00130803
Calendaring : Initial Calendar Build - 235-SUGAR | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-06-25 | 67 |  | N | 235-SUGAR
Calendaring : Initial Calendar Build - 235-SUGAR | Make Updates | User | Radenbaugh, Pauline | 2017-06-25 | 67 |  | N | 235-SUGAR
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Complete MCA / QCT | User | Zahs, Brian | 2017-06-25 | 67 |  | N | 00133290
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian | 2017-06-25 | 22 | 2017-07-17 | N | 00133290
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Nimblify Build is Complete & Ready for Import | User | Zahs, Brian | 2017-06-25 | 26 | 2017-07-21 | N | 00133290
Calendaring : Initial Calendar Build - 260-MODY | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-06-25 | 37 | 2017-08-01 | N | 00134979
Calendaring : Initial Calendar Build - 260-MODY | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-06-25 | 39 | 2017-08-03 | N | 00134979
Calendaring : Initial Calendar Build - 294-ARNEDT | Assign to Analyst | User | van Dijk, Tim | 2017-06-25 | 0 | 2017-06-23 | N | 00124702
Pre-Award Financial - 251-COMER | Feasibility w/Documents received | Role | CTSU Administrator | 2017-06-26 | 28 | 2017-07-24 | N | 00134232
CTSU Pre-Award - 313-CONJEEVARAM | Intake Form Completed | Role | CTSU Coordinator | 2017-06-26 | 0 | 2017-06-26 | N | 313-CONJEEVARAM
Pre-Award Financial - 251-COMER | UFA Completed | Role | CTSU Coordinator | 2017-06-26 | 3 | 2017-06-29 | N | 00134232
Calendaring : Initial Calendar Build - 211-HIGGINS | Acknowledge | Role | CTSU Finance | 2017-06-26 | 28 | 2017-07-24 | N | 00128325
Calendaring : Initial Calendar Build - 216-MODY | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-06-26 | 44 | 2017-08-09 | N | 00134866
Calendaring : Initial Calendar Build - 223-MODY | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-06-26 | 15 | 2017-07-11 | N | 00131377
Calendaring : Initial Calendar Build - 243-MODY | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-06-26 | 43 | 2017-08-08 | N | 00130968
Calendaring : Initial Calendar Build - 244-MODY | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-06-26 | 35 | 2017-07-31 | N | 244-MODY
Pre-Award Financial - 142-FLAHERTY | Budget Negotiations | Role | CTSU Finance | 2017-06-26 | 66 |  | N | 142-FLAHERTY
Pre-Award Financial - 188-RUBENSTEIN | Planning Meeting Completed | Role | CTSU Finance | 2017-06-26 | 66 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 81-HIGGINS | PAN Released | Role | CTSU Finance | 2017-06-26 | 66 |  | N | 81-HIGGINS
Pre-Award Financial - 147-SCHIOPU | PI approved Budget | User | Henry, Robin | 2017-06-26 | 28 | 2017-07-24 | N | 00131329
Pre-Award Financial - 170-SCHIOPU | PI approved Budget | User | Henry, Robin | 2017-06-26 | 31 | 2017-07-27 | N | 00134035
Pre-Award Financial - 56-RAO | Planning Meeting Completed | User | Henry, Robin | 2017-06-26 | 22 | 2017-07-18 | N | 00133286
Calendaring : Amendment Checklist & Process - 00105691 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Hodges, Lynda | 2017-06-26 | 10 | 2017-07-06 | N | 00105691
Calendaring : Amendment Checklist & Process - 00105691 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Hodges, Lynda | 2017-06-26 | 10 | 2017-07-06 | N | 00105691
Calendaring : Initial Calendar Build - 56-RAO | Complete Calendar ( ie. Ready for Financials ) | User | Przykucki, Anne | 2017-06-26 | 44 | 2017-08-09 | N | 00133286
Calendaring : Amendment Checklist & Process - 00113391 | Complete Calendar and Document Approval | User | Radenbaugh, Pauline | 2017-06-26 | 44 | 2017-08-09 | N | 00113391
Pre-Award Financial - 235-SUGAR | Care Designations completed | User | VanderElzen, Liz | 2017-06-26 | 44 | 2017-08-09 | N | 235-SUGAR
Pre-Award Financial - 70-LUGOGO | Internal Budget Finished | User | VanderElzen, Liz | 2017-06-26 | 10 | 2017-07-06 | N | 70-LUGOGO
Pre-Award Financial - 00128743 | OnCore Budget Build | User | Yunk, Jason | 2017-06-26 | 56 | 2017-08-21 | N | 00128743
Calendaring : Initial Calendar Build - 46-HIGGINS | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-06-26 | 63 | 2017-08-28 | N | 46-HIGGINS
Calendaring : Initial Calendar Build - 46-HIGGINS | Make Updates | User | Zahs, Brian | 2017-06-26 | 63 | 2017-08-28 | N | 46-HIGGINS
Calendaring : Initial Calendar Build - 268-NEUMAR | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-06-26 | 59 | 2017-08-24 | N | 268-NEUMAR
Calendaring : Initial Calendar Build - 268-NEUMAR | Make Updates | User | van Dijk, Tim | 2017-06-26 | 59 | 2017-08-24 | N | 268-NEUMAR
Calendaring : Initial Calendar Build - 294-ARNEDT | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-06-26 | 21 | 2017-07-17 | N | 00124702
Calendaring : Initial Calendar Build - HUM00129276 | CRAO Approval Issue & Documented | User | van Dijk, Tim | 2017-06-26 | 0 | 2017-06-26 | N | 00129276
Calendaring : Initial Calendar Build - 175-ORAL | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-06-27 | 0 | 2017-06-27 | N | 175-ORAL
Pre-Award Financial - 00128157 | OnCore Budget Build | User | Farmer, Amber | 2017-06-27 | 64 | 2017-08-30 | N | 00128157
Calendaring : Initial Calendar Build - 205-KHANNA | Attach Build Notes ( as Protocol Doc ) | User | Hess, Aaron | 2017-06-27 | 9 | 2017-07-06 | N | 00132200
Calendaring : Initial Calendar Build - 205-KHANNA | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hess, Aaron | 2017-06-27 | 21 | 2017-07-18 | N | 00132200
Pre-Award Financial - 00125794 | Initiate Post-Award Task List | User | Oliver, Amy | 2017-06-27 | 9 | 2017-07-06 | N | 00125794
Pre-Award Financial - 00128743 | Calendar Released | User | Oliver, Amy | 2017-06-27 | 44 | 2017-08-10 | N | 00128743
Pre-Award Financial - 180-HOFF | Care Designations completed | User | Oliver, Amy | 2017-06-27 | 65 |  | N | 00129450
Calendaring : Initial Calendar Build - 155-ORAL | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-06-27 | 20 | 2017-07-17 | N | 00130803
Calendaring : Initial Calendar Build - 155-ORAL | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-06-27 | 20 | 2017-07-17 | N | 00130803
Calendaring : Initial Calendar Build - 235-SUGAR | Acknowledge | User | VanderElzen, Liz | 2017-06-27 | 65 |  | N | 235-SUGAR
Pre-Award Financial - 49-MARTINEZ | Internal Budget Finished | User | VanderElzen, Liz | 2017-06-27 | 37 | 2017-08-03 | N | 00132020
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian | 2017-06-27 | 28 | 2017-07-25 | N | 00133290
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian | 2017-06-27 | 28 | 2017-07-25 | N | 00133290
Pre-Award Financial - 242-AS-SANIE | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-28 | 64 |  | N | 242-AS-SANIE
Pre-Award Financial - 255-LOK | Feasibility w/Documents received | Role | CTSU Administrator | 2017-06-28 | 64 |  | N | 255-LOK
Pre-Award Financial - 255-LOK | Sponsor Reach out | Role | CTSU Coordinator | 2017-06-28 | 13 | 2017-07-11 | N | 255-LOK
Pre-Award Financial - 255-LOK | UFA Completed | Role | CTSU Coordinator | 2017-06-28 | 13 | 2017-07-11 | N | 255-LOK
Calendaring : Initial Calendar Build - 173-WICKMAN | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-06-28 | 12 | 2017-07-10 | N | 00133542
Calendaring : Initial Calendar Build - 268-NEUMAR | Acknowledge | Role | CTSU Finance | 2017-06-28 | 64 |  | N | 268-NEUMAR
Pre-Award Financial - 96-BESIRLI | PI approved Budget | Role | CTSU Finance | 2017-06-28 | 0 | 2017-05-02 | N | 00129820
Pre-Award Financial - 00130793 | Final Budget | User | Henry, Robin | 2017-06-28 | 64 |  | N | 00130793
Pre-Award Financial - 147-SCHIOPU | Budget Negotiations | User | Henry, Robin | 2017-06-28 | 27 | 2017-07-25 | N | 00131329
Pre-Award Financial - 170-SCHIOPU | Budget Negotiations | User | Henry, Robin | 2017-06-28 | 29 | 2017-07-27 | N | 00134035
Pre-Award Financial - 87-ORAL | Final Budget | User | Henry, Robin | 2017-06-28 | 33 | 2017-07-31 | N | 00130757
CTSU Pre-Award - 314-PARK | Intake Form Completed | User | Munsey, Barbara | 2017-06-28 | 0 | 2017-06-28 | N | 314-PARK
Calendaring : Amendment Checklist & Process - 00113391 | Acknowledge | User | Oliver, Amy | 2017-06-28 | 48 | 2017-08-15 | N | 00113391
Calendaring : Initial Calendar Build - 56-RAO | Acknowledge | User | Oliver, Amy | 2017-06-28 | 47 | 2017-08-14 | N | 00133286
Pre-Award Financial - 00128157 | Calendar Released | User | Oliver, Amy | 2017-06-28 | 63 | 2017-08-30 | N | 00128157
Calendaring : Initial Calendar Build - 243-MODY | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-06-28 | 44 | 2017-08-11 | N | 00130968
Calendaring : Initial Calendar Build - 243-MODY | Make Updates | User | Radenbaugh, Pauline | 2017-06-28 | 44 | 2017-08-11 | N | 00130968
Calendaring : Initial Calendar Build - 244-MODY | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-06-28 | 44 | 2017-08-11 | N | 244-MODY
Calendaring : Initial Calendar Build - 244-MODY | Make Updates | User | Radenbaugh, Pauline | 2017-06-28 | 44 | 2017-08-11 | N | 244-MODY
Calendaring : Initial Calendar Build - 46-HIGGINS | Acknowledge | User | VanderElzen, Liz | 2017-06-28 | 64 |  | N | 46-HIGGINS
Calendaring : Initial Calendar Build - 00125836 | Assign to Analyst | User | Zahs, Brian | 2017-06-28 | 0 | 2017-06-28 | N | 00125836
Calendaring : Initial Calendar Build - 216-MODY | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-06-28 | 43 | 2017-08-10 | N | 00134866
Calendaring : Initial Calendar Build - 216-MODY | Make Updates | User | van Dijk, Tim | 2017-06-28 | 43 | 2017-08-10 | N | 00134866
Calendaring : Initial Calendar Build - 294-ARNEDT | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-06-28 | 19 | 2017-07-17 | N | 00124702
Calendaring : Initial Calendar Build - 294-ARNEDT | Complete MCA / QCT | User | van Dijk, Tim | 2017-06-28 | 8 | 2017-07-06 | N | 00124702
Calendaring : Initial Calendar Build - 294-ARNEDT | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-06-28 | 19 | 2017-07-17 | N | 00124702
Pre-Award Financial - 190-SCHIOPU | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-29 | 0 | 2017-06-29 | N | 00134443
Pre-Award Financial - 261-LUGOGO | Feasibility w/Documents received | Role | CTSU Administrator | 2017-06-29 | 63 |  | N | 261-LUGOGO
CTSU Pre-Award v2 - 323-BOLLING | Intake Form Completed | Role | CTSU Coordinator | 2017-06-29 | 0 | 2017-06-29 | N | 323-BOLLING
Open to Accrual - 00125566 | Project Award Notice (PAN) Received | Role | CTSU Coordinator | 2017-06-29 | 0 | 2017-06-29 | N | 00125566
Pre-Award Financial - 261-LUGOGO | Sponsor Reach out | Role | CTSU Coordinator | 2017-06-29 | 15 | 2017-07-14 | N | 261-LUGOGO
Pre-Award Financial - 261-LUGOGO | UFA Completed | Role | CTSU Coordinator | 2017-06-29 | 15 | 2017-07-14 | N | 261-LUGOGO
CTSU Pre-Award v2 - 00111295 | Internal Budget Finished | Role | CTSU Finance | 2017-06-29 | 63 |  | N | 00111295
Pre-Award Financial - 188-RUBENSTEIN | Care Designations completed | Role | CTSU Finance | 2017-06-29 | 63 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 211-HIGGINS | Internal Budget Finished | User | Henry, Robin | 2017-06-29 | 7 | 2017-07-06 | N | 00128325
Pre-Award Financial - 56-RAO | Care Designations completed | User | Henry, Robin | 2017-06-29 | 40 | 2017-08-08 | N | 00133286
Calendaring : Initial Calendar Build - 241-SILVER | Feasibility Approval Notice Received | User | Hess, Aaron | 2017-06-29 | 0 | 2017-06-29 | N | 00132956
Pre-Award Financial - 69-KHANNA | OnCore Budget Build | User | Oliver, Amy | 2017-06-29 | 63 |  | N | 69-KHANNA
Pre-Award Financial - 46-HIGGINS | Care Designations completed | User | VanderElzen, Liz | 2017-06-29 | 57 | 2017-08-25 | N | 46-HIGGINS
Pre-Award Financial - 70-LUGOGO | PI approved Budget | User | VanderElzen, Liz | 2017-06-29 | 28 | 2017-07-27 | N | 70-LUGOGO
Calendaring : Amendment Checklist & Process - 00121569 2 | Provide PI-Determined Care Designations ( +/- Feedback ) | User | Watson, Donna | 2017-06-29 | 20 | 2017-07-19 | N | 00121569
Calendaring : Initial Calendar Build - 175-ORAL | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-06-29 | 21 | 2017-07-20 | N | 175-ORAL
Calendaring : Initial Calendar Build - 175-ORAL | Make Updates | User | van Dijk, Tim | 2017-06-29 | 4 | 2017-07-03 | N | 175-ORAL
Open to Accrual - 00118461 | Sponsor/Organizing Group Approval Granted for Initiation of Study | User | Ball, Ron | 2017-06-30 | 62 |  | N | 00118461
Pre-Award Financial - 00128743 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-06-30 | 62 |  | N | 00128743
Pre-Award Financial - 246-AS-SANIE | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-06-30 | 62 |  | N | 246-AS-SANIE
Pre-Award Financial - 263-DELMONTE | Feasibility w/Documents received | Role | CTSU Administrator | 2017-06-30 | 62 |  | N | 263-DELMONTE
CTSU Pre-Award v2 - 325-AUCHUS | Intake Form Completed | Role | CTSU Coordinator | 2017-06-30 | 0 | 2017-06-30 | N | 00131840
Open to Accrual - 00125425 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator | 2017-06-30 | 11 | 2017-07-11 | N | 00125425
Pre-Award Financial - 235-SUGAR | IRB Application Submitted | Role | CTSU Coordinator | 2017-06-30 | 62 |  | N | 235-SUGAR
Pre-Award Financial - 242-AS-SANIE | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-06-30 | 62 |  | N | 242-AS-SANIE
Pre-Award Financial - 263-DELMONTE | Sponsor Reach out | Role | CTSU Coordinator | 2017-06-30 | 0 | 2017-06-14 | N | 263-DELMONTE
Pre-Award Financial - 263-DELMONTE | UFA Completed | Role | CTSU Coordinator | 2017-06-30 | 0 | 2017-06-13 | N | 263-DELMONTE
CTSU Post-Award - 00107755 | Next Schedule Reconciliation | Role | CTSU Finance | 2017-06-30 | 62 |  | N | 00107755
CTSU Post-Award - 00113391 | Next Schedule Reconciliation | Role | CTSU Finance | 2017-06-30 | 62 |  | N | 00113391
CTSU Post-Award - 00119175 | Next Schedule Reconciliation | Role | CTSU Finance | 2017-06-30 | 62 |  | N | 00119175
Calendaring : Amendment Checklist & Process - 00107954 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-06-30 | 0 | 2017-06-30 | N | 00107954
Calendaring : Initial Calendar Build - 216-MODY | Acknowledge | Role | CTSU Finance | 2017-06-30 | 41 | 2017-08-10 | N | 00134866
Calendaring : Initial Calendar Build - 243-MODY | Acknowledge | Role | CTSU Finance | 2017-06-30 | 42 | 2017-08-11 | N | 00130968
Calendaring : Initial Calendar Build - 244-MODY | Acknowledge | Role | CTSU Finance | 2017-06-30 | 46 | 2017-08-15 | N | 244-MODY
Pre-Award Financial - 242-AS-SANIE | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-06-30 | 62 |  | N | 242-AS-SANIE
Pre-Award Financial - 242-AS-SANIE | Request MCRU Budget | Role | CTSU Finance | 2017-06-30 | 62 |  | N | 242-AS-SANIE
Pre-Award Financial - 242-AS-SANIE | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-06-30 | 62 |  | N | 242-AS-SANIE
Pre-Award Financial - 96-BESIRLI | Budget Negotiations | Role | CTSU Finance | 2017-06-30 | 0 | 2017-05-03 | N | 00129820
Pre-Award Financial - 00130793 | PAF routed | User | Henry, Robin | 2017-06-30 | 62 |  | N | 00130793
Pre-Award Financial - 87-ORAL | PAF routed | User | Henry, Robin | 2017-06-30 | 32 | 2017-08-01 | N | 00130757
Open to Accrual - 00118461 | MiChart Verifications | User | Miller, Diana | 2017-06-30 | 0 | 2017-06-20 | N | 00118461
Pre-Award Financial - 69-KHANNA | Calendar Released | User | Oliver, Amy | 2017-06-30 | 62 |  | N | 69-KHANNA
Calendaring : Initial Calendar Build - 225-ROSENBLUM | Feasibility Approval Notice Received | User | Radenbaugh, Pauline | 2017-06-30 | 0 | 2017-06-30 | N | 00124224
Calendaring : Initial Calendar Build - 4033CYTOKINETICS-GOUTMAN | Acknowledge | User | Rollins, Matthew | 2017-06-30 | 32 | 2017-08-01 | N | 00130639
Pre-Award Financial - 235-SUGAR | Planning Meeting Completed | User | VanderElzen, Liz | 2017-06-30 | 0 | 2017-06-30 | N | 235-SUGAR
Pre-Award Financial - 49-MARTINEZ | PI approved Budget | User | VanderElzen, Liz | 2017-06-30 | 35 | 2017-08-04 | N | 00132020
CTSU Post-Award - 00066077 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-06-30 | 62 |  | N | 00066077
CTSU Post-Award - 00101092 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-06-30 | 62 |  | N | 00101092
CTSU Post-Award - 00101426 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-06-30 | 62 |  | N | 00101426
CTSU Post-Award - 00107927 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-06-30 | 62 |  | N | 00107927
CTSU Post-Award - 00107954 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-06-30 | 62 |  | N | 00107954
CTSU Post-Award - 00113496 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-06-30 | 62 |  | N | 00113496
CTSU Post-Award - 00114593 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-06-30 | 62 |  | N | 00114593
CTSU Post-Award - 00118570 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-06-30 | 62 |  | N | 00118570
CTSU Post-Award - 00119399 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-06-30 | 62 |  | N | 00119399
CTSU Post-Award - 00123231 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-06-30 | 62 |  | N | 00123231
CTSU Post-Award - 00123861 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-06-30 | 62 |  | N | 00123861
CTSU Post-Award - 00129820 | Date Reconciled | User | Yunk, Jason | 2017-06-30 | 0 | 2017-06-30 | N | 00129820
Calendaring : Initial Calendar Build - 173-WICKMAN | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-06-30 | 10 | 2017-07-10 | N | 00133542
Calendaring : Initial Calendar Build - 173-WICKMAN | Make Updates | User | van Dijk, Tim | 2017-06-30 | 10 | 2017-07-10 | N | 00133542
Pre-Award Financial - 00128157 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-07-01 | 61 |  | N | 00128157
Pre-Award Financial - 190-SCHIOPU | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-01 | 5 | 2017-07-06 | N | 00134443
Calendaring : Initial Calendar Build - 00132363 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-07-01 | 26 | 2017-07-27 | N | 00132363
Calendaring : Initial Calendar Build - 175-ORAL | Acknowledge | Role | CTSU Finance | 2017-07-01 | 11 | 2017-07-12 | N | 175-ORAL
Pre-Award Financial - 190-SCHIOPU | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-07-01 | 5 | 2017-07-06 | N | 00134443
Pre-Award Financial - 190-SCHIOPU | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-07-01 | 4 | 2017-07-05 | N | 00134443
Pre-Award Financial - 205-KHANNA | Internal Budget Finished | User | Henry, Robin | 2017-07-01 | 6 | 2017-07-07 | N | 00132200
Calendaring : Initial Calendar Build - 241-SILVER | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-07-01 | 5 | 2017-07-06 | N | 00132956
Calendaring : Amendment Checklist & Process - 00121569 2 | Complete Calendar and Document Approval | User | Munasinghe, Sadeepa | 2017-07-01 | 27 | 2017-07-28 | N | 00121569
Pre-Award Financial - 180-HOFF | Internal Budget Finished | User | Oliver, Amy | 2017-07-01 | 61 |  | N | 00129450
Calendaring : Initial Calendar Build - 241-SILVER | Assign to Analyst | User | Radenbaugh, Pauline | 2017-07-01 | 5 | 2017-07-06 | N | 00132956
Pre-Award Financial - 70-LUGOGO | Budget Negotiations | User | VanderElzen, Liz | 2017-07-01 | 26 | 2017-07-27 | N | 70-LUGOGO
Calendaring : Initial Calendar Build - 00125836 | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian | 2017-07-01 | 0 | 2017-06-28 | N | 00125836
Pre-Award Financial - 00128743 | Open to Accrual | Role | CTSU Administrator | 2017-07-02 | 60 |  | N | 00128743
Pre-Award Financial - 246-AS-SANIE | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-02 | 60 |  | N | 246-AS-SANIE
CTSU Pre-Award v2 - 00111295 | PI approved Budget | Role | CTSU Finance | 2017-07-02 | 60 |  | N | 00111295
Calendaring : Initial Calendar Build - 173-WICKMAN | Acknowledge | Role | CTSU Finance | 2017-07-02 | 8 | 2017-07-10 | N | 00133542
Calendaring : Initial Calendar Build - 221-MODY | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-07-02 | 18 | 2017-07-20 | N | 00129412
Calendaring : Initial Calendar Build - 260-MODY | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-07-02 | 60 |  | N | 00134979
Pre-Award Financial - 246-AS-SANIE | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-07-02 | 60 |  | N | 246-AS-SANIE
Pre-Award Financial - 246-AS-SANIE | Request MCRU Budget | Role | CTSU Finance | 2017-07-02 | 60 |  | N | 246-AS-SANIE
Pre-Award Financial - 246-AS-SANIE | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-07-02 | 60 |  | N | 246-AS-SANIE
Pre-Award Financial - 205-KHANNA | Billing Calendar Received | User | Henry, Robin | 2017-07-02 | 16 | 2017-07-18 | N | 00132200
Pre-Award Financial - 211-HIGGINS | PI approved Budget | User | Henry, Robin | 2017-07-02 | 10 | 2017-07-12 | N | 00128325
Pre-Award Financial - 155-ORAL | Billing Calendar Received | User | Oliver, Amy | 2017-07-02 | 15 | 2017-07-17 | N | 00130803
Calendaring : Amendment Checklist & Process - 00107954 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-07-02 | 3 | 2017-07-05 | N | 00107954
Calendaring : Initial Calendar Build - 225-ROSENBLUM | Assign to Analyst | User | Radenbaugh, Pauline | 2017-07-02 | 4 | 2017-07-06 | N | 00124224
Calendaring : Initial Calendar Build - 225-ROSENBLUM | Submit Calendar Build Request and Docs to Nimblify | User | Radenbaugh, Pauline | 2017-07-02 | 4 | 2017-07-06 | N | 00124224
Pre-Award Financial - 282-POP-BUSUI | Billing Calendar Received | User | VanderElzen, Liz | 2017-07-02 | 23 | 2017-07-25 | N | 00133290
Pre-Award Financial - 49-MARTINEZ | Budget Negotiations | User | VanderElzen, Liz | 2017-07-02 | 33 | 2017-08-04 | N | 00132020
Pre-Award Financial - 00128157 | Open to Accrual | Role | CTSU Administrator | 2017-07-03 | 59 |  | N | 00128157
Pre-Award Financial - 278-CONJEEVARAM | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-03 | 0 | 2017-07-03 | N | 00133341
Pre-Award Financial - 69-KHANNA | PI Signoff in OnCore | Role | CTSU Administrator | 2017-07-03 | 59 |  | N | 69-KHANNA
CTSU Pre-Award - 326-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-07-03 | 0 | 2017-07-03 | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-07-03 | 0 | 2017-07-03 | N | 327-HIGGINS
Open to Accrual - 00125566 | MiChart Verifications | Role | CTSU Coordinator | 2017-07-03 | 0 | 2017-07-03 | N | 00125566
Calendaring : Amendment Checklist & Process - 00123635 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-07-03 | 0 | 2017-07-03 | N | 00123635
Pre-Award Financial - 188-RUBENSTEIN | Internal Budget Finished | Role | CTSU Finance | 2017-07-03 | 59 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 56-RAO | Internal Budget Finished | User | Henry, Robin | 2017-07-03 | 32 | 2017-08-04 | N | 00133286
Calendaring : Initial Calendar Build - 00124202 | Feasibility Approval Notice Received | User | Hess, Aaron | 2017-07-03 | 0 | 2017-07-03 | N | 00124202
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Feasibility Approval Notice Received | User | Hess, Aaron | 2017-07-03 | 0 | 2017-07-03 | N | 00133341
Calendaring : Initial Calendar Build - 00132363 | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-07-03 | 25 | 2017-07-28 | N | 00132363
Calendaring : Initial Calendar Build - 00132363 | Make Updates | User | Munasinghe, Sadeepa | 2017-07-03 | 24 | 2017-07-27 | N | 00132363
Calendaring : Amendment Checklist & Process - 00107954 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Radenbaugh, Pauline | 2017-07-03 | 4 | 2017-07-07 | N | 00107954
Calendaring : Amendment Checklist & Process - 00107954 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Radenbaugh, Pauline | 2017-07-03 | 4 | 2017-07-07 | N | 00107954
Calendaring : Initial Calendar Build - 287-HUTCHINSON | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-07-03 | 22 | 2017-07-25 | N | 00119926
Pre-Award Financial - 46-HIGGINS | Internal Budget Finished | User | VanderElzen, Liz | 2017-07-03 | 20 | 2017-07-23 | N | 46-HIGGINS
Calendaring : Amendment Checklist & Process - 00121569 2 | Acknowledge | User | Watson, Donna | 2017-07-03 | 16 | 2017-07-19 | N | 00121569
CTSU Pre-Award v2 - 00111295 | Budget Negotiations | Role | CTSU Finance | 2017-07-04 | 58 |  | N | 00111295
Calendaring : Initial Calendar Build - 155-ORAL | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-07-04 | 58 |  | N | 00130803
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-07-04 | 35 | 2017-08-08 | N | 00133290
Pre-Award Financial - 91-ELSE | PAN Released | Role | CTSU Finance | 2017-07-04 | 58 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | PAN Released | Role | CTSU Finance | 2017-07-04 | 58 |  | N | 92-AUCHUS
Pre-Award Financial - 205-KHANNA | PI approved Budget | User | Henry, Robin | 2017-07-04 | 28 | 2017-08-01 | N | 00132200
Calendaring : Initial Calendar Build - 241-SILVER | Nimblify Build is Complete & Ready for Import | User | LaVasseur, Kristen | 2017-07-04 | 27 | 2017-07-31 | N | 00132956
Calendaring : Initial Calendar Build - 205-KHANNA | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Oliver, Amy | 2017-07-04 | 34 | 2017-08-07 | N | 00132200
Pre-Award Financial - 00129427 | OnCore Budget Build | User | Oliver, Amy | 2017-07-04 | 58 |  | N | 00129427
Pre-Award Financial - 180-HOFF | PI approved Budget | User | Oliver, Amy | 2017-07-04 | 58 |  | N | 00129450
Calendaring : Amendment Checklist & Process - 00107954 | ** Items/Services : Addition or Removal of Procedures / Events | User | Radenbaugh, Pauline | 2017-07-04 | 3 | 2017-07-07 | N | 00107954
Calendaring : Initial Calendar Build - 241-SILVER | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-07-04 | 3 | 2017-07-07 | N | 00132956
Calendaring : Initial Calendar Build - 241-SILVER | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-07-04 | 3 | 2017-07-07 | N | 00132956
Pre-Award Financial - 00129652 | Final Budget | User | VanderElzen, Liz | 2017-07-04 | 14 | 2017-07-18 | N | 00129652
Calendaring : Initial Calendar Build - 260-MODY | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-07-04 | 58 |  | N | 00134979
Calendaring : Initial Calendar Build - 260-MODY | Make Updates | User | van Dijk, Tim | 2017-07-04 | 58 |  | N | 00134979
Pre-Award Financial - 255-LOK | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-05 | 57 |  | N | 255-LOK
Pre-Award Financial - 69-KHANNA | Open to Accrual | Role | CTSU Administrator | 2017-07-05 | 57 |  | N | 69-KHANNA
CTSU Pre-Award - 331-FLAHERTY | Intake Form Completed | Role | CTSU Coordinator | 2017-07-05 | 0 | 2017-07-05 | N | 331-FLAHERTY
CTSU Pre-Award - 332-BELLOLI | Intake Form Completed | Role | CTSU Coordinator | 2017-07-05 | 0 | 2017-07-05 | N | 332-BELLOLI
Pre-Award Financial - 00128743 | IRB Application Submitted | Role | CTSU Coordinator | 2017-07-05 | 0 | 2017-07-05 | N | 00128743
Pre-Award Financial - 278-CONJEEVARAM | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-05 | 1 | 2017-07-06 | N | 00133341
Calendaring : Initial Calendar Build - 00132363 | Acknowledge | Role | CTSU Finance | 2017-07-05 | 23 | 2017-07-28 | N | 00132363
Calendaring : Initial Calendar Build - 287-HUTCHINSON | Acknowledge | Role | CTSU Finance | 2017-07-05 | 33 | 2017-08-07 | N | 00119926
Calendaring : Initial Calendar Build - 294-ARNEDT | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-07-05 | 13 | 2017-07-18 | N | 00124702
Pre-Award Financial - 278-CONJEEVARAM | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-07-05 | 5 | 2017-07-10 | N | 00133341
Pre-Award Financial - 278-CONJEEVARAM | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-07-05 | 5 | 2017-07-10 | N | 00133341
Calendaring : Initial Calendar Build - 00124202 | Assign to Analyst | User | Hess, Aaron | 2017-07-05 | 1 | 2017-07-06 | N | 00124202
Calendaring : Initial Calendar Build - 00124202 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-07-05 | 1 | 2017-07-06 | N | 00124202
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-07-05 | 1 | 2017-07-06 | N | 00133341
Pre-Award Financial - 00129427 | Calendar Released | User | Oliver, Amy | 2017-07-05 | 57 |  | N | 00129427
Pre-Award Financial - 71-RICE | PAN Released | User | Oliver, Amy | 2017-07-05 | 57 |  | N | 00134857
Calendaring : Amendment Checklist & Process - 00123635 | Assign to Analyst | User | Przykucki, Anne | 2017-07-05 | 0 | 2017-07-05 | N | 00123635
Calendaring : Amendment Checklist & Process - 00107954 | ** Visits : Addition or Removal of Time Points | User | Radenbaugh, Pauline | 2017-07-05 | 2 | 2017-07-07 | N | 00107954
Calendaring : Amendment Checklist & Process - 00107954 | Request Care Designations | User | Radenbaugh, Pauline | 2017-07-05 | 2 | 2017-07-07 | N | 00107954
Calendaring : Initial Calendar Build - 225-ROSENBLUM | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-07-05 | 1 | 2017-07-06 | N | 00124224
Calendaring : Initial Calendar Build - 225-ROSENBLUM | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-07-05 | 15 | 2017-07-20 | N | 00124224
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Assign to Analyst | User | Radenbaugh, Pauline | 2017-07-05 | 1 | 2017-07-06 | N | 00133341
Pre-Award Financial - 76-KHANNA | OnCore Budget Build | User | Yunk, Jason | 2017-07-05 | 43 | 2017-08-17 | N | 00131837
Calendaring : Initial Calendar Build - 00130757 | CRAO Approval Issue & Documented | User | Zahs, Brian | 2017-07-05 | 0 | 2017-07-05 | N | 00130757
Calendaring : Initial Calendar Build - 230-ROGERS | CRAO Approval Issue & Documented | User | Zahs, Brian | 2017-07-05 | 57 |  | N | 00130272
Pre-Award Financial - 261-LUGOGO | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-06 | 56 |  | N | 261-LUGOGO
Pre-Award Financial - 278-CONJEEVARAM | Feasibility w/Documents received | Role | CTSU Administrator | 2017-07-06 | 0 | 2017-06-27 | N | 00133341
CTSU Pre-Award - 336-KHANNA | Intake Form Completed | Role | CTSU Coordinator | 2017-07-06 | 0 | 2017-07-06 | N | 00133684
CTSU Pre-Award - 337-MIAN | Intake Form Completed | Role | CTSU Coordinator | 2017-07-06 | 0 | 2017-07-06 | N | 337-MIAN
CTSU Pre-Award - 338-MIAN | Intake Form Completed | Role | CTSU Coordinator | 2017-07-06 | 0 | 2017-07-06 | N | 00133457
Pre-Award Financial - 278-CONJEEVARAM | Sponsor Reach out | Role | CTSU Coordinator | 2017-07-06 | 0 | 2017-06-15 | N | 00133341
Pre-Award Financial - 282-POP-BUSUI | IRB Application Submitted | Role | CTSU Coordinator | 2017-07-06 | 14 | 2017-07-20 | N | 00133290
Calendaring : Amendment Checklist & Process - 00105691 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance | 2017-07-06 | 6 | 2017-07-12 | N | 00105691
Calendaring : Initial Calendar Build - 260-MODY | Acknowledge | Role | CTSU Finance | 2017-07-06 | 56 |  | N | 00134979
Pre-Award Financial - 00125425 | Initiate Post-Award Task List | Role | CTSU Finance | 2017-07-06 | 0 | 2017-07-06 | N | 00125425
Pre-Award Financial - 00125566 | Initiate Post-Award Task List | Role | CTSU Finance | 2017-07-06 | 0 | 2017-07-06 | N | 00125566
Pre-Award Financial - 00125786 | Initiate Post-Award Task List | Role | CTSU Finance | 2017-07-06 | 0 | 2017-07-06 | N | 00125786
Pre-Award Financial - 00127537 | Initiate Post-Award Task List | Role | CTSU Finance | 2017-07-06 | 0 | 2017-07-06 | N | 00127537
Pre-Award Financial - 188-RUBENSTEIN | PI approved Budget | Role | CTSU Finance | 2017-07-06 | 56 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 77-CONJEEVARAM | OnCore Budget Build | Role | CTSU Finance | 2017-07-06 | 56 |  | N | 77-CONJEEVARAM
Pre-Award Financial - 205-KHANNA | Budget Negotiations | User | Henry, Robin | 2017-07-06 | 27 | 2017-08-02 | N | 00132200
Pre-Award Financial - 56-RAO | PI approved Budget | User | Henry, Robin | 2017-07-06 | 37 | 2017-08-12 | N | 00133286
Calendar Build - 8-AARONSON | Calendar Build Request sent to Nimblify | User | Hess, Aaron | 2017-07-06 | 0 | 2017-07-06 | N | 00132110
Calendaring : Amendment Checklist & Process - 00105691 | ** Footnote Edits | User | Hodges, Lynda | 2017-07-06 | 0 | 2017-07-06 | N | 00105691
Calendaring : Initial Calendar Build - 241-SILVER | Attach Build Notes ( as Protocol Doc ) | User | LaVasseur, Kristen | 2017-07-06 | 29 | 2017-08-04 | N | 00132956
Pre-Award Financial - 180-HOFF | Budget Negotiations | User | Oliver, Amy | 2017-07-06 | 56 |  | N | 00129450
Pre-Award Financial - 76-KHANNA | Calendar Released | User | Oliver, Amy | 2017-07-06 | 43 | 2017-08-18 | N | 00131837
Pre-Award Financial - 96-BESIRLI | Initiate Post-Award Task List | User | Oliver, Amy | 2017-07-06 | 0 | 2017-07-06 | N | 00129820
Calendaring : Amendment Checklist & Process - 00123635 | ** Footnote Edits | User | Przykucki, Anne | 2017-07-06 | 4 | 2017-07-10 | N | 00123635
Calendaring : Amendment Checklist & Process - 00123635 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Przykucki, Anne | 2017-07-06 | 4 | 2017-07-10 | N | 00123635
Calendaring : Amendment Checklist & Process - 00123635 | ** Visit Tolerance Edits | User | Przykucki, Anne | 2017-07-06 | 4 | 2017-07-10 | N | 00123635
Calendaring : Amendment Checklist & Process - 00123635 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Przykucki, Anne | 2017-07-06 | 1 | 2017-07-07 | N | 00123635
Calendaring : Initial Calendar Build - 155-ORAL | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-07-06 | 56 |  | N | 00130803
Calendaring : Initial Calendar Build - 155-ORAL | Make Updates | User | Radenbaugh, Pauline | 2017-07-06 | 56 |  | N | 00130803
Calendaring : Initial Calendar Build - 241-SILVER | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-07-06 | 35 | 2017-08-10 | N | 00132956
Pre-Award Financial - 00129652 | PAF routed | User | VanderElzen, Liz | 2017-07-06 | 19 | 2017-07-25 | N | 00129652
Pre-Award Financial - 282-POP-BUSUI | Planning Meeting Completed | User | VanderElzen, Liz | 2017-07-06 | 0 | 2017-06-26 | N | 00133290
Pre-Award Financial - 46-HIGGINS | PI approved Budget | User | VanderElzen, Liz | 2017-07-06 | 17 | 2017-07-23 | N | 46-HIGGINS
CTSU Post-Award - 00125786 | Date Reconciled | User | Yunk, Jason | 2017-07-06 | 0 | 2017-07-06 | N | 00125786
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-07-06 | 34 | 2017-08-09 | N | 00133290
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Make Updates | User | Zahs, Brian | 2017-07-06 | 34 | 2017-08-09 | N | 00133290
Calendaring : Initial Calendar Build - 205-KHANNA | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-07-06 | 43 | 2017-08-18 | N | 00132200
Calendaring : Initial Calendar Build - 205-KHANNA | Make Updates | User | van Dijk, Tim | 2017-07-06 | 43 | 2017-08-18 | N | 00132200
Pre-Award Financial - 282-POP-BUSUI | Feasibility w/Documents received | Role | CTSU Administrator | 2017-07-07 | 0 | 2017-06-18 | N | 00133290
Pre-Award Financial - 255-LOK | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-07 | 55 |  | N | 255-LOK
Pre-Award Financial - 242-AS-SANIE | Internal Budget Finished | Role | CTSU Finance | 2017-07-07 | 55 |  | N | 242-AS-SANIE
Pre-Award Financial - 255-LOK | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-07-07 | 55 |  | N | 255-LOK
Pre-Award Financial - 255-LOK | Request MCRU Budget | Role | CTSU Finance | 2017-07-07 | 55 |  | N | 255-LOK
Pre-Award Financial - 255-LOK | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-07-07 | 55 |  | N | 255-LOK
Pre-Award Financial - 263-DELMONTE | Feasibility approved/CRAO Notified | Role | CTSU Finance | 2017-07-07 | 55 |  | N | 263-DELMONTE
Pre-Award Financial - 77-CONJEEVARAM | Calendar Released | Role | CTSU Finance | 2017-07-07 | 55 |  | N | 77-CONJEEVARAM
Calendaring : Amendment Checklist & Process - 00123635 | ** Items/Services : Addition or Removal of Procedures / Events | User | Przykucki, Anne | 2017-07-07 | 3 | 2017-07-10 | N | 00123635
Calendaring : Initial Calendar Build - 225-ROSENBLUM | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-07-07 | 18 | 2017-07-25 | N | 00124224
Calendaring : Initial Calendar Build - 225-ROSENBLUM | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-07-07 | 18 | 2017-07-25 | N | 00124224
Pre-Award Financial - 00108880 | OnCore Budget Build | User | VanderElzen, Liz | 2017-07-07 | 55 |  | N | 00108880
Pre-Award Financial - 235-SUGAR | Internal Budget Finished | User | VanderElzen, Liz | 2017-07-07 | 55 |  | N | 235-SUGAR
Pre-Award Financial - 00126010 | OnCore Budget Build | User | Yunk, Jason | 2017-07-07 | 6 | 2017-07-13 | N | 00126010
Pre-Award Financial - 00128173 | OnCore Budget Build | User | Yunk, Jason | 2017-07-07 | 55 |  | N | 00128173
Calendaring : Initial Calendar Build - 190-SCHIOPU | Complete MCA / QCT | User | van Dijk, Tim | 2017-07-07 | 0 | 2017-07-07 | N | 00134443
Calendaring : Initial Calendar Build - 190-SCHIOPU | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-07-07 | 0 | 2017-07-06 | N | 00134443
Calendaring : Initial Calendar Build - 294-ARNEDT | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-07-07 | 11 | 2017-07-18 | N | 00124702
Calendaring : Initial Calendar Build - 294-ARNEDT | Make Updates | User | van Dijk, Tim | 2017-07-07 | 11 | 2017-07-18 | N | 00124702
Pre-Award Financial - 00129427 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-07-08 | 54 |  | N | 00129427
Pre-Award Financial - 261-LUGOGO | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-08 | 54 |  | N | 261-LUGOGO
Calendaring : Initial Calendar Build - 155-ORAL | Acknowledge | Role | CTSU Finance | 2017-07-08 | 54 |  | N | 00130803
Pre-Award Financial - 188-RUBENSTEIN | Budget Negotiations | Role | CTSU Finance | 2017-07-08 | 54 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 242-AS-SANIE | Billing Calendar Received | Role | CTSU Finance | 2017-07-08 | 54 |  | N | 242-AS-SANIE
Pre-Award Financial - 261-LUGOGO | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-07-08 | 54 |  | N | 261-LUGOGO
Pre-Award Financial - 261-LUGOGO | Request MCRU Budget | Role | CTSU Finance | 2017-07-08 | 54 |  | N | 261-LUGOGO
Pre-Award Financial - 261-LUGOGO | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-07-08 | 54 |  | N | 261-LUGOGO
Calendaring : Initial Calendar Build - 205-KHANNA | Acknowledge | User | Henry, Robin | 2017-07-08 | 48 | 2017-08-25 | N | 00132200
Pre-Award Financial - 56-RAO | Budget Negotiations | User | Henry, Robin | 2017-07-08 | 37 | 2017-08-14 | N | 00133286
Calendaring : Initial Calendar Build - 00124202 | Nimblify Build is Complete & Ready for Import | User | Hess, Aaron | 2017-07-08 | 0 | 2017-07-08 | N | 00124202
Calendaring : Amendment Checklist & Process - 00105691 | Complete Calendar and Document Approval | User | Hodges, Lynda | 2017-07-08 | 0 | 2017-07-06 | N | 00105691
Pre-Award Financial - 00108880 | Calendar Released | User | Oliver, Amy | 2017-07-08 | 54 |  | N | 00108880
Pre-Award Financial - 00126010 | Calendar Released | User | Oliver, Amy | 2017-07-08 | 45 | 2017-08-22 | N | 00126010
Pre-Award Financial - 00128173 | Calendar Released | User | Oliver, Amy | 2017-07-08 | 54 |  | N | 00128173
Calendaring : Amendment Checklist & Process - 00123635 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Przykucki, Anne | 2017-07-08 | 2 | 2017-07-10 | N | 00123635
Calendaring : Amendment Checklist & Process - 00123635 | ** Visits : Addition or Removal of Time Points | User | Przykucki, Anne | 2017-07-08 | 2 | 2017-07-10 | N | 00123635
Calendaring : Amendment Checklist & Process - 00123635 | Update RSH Source in MBECT | User | Przykucki, Anne | 2017-07-08 | 2 | 2017-07-10 | N | 00123635
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-07-08 | 0 | 2017-07-07 | N | 00133341
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-07-08 | 0 | 2017-07-07 | N | 00133341
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-07-08 | 5 | 2017-07-13 | N | 00133341
Calendaring : Initial Calendar Build - 282-POP-BUSUI | Acknowledge | User | VanderElzen, Liz | 2017-07-08 | 38 | 2017-08-15 | N | 00133290
Pre-Award Financial - 46-HIGGINS | Budget Negotiations | User | VanderElzen, Liz | 2017-07-08 | 54 |  | N | 46-HIGGINS
Calendaring : Initial Calendar Build - 00124202 | Complete MCA / QCT | User | Zahs, Brian | 2017-07-08 | 45 | 2017-08-22 | N | 00124202
Calendaring : Initial Calendar Build - 00124202 | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian | 2017-07-08 | 44 | 2017-08-21 | N | 00124202
Pre-Award Financial - 263-DELMONTE | Request Research Pharmacy Budget | Role | CTSU Administrator | 2017-07-09 | 53 |  | N | 263-DELMONTE
Pre-Award Financial - 76-KHANNA | PI Signoff in OnCore | Role | CTSU Administrator | 2017-07-09 | 53 |  | N | 00131837
Pre-Award Financial - 263-DELMONTE | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-09 | 53 |  | N | 263-DELMONTE
CTSU Pre-Award v2 - 82-BOLLING | Final Budget | Role | CTSU Finance | 2017-07-09 | 53 |  | N | 82-BOLLING
Calendaring : Amendment Checklist & Process - 00104658 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-07-09 | 0 | 2017-07-09 | N | 00104658
Calendaring : Initial Calendar Build - 294-ARNEDT | Acknowledge | Role | CTSU Finance | 2017-07-09 | 9 | 2017-07-18 | N | 00124702
Pre-Award Financial - 263-DELMONTE | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-07-09 | 53 |  | N | 263-DELMONTE
Pre-Award Financial - 263-DELMONTE | Request MCRU Budget | Role | CTSU Finance | 2017-07-09 | 53 |  | N | 263-DELMONTE
Pre-Award Financial - 190-SCHIOPU | Billing Calendar Received | User | Henry, Robin | 2017-07-09 | 0 | 2017-07-07 | N | 00134443
Pre-Award Financial - 205-KHANNA | Care Designations completed | User | Henry, Robin | 2017-07-09 | 16 | 2017-07-25 | N | 00132200
Core Sponsor Documents for Study Feasibility & Start Up - General - 192-ALAM | Sponsor Budget | User | Munsey, Barbara | 2017-07-09 | 0 | 2017-07-09 | N | 192-ALAM
Core Sponsor Documents for Study Feasibility & Start Up - General - 192-ALAM | Sponsor Contract | User | Munsey, Barbara | 2017-07-09 | 0 | 2017-07-09 | N | 192-ALAM
Pre-Award Financial - 155-ORAL | Care Designations completed | User | Oliver, Amy | 2017-07-09 | 53 |  | N | 00130803
Pre-Award Financial - 282-POP-BUSUI | Care Designations completed | User | VanderElzen, Liz | 2017-07-09 | 25 | 2017-08-03 | N | 00133290
CTSU Post-Award - 00129851 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-07-09 | 53 |  | N | 00129851
Pre-Award Financial - 00129427 | Open to Accrual | Role | CTSU Administrator | 2017-07-10 | 52 |  | N | 00129427
Pre-Award Financial - 77-CONJEEVARAM | PI Signoff in OnCore | Role | CTSU Administrator | 2017-07-10 | 52 |  | N | 77-CONJEEVARAM
CTSU Pre-Award - 341-STOFFEL | Intake Form Completed | Role | CTSU Coordinator | 2017-07-10 | 0 | 2017-07-10 | N | 00134997
CTSU Pre-Award - 342-HUMES | Intake Form Completed | Role | CTSU Finance | 2017-07-10 | 0 | 2017-07-10 | N | 342-HUMES
Calendaring : Amendment Checklist & Process - 00105691 | Acknowledge | Role | CTSU Finance | 2017-07-10 | 2 | 2017-07-12 | N | 00105691
Calendaring : Specification Update Request(s) - 00126707 | Submit Update Request(s) | Role | CTSU Finance | 2017-07-10 | 0 | 2017-07-10 | N | 00126707
Pre-Award Financial - 142-FLAHERTY | Final Budget | Role | CTSU Finance | 2017-07-10 | 52 |  | N | 142-FLAHERTY
Pre-Award Financial - 242-AS-SANIE | PI approved Budget | Role | CTSU Finance | 2017-07-10 | 52 |  | N | 242-AS-SANIE
Pre-Award Financial - 246-AS-SANIE | Billing Calendar Received | Role | CTSU Finance | 2017-07-10 | 52 |  | N | 246-AS-SANIE
Pre-Award Financial - 81-HIGGINS | OnCore Budget Build | Role | CTSU Finance | 2017-07-10 | 52 |  | N | 81-HIGGINS
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-07-10 | 7 | 2017-07-17 | N | 00133341
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-07-10 | 7 | 2017-07-17 | N | 00133341
Pre-Award Financial - 235-SUGAR | PI approved Budget | User | VanderElzen, Liz | 2017-07-10 | 52 |  | N | 235-SUGAR
Calendaring : Amendment Checklist & Process - 00107954 | Provide PI-Determined Care Designations ( +/- Feedback ) | User | Yunk, Jason | 2017-07-10 | 22 | 2017-08-01 | N | 00107954
Calendaring : Initial Calendar Build - 00124202 | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian | 2017-07-10 | 43 | 2017-08-22 | N | 00124202
Calendaring : Initial Calendar Build - 00124202 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian | 2017-07-10 | 42 | 2017-08-21 | N | 00124202
Calendaring : Initial Calendar Build - 190-SCHIOPU | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-07-10 | 0 | 2017-07-07 | N | 00134443
Calendaring : Initial Calendar Build - 00131311 | Feasibility Approval Notice Received | Role | CRAO | 2017-07-11 | 1 | 2017-07-12 | N | 00131311
Pre-Award Financial - 00108880 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-07-11 | 51 |  | N | 00108880
Pre-Award Financial - 00126010 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-07-11 | 51 |  | N | 00126010
Pre-Award Financial - 00128173 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-07-11 | 51 |  | N | 00128173
Pre-Award Financial - 76-KHANNA | Open to Accrual | Role | CTSU Administrator | 2017-07-11 | 51 |  | N | 00131837
CTSU Pre-Award v2 - 82-BOLLING | PAF routed | Role | CTSU Finance | 2017-07-11 | 51 |  | N | 82-BOLLING
Pre-Award Financial - 81-HIGGINS | Calendar Released | Role | CTSU Finance | 2017-07-11 | 51 |  | N | 81-HIGGINS
Calendaring : Initial Calendar Build - 223-MODY | Complete Calendar ( ie. Ready for Financials ) | User | Hodges, Lynda | 2017-07-11 | 2 | 2017-07-13 | N | 00131377
Calendaring : Initial Calendar Build - 223-MODY | Make Updates | User | Hodges, Lynda | 2017-07-11 | 2 | 2017-07-13 | N | 00131377
Pre-Award Financial - SLS-III | Created CTRF & "Notify ORSP" | User | Oliver, Amy | 2017-07-11 | 0 | 2017-07-11 | N | 00131953
Calendaring : Amendment Checklist & Process - 00104658 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-07-11 | 14 | 2017-07-25 | N | 00104658
Calendaring : Amendment Checklist & Process - 00106894 | AME Calendaring Process Initiated | User | Radenbaugh, Pauline | 2017-07-11 | 0 | 2017-07-11 | N | 00106894
CTSU Pre-Award v2 - 415-ROMANO | Feasibility w/Documents received | Role | CTSU Administrator | 2017-07-12 | 0 | 2017-07-12 | N | 415-ROMANO
Pre-Award Financial - 298-SCHIOPU | Feasibility w/Documents received | Role | CTSU Administrator | 2017-07-12 | 50 |  | N | 298-SCHIOPU
Pre-Award Financial - 77-CONJEEVARAM | Open to Accrual | Role | CTSU Administrator | 2017-07-12 | 50 |  | N | 77-CONJEEVARAM
CTSU Pre-Award - 346-BAPTIST | Intake Form Completed | Role | CTSU Coordinator | 2017-07-12 | 0 | 2017-07-12 | N | 346-BAPTIST
CTSU Pre-Award - 347-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-07-12 | 0 | 2017-07-12 | N | 347-HIGGINS
Pre-Award Financial - 298-SCHIOPU | Sponsor Reach out | Role | CTSU Coordinator | 2017-07-12 | 0 | 2017-07-10 | N | 298-SCHIOPU
Pre-Award Financial - 298-SCHIOPU | UFA Completed | Role | CTSU Coordinator | 2017-07-12 | 0 | 2017-07-10 | N | 298-SCHIOPU
CTSU Pre-Award v2 - 82-BOLLING | OnCore Budget Build | Role | CTSU Finance | 2017-07-12 | 50 |  | N | 82-BOLLING
Calendaring : Amendment Checklist & Process - 00109407 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-07-12 | 0 | 2017-07-12 | N | 00109407
Pre-Award Financial - 142-FLAHERTY | PAF routed | Role | CTSU Finance | 2017-07-12 | 50 |  | N | 142-FLAHERTY
Pre-Award Financial - 242-AS-SANIE | Budget Negotiations | Role | CTSU Finance | 2017-07-12 | 50 |  | N | 242-AS-SANIE
Pre-Award Financial - 242-AS-SANIE | Planning Meeting Completed | Role | CTSU Finance | 2017-07-12 | 50 |  | N | 242-AS-SANIE
Calendaring : Initial Calendar Build - 00131311 | Assign to Analyst | User | Greene, Paula | 2017-07-12 | 0 | 2017-07-12 | N | 00131311
Calendaring : Specification Update Request(s) - 00126707 | Assign to Analyst | User | Greene, Paula | 2017-07-12 | 0 | 2017-07-10 | N | 00126707
Pre-Award Financial - 147-SCHIOPU | Final Budget | User | Henry, Robin | 2017-07-12 | 26 | 2017-08-07 | N | 00131329
Pre-Award Financial - 170-SCHIOPU | Final Budget | User | Henry, Robin | 2017-07-12 | 44 | 2017-08-25 | N | 00134035
Calendaring : Initial Calendar Build - 00131311 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-07-12 | 0 | 2017-07-12 | N | 00131311
Calendaring : Initial Calendar Build - 221-MODY | Attach Build Notes ( as Protocol Doc ) | User | Hodges, Lynda | 2017-07-12 | 2 | 2017-07-14 | N | 00129412
Calendaring : Amendment Checklist & Process - 00107954 | Complete Calendar and Document Approval | User | Radenbaugh, Pauline | 2017-07-12 | 41 | 2017-08-22 | N | 00107954
Pre-Award Financial - 235-SUGAR | Budget Negotiations | User | VanderElzen, Liz | 2017-07-12 | 50 |  | N | 235-SUGAR
Calendaring : Initial Calendar Build - 190-SCHIOPU | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-07-12 | 0 | 2017-07-07 | N | 00134443
Calendaring : Initial Calendar Build - 190-SCHIOPU | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-07-12 | 0 | 2017-07-07 | N | 00134443
Calendaring : Initial Calendar Build - 112-FLAHERTY | Feasibility Approval Notice Received | Role | CRAO | 2017-07-13 | 1 | 2017-07-14 | N | 112-FLAHERTY
Calendaring : Initial Calendar Build - 112-FLAHERTY | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO | 2017-07-13 | 1 | 2017-07-14 | N | 112-FLAHERTY
Calendaring : Initial Calendar Build - 336-KHANNA | Feasibility Approval Notice Received | Role | CRAO | 2017-07-13 | 0 | 2017-07-13 | N | 00133684
CTSU Pre-Award - 336-KHANNA | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-13 | 0 | 2017-07-13 | N | 00133684
Open to Accrual - 00129716 | IRB Approval | Role | CTSU Administrator | 2017-07-13 | 0 | 2017-07-13 | N | 00129716
Pre-Award Financial - 00108880 | Open to Accrual | Role | CTSU Administrator | 2017-07-13 | 49 |  | N | 00108880
Pre-Award Financial - 00126010 | Open to Accrual | Role | CTSU Administrator | 2017-07-13 | 49 |  | N | 00126010
Pre-Award Financial - 00128173 | Open to Accrual | Role | CTSU Administrator | 2017-07-13 | 49 |  | N | 00128173
Pre-Award Financial - 112-FLAHERTY | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-13 | 0 | 2017-07-13 | N | 112-FLAHERTY
CTSU Pre-Award - 348-CHEY | Intake Form Completed | Role | CTSU Coordinator | 2017-07-13 | 0 | 2017-07-13 | N | 348-CHEY
CTSU Pre-Award v2 - 82-BOLLING | Calendar Released | Role | CTSU Finance | 2017-07-13 | 49 |  | N | 82-BOLLING
Calendaring : Initial Calendar Build - 223-MODY | Acknowledge | Role | CTSU Finance | 2017-07-13 | 0 | 2017-07-13 | N | 00131377
Calendaring : Initial Calendar Build - 336-KHANNA | Assign to Analyst | User | Greene, Paula | 2017-07-13 | 0 | 2017-07-13 | N | 00133684
Pre-Award Financial - 190-SCHIOPU | Planning Meeting Completed | User | Henry, Robin | 2017-07-13 | 4 | 2017-07-17 | N | 00134443
Pre-Award Financial - 278-CONJEEVARAM | Billing Calendar Received | User | Henry, Robin | 2017-07-13 | 4 | 2017-07-17 | N | 00133341
Calendaring : Initial Calendar Build - 336-KHANNA | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-07-13 | 0 | 2017-07-13 | N | 00133684
Calendaring : Amendment Checklist & Process - 00108139 | ** Footnote Edits | User | Hodges, Lynda | 2017-07-13 | 0 | 2017-07-13 | N | 00108139
Calendaring : Amendment Checklist & Process - 00108139 | ** Items/Services : Addition or Removal of Procedures / Events | User | Hodges, Lynda | 2017-07-13 | 0 | 2017-07-13 | N | 00108139
Calendaring : Amendment Checklist & Process - 00108139 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Hodges, Lynda | 2017-07-13 | 0 | 2017-07-13 | N | 00108139
Calendaring : Amendment Checklist & Process - 00108139 | ** Visits : Addition or Removal of Time Points | User | Hodges, Lynda | 2017-07-13 | 0 | 2017-07-13 | N | 00108139
Calendaring : Amendment Checklist & Process - 00108139 | Request Care Designations | User | Hodges, Lynda | 2017-07-13 | 0 | 2017-07-13 | N | 00108139
Calendaring : Initial Calendar Build - 00126707 | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa | 2017-07-13 | 0 | 2017-07-13 | N | 00126707
Calendaring : Amendment Checklist & Process - 00106894 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-07-13 | 14 | 2017-07-27 | N | 00106894
Pre-Award Financial - 282-POP-BUSUI | Internal Budget Finished | User | VanderElzen, Liz | 2017-07-13 | 0 | 2017-06-26 | N | 00133290
CTSU Post-Award - 00125425 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-07-13 | 49 |  | N | 00125425
CTSU Post-Award - 00127537 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-07-13 | 49 |  | N | 00127537
Pre-Award Financial - 81-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-07-14 | 48 |  | N | 81-HIGGINS
CTSU Pre-Award - 350-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-07-14 | 0 | 2017-07-14 | N | 00133054
CTSU Pre-Award - 351-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-07-14 | 0 | 2017-07-14 | N | 00134870
Pre-Award Financial - 242-AS-SANIE | Final Budget | Role | CTSU Finance | 2017-07-14 | 48 |  | N | 242-AS-SANIE
Pre-Award Financial - 96-BESIRLI | Final Budget | Role | CTSU Finance | 2017-07-14 | 0 | 2017-05-08 | N | 00129820
Calendaring : Initial Calendar Build - 112-FLAHERTY | Assign to Analyst | User | Greene, Paula | 2017-07-14 | 0 | 2017-07-14 | N | 112-FLAHERTY
Pre-Award Financial - 147-SCHIOPU | PAF routed | User | Henry, Robin | 2017-07-14 | 48 |  | N | 00131329
Pre-Award Financial - 170-SCHIOPU | PAF routed | User | Henry, Robin | 2017-07-14 | 48 |  | N | 00134035
Calendaring : Amendment Checklist & Process - 00109407 | Assign to Analyst | User | Hess, Aaron | 2017-07-14 | 48 |  | N | 00109407
Calendaring : Initial Calendar Build - 221-MODY | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hodges, Lynda | 2017-07-14 | 3 | 2017-07-17 | N | 00129412
Calendaring : Amendment Checklist & Process - 00107954 | Acknowledge | User | Oliver, Amy | 2017-07-14 | 48 |  | N | 00107954
Pre-Award Financial - 00130793 | PAN Released | User | Oliver, Amy | 2017-07-14 | 48 |  | N | 00130793
Pre-Award Financial - 87-ORAL | PAN Released | User | Oliver, Amy | 2017-07-14 | 48 |  | N | 00130757
Calendaring : Amendment Checklist & Process - 00106894 | ** Footnote Edits | User | Radenbaugh, Pauline | 2017-07-14 | 13 | 2017-07-27 | N | 00106894
Calendaring : Amendment Checklist & Process - 00106894 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Radenbaugh, Pauline | 2017-07-14 | 13 | 2017-07-27 | N | 00106894
Calendaring : Amendment Checklist & Process - 00106894 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Radenbaugh, Pauline | 2017-07-14 | 13 | 2017-07-27 | N | 00106894
CTSU Post-Award - 00125566 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-07-14 | 48 |  | N | 00125566
Calendar Build - 8-AARONSON | MBECT SVS ( MBECT Single-Visit-Shell ) : built & coded | User | Zahs, Brian | 2017-07-14 | 0 | 2017-07-14 | N | 00132110
Calendaring : Initial Calendar Build - 00129709 | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-07-14 | 3 | 2017-07-17 | N | 00129709
CTSU Pre-Award - 336-KHANNA | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-15 | 0 | 2017-07-13 | N | 00133684
Pre-Award Financial - 112-FLAHERTY | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-15 | 12 | 2017-07-27 | N | 112-FLAHERTY
Pre-Award Financial - 242-AS-SANIE | Care Designations completed | Role | CTSU Finance | 2017-07-15 | 47 |  | N | 242-AS-SANIE
Pre-Award Financial - 255-LOK | Billing Calendar Received | Role | CTSU Finance | 2017-07-15 | 47 |  | N | 255-LOK
Pre-Award Financial - 261-LUGOGO | Internal Budget Finished | Role | CTSU Finance | 2017-07-15 | 47 |  | N | 261-LUGOGO
CTSU Pre-Award - 336-KHANNA | Created CTRF & "Notify ORSP" | User | Henry, Robin | 2017-07-15 | 3 | 2017-07-18 | N | 00133684
CTSU Pre-Award - 336-KHANNA | Request Research Pharmacy Budget | User | Henry, Robin | 2017-07-15 | 25 | 2017-08-09 | N | 00133684
Calendaring : Amendment Checklist & Process - 00109407 | ** Footnote Edits | User | Hess, Aaron | 2017-07-15 | 47 |  | N | 00109407
Calendaring : Amendment Checklist & Process - 00109407 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Hess, Aaron | 2017-07-15 | 47 |  | N | 00109407
Calendaring : Amendment Checklist & Process - 00109407 | ** Visit Tolerance Edits | User | Hess, Aaron | 2017-07-15 | 47 |  | N | 00109407
Calendaring : Amendment Checklist & Process - 00109407 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Hess, Aaron | 2017-07-15 | 47 |  | N | 00109407
Calendaring : Amendment Checklist & Process - 00123635 | Complete Calendar and Document Approval | User | Przykucki, Anne | 2017-07-15 | 0 | 2017-07-14 | N | 00123635
Calendaring : Initial Calendar Build - 00131311 | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-07-15 | 2 | 2017-07-17 | N | 00131311
Calendaring : Initial Calendar Build - 00131311 | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline | 2017-07-15 | 2 | 2017-07-17 | N | 00131311
Calendaring : Initial Calendar Build - 00131311 | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-07-15 | 2 | 2017-07-17 | N | 00131311
Pre-Award Financial - 112-FLAHERTY | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-07-15 | 47 |  | N | 112-FLAHERTY
Pre-Award Financial - 112-FLAHERTY | Request Research Pharmacy Budget | User | VanderElzen, Liz | 2017-07-15 | 4 | 2017-07-19 | N | 112-FLAHERTY
Pre-Award Financial - 70-LUGOGO | Final Budget | User | VanderElzen, Liz | 2017-07-15 | 47 |  | N | 70-LUGOGO
CTSU Pre-Award v2 - 82-BOLLING | PI Signoff in OnCore | Role | CTSU Administrator | 2017-07-16 | 46 |  | N | 82-BOLLING
Pre-Award Financial - 81-HIGGINS | Open to Accrual | Role | CTSU Administrator | 2017-07-16 | 46 |  | N | 81-HIGGINS
CTSU Pre-Award - 354-PAGANI | Intake Form Completed | Role | CTSU Finance | 2017-07-16 | 0 | 2017-07-16 | N | 354-PAGANI
Pre-Award Financial - 242-AS-SANIE | PAF routed | Role | CTSU Finance | 2017-07-16 | 46 |  | N | 242-AS-SANIE
Pre-Award Financial - 246-AS-SANIE | Planning Meeting Completed | Role | CTSU Finance | 2017-07-16 | 46 |  | N | 246-AS-SANIE
Pre-Award Financial - 261-LUGOGO | Billing Calendar Received | Role | CTSU Finance | 2017-07-16 | 46 |  | N | 261-LUGOGO
Pre-Award Financial - 190-SCHIOPU | Care Designations completed | User | Henry, Robin | 2017-07-16 | 9 | 2017-07-25 | N | 00134443
Calendaring : Amendment Checklist & Process - 00109407 | ** Items/Services : Addition or Removal of Procedures / Events | User | Hess, Aaron | 2017-07-16 | 46 |  | N | 00109407
Calendaring : Initial Calendar Build - 336-KHANNA | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-07-16 | 46 |  | N | 00133684
Calendaring : Initial Calendar Build - 336-KHANNA | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-07-16 | 2 | 2017-07-18 | N | 00133684
Calendaring : Initial Calendar Build - 336-KHANNA | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-07-16 | 2 | 2017-07-18 | N | 00133684
Calendaring : Amendment Checklist & Process - 00106894 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Radenbaugh, Pauline | 2017-07-16 | 11 | 2017-07-27 | N | 00106894
Pre-Award Financial - 282-POP-BUSUI | PI approved Budget | User | VanderElzen, Liz | 2017-07-16 | 0 | 2017-06-29 | N | 00133290
Pre-Award Financial - 49-MARTINEZ | Final Budget | User | VanderElzen, Liz | 2017-07-16 | 46 |  | N | 00132020
Calendaring : Initial Calendar Build - 00129709 | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-07-16 | 1 | 2017-07-17 | N | 00129709
Calendaring : Initial Calendar Build - 00129709 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-07-16 | 1 | 2017-07-17 | N | 00129709
Calendaring : Initial Calendar Build - 112-FLAHERTY | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-07-16 | 4 | 2017-07-20 | N | 112-FLAHERTY
Calendaring : Initial Calendar Build - 357-GRANT 2 | Feasibility Approval Notice Received | Role | CRAO | 2017-07-17 | 0 | 2017-07-17 | N | 00119336
CTSU Pre-Award - 313-CONJEEVARAM | Feasibility w/Documents received | Role | CTSU Administrator | 2017-07-17 | 45 |  | N | 313-CONJEEVARAM
CTSU Pre-Award - 313-CONJEEVARAM | Sponsor Reach out | Role | CTSU Coordinator | 2017-07-17 | 38 | 2017-08-24 | N | 313-CONJEEVARAM
CTSU Pre-Award - 313-CONJEEVARAM | UFA Completed | Role | CTSU Coordinator | 2017-07-17 | 38 | 2017-08-24 | N | 313-CONJEEVARAM
Pre-Award Financial - 278-CONJEEVARAM | IRB Application Submitted | Role | CTSU Coordinator | 2017-07-17 | 45 |  | N | 00133341
Calendaring : Amendment Checklist & Process - 00123635 | Acknowledge | Role | CTSU Finance | 2017-07-17 | 0 | 2017-07-17 | N | 00123635
Calendaring : Amendment Checklist & Process - HUM00129276 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-07-17 | 0 | 2017-07-17 | N | 00129276
Calendaring : Initial Calendar Build - 00124202 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-07-17 | 45 |  | N | 00124202
Pre-Award Financial - 246-AS-SANIE | Care Designations completed | Role | CTSU Finance | 2017-07-17 | 45 |  | N | 246-AS-SANIE
Pre-Award Financial - 263-DELMONTE | Billing Calendar Received | Role | CTSU Finance | 2017-07-17 | 45 |  | N | 263-DELMONTE
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Henry, Robin | 2017-07-17 | 35 | 2017-08-21 | N | 00133341
Pre-Award Financial - 278-CONJEEVARAM | Planning Meeting Completed | User | Henry, Robin | 2017-07-17 | 10 | 2017-07-27 | N | 00133341
Calendaring : Amendment Checklist & Process - 00109407 | ** Other | User | Hess, Aaron | 2017-07-17 | 45 |  | N | 00109407
Calendaring : Amendment Checklist & Process - 00109407 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Hess, Aaron | 2017-07-17 | 45 |  | N | 00109407
Calendaring : Amendment Checklist & Process - 00109407 | ** Visits : Addition or Removal of Time Points | User | Hess, Aaron | 2017-07-17 | 45 |  | N | 00109407
Calendaring : Amendment Checklist & Process - 00109407 | Request Care Designations | User | Hess, Aaron | 2017-07-17 | 45 |  | N | 00109407
Calendaring : Amendment Checklist & Process - 00109407 | Update RSH Source in MBECT | User | Hess, Aaron | 2017-07-17 | 45 |  | N | 00109407
Calendaring : Specification Update Request(s) - 00126707 | Make Update(s) | User | Munasinghe, Sadeepa | 2017-07-17 | 0 | 2017-07-11 | N | 00126707
Calendaring : Initial Calendar Build - 00131311 | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-07-17 | 0 | 2017-07-17 | N | 00131311
Calendaring : Initial Calendar Build - 00131311 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-07-17 | 0 | 2017-07-17 | N | 00131311
Pre-Award Financial - 70-LUGOGO | PAF routed | User | VanderElzen, Liz | 2017-07-17 | 45 |  | N | 70-LUGOGO
Calendaring : Initial Calendar Build - 112-FLAHERTY | Complete MCA / QCT | User | van Dijk, Tim | 2017-07-17 | 3 | 2017-07-20 | N | 112-FLAHERTY
Calendaring : Initial Calendar Build - 112-FLAHERTY | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-07-17 | 3 | 2017-07-20 | N | 112-FLAHERTY
Calendaring : Initial Calendar Build - 00131904 | Feasibility Approval Notice Received | Role | CRAO | 2017-07-18 | 0 | 2017-07-18 | N | 00131904
CTSU Pre-Award v2 - 82-BOLLING | Open to Accrual | Role | CTSU Administrator | 2017-07-18 | 44 |  | N | 82-BOLLING
CTSU Pre-Award - 359-SMITH | Intake Form Completed | Role | CTSU Coordinator | 2017-07-18 | 0 | 2017-07-18 | N | 359-SMITH
Pre-Award Financial - 56-RAO | IRB Application Submitted | Role | CTSU Coordinator | 2017-07-18 | 44 |  | N | 00133286
CTSU Pre-Award v2 - 00111295 | Final Budget | Role | CTSU Finance | 2017-07-18 | 44 |  | N | 00111295
Calendaring : Amendment Checklist & Process - 162-PIPE | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-07-18 | 0 | 2017-07-18 | N | 00131320
Pre-Award Financial - 242-AS-SANIE | PAN Released | Role | CTSU Finance | 2017-07-18 | 44 |  | N | 242-AS-SANIE
Pre-Award Financial - 261-LUGOGO | PI approved Budget | Role | CTSU Finance | 2017-07-18 | 44 |  | N | 261-LUGOGO
Pre-Award Financial - 91-ELSE | OnCore Budget Build | Role | CTSU Finance | 2017-07-18 | 44 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | OnCore Budget Build | Role | CTSU Finance | 2017-07-18 | 44 |  | N | 92-AUCHUS
Calendaring : Amendment Checklist & Process - 00108139 | Provide PI-Determined Care Designations ( +/- Feedback ) | User | Frisch, Karen | 2017-07-18 | 0 | 2017-07-14 | N | 00108139
Pre-Award Financial - 211-HIGGINS | Final Budget | User | Henry, Robin | 2017-07-18 | 0 | 2017-07-12 | N | 00128325
Calendaring : Initial Calendar Build - 223-MODY | CRAO Approval Issue & Documented | User | Hodges, Lynda | 2017-07-18 | 0 | 2017-07-18 | N | 00131377
Calendaring : Initial Calendar Build - 336-KHANNA | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-07-18 | 0 | 2017-07-18 | N | 00133684
Calendaring : Initial Calendar Build - 336-KHANNA | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-07-18 | 2 | 2017-07-20 | N | 00133684
CTSU Pre-Award - 314-PARK | Sponsor Reach out | User | Munsey, Barbara | 2017-07-18 | 0 | 2017-07-18 | N | 314-PARK
Pre-Award Financial - 282-POP-BUSUI | Budget Negotiations | User | VanderElzen, Liz | 2017-07-18 | 0 | 2017-06-29 | N | 00133290
Pre-Award Financial - 49-MARTINEZ | PAF routed | User | VanderElzen, Liz | 2017-07-18 | 44 |  | N | 00132020
Calendaring : Specification Update Request(s) - 00130575 | ** Request(s) to Add Unscheduled Procedure(s) | User | Yunk, Jason | 2017-07-18 | 0 | 2017-07-18 | N | 00130575
Calendaring : Specification Update Request(s) - 00130575 | ** Structural Edits | User | Yunk, Jason | 2017-07-18 | 0 | 2017-07-18 | N | 00130575
Calendaring : Specification Update Request(s) - 00130575 | Submit Update Request(s) | User | Yunk, Jason | 2017-07-18 | 0 | 2017-07-18 | N | 00130575
Calendaring : Initial Calendar Build - 112-FLAHERTY | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-07-18 | 2 | 2017-07-20 | N | 112-FLAHERTY
Calendaring : Initial Calendar Build - 112-FLAHERTY | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-07-18 | 2 | 2017-07-20 | N | 112-FLAHERTY
CTSU Pre-Award - 341-STOFFEL | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-19 | 0 | 2017-07-19 | N | 00134997
CTSU Pre-Award v2 - 415-ROMANO | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-19 | 43 |  | N | 415-ROMANO
Pre-Award Financial - 298-SCHIOPU | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-19 | 43 |  | N | 298-SCHIOPU
CTSU Pre-Award v2 - 361-HASAN | Intake Form Completed | Role | CTSU Coordinator | 2017-07-19 | 0 | 2017-07-19 | N | 361-HASAN
Calendaring : Initial Calendar Build - 190-SCHIOPU | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-07-19 | 6 | 2017-07-25 | N | 00134443
Calendaring : Specification Update Request(s) - 00126707 | Acknowledge | Role | CTSU Finance | 2017-07-19 | 0 | 2017-07-11 | N | 00126707
Pre-Award Financial - 255-LOK | Planning Meeting Completed | Role | CTSU Finance | 2017-07-19 | 43 |  | N | 255-LOK
Pre-Award Financial - 91-ELSE | Calendar Released | Role | CTSU Finance | 2017-07-19 | 43 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | Calendar Released | Role | CTSU Finance | 2017-07-19 | 43 |  | N | 92-AUCHUS
Core Sponsor Documents for Study Feasibility & Start Up - General - 314-PARK | Informed Consent | User | Chen, Tina | 2017-07-19 | 43 |  | N | 314-PARK
Core Sponsor Documents for Study Feasibility & Start Up - General - 314-PARK | Initial contact with sponsor | User | Chen, Tina | 2017-07-19 | 43 |  | N | 314-PARK
Core Sponsor Documents for Study Feasibility & Start Up - General - 314-PARK | Investigational Drug Brochure / Investigator's Brochure | User | Chen, Tina | 2017-07-19 | 43 |  | N | 314-PARK
Core Sponsor Documents for Study Feasibility & Start Up - General - 314-PARK | Protocol (and any approved Amendments) | User | Chen, Tina | 2017-07-19 | 43 |  | N | 314-PARK
Calendaring : Initial Calendar Build - 341-STOFFEL | Feasibility Approval Notice Received | User | Greene, Paula | 2017-07-19 | 1 | 2017-07-20 | N | 00134997
Calendaring : Initial Calendar Build - 00124202 | Make Updates | User | Hess, Aaron | 2017-07-19 | 43 |  | N | 00124202
Calendaring : Initial Calendar Build - 357-GRANT 2 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-07-19 | 0 | 2017-07-18 | N | 00119336
Calendaring : Initial Calendar Build - 357-GRANT 2 | Assign to Analyst | User | Munasinghe, Sadeepa | 2017-07-19 | 0 | 2017-07-17 | N | 00119336
Core Sponsor Documents for Study Feasibility & Start Up - General - 314-PARK | Sponsor Budget | User | Munsey, Barbara | 2017-07-19 | 43 |  | N | 314-PARK
Core Sponsor Documents for Study Feasibility & Start Up - General - 314-PARK | Sponsor Contract | User | Munsey, Barbara | 2017-07-19 | 43 |  | N | 314-PARK
Core Sponsor Documents for Study Feasibility & Start Up - General - 314-PARK | U-M Planning Questionnaire | User | Munsey, Barbara | 2017-07-19 | 43 |  | N | 314-PARK
Pre-Award Financial - 71-RICE | OnCore Budget Build | User | Oliver, Amy | 2017-07-19 | 43 |  | N | 00134857
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-07-19 | 34 | 2017-08-22 | N | 00133341
Calendaring : Initial Calendar Build - 00124202 | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-07-19 | 34 | 2017-08-22 | N | 00124202
Calendaring : Amendment Checklist & Process - HUM00129276 | Assign to Analyst | User | van Dijk, Tim | 2017-07-19 | 0 | 2017-07-18 | N | 00129276
Calendaring : Initial Calendar Build - 00125836 | CRAO Approval Issue & Documented | Role | CRAO | 2017-07-20 | 0 | 2017-07-20 | N | 00125836
Pre-Award Financial - 23-GUPTA | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-20 | 0 | 2017-07-20 | N | 00134236
CTSU Pre-Award v2 - 00111295 | PAF routed | Role | CTSU Finance | 2017-07-20 | 42 |  | N | 00111295
Pre-Award Financial - 242-AS-SANIE | OnCore Budget Build | Role | CTSU Finance | 2017-07-20 | 42 |  | N | 242-AS-SANIE
Pre-Award Financial - 261-LUGOGO | Budget Negotiations | Role | CTSU Finance | 2017-07-20 | 42 |  | N | 261-LUGOGO
Pre-Award Financial - 261-LUGOGO | Planning Meeting Completed | Role | CTSU Finance | 2017-07-20 | 42 |  | N | 261-LUGOGO
Calendaring : Initial Calendar Build - 341-STOFFEL | Assign to Analyst | User | Greene, Paula | 2017-07-20 | 0 | 2017-07-20 | N | 00134997
Calendaring : Initial Calendar Build - 341-STOFFEL | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-07-20 | 0 | 2017-07-20 | N | 00134997
Pre-Award Financial - 190-SCHIOPU | Internal Budget Finished | User | Henry, Robin | 2017-07-20 | 14 | 2017-08-03 | N | 00134443
Pre-Award Financial - 205-KHANNA | Final Budget | User | Henry, Robin | 2017-07-20 | 21 | 2017-08-10 | N | 00132200
Pre-Award Financial - 278-CONJEEVARAM | Care Designations completed | User | Henry, Robin | 2017-07-20 | 19 | 2017-08-08 | N | 00133341
Calendaring : Initial Calendar Build - 00131904 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron | 2017-07-20 | 0 | 2017-07-18 | N | 00131904
Calendaring : Amendment Checklist & Process - 00108139 | Complete Calendar and Document Approval | User | Hodges, Lynda | 2017-07-20 | 0 | 2017-07-17 | N | 00108139
Calendaring : Initial Calendar Build - 221-MODY | Complete Calendar ( ie. Ready for Financials ) | User | Hodges, Lynda | 2017-07-20 | 0 | 2017-07-20 | N | 00129412
Calendaring : Initial Calendar Build - 221-MODY | Make Updates | User | Hodges, Lynda | 2017-07-20 | 0 | 2017-07-20 | N | 00129412
Calendaring : Initial Calendar Build - 00131904 | Assign to Analyst | User | Munasinghe, Sadeepa | 2017-07-20 | 0 | 2017-07-18 | N | 00131904
Pre-Award Financial - 239-KORLEY | Feasibility w/Documents received | User | Munsey, Barbara | 2017-07-20 | 0 | 2017-07-20 | N | 00129045
Pre-Award Financial - 180-HOFF | Final Budget | User | Oliver, Amy | 2017-07-20 | 42 |  | N | 00129450
Pre-Award Financial - 71-RICE | Calendar Released | User | Oliver, Amy | 2017-07-20 | 42 |  | N | 00134857
Calendaring : Specification Update Request(s) - 00130575 | Assign to Analyst | User | Radenbaugh, Pauline | 2017-07-20 | 5 | 2017-07-25 | N | 00130575
Pre-Award Financial - 00129652 | PAN Released | User | VanderElzen, Liz | 2017-07-20 | 42 |  | N | 00129652
Calendaring : Initial Calendar Build - 58-BONIFANT | CRAO Approval Issue & Documented | User | Zahs, Brian | 2017-07-20 | 42 |  | N | 00132916
Calendaring : Amendment Checklist & Process - 162-PIPE | Assign to Analyst | User | van Dijk, Tim | 2017-07-20 | 5 | 2017-07-25 | N | 00131320
Calendaring : Amendment Checklist & Process - HUM00129276 | ** Footnote Edits | User | van Dijk, Tim | 2017-07-20 | 6 | 2017-07-26 | N | 00129276
Calendaring : Amendment Checklist & Process - HUM00129276 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | van Dijk, Tim | 2017-07-20 | 6 | 2017-07-26 | N | 00129276
Calendaring : Amendment Checklist & Process - HUM00129276 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | van Dijk, Tim | 2017-07-20 | 0 | 2017-07-20 | N | 00129276
Calendaring : Initial Calendar Build - 179-LUGOGO | Feasibility Approval Notice Received | Role | CRAO | 2017-07-21 | 0 | 2017-07-21 | N | 179-LUGOGO
Calendaring : Initial Calendar Build - 23-GUPTA | Feasibility Approval Notice Received | Role | CRAO | 2017-07-21 | 0 | 2017-07-21 | N | 00134236
Calendaring : Initial Calendar Build - 239-KORLEY | Feasibility Approval Notice Received | Role | CRAO | 2017-07-21 | 0 | 2017-07-21 | N | 00129045
Calendaring : Initial Calendar Build - 350-HIGGINS | Feasibility Approval Notice Received | Role | CRAO | 2017-07-21 | 3 | 2017-07-24 | N | 00133054
Calendaring : Initial Calendar Build - 351-HIGGINS | Feasibility Approval Notice Received | Role | CRAO | 2017-07-21 | 3 | 2017-07-24 | N | 00134870
CTSU Pre-Award - 350-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-21 | 0 | 2017-07-21 | N | 00133054
CTSU Pre-Award - 351-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-21 | 0 | 2017-07-21 | N | 00134870
CTSU Pre-Award v2 - 325-AUCHUS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-07-21 | 19 | 2017-08-09 | N | 00131840
Pre-Award Financial - 179-LUGOGO | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-21 | 0 | 2017-07-21 | N | 179-LUGOGO
CTSU Pre-Award - 341-STOFFEL | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-21 | 0 | 2017-07-20 | N | 00134997
CTSU Pre-Award v2 - 361-HASAN | Sponsor Reach out | Role | CTSU Coordinator | 2017-07-21 | 0 | 2017-07-21 | N | 361-HASAN
CTSU Pre-Award v2 - 415-ROMANO | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-21 | 41 |  | N | 415-ROMANO
Pre-Award Financial - 298-SCHIOPU | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-21 | 41 |  | N | 298-SCHIOPU
CTSU Pre-Award - 341-STOFFEL | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-07-21 | 0 | 2017-07-14 | N | 00134997
CTSU Pre-Award - 341-STOFFEL | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-07-21 | 10 | 2017-07-31 | N | 00134997
CTSU Pre-Award v2 - 00111295 | OnCore Budget Build | Role | CTSU Finance | 2017-07-21 | 41 |  | N | 00111295
CTSU Pre-Award v2 - 415-ROMANO | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-07-21 | 41 |  | N | 415-ROMANO
Calendaring : Initial Calendar Build - 00124202 | Acknowledge | Role | CTSU Finance | 2017-07-21 | 41 |  | N | 00124202
Pre-Award Financial - 239-KORLEY | Feasibility approved/CRAO Notified | Role | CTSU Finance | 2017-07-21 | 0 | 2017-07-21 | N | 00129045
Pre-Award Financial - 242-AS-SANIE | Calendar Released | Role | CTSU Finance | 2017-07-21 | 41 |  | N | 242-AS-SANIE
Pre-Award Financial - 298-SCHIOPU | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-07-21 | 41 |  | N | 298-SCHIOPU
Pre-Award Financial - 298-SCHIOPU | Request MCRU Budget | Role | CTSU Finance | 2017-07-21 | 41 |  | N | 298-SCHIOPU
Pre-Award Financial - 298-SCHIOPU | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-07-21 | 41 |  | N | 298-SCHIOPU
Calendaring : Initial Calendar Build - 179-LUGOGO | Assign to Analyst | User | Greene, Paula | 2017-07-21 | 0 | 2017-07-21 | N | 179-LUGOGO
Calendaring : Initial Calendar Build - 179-LUGOGO | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-07-21 | 0 | 2017-07-21 | N | 179-LUGOGO
Calendaring : Initial Calendar Build - 23-GUPTA | Assign to Analyst | User | Greene, Paula | 2017-07-21 | 0 | 2017-07-21 | N | 00134236
Calendaring : Initial Calendar Build - 23-GUPTA | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-07-21 | 0 | 2017-07-21 | N | 00134236
Calendaring : Initial Calendar Build - 239-KORLEY | Assign to Analyst | User | Greene, Paula | 2017-07-21 | 0 | 2017-07-21 | N | 00129045
Calendaring : Initial Calendar Build - 239-KORLEY | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-07-21 | 0 | 2017-07-21 | N | 00129045
Calendaring : Initial Calendar Build - 350-HIGGINS | Assign to Analyst | User | Greene, Paula | 2017-07-21 | 3 | 2017-07-24 | N | 00133054
Calendaring : Initial Calendar Build - 351-HIGGINS | Assign to Analyst | User | Greene, Paula | 2017-07-21 | 3 | 2017-07-24 | N | 00134870
Calendaring : Initial Calendar Build - 351-HIGGINS | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-07-21 | 3 | 2017-07-24 | N | 00134870
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Acknowledge | User | Henry, Robin | 2017-07-21 | 35 | 2017-08-25 | N | 00133341
Calendaring : Initial Calendar Build - 221-MODY | CRAO Approval Issue & Documented | User | Hodges, Lynda | 2017-07-21 | 0 | 2017-07-21 | N | 00129412
CTSU Pre-Award - 363-PARK | Intake Form Completed | User | Munsey, Barbara | 2017-07-21 | 0 | 2017-07-21 | N | 363-PARK
CTSU Post-Award - 00125794 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-07-21 | 41 |  | N | 00125794
Calendar Build - 8-AARONSON | Specification has been Imported / Michiganized and is ready for Finance / Study team review, feedback and determination of care designations | User | Zahs, Brian | 2017-07-21 | 0 | 2017-07-21 | N | 00132110
Calendaring : Amendment Checklist & Process - 162-PIPE | ** Footnote Edits | User | van Dijk, Tim | 2017-07-21 | 10 | 2017-07-31 | N | 00131320
Calendaring : Amendment Checklist & Process - 162-PIPE | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | van Dijk, Tim | 2017-07-21 | 10 | 2017-07-31 | N | 00131320
Calendaring : Amendment Checklist & Process - 162-PIPE | ** Visit Tolerance Edits | User | van Dijk, Tim | 2017-07-21 | 10 | 2017-07-31 | N | 00131320
Calendaring : Amendment Checklist & Process - 162-PIPE | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | van Dijk, Tim | 2017-07-21 | 6 | 2017-07-27 | N | 00131320
Calendaring : Amendment Checklist & Process - HUM00129276 | ** Items/Services : Addition or Removal of Procedures / Events | User | van Dijk, Tim | 2017-07-21 | 5 | 2017-07-26 | N | 00129276
Calendaring : Initial Calendar Build - 190-SCHIOPU | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-07-21 | 25 | 2017-08-15 | N | 00134443
Calendaring : Initial Calendar Build - 190-SCHIOPU | Make Updates | User | van Dijk, Tim | 2017-07-21 | 10 | 2017-07-31 | N | 00134443
Pre-Award Financial - 91-ELSE | PI Signoff in OnCore | Role | CTSU Administrator | 2017-07-22 | 40 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-07-22 | 40 |  | N | 92-AUCHUS
Pre-Award Financial - 23-GUPTA | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-22 | 0 | 2017-07-13 | N | 00134236
CTSU Pre-Award v2 - 00111295 | Calendar Released | Role | CTSU Finance | 2017-07-22 | 40 |  | N | 00111295
Calendaring : Initial Calendar Build - 221-MODY | Acknowledge | Role | CTSU Finance | 2017-07-22 | 0 | 2017-07-20 | N | 00129412
Pre-Award Financial - 188-RUBENSTEIN | Final Budget | Role | CTSU Finance | 2017-07-22 | 40 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 255-LOK | Care Designations completed | Role | CTSU Finance | 2017-07-22 | 40 |  | N | 255-LOK
Calendaring : Amendment Checklist & Process - 00108139 | Acknowledge | User | Dahlgren, Molly | 2017-07-22 | 0 | 2017-07-18 | N | 00108139
Calendaring : Amendment Checklist & Process - 00109407 | Provide PI-Determined Care Designations ( +/- Feedback ) | User | Deweese, Braden | 2017-07-22 | 40 |  | N | 00109407
Pre-Award Financial - 205-KHANNA | PAF routed | User | Henry, Robin | 2017-07-22 | 26 | 2017-08-17 | N | 00132200
Pre-Award Financial - 23-GUPTA | Created CTRF & "Notify ORSP" | User | Henry, Robin | 2017-07-22 | 11 | 2017-08-02 | N | 00134236
Pre-Award Financial - 23-GUPTA | Request Research Pharmacy Budget | User | Henry, Robin | 2017-07-22 | 9 | 2017-07-31 | N | 00134236
Pre-Award Financial - 56-RAO | Final Budget | User | Henry, Robin | 2017-07-22 | 40 |  | N | 00133286
Calendaring : Initial Calendar Build - 357-GRANT 2 | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-07-22 | 0 | 2017-07-21 | N | 00119336
Calendaring : Initial Calendar Build - 357-GRANT 2 | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-07-22 | 0 | 2017-07-22 | N | 00119336
Pre-Award Financial - 180-HOFF | PAF routed | User | Oliver, Amy | 2017-07-22 | 40 |  | N | 00129450
Pre-Award Financial - 46-HIGGINS | Final Budget | User | VanderElzen, Liz | 2017-07-22 | 40 |  | N | 46-HIGGINS
Calendaring : Amendment Checklist & Process - 162-PIPE | ** Items/Services : Addition or Removal of Procedures / Events | User | van Dijk, Tim | 2017-07-22 | 9 | 2017-07-31 | N | 00131320
Calendaring : Amendment Checklist & Process - HUM00129276 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | van Dijk, Tim | 2017-07-22 | 4 | 2017-07-26 | N | 00129276
Calendaring : Amendment Checklist & Process - HUM00129276 | ** Visits : Addition or Removal of Time Points | User | van Dijk, Tim | 2017-07-22 | 4 | 2017-07-26 | N | 00129276
Calendaring : Amendment Checklist & Process - HUM00129276 | Request Care Designations | User | van Dijk, Tim | 2017-07-22 | 4 | 2017-07-26 | N | 00129276
Calendaring : Amendment Checklist & Process - HUM00129276 | Update RSH Source in MBECT | User | van Dijk, Tim | 2017-07-22 | 4 | 2017-07-26 | N | 00129276
Calendaring : Initial Calendar Build - 00129709 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Boyd, Collin | 2017-07-23 | 9 | 2017-08-01 | N | 00129709
Pre-Award Financial - 71-RICE | PI Signoff in OnCore | Role | CTSU Administrator | 2017-07-23 | 39 |  | N | 00134857
CTSU Pre-Award - 350-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-23 | 4 | 2017-07-27 | N | 00133054
CTSU Pre-Award - 351-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-23 | 4 | 2017-07-27 | N | 00134870
Pre-Award Financial - 179-LUGOGO | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-23 | 0 | 2017-07-21 | N | 179-LUGOGO
Pre-Award Financial - 263-DELMONTE | Planning Meeting Scheduled | Role | CTSU Coordinator | 2017-07-23 | 39 |  | N | 263-DELMONTE
CTSU Pre-Award - 350-HIGGINS | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-07-23 | 4 | 2017-07-27 | N | 00133054
CTSU Pre-Award - 350-HIGGINS | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-07-23 | 16 | 2017-08-08 | N | 00133054
Pre-Award Financial - 246-AS-SANIE | Internal Budget Finished | Role | CTSU Finance | 2017-07-23 | 39 |  | N | 246-AS-SANIE
Pre-Award Financial - 261-LUGOGO | Care Designations completed | Role | CTSU Finance | 2017-07-23 | 39 |  | N | 261-LUGOGO
CTSU Pre-Award - 336-KHANNA | Billing Calendar Received | User | Henry, Robin | 2017-07-23 | 0 | 2017-07-20 | N | 00133684
Calendaring : Initial Calendar Build - 190-SCHIOPU | Acknowledge | User | Henry, Robin | 2017-07-23 | 24 | 2017-08-16 | N | 00134443
Pre-Award Financial - 190-SCHIOPU | PI approved Budget | User | Henry, Robin | 2017-07-23 | 16 | 2017-08-08 | N | 00134443
Calendaring : Initial Calendar Build - 00131904 | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-07-23 | 26 | 2017-08-18 | N | 00131904
Calendaring : Initial Calendar Build - 00131904 | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-07-23 | 3 | 2017-07-26 | N | 00131904
Calendaring : Initial Calendar Build - 00131904 | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-07-23 | 7 | 2017-07-30 | N | 00131904
Calendaring : Amendment Checklist & Process - 00106894 | Complete Calendar and Document Approval | User | Radenbaugh, Pauline | 2017-07-23 | 4 | 2017-07-27 | N | 00106894
CTSU Pre-Award - 351-HIGGINS | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-07-23 | 30 | 2017-08-22 | N | 00134870
CTSU Pre-Award - 351-HIGGINS | Request Research Pharmacy Budget | User | VanderElzen, Liz | 2017-07-23 | 30 | 2017-08-22 | N | 00134870
Pre-Award Financial - 112-FLAHERTY | Billing Calendar Received | User | VanderElzen, Liz | 2017-07-23 | 0 | 2017-07-20 | N | 112-FLAHERTY
Pre-Award Financial - 179-LUGOGO | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-07-23 | 1 | 2017-07-24 | N | 179-LUGOGO
Pre-Award Financial - 179-LUGOGO | Request Research Pharmacy Budget | User | VanderElzen, Liz | 2017-07-23 | 1 | 2017-07-24 | N | 179-LUGOGO
Calendaring : Amendment Checklist & Process - 162-PIPE | ** Other | User | van Dijk, Tim | 2017-07-23 | 8 | 2017-07-31 | N | 00131320
Calendaring : Amendment Checklist & Process - 162-PIPE | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | van Dijk, Tim | 2017-07-23 | 8 | 2017-07-31 | N | 00131320
Calendaring : Amendment Checklist & Process - 162-PIPE | ** Visits : Addition or Removal of Time Points | User | van Dijk, Tim | 2017-07-23 | 8 | 2017-07-31 | N | 00131320
Calendaring : Amendment Checklist & Process - 162-PIPE | Request Care Designations | User | van Dijk, Tim | 2017-07-23 | 12 | 2017-08-04 | N | 00131320
Calendaring : Amendment Checklist & Process - 162-PIPE | Update RSH Source in MBECT | User | van Dijk, Tim | 2017-07-23 | 12 | 2017-08-04 | N | 00131320
Calendaring : Initial Calendar Build - 341-STOFFEL | Complete MCA / QCT | User | van Dijk, Tim | 2017-07-23 | 3 | 2017-07-26 | N | 00134997
Calendaring : Initial Calendar Build - 341-STOFFEL | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-07-23 | 3 | 2017-07-26 | N | 00134997
Calendaring : Initial Calendar Build - 341-STOFFEL | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-07-23 | 15 | 2017-08-07 | N | 00134997
CTSU Pre-Award - 313-CONJEEVARAM | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-24 | 38 |  | N | 313-CONJEEVARAM
CTSU Pre-Award - 326-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-07-24 | 28 | 2017-08-21 | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-07-24 | 28 | 2017-08-21 | N | 327-HIGGINS
CTSU Pre-Award v2 - 364-KHAJA | Feasibility w/Documents received | Role | CTSU Administrator | 2017-07-24 | 38 |  | N | 364-KHAJA
Pre-Award Financial - 242-AS-SANIE | PI Signoff in OnCore | Role | CTSU Administrator | 2017-07-24 | 38 |  | N | 242-AS-SANIE
Pre-Award Financial - 91-ELSE | Open to Accrual | Role | CTSU Administrator | 2017-07-24 | 38 |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | Open to Accrual | Role | CTSU Administrator | 2017-07-24 | 38 |  | N | 92-AUCHUS
CTSU Pre-Award - 336-KHANNA | IRB Application Submitted | Role | CTSU Coordinator | 2017-07-24 | 38 |  | N | 00133684
CTSU Pre-Award v2 - 364-KHAJA | Intake Form Completed | Role | CTSU Coordinator | 2017-07-24 | 0 | 2017-07-24 | N | 364-KHAJA
Calendaring : Initial Calendar Build - 00131311 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-07-24 | 0 | 2017-07-21 | N | 00131311
Pre-Award Financial - 188-RUBENSTEIN | PAF routed | Role | CTSU Finance | 2017-07-24 | 38 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 263-DELMONTE | Care Designations completed | Role | CTSU Finance | 2017-07-24 | 38 |  | N | 263-DELMONTE
Calendaring : Initial Calendar Build - 350-HIGGINS | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-07-24 | 0 | 2017-07-24 | N | 00133054
CTSU Pre-Award - 336-KHANNA | Planning Meeting Completed | User | Henry, Robin | 2017-07-24 | 0 | 2017-07-24 | N | 00133684
Pre-Award Financial - 278-CONJEEVARAM | Internal Budget Finished | User | Henry, Robin | 2017-07-24 | 15 | 2017-08-08 | N | 00133341
Pre-Award Financial - 56-RAO | PAF routed | User | Henry, Robin | 2017-07-24 | 38 |  | N | 00133286
Calendaring : Amendment Checklist & Process - 00109407 | Complete Calendar and Document Approval | User | Hess, Aaron | 2017-07-24 | 38 |  | N | 00109407
Calendaring : Initial Calendar Build - 23-GUPTA | Complete MCA / QCT | User | Hodges, Lynda | 2017-07-24 | 10 | 2017-08-03 | N | 00134236
Calendaring : Initial Calendar Build - 23-GUPTA | Complete SVS & Pricing List ( Built & Coded ) | User | Hodges, Lynda | 2017-07-24 | 1 | 2017-07-25 | N | 00134236
Calendaring : Initial Calendar Build - 351-HIGGINS | Complete MCA / QCT | User | Hodges, Lynda | 2017-07-24 | 1 | 2017-07-25 | N | 00134870
Calendaring : Initial Calendar Build - 351-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) | User | Hodges, Lynda | 2017-07-24 | 1 | 2017-07-25 | N | 00134870
Calendaring : Initial Calendar Build - 350-HIGGINS | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-07-24 | 2 | 2017-07-26 | N | 00133054
Calendaring : Initial Calendar Build - 350-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-07-24 | 7 | 2017-07-31 | N | 00133054
Calendaring : Initial Calendar Build - 357-GRANT 2 | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-07-24 | 7 | 2017-07-31 | N | 00119336
Calendaring : Initial Calendar Build - 357-GRANT 2 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-07-24 | 14 | 2017-08-07 | N | 00119336
Calendaring : Initial Calendar Build - 239-KORLEY | Complete MCA / QCT | User | Radenbaugh, Pauline | 2017-07-24 | 1 | 2017-07-25 | N | 00129045
Calendaring : Initial Calendar Build - 239-KORLEY | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline | 2017-07-24 | 3 | 2017-07-27 | N | 00129045
Pre-Award Financial - 46-HIGGINS | PAF routed | User | VanderElzen, Liz | 2017-07-24 | 38 |  | N | 46-HIGGINS
Calendaring : Initial Calendar Build - 179-LUGOGO | Complete MCA / QCT | User | van Dijk, Tim | 2017-07-24 | 14 | 2017-08-07 | N | 179-LUGOGO
Calendaring : Initial Calendar Build - 179-LUGOGO | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-07-24 | 3 | 2017-07-27 | N | 179-LUGOGO
Calendaring : Initial Calendar Build - 179-LUGOGO | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-07-24 | 11 | 2017-08-04 | N | 179-LUGOGO
CTSU Pre-Award v2 - 00111295 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-07-25 | 37 |  | N | 00111295
Pre-Award Financial - 71-RICE | Open to Accrual | Role | CTSU Administrator | 2017-07-25 | 37 |  | N | 00134857
Pre-Award Financial - FONTANA-1 | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-25 | 0 | 2017-07-25 | N | 00133153
CTSU Pre-Award - 370-LOK | Intake Form Completed | Role | CTSU Coordinator | 2017-07-25 | 0 | 2017-07-25 | N | 370-LOK
CTSU Pre-Award - 371-LOK | Intake Form Completed | Role | CTSU Coordinator | 2017-07-25 | 0 | 2017-07-25 | N | 371-LOK
CTSU Pre-Award v2 - 82-BOLLING | Initiate Post-Award Task List | Role | CTSU Finance | 2017-07-25 | 37 |  | N | 82-BOLLING
CTSU Pre-Award v2 - 82-BOLLING | PAN Released | Role | CTSU Finance | 2017-07-25 | 37 |  | N | 82-BOLLING
Calendaring : Amendment Checklist & Process - 00106894 | Acknowledge | Role | CTSU Finance | 2017-07-25 | 21 | 2017-08-15 | N | 00106894
Calendaring : Initial Calendar Build - 225-ROSENBLUM | Acknowledge | Role | CTSU Finance | 2017-07-25 | 6 | 2017-07-31 | N | 00124224
Calendaring : Initial Calendar Build - 336-KHANNA | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-07-25 | 0 | 2017-07-24 | N | 00133684
Calendaring : Initial Calendar Build - 00133153 | Assign to Analyst | User | Greene, Paula | 2017-07-25 | 0 | 2017-07-25 | N | 00133153
Calendaring : Initial Calendar Build - 00133153 | Feasibility Approval Notice Received | User | Greene, Paula | 2017-07-25 | 0 | 2017-07-25 | N | 00133153
Calendaring : Initial Calendar Build - 00133153 | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-07-25 | 0 | 2017-07-25 | N | 00133153
Calendaring : Initial Calendar Build - 132040 | Assign to Analyst | User | Greene, Paula | 2017-07-25 | 0 | 2017-07-25 | N | 00132040
Calendaring : Initial Calendar Build - 132040 | Feasibility Approval Notice Received | User | Greene, Paula | 2017-07-25 | 0 | 2017-07-25 | N | 00132040
Calendaring : Initial Calendar Build - 132040 | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-07-25 | 0 | 2017-07-25 | N | 00132040
Calendaring : Initial Calendar Build - 192-ALAM | Assign to Analyst | User | Greene, Paula | 2017-07-25 | 0 | 2017-07-25 | N | 192-ALAM
Calendaring : Initial Calendar Build - 192-ALAM | Feasibility Approval Notice Received | User | Greene, Paula | 2017-07-25 | 0 | 2017-07-25 | N | 192-ALAM
Calendaring : Initial Calendar Build - 192-ALAM | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-07-25 | 0 | 2017-07-25 | N | 192-ALAM
Calendaring : Initial Calendar Build - 358-SHELLHAAS | Assign to Analyst | User | Greene, Paula | 2017-07-25 | 0 | 2017-07-25 | N | 00133339
Calendaring : Initial Calendar Build - 358-SHELLHAAS | Feasibility Approval Notice Received | User | Greene, Paula | 2017-07-25 | 0 | 2017-07-25 | N | 00133339
Calendaring : Initial Calendar Build - 358-SHELLHAAS | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-07-25 | 0 | 2017-07-25 | N | 00133339
Calendaring : Initial Calendar Build - CY5022 | Assign to Analyst | User | Greene, Paula | 2017-07-25 | 0 | 2017-07-25 | N | 00132631
Calendaring : Initial Calendar Build - CY5022 | Feasibility Approval Notice Received | User | Greene, Paula | 2017-07-25 | 0 | 2017-07-25 | N | 00132631
Calendaring : Initial Calendar Build - CY5022 | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-07-25 | 0 | 2017-07-25 | N | 00132631
Pre-Award Financial - 190-SCHIOPU | Budget Negotiations | User | Henry, Robin | 2017-07-25 | 15 | 2017-08-09 | N | 00134443
Calendaring : Initial Calendar Build - 23-GUPTA | Nimblify Build is Complete & Ready for Import | User | Hodges, Lynda | 2017-07-25 | 9 | 2017-08-03 | N | 00134236
Calendaring : Initial Calendar Build - 351-HIGGINS | Nimblify Build is Complete & Ready for Import | User | Hodges, Lynda | 2017-07-25 | 1 | 2017-07-26 | N | 00134870
Calendaring : Initial Calendar Build - 00131904 | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-07-25 | 17 | 2017-08-11 | N | 00131904
Calendaring : Initial Calendar Build - 00131904 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-07-25 | 17 | 2017-08-11 | N | 00131904
Calendaring : Specification Update Request(s) - 00130575 | Make Update(s) | User | Radenbaugh, Pauline | 2017-07-25 | 0 | 2017-07-25 | N | 00130575
Calendaring : Specification Update Request(s) - 00130575 | Re-Complete Calendar | User | Radenbaugh, Pauline | 2017-07-25 | 1 | 2017-07-26 | N | 00130575
Calendaring : Initial Calendar Build - 112-FLAHERTY | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-07-25 | 37 |  | N | 112-FLAHERTY
Calendaring : Initial Calendar Build - 00129709 | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-07-25 | 15 | 2017-08-09 | N | 00129709
Calendaring : Initial Calendar Build - 341-STOFFEL | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-07-25 | 13 | 2017-08-07 | N | 00134997
Calendaring : Initial Calendar Build - 341-STOFFEL | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-07-25 | 17 | 2017-08-11 | N | 00134997
CTSU Pre-Award - 332-BELLOLI | Feasibility w/Documents received | Role | CTSU Administrator | 2017-07-26 | 33 | 2017-08-28 | N | 332-BELLOLI
Pre-Award Financial - 242-AS-SANIE | Open to Accrual | Role | CTSU Administrator | 2017-07-26 | 36 |  | N | 242-AS-SANIE
CTSU Pre-Award - 313-CONJEEVARAM | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-26 | 36 |  | N | 313-CONJEEVARAM
CTSU Pre-Award - 331-FLAHERTY | Sponsor Reach out | Role | CTSU Coordinator | 2017-07-26 | 12 | 2017-08-07 | N | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | UFA Completed | Role | CTSU Coordinator | 2017-07-26 | 12 | 2017-08-07 | N | 331-FLAHERTY
CTSU Pre-Award - 332-BELLOLI | Sponsor Reach out | Role | CTSU Coordinator | 2017-07-26 | 0 | 2017-07-20 | N | 332-BELLOLI
CTSU Pre-Award - 332-BELLOLI | UFA Completed | Role | CTSU Coordinator | 2017-07-26 | 0 | 2017-07-19 | N | 332-BELLOLI
CTSU Pre-Award - 313-CONJEEVARAM | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-07-26 | 36 |  | N | 313-CONJEEVARAM
CTSU Pre-Award - 313-CONJEEVARAM | Request MCRU Budget | Role | CTSU Finance | 2017-07-26 | 36 |  | N | 313-CONJEEVARAM
CTSU Pre-Award - 313-CONJEEVARAM | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-07-26 | 36 |  | N | 313-CONJEEVARAM
CTSU Pre-Award - 375-JAMERSON | Intake Form Completed | Role | CTSU Finance | 2017-07-26 | 0 | 2017-07-26 | N | 375-JAMERSON
Calendaring : Amendment Checklist & Process - 00122815 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-07-26 | 1 | 2017-07-27 | N | 00122815
Pre-Award Financial - 142-FLAHERTY | PAN Released | Role | CTSU Finance | 2017-07-26 | 36 |  | N | 142-FLAHERTY
Pre-Award Financial - 246-AS-SANIE | PI approved Budget | Role | CTSU Finance | 2017-07-26 | 36 |  | N | 246-AS-SANIE
Pre-Award Financial - 255-LOK | Internal Budget Finished | Role | CTSU Finance | 2017-07-26 | 36 |  | N | 255-LOK
Calendaring : Amendment Checklist & Process - 00109407 | Acknowledge | User | Deweese, Braden | 2017-07-26 | 36 |  | N | 00109407
Calendaring : Initial Calendar Build - 00131311 | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-07-26 | 0 | 2017-07-24 | N | 00131311
Calendaring : Initial Calendar Build - 00131311 | Make Updates | User | Radenbaugh, Pauline | 2017-07-26 | 0 | 2017-07-24 | N | 00131311
Calendaring : Initial Calendar Build - 239-KORLEY | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline | 2017-07-26 | 1 | 2017-07-27 | N | 00129045
Calendaring : Initial Calendar Build - 239-KORLEY | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline | 2017-07-26 | 5 | 2017-07-31 | N | 00129045
Pre-Award Financial - 235-SUGAR | Final Budget | User | VanderElzen, Liz | 2017-07-26 | 36 |  | N | 235-SUGAR
Calendaring : Specification Update Request(s) - 00128531 | ** Structural Edits | User | Yunk, Jason | 2017-07-26 | 0 | 2017-07-26 | N | 00128531
Calendaring : Initial Calendar Build - 132040 | Nimblify Build is Complete & Ready for Import | User | Zahs, Brian | 2017-07-26 | 0 | 2017-07-26 | N | 00132040
Calendaring : Initial Calendar Build - 179-LUGOGO | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-07-26 | 9 | 2017-08-04 | N | 179-LUGOGO
Calendaring : Initial Calendar Build - 179-LUGOGO | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-07-26 | 16 | 2017-08-11 | N | 179-LUGOGO
CTSU Pre-Award - 337-MIAN | Feasibility w/Documents received | Role | CTSU Administrator | 2017-07-27 | 0 | 2017-07-27 | N | 337-MIAN
CTSU Pre-Award - 338-MIAN | Feasibility w/Documents received | Role | CTSU Administrator | 2017-07-27 | 0 | 2017-07-27 | N | 00133457
CTSU Pre-Award v2 - 00111295 | Open to Accrual | Role | CTSU Administrator | 2017-07-27 | 35 |  | N | 00111295
Pre-Award Financial - 110-SCHIOPU | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-27 | 0 | 2017-07-27 | N | 00134444
Pre-Award Financial - 251-COMER | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-27 | 0 | 2017-07-27 | N | 00134232
CTSU Pre-Award - 336-KHANNA | UFA Completed | Role | CTSU Coordinator | 2017-07-27 | 29 | 2017-08-25 | N | 00133684
Pre-Award Financial - 00130575 | IRB Application Submitted | Role | CTSU Coordinator | 2017-07-27 | 0 | 2017-07-27 | N | 00130575
Pre-Award Financial - FONTANA-1 | IRB Application Submitted | Role | CTSU Coordinator | 2017-07-27 | 0 | 2017-07-27 | N | 00133153
Pre-Award Financial - FONTANA-1 | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-27 | 0 | 2017-07-25 | N | 00133153
Calendaring : Amendment Checklist & Process - HUM00129276 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance | 2017-07-27 | 0 | 2017-07-27 | N | 00129276
Calendaring : Initial Calendar Build - 110-SCHIOPU | Assign to Analyst | User | Greene, Paula | 2017-07-27 | 0 | 2017-07-27 | N | 00134444
Calendaring : Initial Calendar Build - 110-SCHIOPU | Feasibility Approval Notice Received | User | Greene, Paula | 2017-07-27 | 0 | 2017-07-27 | N | 00134444
Calendaring : Initial Calendar Build - 110-SCHIOPU | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-07-27 | 0 | 2017-07-27 | N | 00134444
Calendaring : Initial Calendar Build - 251-COMER | Assign to Analyst | User | Greene, Paula | 2017-07-27 | 0 | 2017-07-27 | N | 00134232
Calendaring : Initial Calendar Build - 251-COMER | Feasibility Approval Notice Received | User | Greene, Paula | 2017-07-27 | 0 | 2017-07-27 | N | 00134232
Calendaring : Initial Calendar Build - 251-COMER | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-07-27 | 0 | 2017-07-27 | N | 00134232
Pre-Award Financial - 278-CONJEEVARAM | PI approved Budget | User | Henry, Robin | 2017-07-27 | 13 | 2017-08-09 | N | 00133341
Pre-Award Financial - FONTANA-1 | Created CTRF & "Notify ORSP" | User | Henry, Robin | 2017-07-27 | 0 | 2017-07-25 | N | 00133153
Pre-Award Financial - FONTANA-1 | Request Research Pharmacy Budget | User | Henry, Robin | 2017-07-27 | 0 | 2017-06-01 | N | 00133153
Calendaring : Initial Calendar Build - 23-GUPTA | Attach Build Notes ( as Protocol Doc ) | User | Hodges, Lynda | 2017-07-27 | 7 | 2017-08-03 | N | 00134236
Calendaring : Initial Calendar Build - 351-HIGGINS | Attach Build Notes ( as Protocol Doc ) | User | Hodges, Lynda | 2017-07-27 | 0 | 2017-07-26 | N | 00134870
Calendaring : Initial Calendar Build - 351-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hodges, Lynda | 2017-07-27 | 1 | 2017-07-28 | N | 00134870
Calendaring : Initial Calendar Build - 336-KHANNA | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-07-27 | 13 | 2017-08-09 | N | 00133684
Calendaring : Initial Calendar Build - 350-HIGGINS | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-07-27 | 0 | 2017-07-26 | N | 00133054
Calendaring : Initial Calendar Build - 00129709 | Acknowledge | User | Rollins, Matthew | 2017-07-27 | 22 | 2017-08-18 | N | 00129709
Pre-Award Financial - 112-FLAHERTY | Planning Meeting Completed | User | VanderElzen, Liz | 2017-07-27 | 6 | 2017-08-02 | N | 112-FLAHERTY
Calendaring : Specification Update Request(s) - 00130575 | Acknowledge | User | Yunk, Jason | 2017-07-27 | 0 | 2017-07-26 | N | 00130575
Calendaring : Initial Calendar Build - 00128531 | CRAO Approval Issue & Documented | User | Zahs, Brian | 2017-07-27 | 0 | 2017-07-27 | N | 00128531
Calendaring : Initial Calendar Build - 112-FLAHERTY | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-07-27 | 35 |  | N | 112-FLAHERTY
Calendaring : Initial Calendar Build - 112-FLAHERTY | Make Updates | User | van Dijk, Tim | 2017-07-27 | 35 |  | N | 112-FLAHERTY
Calendaring : Amendment Checklist & Process - 162-PIPE | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance | 2017-07-28 | 14 | 2017-08-11 | N | 00131320
Calendaring : Initial Calendar Build - 00131311 | Acknowledge | Role | CTSU Finance | 2017-07-28 | 34 |  | N | 00131311
Pre-Award Financial - 246-AS-SANIE | Budget Negotiations | Role | CTSU Finance | 2017-07-28 | 34 |  | N | 246-AS-SANIE
Pre-Award Financial - 96-BESIRLI | PAF routed | Role | CTSU Finance | 2017-07-28 | 0 | 2017-05-09 | N | 00129820
Pre-Award Financial - 87-ORAL | OnCore Budget Build | User | Farmer, Amber | 2017-07-28 | 33 | 2017-08-30 | N | 00130757
Calendaring : Initial Calendar Build - 232-GIPSON | Assign to Analyst | User | Greene, Paula | 2017-07-28 | 3 | 2017-07-31 | N | 232-GIPSON
Calendaring : Initial Calendar Build - 232-GIPSON | Feasibility Approval Notice Received | User | Greene, Paula | 2017-07-28 | 0 | 2017-07-28 | N | 232-GIPSON
Calendaring : Initial Calendar Build - 232-GIPSON | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-07-28 | 0 | 2017-07-28 | N | 232-GIPSON
Pre-Award Financial - 00130793 | OnCore Budget Build | User | Henry, Robin | 2017-07-28 | 34 |  | N | 00130793
Calendaring : Amendment Checklist & Process - 00122815 | Assign to Analyst | User | Hodges, Lynda | 2017-07-28 | 0 | 2017-07-27 | N | 00122815
Calendaring : Initial Calendar Build - 358-SHELLHAAS | Complete MCA / QCT | User | Hodges, Lynda | 2017-07-28 | 0 | 2017-07-26 | N | 00133339
Calendaring : Initial Calendar Build - 358-SHELLHAAS | Complete SVS & Pricing List ( Built & Coded ) | User | Hodges, Lynda | 2017-07-28 | 0 | 2017-07-27 | N | 00133339
Calendaring : Initial Calendar Build - 358-SHELLHAAS | Nimblify Build is Complete & Ready for Import | User | Hodges, Lynda | 2017-07-28 | 6 | 2017-08-03 | N | 00133339
Calendaring : Initial Calendar Build - 192-ALAM | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-07-28 | 34 |  | N | 192-ALAM
Calendaring : Initial Calendar Build - 192-ALAM | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-07-28 | 5 | 2017-08-02 | N | 192-ALAM
Calendaring : Initial Calendar Build - 192-ALAM | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-07-28 | 3 | 2017-07-31 | N | 192-ALAM
Pre-Award Financial - 147-SCHIOPU | PAN Released | User | Oliver, Amy | 2017-07-28 | 34 |  | N | 00131329
Pre-Award Financial - 170-SCHIOPU | PAN Released | User | Oliver, Amy | 2017-07-28 | 34 |  | N | 00134035
Calendaring : Initial Calendar Build - CY5022 | Complete MCA / QCT | User | Przykucki, Anne | 2017-07-28 | 0 | 2017-07-27 | N | 00132631
Calendaring : Initial Calendar Build - CY5022 | Complete SVS & Pricing List ( Built & Coded ) | User | Przykucki, Anne | 2017-07-28 | 4 | 2017-08-01 | N | 00132631
Calendaring : Initial Calendar Build - CY5022 | Nimblify Build is Complete & Ready for Import | User | Przykucki, Anne | 2017-07-28 | 3 | 2017-07-31 | N | 00132631
Pre-Award Financial - 235-SUGAR | PAF routed | User | VanderElzen, Liz | 2017-07-28 | 34 |  | N | 235-SUGAR
Calendaring : Initial Calendar Build - 132040 | Complete MCA / QCT | User | Zahs, Brian | 2017-07-28 | 34 |  | N | 00132040
Calendaring : Initial Calendar Build - 132040 | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian | 2017-07-28 | 0 | 2017-07-27 | N | 00132040
Calendaring : Initial Calendar Build - 00133153 | Complete MCA / QCT | User | van Dijk, Tim | 2017-07-28 | 6 | 2017-08-03 | N | 00133153
Calendaring : Initial Calendar Build - 00133153 | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-07-28 | 3 | 2017-07-31 | N | 00133153
Calendaring : Initial Calendar Build - 00133153 | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-07-28 | 3 | 2017-07-31 | N | 00133153
Pre-Award Financial - 110-SCHIOPU | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-29 | 0 | 2017-07-27 | N | 00134444
Pre-Award Financial - 251-COMER | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-07-29 | 0 | 2017-07-27 | N | 00134232
CTSU Pre-Award v2 - 415-ROMANO | Billing Calendar Received | Role | CTSU Finance | 2017-07-29 | 33 |  | N | 415-ROMANO
Calendaring : Initial Calendar Build - 336-KHANNA | Acknowledge | Role | CTSU Finance | 2017-07-29 | 16 | 2017-08-14 | N | 00133684
Pre-Award Financial - 110-SCHIOPU | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-07-29 | 9 | 2017-08-07 | N | 00134444
Pre-Award Financial - 255-LOK | PI approved Budget | Role | CTSU Finance | 2017-07-29 | 33 |  | N | 255-LOK
Pre-Award Financial - 298-SCHIOPU | Billing Calendar Received | Role | CTSU Finance | 2017-07-29 | 33 |  | N | 298-SCHIOPU
CTSU Pre-Award - 341-STOFFEL | Billing Calendar Received | User | Henry, Robin | 2017-07-29 | 13 | 2017-08-11 | N | 00134997
Pre-Award Financial - 110-SCHIOPU | Request Research Pharmacy Budget | User | Henry, Robin | 2017-07-29 | 0 | 2017-06-05 | N | 00134444
Pre-Award Financial - 278-CONJEEVARAM | Budget Negotiations | User | Henry, Robin | 2017-07-29 | 16 | 2017-08-14 | N | 00133341
Calendaring : Amendment Checklist & Process - 00122815 | ** Footnote Edits | User | Hodges, Lynda | 2017-07-29 | 0 | 2017-07-27 | N | 00122815
Calendaring : Amendment Checklist & Process - 00122815 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Hodges, Lynda | 2017-07-29 | 0 | 2017-07-27 | N | 00122815
Calendaring : Amendment Checklist & Process - 00122815 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Hodges, Lynda | 2017-07-29 | 0 | 2017-07-27 | N | 00122815
Calendaring : Initial Calendar Build - 350-HIGGINS | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-07-29 | 0 | 2017-07-26 | N | 00133054
Calendaring : Initial Calendar Build - 350-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-07-29 | 17 | 2017-08-15 | N | 00133054
Pre-Award Financial - 00130793 | Calendar Released | User | Oliver, Amy | 2017-07-29 | 33 |  | N | 00130793
Pre-Award Financial - 87-ORAL | Calendar Released | User | Oliver, Amy | 2017-07-29 | 32 | 2017-08-30 | N | 00130757
Calendaring : Initial Calendar Build - 112-FLAHERTY | Acknowledge | User | VanderElzen, Liz | 2017-07-29 | 33 |  | N | 112-FLAHERTY
Pre-Award Financial - 251-COMER | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-07-29 | 3 | 2017-08-01 | N | 00134232
Pre-Award Financial - 235-SUGAR | OnCore Budget Build | User | Yunk, Jason | 2017-07-29 | 33 |  | N | 235-SUGAR
Calendaring : Amendment Checklist & Process - HUM00129276 | Complete Calendar and Document Approval | User | van Dijk, Tim | 2017-07-29 | 2 | 2017-07-31 | N | 00129276
Pre-Award Financial - 263-DELMONTE | Internal Budget Finished | Role | CTSU Finance | 2017-07-30 | 32 |  | N | 263-DELMONTE
CTSU Pre-Award - 336-KHANNA | Care Designations completed | User | Henry, Robin | 2017-07-30 | 15 | 2017-08-14 | N | 00133684
Pre-Award Financial - 23-GUPTA | Billing Calendar Received | User | Henry, Robin | 2017-07-30 | 10 | 2017-08-09 | N | 00134236
Calendaring : Initial Calendar Build - 358-SHELLHAAS | Attach Build Notes ( as Protocol Doc ) | User | Hodges, Lynda | 2017-07-30 | 4 | 2017-08-03 | N | 00133339
Calendaring : Initial Calendar Build - 110-SCHIOPU | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-07-30 | 32 |  | N | 00134444
Calendaring : Initial Calendar Build - 110-SCHIOPU | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-07-30 | 19 | 2017-08-18 | N | 00134444
Calendaring : Initial Calendar Build - 110-SCHIOPU | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-07-30 | 4 | 2017-08-03 | N | 00134444
Calendaring : Initial Calendar Build - 192-ALAM | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-07-30 | 1 | 2017-07-31 | N | 192-ALAM
Calendaring : Initial Calendar Build - 192-ALAM | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-07-30 | 25 | 2017-08-24 | N | 192-ALAM
Pre-Award Financial - 235-SUGAR | Calendar Released | User | Oliver, Amy | 2017-07-30 | 32 |  | N | 235-SUGAR
Calendaring : Initial Calendar Build - CY5022 | Attach Build Notes ( as Protocol Doc ) | User | Przykucki, Anne | 2017-07-30 | 2 | 2017-08-01 | N | 00132631
Calendaring : Initial Calendar Build - CY5022 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Przykucki, Anne | 2017-07-30 | 2 | 2017-08-01 | N | 00132631
Pre-Award Financial - 112-FLAHERTY | Care Designations completed | User | VanderElzen, Liz | 2017-07-30 | 32 |  | N | 112-FLAHERTY
CTSU Post-Award - 00129820 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-07-30 | 32 |  | N | 00129820
Calendaring : Initial Calendar Build - 132040 | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian | 2017-07-30 | 0 | 2017-07-28 | N | 00132040
Calendaring : Initial Calendar Build - 132040 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian | 2017-07-30 | 0 | 2017-07-28 | N | 00132040
Calendaring : Initial Calendar Build - 251-COMER | Complete MCA / QCT | User | Zahs, Brian | 2017-07-30 | 32 |  | N | 00134232
Calendaring : Initial Calendar Build - 251-COMER | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian | 2017-07-30 | 2 | 2017-08-01 | N | 00134232
Calendaring : Initial Calendar Build - 251-COMER | Nimblify Build is Complete & Ready for Import | User | Zahs, Brian | 2017-07-30 | 2 | 2017-08-01 | N | 00134232
Calendaring : Amendment Checklist & Process - 162-PIPE | Complete Calendar and Document Approval | User | van Dijk, Tim | 2017-07-30 | 12 | 2017-08-11 | N | 00131320
Calendaring : Initial Calendar Build - 00133153 | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-07-30 | 1 | 2017-07-31 | N | 00133153
Calendaring : Initial Calendar Build - 00133153 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-07-30 | 3 | 2017-08-02 | N | 00133153
CTSU Pre-Award - 341-STOFFEL | Feasibility w/Documents received | Role | CTSU Administrator | 2017-07-31 | 0 | 2017-07-17 | N | 00134997
CTSU Pre-Award v2 - 364-KHAJA | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-07-31 | 31 |  | N | 364-KHAJA
CTSU Pre-Award v2 - 380-LOK | Intake Form Completed | Role | CTSU Coordinator | 2017-07-31 | 0 | 2017-07-31 | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-07-31 | 0 | 2017-07-31 | N | 381-HIGGINS
Open to Accrual - 00129820 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator | 2017-07-31 | 0 | 2017-07-31 | N | 00129820
Open to Accrual - 00129820 | Contract Executed | Role | CTSU Coordinator | 2017-07-31 | 0 | 2017-05-15 | N | 00129820
Open to Accrual - 00129820 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator | 2017-07-31 | 0 | 2017-07-31 | N | 00129820
Open to Accrual - 00129820 | MiChart Verifications | Role | CTSU Coordinator | 2017-07-31 | 1 | 2017-08-01 | N | 00129820
Open to Accrual - 00129820 | Other Personnel Notified | Role | CTSU Coordinator | 2017-07-31 | 0 | 2017-07-31 | N | 00129820
Open to Accrual - 00129820 | Project Award Notice (PAN) Received | Role | CTSU Coordinator | 2017-07-31 | 0 | 2017-06-30 | N | 00129820
Open to Accrual - 00129820 | Provisions for Support and Services Finalized | Role | CTSU Coordinator | 2017-07-31 | 0 | 2017-07-31 | N | 00129820
Open to Accrual - 00129820 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator | 2017-07-31 | 0 | 2017-07-31 | N | 00129820
Open to Accrual - 00129820 | Study Files Established | Role | CTSU Coordinator | 2017-07-31 | 0 | 2017-07-31 | N | 00129820
Open to Accrual - 00129820 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator | 2017-07-31 | 0 | 2017-07-31 | N | 00129820
Calendaring : Amendment Checklist & Process - HUM00129276 | Acknowledge | Role | CTSU Finance | 2017-07-31 | 9 | 2017-08-09 | N | 00129276
Calendaring : Initial Calendar Build - 357-GRANT 2 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-07-31 | 29 | 2017-08-29 | N | 00119336
Open to Accrual - 00129820 | Budget Finalized | Role | CTSU Finance | 2017-07-31 | 0 | 2017-05-15 | N | 00129820
Pre-Award Financial - 255-LOK | Budget Negotiations | Role | CTSU Finance | 2017-07-31 | 31 |  | N | 255-LOK
CTSU Pre-Award - 336-KHANNA | Internal Budget Finished | User | Henry, Robin | 2017-07-31 | 21 | 2017-08-21 | N | 00133684
Calendaring : Amendment Checklist & Process - 00122815 | ** Visits : Addition or Removal of Time Points | User | Hodges, Lynda | 2017-07-31 | 0 | 2017-07-27 | N | 00122815
Calendaring : Amendment Checklist & Process - 00122815 | Request Care Designations | User | Hodges, Lynda | 2017-07-31 | 0 | 2017-07-27 | N | 00122815
Pre-Award Financial - 70-LUGOGO | PAN Released | User | Oliver, Amy | 2017-07-31 | 31 |  | N | 70-LUGOGO
CTSU Pre-Award - 350-HIGGINS | Billing Calendar Received | User | VanderElzen, Liz | 2017-07-31 | 15 | 2017-08-15 | N | 00133054
CTSU Pre-Award - 351-HIGGINS | Billing Calendar Received | User | VanderElzen, Liz | 2017-07-31 | 0 | 2017-07-28 | N | 00134870
Pre-Award Financial - 179-LUGOGO | Billing Calendar Received | User | VanderElzen, Liz | 2017-07-31 | 11 | 2017-08-11 | N | 179-LUGOGO
CTSU Post-Award - 00089260 | Date Reconciled | User | Yunk, Jason | 2017-07-31 | 0 | 2017-05-31 | N | 00089260
Calendaring : Amendment Checklist & Process - 00123231 | AME Calendaring Process Initiated | User | Yunk, Jason | 2017-07-31 | 0 | 2017-07-31 | N | 00123231
Calendaring : Initial Calendar Build - 232-GIPSON | Complete MCA / QCT | User | Zahs, Brian | 2017-07-31 | 31 |  | N | 232-GIPSON
Calendaring : Initial Calendar Build - 232-GIPSON | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian | 2017-07-31 | 1 | 2017-08-01 | N | 232-GIPSON
Calendaring : Initial Calendar Build - 232-GIPSON | Nimblify Build is Complete & Ready for Import | User | Zahs, Brian | 2017-07-31 | 1 | 2017-08-01 | N | 232-GIPSON
Calendaring : Initial Calendar Build - 236-NASR | CRAO Approval Issue & Documented | Role | CRAO | 2017-08-01 | 0 | 2017-08-01 | N | 00131580
CTSU Pre-Award - 337-MIAN | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-01 | 0 | 2017-08-01 | N | 337-MIAN
CTSU Pre-Award - 338-MIAN | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-01 | 0 | 2017-08-01 | N | 00133457
Pre-Award Financial - 00130793 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-01 | 30 |  | N | 00130793
Pre-Award Financial - 86-AUCHUS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-01 | 0 | 2017-08-01 | N | 00132700
Pre-Award Financial - 87-ORAL | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-01 | 30 |  | N | 00130757
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Intake Form Completed | Role | CTSU Coordinator | 2017-08-01 | 0 | 2017-08-01 | N | 385-MCLAUGHLIN
Open to Accrual - 00129427 | IRB Approval | Role | CTSU Coordinator | 2017-08-01 | 0 | 2017-08-01 | N | 00129427
Pre-Award Financial - 170-SCHIOPU | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-01 | 0 | 2017-08-01 | N | 00134035
CTSU Post-Award - 00124920 | Date Reconciled | Role | CTSU Finance | 2017-08-01 | 0 | 2017-08-01 | N | 00124920
CTSU Pre-Award - 375-JAMERSON | UFA Completed | Role | CTSU Finance | 2017-08-01 | 0 | 2017-08-01 | N | 375-JAMERSON
Calendaring : Amendment Checklist & Process - 162-PIPE | Acknowledge | Role | CTSU Finance | 2017-08-01 | 30 |  | N | 00131320
Calendaring : Initial Calendar Build - 00131904 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Cohan, Lynn | 2017-08-01 | 13 | 2017-08-14 | N | 00131904
Calendaring : Initial Calendar Build - 00132700 | Assign to Analyst | User | Greene, Paula | 2017-08-01 | 0 | 2017-08-01 | N | 00132700
Calendaring : Initial Calendar Build - 00132700 | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-01 | 0 | 2017-08-01 | N | 00132700
Calendaring : Initial Calendar Build - 00132700 | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-01 | 0 | 2017-08-01 | N | 00132700
Calendaring : Initial Calendar Build - 337-MIAN | Assign to Analyst | User | Greene, Paula | 2017-08-01 | 2 | 2017-08-03 | N | 337-MIAN
Calendaring : Initial Calendar Build - 337-MIAN | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-01 | 1 | 2017-08-02 | N | 337-MIAN
Calendaring : Initial Calendar Build - 337-MIAN | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-01 | 1 | 2017-08-02 | N | 337-MIAN
Calendaring : Initial Calendar Build - 338-MIAN | Assign to Analyst | User | Greene, Paula | 2017-08-01 | 2 | 2017-08-03 | N | 00133457
Calendaring : Initial Calendar Build - 338-MIAN | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-01 | 1 | 2017-08-02 | N | 00133457
Calendaring : Initial Calendar Build - 338-MIAN | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-01 | 1 | 2017-08-02 | N | 00133457
Calendaring : Initial Calendar Build - 341-STOFFEL | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Henry, Robin | 2017-08-01 | 14 | 2017-08-15 | N | 00134997
Open to Accrual - 00124920 | Adequate Equipment and Supplies Available | User | Huffman, Kate | 2017-08-01 | 30 |  | N | 00124920
Open to Accrual - 00124920 | Budget Finalized | User | Huffman, Kate | 2017-08-01 | 0 | 2017-03-29 | N | 00124920
Open to Accrual - 00124920 | Contract Executed | User | Huffman, Kate | 2017-08-01 | 0 | 2017-03-29 | N | 00124920
Open to Accrual - 00124920 | IRB Approval | User | Huffman, Kate | 2017-08-01 | 0 | 2017-06-29 | N | 00124920
Open to Accrual - 00124920 | Investigational Drug/Device Supplies Available | User | Huffman, Kate | 2017-08-01 | 30 |  | N | 00124920
Open to Accrual - 00124920 | MiChart Verifications | User | Huffman, Kate | 2017-08-01 | 0 | 2017-08-01 | N | 00124920
Open to Accrual - 00124920 | Other Personnel Notified | User | Huffman, Kate | 2017-08-01 | 30 |  | N | 00124920
Open to Accrual - 00124920 | Project Award Notice (PAN) Received | User | Huffman, Kate | 2017-08-01 | 0 | 2017-08-01 | N | 00124920
Open to Accrual - 00124920 | Provisions for Support and Services Finalized | User | Huffman, Kate | 2017-08-01 | 30 |  | N | 00124920
Open to Accrual - 00124920 | Sponsor/Organizing Group Approval Granted for Initiation of Study | User | Huffman, Kate | 2017-08-01 | 30 |  | N | 00124920
Open to Accrual - 00124920 | Study Files Established | User | Huffman, Kate | 2017-08-01 | 30 |  | N | 00124920
Open to Accrual - 00124920 | Study Team Roles/Responsibilities Finalized | User | Huffman, Kate | 2017-08-01 | 30 |  | N | 00124920
Calendaring : Initial Calendar Build - 110-SCHIOPU | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-08-01 | 13 | 2017-08-14 | N | 00134444
Calendaring : Initial Calendar Build - 110-SCHIOPU | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-08-01 | 17 | 2017-08-18 | N | 00134444
Calendaring : Initial Calendar Build - 4033CYTOKINETICS-GOUTMAN | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa | 2017-08-01 | 3 | 2017-08-04 | N | 00130639
Pre-Award Financial - 49-MARTINEZ | PAN Released | User | Oliver, Amy | 2017-08-01 | 30 |  | N | 00132020
Pre-Award Financial - 282-POP-BUSUI | Final Budget | User | VanderElzen, Liz | 2017-08-01 | 0 | 2017-07-25 | N | 00133290
CTSU Post-Award - 00129716 | Date Reconciled | User | Yunk, Jason | 2017-08-01 | 0 | 2017-08-01 | N | 00129716
Calendaring : Initial Calendar Build - 251-COMER | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian | 2017-08-01 | 13 | 2017-08-14 | N | 00134232
Calendaring : Initial Calendar Build - 251-COMER | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian | 2017-08-01 | 1 | 2017-08-02 | N | 00134232
Calendaring : Specification Update Request(s) - 00128531 | Make Update(s) | User | Zahs, Brian | 2017-08-01 | 2 | 2017-08-03 | N | 00128531
Calendaring : Specification Update Request(s) - 00128531 | Re-Complete Calendar | User | Zahs, Brian | 2017-08-01 | 3 | 2017-08-04 | N | 00128531
CTSU Pre-Award - 332-BELLOLI | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-02 | 27 | 2017-08-29 | N | 332-BELLOLI
Pre-Award Financial - 235-SUGAR | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-02 | 29 |  | N | 235-SUGAR
CTSU Pre-Award - 341-STOFFEL | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-02 | 21 | 2017-08-23 | N | 00134997
CTSU Pre-Award - 347-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator | 2017-08-02 | 0 | 2017-07-26 | N | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | UFA Completed | Role | CTSU Coordinator | 2017-08-02 | 0 | 2017-07-26 | N | 347-HIGGINS
CTSU Pre-Award v2 - 364-KHAJA | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-02 | 29 |  | N | 364-KHAJA
CTSU Pre-Award v2 - 415-ROMANO | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-02 | 29 |  | N | 415-ROMANO
Pre-Award Financial - 23-GUPTA | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-02 | 0 | 2017-08-02 | N | 00134236
Pre-Award Financial - 298-SCHIOPU | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-02 | 29 |  | N | 298-SCHIOPU
Pre-Award Financial - 86-AUCHUS | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-02 | 0 | 2017-08-02 | N | 00132700
CTSU Pre-Award - 354-PAGANI | UFA Completed | Role | CTSU Finance | 2017-08-02 | 0 | 2017-08-02 | N | 354-PAGANI
CTSU Pre-Award - 375-JAMERSON | Sponsor Reach out | Role | CTSU Finance | 2017-08-02 | 0 | 2017-08-02 | N | 375-JAMERSON
CTSU Pre-Award v2 - 364-KHAJA | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-02 | 29 |  | N | 364-KHAJA
CTSU Pre-Award v2 - 364-KHAJA | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-02 | 29 |  | N | 364-KHAJA
CTSU Pre-Award v2 - 415-ROMANO | Planning Meeting Completed | Role | CTSU Finance | 2017-08-02 | 29 |  | N | 415-ROMANO
Calendaring : Initial Calendar Build - 179-LUGOGO | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-08-02 | 22 | 2017-08-24 | N | 179-LUGOGO
Pre-Award Financial - 263-DELMONTE | PI approved Budget | Role | CTSU Finance | 2017-08-02 | 29 |  | N | 263-DELMONTE
Pre-Award Financial - 298-SCHIOPU | Planning Meeting Completed | Role | CTSU Finance | 2017-08-02 | 29 |  | N | 298-SCHIOPU
Spec. Updates for 121569 (KLV) : add unsched. procedures & clarify SF details | ** Request for Clarification | Role | CTSU Finance | 2017-08-02 | 0 | 2017-08-02 | N | 00121569
CTSU Pre-Award - 341-STOFFEL | Planning Meeting Completed | User | Henry, Robin | 2017-08-02 | 0 | 2017-08-01 | N | 00134997
Calendaring : Amendment Checklist & Process - 00123231 | Assign to Analyst | User | Hodges, Lynda | 2017-08-02 | 0 | 2017-08-01 | N | 00123231
Spec Update Req. 120786 (KLV) Adding 2-WPostDose time point that was missed | ** Structural Edits | User | LaVasseur, Kristen | 2017-08-02 | 0 | 2017-08-02 | N | 00120786
Spec Update Req. 120786 (KLV) Adding 2-WPostDose time point that was missed | Assign to Analyst | User | LaVasseur, Kristen | 2017-08-02 | 0 | 2017-08-02 | N | 00120786
Spec Update Req. 120786 (KLV) Adding 2-WPostDose time point that was missed | Submit Update Request(s) | User | LaVasseur, Kristen | 2017-08-02 | 0 | 2017-08-02 | N | 00120786
Calendaring : Initial Calendar Build - 357-GRANT 2 | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-08-02 | 29 |  | N | 00119336
Spec. Updates for 121569 (KLV) : add unsched. procedures & clarify SF details | ** Request(s) to Add Unscheduled Procedure(s) | User | Watson, Donna | 2017-08-02 | 0 | 2017-08-02 | N | 00121569
Calendaring : Initial Calendar Build - 232-GIPSON | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian | 2017-08-02 | 12 | 2017-08-14 | N | 232-GIPSON
Calendaring : Initial Calendar Build - 232-GIPSON | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian | 2017-08-02 | 12 | 2017-08-14 | N | 232-GIPSON
Spec. Updates for 121569 (KLV) : add unsched. procedures & clarify SF details | Submit Update Request(s) |  |  | 2017-08-02 | 0 | 2017-08-02 | N | 00121569
CTSU Pre-Award - 348-CHEY | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-03 | 28 |  | N | 348-CHEY
Pre-Award Financial - 00130793 | Open to Accrual | Role | CTSU Administrator | 2017-08-03 | 28 |  | N | 00130793
Pre-Award Financial - 87-ORAL | Open to Accrual | Role | CTSU Administrator | 2017-08-03 | 28 |  | N | 00130757
CTSU Pre-Award - 337-MIAN | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-03 | 0 | 2017-08-02 | N | 337-MIAN
CTSU Pre-Award - 338-MIAN | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-03 | 0 | 2017-08-02 | N | 00133457
CTSU Pre-Award - 348-CHEY | Sponsor Reach out | Role | CTSU Coordinator | 2017-08-03 | 28 |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | UFA Completed | Role | CTSU Coordinator | 2017-08-03 | 28 |  | N | 348-CHEY
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Sponsor Reach out | Role | CTSU Coordinator | 2017-08-03 | 0 | 2017-08-03 | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 390-DAY | Intake Form Completed | Role | CTSU Coordinator | 2017-08-03 | 0 | 2017-08-03 | N | 390-DAY
Pre-Award Financial - 86-AUCHUS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-03 | 0 | 2017-08-01 | N | 00132700
CTSU Pre-Award - 313-CONJEEVARAM | Billing Calendar Received | Role | CTSU Finance | 2017-08-03 | 28 |  | N | 313-CONJEEVARAM
CTSU Pre-Award - 337-MIAN | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-03 | 0 | 2017-07-13 | N | 337-MIAN
CTSU Pre-Award - 338-MIAN | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-03 | 0 | 2017-07-13 | N | 00133457
CTSU Pre-Award - 354-PAGANI | Sponsor Reach out | Role | CTSU Finance | 2017-08-03 | 0 | 2017-08-03 | N | 354-PAGANI
CTSU Pre-Award v2 - 00111295 | Initiate Post-Award Task List | Role | CTSU Finance | 2017-08-03 | 28 |  | N | 00111295
CTSU Pre-Award v2 - 00111295 | PAN Released | Role | CTSU Finance | 2017-08-03 | 28 |  | N | 00111295
Pre-Award Financial - 261-LUGOGO | Final Budget | Role | CTSU Finance | 2017-08-03 | 28 |  | N | 261-LUGOGO
Pre-Award Financial - 86-AUCHUS | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-03 | 1 | 2017-08-04 | N | 00132700
CTSU Pre-Award - 336-KHANNA | PI approved Budget | User | Henry, Robin | 2017-08-03 | 22 | 2017-08-25 | N | 00133684
Pre-Award Financial - 23-GUPTA | Planning Meeting Completed | User | Henry, Robin | 2017-08-03 | 0 | 2017-07-17 | N | 00134236
Pre-Award Financial - 86-AUCHUS | Created CTRF & "Notify ORSP" | User | Henry, Robin | 2017-08-03 | 0 | 2017-08-01 | N | 00132700
Calendaring : Amendment Checklist & Process - 00123231 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Hodges, Lynda | 2017-08-03 | 0 | 2017-08-02 | N | 00123231
Calendaring : Initial Calendar Build - 23-GUPTA | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hodges, Lynda | 2017-08-03 | 5 | 2017-08-08 | N | 00134236
Calendaring : Initial Calendar Build - 358-SHELLHAAS | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hodges, Lynda | 2017-08-03 | 7 | 2017-08-10 | N | 00133339
Calendaring : Initial Calendar Build - 00131904 | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-08-03 | 11 | 2017-08-14 | N | 00131904
Calendaring : Initial Calendar Build - 00131904 | Make Updates | User | Munasinghe, Sadeepa | 2017-08-03 | 11 | 2017-08-14 | N | 00131904
Calendaring : Specification Update Request(s) - 00128531 | Acknowledge | User | Oliver, Amy | 2017-08-03 | 28 |  | N | 00128531
Pre-Award Financial - 155-ORAL | PAF routed | User | Oliver, Amy | 2017-08-03 | 0 | 2017-05-30 | N | 00130803
Calendaring : Initial Calendar Build - 351-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-08-03 | 8 | 2017-08-11 | N | 00134870
Pre-Award Financial - 112-FLAHERTY | Internal Budget Finished | User | VanderElzen, Liz | 2017-08-03 | 0 | 2017-07-28 | N | 112-FLAHERTY
Pre-Award Financial - 282-POP-BUSUI | PAF routed | User | VanderElzen, Liz | 2017-08-03 | 0 | 2017-07-26 | N | 00133290
Pre-Award Financial - 00129652 | OnCore Budget Build | User | Yunk, Jason | 2017-08-03 | 15 | 2017-08-18 | N | 00129652
Open to Accrual - 00121569 2 | Other Personnel Notified | User | Ziolkowski, Jaimie | 2017-08-03 | 0 | 2017-07-31 | N | 00121569
Calendaring : Initial Calendar Build - 341-STOFFEL | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-08-03 | 12 | 2017-08-15 | N | 00134997
Calendaring : Initial Calendar Build - 341-STOFFEL | Make Updates | User | van Dijk, Tim | 2017-08-03 | 12 | 2017-08-15 | N | 00134997
CTSU Pre-Award - 350-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-04 | 0 | 2017-07-21 | N | 00133054
CTSU Pre-Award - 351-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-04 | 0 | 2017-07-21 | N | 00134870
Pre-Award Financial - 235-SUGAR | Open to Accrual | Role | CTSU Administrator | 2017-08-04 | 27 |  | N | 235-SUGAR
CTSU Pre-Award - 332-BELLOLI | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-04 | 25 | 2017-08-29 | N | 332-BELLOLI
CTSU Pre-Award - 350-HIGGINS | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-04 | 27 |  | N | 00133054
CTSU Pre-Award - 351-HIGGINS | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-04 | 27 |  | N | 00134870
CTSU Pre-Award - 332-BELLOLI | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-04 | 27 |  | N | 332-BELLOLI
CTSU Pre-Award - 332-BELLOLI | Request MCRU Budget | Role | CTSU Finance | 2017-08-04 | 27 |  | N | 332-BELLOLI
CTSU Pre-Award - 332-BELLOLI | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-04 | 27 |  | N | 332-BELLOLI
CTSU Pre-Award - 350-HIGGINS | Planning Meeting Completed | Role | CTSU Finance | 2017-08-04 | 7 | 2017-08-11 | N | 00133054
CTSU Pre-Award - 363-PARK | UFA Completed | Role | CTSU Finance | 2017-08-04 | 0 | 2017-08-04 | N | 363-PARK
Calendaring : Initial Calendar Build - 357-GRANT 2 | Acknowledge | Role | CTSU Finance | 2017-08-04 | 27 |  | N | 00119336
Pre-Award Financial - 263-DELMONTE | Budget Negotiations | Role | CTSU Finance | 2017-08-04 | 27 |  | N | 263-DELMONTE
Pre-Award Financial - FONTANA-1 | Billing Calendar Received | User | Henry, Robin | 2017-08-04 | 0 | 2017-08-02 | N | 00133153
Pre-Award Financial - 00129652 | Calendar Released | User | Oliver, Amy | 2017-08-04 | 14 | 2017-08-18 | N | 00129652
Calendaring : Initial Calendar Build - 239-KORLEY | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline | 2017-08-04 | 0 | 2017-07-31 | N | 00129045
CTSU Pre-Award - 351-HIGGINS | Planning Meeting Completed | User | VanderElzen, Liz | 2017-08-04 | 7 | 2017-08-11 | N | 00134870
Pre-Award Financial - 179-LUGOGO | Planning Meeting Completed | User | VanderElzen, Liz | 2017-08-04 | 7 | 2017-08-11 | N | 179-LUGOGO
Pre-Award Financial - 282-POP-BUSUI | OnCore Budget Build | User | Yunk, Jason | 2017-08-04 | 14 | 2017-08-18 | N | 00133290
Calendaring : Initial Calendar Build - 00132700 | Complete MCA / QCT | User | Zahs, Brian | 2017-08-04 | 27 |  | N | 00132700
Calendaring : Initial Calendar Build - 00132700 | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian | 2017-08-04 | 6 | 2017-08-10 | N | 00132700
Calendaring : Initial Calendar Build - 00132700 | Nimblify Build is Complete & Ready for Import | User | Zahs, Brian | 2017-08-04 | 5 | 2017-08-09 | N | 00132700
Calendaring : Initial Calendar Build - 179-LUGOGO | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-08-04 | 20 | 2017-08-24 | N | 179-LUGOGO
Calendaring : Initial Calendar Build - 179-LUGOGO | Make Updates | User | van Dijk, Tim | 2017-08-04 | 20 | 2017-08-24 | N | 179-LUGOGO
Calendaring : Initial Calendar Build - 337-MIAN | Complete MCA / QCT | User | van Dijk, Tim | 2017-08-04 | 3 | 2017-08-07 | N | 337-MIAN
Calendaring : Initial Calendar Build - 337-MIAN | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-08-04 | 0 | 2017-08-04 | N | 337-MIAN
Calendaring : Initial Calendar Build - 337-MIAN | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-08-04 | 5 | 2017-08-09 | N | 337-MIAN
Calendaring : Initial Calendar Build - 338-MIAN | Complete MCA / QCT | User | van Dijk, Tim | 2017-08-04 | 3 | 2017-08-07 | N | 00133457
Calendaring : Initial Calendar Build - 338-MIAN | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-08-04 | 0 | 2017-08-04 | N | 00133457
Calendaring : Initial Calendar Build - 338-MIAN | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-08-04 | 3 | 2017-08-07 | N | 00133457
Spec. Updates for 121569 (KLV) : add unsched. procedures & clarify SF details | Assign to Analyst |  |  | 2017-08-04 | 0 | 2017-08-02 | N | 00121569
CTSU Pre-Award v2 - 415-ROMANO | Care Designations completed | Role | CTSU Finance | 2017-08-05 | 26 |  | N | 415-ROMANO
Calendaring : Amendment Checklist & Process - 00122815 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance | 2017-08-05 | 3 | 2017-08-08 | N | 00122815
Pre-Award Financial - 261-LUGOGO | PAF routed | Role | CTSU Finance | 2017-08-05 | 26 |  | N | 261-LUGOGO
Pre-Award Financial - 298-SCHIOPU | Care Designations completed | Role | CTSU Finance | 2017-08-05 | 26 |  | N | 298-SCHIOPU
Calendaring : Initial Calendar Build - 00131904 | Acknowledge | User | Cohan, Lynn | 2017-08-05 | 10 | 2017-08-15 | N | 00131904
CTSU Pre-Award - 336-KHANNA | Budget Negotiations | User | Henry, Robin | 2017-08-05 | 23 | 2017-08-28 | N | 00133684
CTSU Pre-Award - 341-STOFFEL | Care Designations completed | User | Henry, Robin | 2017-08-05 | 10 | 2017-08-15 | N | 00134997
Calendaring : Initial Calendar Build - 341-STOFFEL | Acknowledge | User | Henry, Robin | 2017-08-05 | 26 |  | N | 00134997
Pre-Award Financial - 205-KHANNA | PAN Released | User | Henry, Robin | 2017-08-05 | 26 |  | N | 00132200
Pre-Award Financial - 180-HOFF | PAN Released | User | Oliver, Amy | 2017-08-05 | 26 |  | N | 00129450
Pre-Award Financial - 205-KHANNA | Initiate Post-Award Task List | User | Oliver, Amy | 2017-08-05 | 26 |  | N | 00132200
Pre-Award Financial - 282-POP-BUSUI | Calendar Released | User | Oliver, Amy | 2017-08-05 | 13 | 2017-08-18 | N | 00133290
Calendaring : Initial Calendar Build - 350-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-08-05 | 19 | 2017-08-24 | N | 00133054
Calendaring : Initial Calendar Build - 132040 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Boyd, Collin | 2017-08-06 | 0 | 2017-07-31 | N | 00132040
Calendaring : Initial Calendar Build - CY5022 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Boyd, Collin | 2017-08-06 | 9 | 2017-08-15 | N | 00132631
Calendaring : Initial Calendar Build - 00133153 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-08-06 | 4 | 2017-08-10 | N | 00133153
Calendaring : Initial Calendar Build - 179-LUGOGO | Acknowledge | Role | CTSU Finance | 2017-08-06 | 25 |  | N | 179-LUGOGO
Pre-Award Financial - 239-KORLEY | Billing Calendar Received | Role | CTSU Finance | 2017-08-06 | 0 | 2017-08-06 | N | 00129045
Pre-Award Financial - 239-KORLEY | Care Designations completed | Role | CTSU Finance | 2017-08-06 | 0 | 2017-08-06 | N | 00129045
Pre-Award Financial - 110-SCHIOPU | Billing Calendar Received | User | Henry, Robin | 2017-08-06 | 15 | 2017-08-21 | N | 00134444
Pre-Award Financial - 23-GUPTA | Care Designations completed | User | Henry, Robin | 2017-08-06 | 18 | 2017-08-24 | N | 00134236
Calendaring : Initial Calendar Build - 192-ALAM | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Munsey, Barbara | 2017-08-06 | 24 | 2017-08-30 | N | 192-ALAM
Calendaring : Initial Calendar Build - 239-KORLEY | Acknowledge | User | Munsey, Barbara | 2017-08-06 | 11 | 2017-08-17 | N | 00129045
Pre-Award Financial - 112-FLAHERTY | PI approved Budget | User | VanderElzen, Liz | 2017-08-06 | 0 | 2017-08-03 | N | 112-FLAHERTY
Pre-Award Financial - 251-COMER | Billing Calendar Received | User | VanderElzen, Liz | 2017-08-06 | 0 | 2017-08-02 | N | 00134232
CTSU Post-Award - 00125786 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-08-06 | 25 |  | N | 00125786
Calendaring : Initial Calendar Build - 00132700 | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian | 2017-08-06 | 4 | 2017-08-10 | N | 00132700
Calendaring : Initial Calendar Build - 00132700 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian | 2017-08-06 | 4 | 2017-08-10 | N | 00132700
Calendaring : Initial Calendar Build - 337-MIAN | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-08-06 | 3 | 2017-08-09 | N | 337-MIAN
Calendaring : Initial Calendar Build - 337-MIAN | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-08-06 | 3 | 2017-08-09 | N | 337-MIAN
Calendaring : Initial Calendar Build - 338-MIAN | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-08-06 | 1 | 2017-08-07 | N | 00133457
Calendaring : Initial Calendar Build - 338-MIAN | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-08-06 | 1 | 2017-08-07 | N | 00133457
Pre-Award Financial - 00129652 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-07 | 24 |  | N | 00129652
CTSU Pre-Award - 313-CONJEEVARAM | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-07 | 24 |  | N | 313-CONJEEVARAM
CTSU Pre-Award v2 - 393-HYZY | Intake Form Completed | Role | CTSU Coordinator | 2017-08-07 | 0 | 2017-08-07 | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | Intake Form Completed | Role | CTSU Coordinator | 2017-08-07 | 0 | 2017-08-07 | N | 396-SCHIOPU
CTSU Pre-Award v2 - 397-HODISH | Intake Form Completed | Role | CTSU Coordinator | 2017-08-07 | 0 | 2017-08-07 | N | 397-HODISH
CTSU Pre-Award - 313-CONJEEVARAM | Planning Meeting Completed | Role | CTSU Finance | 2017-08-07 | 24 |  | N | 313-CONJEEVARAM
Calendar & Budget Retrofit - 00091655 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-07 | 0 | 2017-08-07 | N | 00091655
Calendar & Budget Retrofit - 00113535 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-07 | 0 | 2017-08-07 | N | 00113535
Calendar & Budget Retrofit - 00120231 | Initiate Updates | Role | CTSU Finance | 2017-08-07 | 0 | 2017-08-07 | N | 00120231
Calendar & Budget Retrofit - 00120231 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-07 | 0 | 2017-08-07 | N | 00120231
Calendar & Budget Retrofit - 00127913 | Initiate Updates | Role | CTSU Finance | 2017-08-07 | 0 | 2017-08-07 | N | 00127913
Calendar & Budget Retrofit - 00127913 | Questions | Role | CTSU Finance | 2017-08-07 | 1 | 2017-08-08 | N | 00127913
Calendar & Budget Retrofit - 00127913 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-07 | 0 | 2017-08-07 | N | 00127913
Pre-Award Financial - 188-RUBENSTEIN | PAN Released | Role | CTSU Finance | 2017-08-07 | 24 |  | N | 188-RUBENSTEIN
Open to Accrual - 4033CYTOKINETICS-GOUTMAN | Adequate Equipment and Supplies Available | User | Duell, Jayna | 2017-08-07 | 21 | 2017-08-28 | N | 00130639
Open to Accrual - 4033CYTOKINETICS-GOUTMAN | IRB Approval | User | Duell, Jayna | 2017-08-07 | 24 |  | N | 00130639
Open to Accrual - 4033CYTOKINETICS-GOUTMAN | Investigational Drug/Device Supplies Available | User | Duell, Jayna | 2017-08-07 | 24 |  | N | 00130639
Open to Accrual - 4033CYTOKINETICS-GOUTMAN | Other Personnel Notified | User | Duell, Jayna | 2017-08-07 | 15 | 2017-08-22 | N | 00130639
Open to Accrual - 4033CYTOKINETICS-GOUTMAN | Provisions for Support and Services Finalized | User | Duell, Jayna | 2017-08-07 | 24 |  | N | 00130639
Open to Accrual - 4033CYTOKINETICS-GOUTMAN | Study Files Established | User | Duell, Jayna | 2017-08-07 | 10 | 2017-08-17 | N | 00130639
Open to Accrual - 4033CYTOKINETICS-GOUTMAN | Study Team Roles/Responsibilities Finalized | User | Duell, Jayna | 2017-08-07 | 10 | 2017-08-17 | N | 00130639
CTSU Pre-Award v2 - 419-PIPE 2 | Created CTRF & "Notify ORSP" | User | Earwood, Rebecca | 2017-08-07 | 0 | 2017-08-07 | N | 00130583
Calendar & Budget Retrofit - 00124702 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-07 | 0 | 2017-08-07 | N | 00124702
Calendar & Budget Retrofit - 00124722 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-07 | 0 | 2017-08-07 | N | 00124722
Calendar & Budget Retrofit - 00127988 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-07 | 0 | 2017-08-07 | N | 00127988
Calendar & Budget Retrofit - 00129276 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-07 | 0 | 2017-08-07 | N | 00129276
Calendar & Budget Retrofit - 00129943 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-07 | 0 | 2017-08-07 | N | 00129943
Calendar & Budget Retrofit - 00131463 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-07 | 0 | 2017-08-07 | N | 00131463
Calendar & Budget Retrofit - 00131580 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-07 | 0 | 2017-08-07 | N | 00131580
Calendar & Budget Retrofit - 00132916 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-07 | 0 | 2017-08-07 | N | 00132916
Calendaring : Amendment Checklist & Process - 00122815 | Complete Calendar and Document Approval | User | Hodges, Lynda | 2017-08-07 | 2 | 2017-08-09 | N | 00122815
Spec Update Req. 120786 (KLV) Adding 2-WPostDose time point that was missed | Make Update(s) | User | LaVasseur, Kristen | 2017-08-07 | 2 | 2017-08-09 | N | 00120786
Spec Update Req. 120786 (KLV) Adding 2-WPostDose time point that was missed | Re-Complete Calendar | User | LaVasseur, Kristen | 2017-08-07 | 2 | 2017-08-09 | N | 00120786
Open to Accrual - 4033CYTOKINETICS-GOUTMAN | MiChart Verifications | User | Miller, Diana | 2017-08-07 | 2 | 2017-08-09 | N | 00130639
Calendaring : Initial Calendar Build - 295-ARNEDT | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa | 2017-08-07 | 15 | 2017-08-22 | N | 00130209
Calendaring : Initial Calendar Build - 350-HIGGINS | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-08-07 | 21 | 2017-08-28 | N | 00133054
Calendar & Budget Retrofit - 00122254 | Received calendar from Niyati | User | Oliver, Amy | 2017-08-07 | 0 | 2017-08-07 | N | 00122254
Calendar & Budget Retrofit - 00124920 | Received calendar from Niyati | User | Oliver, Amy | 2017-08-07 | 0 | 2017-08-07 | N | 00124920
Calendar & Budget Retrofit - 00125566 | Received calendar from Niyati | User | Oliver, Amy | 2017-08-07 | 0 | 2017-08-07 | N | 00125566
Calendar & Budget Retrofit - 00127136 | Received calendar from Niyati | User | Oliver, Amy | 2017-08-07 | 0 | 2017-08-07 | N | 00127136
Calendar & Budget Retrofit - 00127505 | Received calendar from Niyati | User | Oliver, Amy | 2017-08-07 | 0 | 2017-08-07 | N | 00127505
Calendar & Budget Retrofit - 00128325 | Received calendar from Niyati | User | Oliver, Amy | 2017-08-07 | 0 | 2017-08-07 | N | 00128325
Calendar & Budget Retrofit - 00128531 | Received calendar from Niyati | User | Oliver, Amy | 2017-08-07 | 0 | 2017-08-07 | N | 00128531
Calendar & Budget Retrofit - 00128743 | Received calendar from Niyati | User | Oliver, Amy | 2017-08-07 | 0 | 2017-08-07 | N | 00128743
Pre-Award Financial - 180-HOFF | OnCore Budget Build | User | Oliver, Amy | 2017-08-07 | 24 |  | N | 00129450
Pre-Award Financial - 46-HIGGINS | PAN Released | User | Oliver, Amy | 2017-08-07 | 24 |  | N | 46-HIGGINS
Pre-Award Financial - 56-RAO | PAN Released | User | Oliver, Amy | 2017-08-07 | 24 |  | N | 00133286
Open to Accrual - 4033CYTOKINETICS-GOUTMAN | Contract Executed | User | Rollins, Matthew | 2017-08-07 | 24 |  | N | 00130639
CTSU Pre-Award - 350-HIGGINS | Care Designations completed | User | VanderElzen, Liz | 2017-08-07 | 17 | 2017-08-24 | N | 00133054
CTSU Pre-Award - 351-HIGGINS | Care Designations completed | User | VanderElzen, Liz | 2017-08-07 | 4 | 2017-08-11 | N | 00134870
Pre-Award Financial - 179-LUGOGO | Care Designations completed | User | VanderElzen, Liz | 2017-08-07 | 17 | 2017-08-24 | N | 179-LUGOGO
Open to Accrual - 4033CYTOKINETICS-GOUTMAN | Budget Finalized | User | Watson, Donna | 2017-08-07 | 15 | 2017-08-22 | N | 00130639
CTSU Pre-Award - 359-SMITH | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-08 | 23 |  | N | 359-SMITH
Pre-Award Financial - 282-POP-BUSUI | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-08 | 23 |  | N | 00133290
Pre-Award Financial - 96-BESIRLI | Open to Accrual | Role | CTSU Administrator | 2017-08-08 | 0 | 2017-08-08 | N | 00129820
CTSU Pre-Award - 359-SMITH | Sponsor Reach out | Role | CTSU Coordinator | 2017-08-08 | 0 | 2017-08-02 | N | 359-SMITH
CTSU Pre-Award - 359-SMITH | UFA Completed | Role | CTSU Coordinator | 2017-08-08 | 0 | 2017-08-02 | N | 359-SMITH
CTSU Pre-Award v2 - 403-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-08-08 | 0 | 2017-08-08 | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-08-08 | 0 | 2017-08-08 | N | 00134896
Calendar & Budget Retrofit - 00091655 | Initiate Updates | Role | CTSU Finance | 2017-08-08 | 0 | 2017-08-07 | N | 00091655
Calendar & Budget Retrofit - 00091655 | Questions | Role | CTSU Finance | 2017-08-08 | 0 | 2017-08-08 | N | 00091655
Calendar & Budget Retrofit - 00113535 | Initiate Updates | Role | CTSU Finance | 2017-08-08 | 0 | 2017-08-07 | N | 00113535
Calendar & Budget Retrofit - 00113535 | Review & Release Calendar | Role | CTSU Finance | 2017-08-08 | 0 | 2017-08-08 | N | 00113535
Calendar Build - 8-AARONSON | Care Designations +/- finance / study-team feedback submitted to CRAO for OnCore entry | Role | CTSU Finance | 2017-08-08 | 0 | 2017-08-08 | N | 00132110
Calendaring : Specification Update Request(s) - 00091655 | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance | 2017-08-08 | 0 | 2017-08-08 | N | 00091655
Calendaring : Specification Update Request(s) - 00127913 | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance | 2017-08-08 | 0 | 2017-08-08 | N | 00127913
Calendar & Budget Retrofit - 00129276 | Initiate Updates | User | Glorioso, Michelle | 2017-08-08 | 0 | 2017-08-08 | N | 00129276
Calendar & Budget Retrofit - 00129276 | Questions | User | Glorioso, Michelle | 2017-08-08 | 1 | 2017-08-09 | N | 00129276
Calendar & Budget Retrofit - 00132916 | Initiate Updates | User | Glorioso, Michelle | 2017-08-08 | 0 | 2017-08-08 | N | 00132916
Calendar & Budget Retrofit - 00132916 | Questions | User | Glorioso, Michelle | 2017-08-08 | 0 | 2017-08-08 | N | 00132916
Calendar & Budget Retrofit - 00124702 | Initiate Updates | User | Gorowski, Teresa | 2017-08-08 | 2 | 2017-08-10 | N | 00124702
Calendar & Budget Retrofit - 00124722 | Initiate Updates | User | Gorowski, Teresa | 2017-08-08 | 0 | 2017-08-08 | N | 00124722
Calendar & Budget Retrofit - 00131463 | Initiate Updates | User | Gorowski, Teresa | 2017-08-08 | 3 | 2017-08-11 | N | 00131463
Calendaring : Initial Calendar Build - 110-SCHIOPU | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Henry, Robin | 2017-08-08 | 15 | 2017-08-23 | N | 00134444
Pre-Award Financial - 190-SCHIOPU | Final Budget | User | Henry, Robin | 2017-08-08 | 23 |  | N | 00134443
Pre-Award Financial - FONTANA-1 | Planning Meeting Completed | User | Henry, Robin | 2017-08-08 | 0 | 2017-07-27 | N | 00133153
Calendaring : Initial Calendar Build - 192-ALAM | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-08-08 | 23 |  | N | 192-ALAM
Calendaring : Initial Calendar Build - 192-ALAM | Make Updates | User | Munasinghe, Sadeepa | 2017-08-08 | 23 |  | N | 192-ALAM
Spec. Update for 118070 (KLV) per office hours discussion (8.11.17) | ** Other Request(s) | User | Munsey, Barbara | 2017-08-08 | 3 | 2017-08-11 | N | 00118070
Spec. Update for 118070 (KLV) per office hours discussion (8.11.17) | Submit Update Request(s) | User | Munsey, Barbara | 2017-08-08 | 0 | 2017-08-08 | N | 00118070
Spec. Updates for 108077 (KLV) per review @ office hours on 8.11.17 | ** Other Request(s) | User | Munsey, Barbara | 2017-08-08 | 0 | 2017-08-08 | N | 00108077
Spec. Updates for 108077 (KLV) per review @ office hours on 8.11.17 | Submit Update Request(s) | User | Munsey, Barbara | 2017-08-08 | 0 | 2017-08-08 | N | 00108077
Pre-Award Financial - 180-HOFF | Calendar Released | User | Oliver, Amy | 2017-08-08 | 23 |  | N | 00129450
Calendaring : Initial Calendar Build - CY5022 | Complete Calendar ( ie. Ready for Financials ) | User | Przykucki, Anne | 2017-08-08 | 8 | 2017-08-16 | N | 00132631
Calendaring : Initial Calendar Build - 251-COMER | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-08-08 | 3 | 2017-08-11 | N | 00134232
Pre-Award Financial - 112-FLAHERTY | Budget Negotiations | User | VanderElzen, Liz | 2017-08-08 | 15 | 2017-08-23 | N | 112-FLAHERTY
Calendar & Budget Retrofit - 00122254 | Initiate Updates | User | Yunk, Jason | 2017-08-08 | 0 | 2017-08-07 | N | 00122254
Calendar & Budget Retrofit - 00122254 | Questions | User | Yunk, Jason | 2017-08-08 | 1 | 2017-08-09 | N | 00122254
Calendar & Budget Retrofit - 00124920 | Initiate Updates | User | Yunk, Jason | 2017-08-08 | 0 | 2017-08-07 | N | 00124920
Calendar & Budget Retrofit - 00125566 | Initiate Updates | User | Yunk, Jason | 2017-08-08 | 0 | 2017-08-08 | N | 00125566
Calendar & Budget Retrofit - 00127136 | Initiate Updates | User | Yunk, Jason | 2017-08-08 | 0 | 2017-08-08 | N | 00127136
Calendar & Budget Retrofit - 00127505 | Initiate Updates | User | Yunk, Jason | 2017-08-08 | 0 | 2017-08-08 | N | 00127505
Calendar & Budget Retrofit - 00128325 | Initiate Updates | User | Yunk, Jason | 2017-08-08 | 0 | 2017-08-08 | N | 00128325
Calendar & Budget Retrofit - 00128325 | Questions | User | Yunk, Jason | 2017-08-08 | 1 | 2017-08-09 | N | 00128325
Calendar & Budget Retrofit - 00128531 | Initiate Updates | User | Yunk, Jason | 2017-08-08 | 0 | 2017-08-08 | N | 00128531
Calendar & Budget Retrofit - 00128531 | Questions | User | Yunk, Jason | 2017-08-08 | 0 | 2017-08-08 | N | 00128531
Calendar & Budget Retrofit - 00128743 | Initiate Updates | User | Yunk, Jason | 2017-08-08 | 0 | 2017-08-08 | N | 00128743
Calendaring : Initial Calendar Build - 132040 | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-08-08 | 7 | 2017-08-15 | N | 00132040
Calendaring : Initial Calendar Build - 132040 | Make Updates | User | Zahs, Brian | 2017-08-08 | 7 | 2017-08-15 | N | 00132040
Calendaring : Initial Calendar Build - 00133153 | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-08-08 | 2 | 2017-08-10 | N | 00133153
Calendaring : Initial Calendar Build - 00133153 | Make Updates | User | van Dijk, Tim | 2017-08-08 | 2 | 2017-08-10 | N | 00133153
CTSU Pre-Award v2 - 361-HASAN | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-09 | 22 |  | N | 361-HASAN
Pre-Award Financial - 00129652 | Open to Accrual | Role | CTSU Administrator | 2017-08-09 | 22 |  | N | 00129652
CTSU Pre-Award v2 - 361-HASAN | UFA Completed | Role | CTSU Coordinator | 2017-08-09 | 22 |  | N | 361-HASAN
CTSU Pre-Award v2 - 410-PAULUS | Intake Form Completed | Role | CTSU Coordinator | 2017-08-09 | 0 | 2017-08-09 | N | 410-PAULUS
CTSU Pre-Award v2 - 415-ROMANO | Internal Budget Finished | Role | CTSU Finance | 2017-08-09 | 22 |  | N | 415-ROMANO
Calendaring : Amendment Checklist & Process - 00122815 | Acknowledge | Role | CTSU Finance | 2017-08-09 | 0 | 2017-08-09 | N | 00122815
Calendaring : Initial Calendar Build - 232-GIPSON | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-08-09 | 22 |  | N | 232-GIPSON
Pre-Award Financial - 142-FLAHERTY | OnCore Budget Build | Role | CTSU Finance | 2017-08-09 | 22 |  | N | 142-FLAHERTY
Pre-Award Financial - 222-STEIGERWALT | Feasibility approved/CRAO Notified | Role | CTSU Finance | 2017-08-09 | 0 | 2017-08-09 | N | 227-STEIGERWALT
Pre-Award Financial - 298-SCHIOPU | Internal Budget Finished | Role | CTSU Finance | 2017-08-09 | 22 |  | N | 298-SCHIOPU
Spec Update Req. 120786 (KLV) Adding 2-WPostDose time point that was missed | Acknowledge | User | Fitzpatrick, Patti | 2017-08-09 | 2 | 2017-08-11 | N | 00120786
CTSU Pre-Award - 341-STOFFEL | Internal Budget Finished | User | Henry, Robin | 2017-08-09 | 0 | 2017-08-07 | N | 00134997
Spec. Updates for 121569 (KLV) : add unsched. procedures & clarify SF details | Make Update(s) | User | LaVasseur, Kristen | 2017-08-09 | 0 | 2017-08-09 | N | 00121569
Spec. Updates for 121569 (KLV) : add unsched. procedures & clarify SF details | Re-Complete Calendar | User | LaVasseur, Kristen | 2017-08-09 | 22 |  | N | 00121569
Open to Accrual - 00120786 | MiChart Verifications | User | Miller, Diana | 2017-08-09 | 0 | 2017-08-09 | N | 00120786
Calendaring : Initial Calendar Build - 350-HIGGINS | Acknowledge | User | VanderElzen, Liz | 2017-08-09 | 22 |  | N | 00133054
Open to Accrual - 00121569 2 | Budget Finalized | User | Boyd, Collin | 2017-08-10 | 21 |  | N | 00121569
CTSU Pre-Award - 348-CHEY | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-10 | 21 |  | N | 348-CHEY
Pre-Award Financial - 282-POP-BUSUI | Open to Accrual | Role | CTSU Administrator | 2017-08-10 | 21 |  | N | 00133290
CTSU Post-Award - 00127505 | Date Reconciled | Role | CTSU Finance | 2017-08-10 | 0 | 2017-08-10 | N | 00127505
CTSU Pre-Award - 313-CONJEEVARAM | Care Designations completed | Role | CTSU Finance | 2017-08-10 | 21 |  | N | 313-CONJEEVARAM
CTSU Pre-Award v2 - 364-KHAJA | Billing Calendar Received | Role | CTSU Finance | 2017-08-10 | 21 |  | N | 364-KHAJA
Calendaring : Initial Calendar Build - 00133153 | Acknowledge | Role | CTSU Finance | 2017-08-10 | 0 | 2017-08-10 | N | 00133153
Calendaring : Initial Calendar Build - 192-ALAM | Acknowledge | Role | CTSU Finance | 2017-08-10 | 21 |  | N | 192-ALAM
Calendaring : Initial Calendar Build - 358-SHELLHAAS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-08-10 | 21 |  | N | 00133339
Pre-Award Financial - 110-SCHIOPU | Planning Meeting Completed | Role | CTSU Finance | 2017-08-10 | 0 | 2017-08-08 | N | 00134444
Pre-Award Financial - 142-FLAHERTY | Calendar Released | Role | CTSU Finance | 2017-08-10 | 21 |  | N | 142-FLAHERTY
Calendaring : Initial Calendar Build - 132040 | Acknowledge | User | Frasier, Lora | 2017-08-10 | 12 | 2017-08-22 | N | 00132040
Calendaring : Specification Update Request(s) - 00127505 | Assign to Analyst | User | Greene, Paula | 2017-08-10 | 1 | 2017-08-11 | N | 00127505
Calendaring : Initial Calendar Build - 23-GUPTA | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Henry, Robin | 2017-08-10 | 14 | 2017-08-24 | N | 00134236
Pre-Award Financial - 190-SCHIOPU | PAF routed | User | Henry, Robin | 2017-08-10 | 21 |  | N | 00134443
Pre-Award Financial - 23-GUPTA | Internal Budget Finished | User | Henry, Robin | 2017-08-10 | 0 | 2017-07-21 | N | 00134236
Calendaring : Initial Calendar Build - 110-SCHIOPU | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-08-10 | 21 |  | N | 00134444
Calendaring : Initial Calendar Build - 110-SCHIOPU | Make Updates | User | Munasinghe, Sadeepa | 2017-08-10 | 21 |  | N | 00134444
Calendar & Budget Retrofit - 00127505 | Questions | User | Oliver, Amy | 2017-08-10 | 0 | 2017-08-10 | N | 00127505
Calendaring : Initial Calendar Build - CY5022 | Acknowledge | User | Rollins, Matthew | 2017-08-10 | 21 |  | N | 00132631
Pre-Award Financial - 251-COMER | Planning Meeting Completed | User | VanderElzen, Liz | 2017-08-10 | 0 | 2017-08-09 | N | 00134232
Calendaring : Specification Update Request(s) - 00127136 2 | Submit Update Request(s) | User | Yunk, Jason | 2017-08-10 | 21 |  | N | 00127136
Calendar Build - 8-AARONSON | Feedback incorporated / resolved | User | Zahs, Brian | 2017-08-10 | 11 | 2017-08-21 | N | 00132110
Calendaring : Initial Calendar Build - 251-COMER | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-08-10 | 4 | 2017-08-14 | N | 00134232
Calendaring : Initial Calendar Build - 251-COMER | Make Updates | User | Zahs, Brian | 2017-08-10 | 4 | 2017-08-14 | N | 00134232
Spec. Update for 118070 (KLV) per office hours discussion (8.11.17) | Assign to Analyst |  |  | 2017-08-10 | 0 | 2017-08-08 | N | 00118070
Spec. Updates for 108077 (KLV) per review @ office hours on 8.11.17 | Assign to Analyst |  |  | 2017-08-10 | 0 | 2017-08-08 | N | 00108077
CTSU Pre-Award v2 - 409-NASR | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-11 | 0 | 2017-08-11 | N | 409-NASR
Pre-Award Financial - 180-HOFF | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-11 | 20 |  | N | 00129450
Pre-Award Financial - 203-ELSE | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-11 | 0 | 2017-08-11 | N | 00132173
CTSU Pre-Award v2 - 415-ROMANO | Intake Form Completed | Role | CTSU Coordinator | 2017-08-11 | 0 | 2017-08-11 | N | 415-ROMANO
CTSU Pre-Award - 309-MOROI | Internal Budget Finished | Role | CTSU Finance | 2017-08-11 | 0 | 2017-07-20 | N | 309-MOROI
Calendar & Budget Retrofit - 00091655 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-11 | 0 | 2017-08-09 | N | 00091655
Calendar & Budget Retrofit - 00091655 | Review & Release Calendar | Role | CTSU Finance | 2017-08-11 | 0 | 2017-08-09 | N | 00091655
Calendar & Budget Retrofit - 00113535 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-11 | 0 | 2017-08-09 | N | 00113535
Calendar & Budget Retrofit - 00120231 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-11 | 0 | 2017-08-09 | N | 00120231
Calendar & Budget Retrofit - 00120231 | Review & Release Calendar | Role | CTSU Finance | 2017-08-11 | 0 | 2017-08-09 | N | 00120231
Calendar & Budget Retrofit - 00127913 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-11 | 0 | 2017-08-09 | N | 00127913
Calendar & Budget Retrofit - 00127913 | Review & Release Calendar | Role | CTSU Finance | 2017-08-11 | 0 | 2017-08-08 | N | 00127913
Pre-Award Financial - 246-AS-SANIE | Final Budget | Role | CTSU Finance | 2017-08-11 | 20 |  | N | 246-AS-SANIE
Calendar & Budget Retrofit - 00124702 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-11 | 0 | 2017-08-11 | N | 00124702
Calendar & Budget Retrofit - 00124722 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-11 | 0 | 2017-08-11 | N | 00124722
Calendar & Budget Retrofit - 00127988 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-11 | 0 | 2017-08-11 | N | 00127988
Calendar & Budget Retrofit - 00129276 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-11 | 0 | 2017-08-11 | N | 00129276
Calendar & Budget Retrofit - 00129943 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-11 | 0 | 2017-08-11 | N | 00129943
Calendar & Budget Retrofit - 00131463 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-11 | 0 | 2017-08-11 | N | 00131463
Calendar & Budget Retrofit - 00131580 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-11 | 0 | 2017-08-11 | N | 00131580
Calendar & Budget Retrofit - 00132916 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-11 | 0 | 2017-08-11 | N | 00132916
Calendar & Budget Retrofit - 00129276 | Review & Release Calendar | User | Glorioso, Michelle | 2017-08-11 | 0 | 2017-08-11 | N | 00129276
Calendar & Budget Retrofit - 00132916 | Review & Release Calendar | User | Glorioso, Michelle | 2017-08-11 | 0 | 2017-08-09 | N | 00132916
Calendar & Budget Retrofit - 00124702 | Review & Release Calendar | User | Gorowski, Teresa | 2017-08-11 | 0 | 2017-08-10 | N | 00124702
Calendar & Budget Retrofit - 00124722 | Review & Release Calendar | User | Gorowski, Teresa | 2017-08-11 | 0 | 2017-08-08 | N | 00124722
Calendar & Budget Retrofit - 00131463 | Review & Release Calendar | User | Gorowski, Teresa | 2017-08-11 | 0 | 2017-08-11 | N | 00131463
Calendaring : Initial Calendar Build - 409-NASR | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-11 | 0 | 2017-08-11 | N | 409-NASR
Calendaring : Initial Calendar Build - 409-NASR | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-11 | 0 | 2017-08-11 | N | 409-NASR
Pre-Award Financial - 147-SCHIOPU | OnCore Budget Build | User | Henry, Robin | 2017-08-11 | 20 |  | N | 00131329
Pre-Award Financial - 170-SCHIOPU | OnCore Budget Build | User | Henry, Robin | 2017-08-11 | 20 |  | N | 00134035
Pre-Award Financial - 86-AUCHUS | Billing Calendar Received | User | Henry, Robin | 2017-08-11 | 0 | 2017-08-10 | N | 00132700
Pre-Award Financial - FONTANA-1 | Care Designations completed | User | Henry, Robin | 2017-08-11 | 0 | 2017-08-08 | N | 00133153
Calendaring : Initial Calendar Build - 351-HIGGINS | Complete Calendar ( ie. Ready for Financials ) | User | Hodges, Lynda | 2017-08-11 | 3 | 2017-08-14 | N | 00134870
131463 Spec Update Request(s) - simplify labs & add unscheduled procedures | ** Other Request(s) | User | LaVasseur, Kristen | 2017-08-11 | 0 | 2017-08-11 | N | 00131463
131463 Spec Update Request(s) - simplify labs & add unscheduled procedures | ** Request(s) to Add Unscheduled Procedure(s) | User | LaVasseur, Kristen | 2017-08-11 | 0 | 2017-08-11 | N | 00131463
131463 Spec Update Request(s) - simplify labs & add unscheduled procedures | Submit Update Request(s) | User | LaVasseur, Kristen | 2017-08-11 | 0 | 2017-08-11 | N | 00131463
Calendar & Budget Retrofit - 00124920 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-11 | 0 | 2017-08-10 | N | 00124920
Calendar & Budget Retrofit - 00124920 | Review & Release Calendar | User | Oliver, Amy | 2017-08-11 | 0 | 2017-08-10 | N | 00124920
Calendar & Budget Retrofit - 00125566 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-11 | 0 | 2017-08-10 | N | 00125566
Calendar & Budget Retrofit - 00125566 | Review & Release Calendar | User | Oliver, Amy | 2017-08-11 | 0 | 2017-08-10 | N | 00125566
Calendar & Budget Retrofit - 00127136 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-11 | 0 | 2017-08-10 | N | 00127136
Calendar & Budget Retrofit - 00127136 | Review & Release Calendar | User | Oliver, Amy | 2017-08-11 | 0 | 2017-08-10 | N | 00127136
Calendar & Budget Retrofit - 00127505 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-11 | 0 | 2017-08-10 | N | 00127505
Calendar & Budget Retrofit - 00127505 | Review & Release Calendar | User | Oliver, Amy | 2017-08-11 | 0 | 2017-08-10 | N | 00127505
Calendar & Budget Retrofit - 00128325 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-11 | 0 | 2017-08-10 | N | 00128325
Calendar & Budget Retrofit - 00128325 | Review & Release Calendar | User | Oliver, Amy | 2017-08-11 | 0 | 2017-08-10 | N | 00128325
Calendar & Budget Retrofit - 00128531 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-11 | 0 | 2017-08-10 | N | 00128531
Calendar & Budget Retrofit - 00128531 | Review & Release Calendar | User | Oliver, Amy | 2017-08-11 | 0 | 2017-08-10 | N | 00128531
Calendar & Budget Retrofit - 00128743 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-11 | 0 | 2017-08-10 | N | 00128743
Calendar & Budget Retrofit - 00128743 | Review & Release Calendar | User | Oliver, Amy | 2017-08-11 | 0 | 2017-08-10 | N | 00128743
Pre-Award Financial - 96-BESIRLI | PAN Released | User | Oliver, Amy | 2017-08-11 | 0 | 2017-06-30 | N | 00129820
Open to Accrual - 4033CYTOKINETICS-GOUTMAN | Project Award Notice (PAN) Received | User | Rollins, Matthew | 2017-08-11 | 20 |  | N | 00130639
CTSU Pre-Award - 337-MIAN | Billing Calendar Received | User | VanderElzen, Liz | 2017-08-11 | 0 | 2017-08-09 | N | 337-MIAN
CTSU Pre-Award - 338-MIAN | Billing Calendar Received | User | VanderElzen, Liz | 2017-08-11 | 0 | 2017-08-07 | N | 00133457
CTSU Pre-Award - 350-HIGGINS | Internal Budget Finished | User | VanderElzen, Liz | 2017-08-11 | 10 | 2017-08-21 | N | 00133054
CTSU Pre-Award - 351-HIGGINS | Internal Budget Finished | User | VanderElzen, Liz | 2017-08-11 | 6 | 2017-08-17 | N | 00134870
Pre-Award Financial - 179-LUGOGO | Internal Budget Finished | User | VanderElzen, Liz | 2017-08-11 | 20 |  | N | 179-LUGOGO
Pre-Award Financial - 235-SUGAR | Initiate Post-Award Task List | User | VanderElzen, Liz | 2017-08-11 | 20 |  | N | 235-SUGAR
Pre-Award Financial - 235-SUGAR | PAN Released | User | VanderElzen, Liz | 2017-08-11 | 20 |  | N | 235-SUGAR
Calendar Build - 8-AARONSON | Care designations entered ( per PI determinations) | User | Zahs, Brian | 2017-08-11 | 13 | 2017-08-24 | N | 00132110
Calendaring : Initial Calendar Build - 232-GIPSON | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-08-11 | 20 |  | N | 232-GIPSON
Calendaring : Initial Calendar Build - 232-GIPSON | Make Updates | User | Zahs, Brian | 2017-08-11 | 20 |  | N | 232-GIPSON
Spec. Updates for 121569 (KLV) : add unsched. procedures & clarify SF details | Acknowledge |  |  | 2017-08-11 | 20 |  | N | 00121569
CTSU Pre-Award - 348-CHEY | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-12 | 19 |  | N | 348-CHEY
CTSU Pre-Award - 332-BELLOLI | Billing Calendar Received | Role | CTSU Finance | 2017-08-12 | 19 |  | N | 332-BELLOLI
CTSU Pre-Award - 348-CHEY | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-12 | 19 |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Request MCRU Budget | Role | CTSU Finance | 2017-08-12 | 19 |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-12 | 19 |  | N | 348-CHEY
CTSU Pre-Award v2 - 415-ROMANO | PI approved Budget | Role | CTSU Finance | 2017-08-12 | 19 |  | N | 415-ROMANO
Calendaring : Initial Calendar Build - 110-SCHIOPU | Acknowledge | Role | CTSU Finance | 2017-08-12 | 19 |  | N | 00134444
Pre-Award Financial - 298-SCHIOPU | PI approved Budget | Role | CTSU Finance | 2017-08-12 | 19 |  | N | 298-SCHIOPU
CTSU Pre-Award - 341-STOFFEL | PI approved Budget | User | Henry, Robin | 2017-08-12 | 9 | 2017-08-21 | N | 00134997
Pre-Award Financial - 278-CONJEEVARAM | Final Budget | User | Henry, Robin | 2017-08-12 | 9 | 2017-08-21 | N | 00133341
Calendaring : Initial Calendar Build - 358-SHELLHAAS | Complete Calendar ( ie. Ready for Financials ) | User | Hodges, Lynda | 2017-08-12 | 19 |  | N | 00133339
Calendaring : Initial Calendar Build - 358-SHELLHAAS | Make Updates | User | Hodges, Lynda | 2017-08-12 | 19 |  | N | 00133339
Calendaring : Specification Update Request(s) - 00127136 2 | Assign to Analyst | User | Munasinghe, Sadeepa | 2017-08-12 | 19 |  | N | 00127136
Pre-Award Financial - 147-SCHIOPU | Calendar Released | User | Oliver, Amy | 2017-08-12 | 19 |  | N | 00131329
Pre-Award Financial - 170-SCHIOPU | Calendar Released | User | Oliver, Amy | 2017-08-12 | 19 |  | N | 00134035
Calendaring : Initial Calendar Build - 251-COMER | Acknowledge | User | VanderElzen, Liz | 2017-08-12 | 11 | 2017-08-23 | N | 00134232
Pre-Award Financial - 96-BESIRLI | OnCore Budget Build | User | Yunk, Jason | 2017-08-12 | 0 | 2017-06-06 | N | 00129820
Pre-Award Financial - 142-FLAHERTY | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-13 | 18 |  | N | 142-FLAHERTY
Pre-Award Financial - 180-HOFF | Open to Accrual | Role | CTSU Administrator | 2017-08-13 | 18 |  | N | 00129450
CTSU Pre-Award v2 - 409-NASR | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-13 | 7 | 2017-08-20 | N | 409-NASR
CTSU Pre-Award v2 - 409-NASR | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-13 | 2 | 2017-08-15 | N | 409-NASR
CTSU Pre-Award v2 - 409-NASR | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-13 | 18 |  | N | 409-NASR
Calendaring : Initial Calendar Build - 232-GIPSON | Acknowledge | Role | CTSU Finance | 2017-08-13 | 18 |  | N | 232-GIPSON
Pre-Award Financial - 246-AS-SANIE | PAF routed | Role | CTSU Finance | 2017-08-13 | 18 |  | N | 246-AS-SANIE
Calendaring : Initial Calendar Build - 00132700 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Henry, Robin | 2017-08-13 | 4 | 2017-08-17 | N | 00132700
Pre-Award Financial - 110-SCHIOPU | Care Designations completed | User | Henry, Robin | 2017-08-13 | 10 | 2017-08-23 | N | 00134444
Pre-Award Financial - 23-GUPTA | PI approved Budget | User | Henry, Robin | 2017-08-13 | 0 | 2017-08-03 | N | 00134236
131463 Spec Update Request(s) - simplify labs & add unscheduled procedures | Assign to Analyst | User | LaVasseur, Kristen | 2017-08-13 | 0 | 2017-08-11 | N | 00131463
Calendaring : Initial Calendar Build - 337-MIAN | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-08-13 | 15 | 2017-08-28 | N | 337-MIAN
Calendaring : Initial Calendar Build - 338-MIAN | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-08-13 | 15 | 2017-08-28 | N | 00133457
Calendaring : Initial Calendar Build - 351-HIGGINS | Acknowledge | User | VanderElzen, Liz | 2017-08-13 | 2 | 2017-08-15 | N | 00134870
Pre-Award Financial - 251-COMER | Care Designations completed | User | VanderElzen, Liz | 2017-08-13 | 0 | 2017-08-11 | N | 00134232
Calendar Build - 8-AARONSON | CRAO Approval issued / documented | User | Zahs, Brian | 2017-08-13 | 11 | 2017-08-24 | N | 00132110
CTSU Pre-Award v2 - 364-KHAJA | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-14 | 17 |  | N | 364-KHAJA
CTSU Pre-Award - 309-MOROI | PI approved Budget | Role | CTSU Finance | 2017-08-14 | 0 | 2017-07-20 | N | 309-MOROI
CTSU Pre-Award - 313-CONJEEVARAM | Internal Budget Finished | Role | CTSU Finance | 2017-08-14 | 17 |  | N | 313-CONJEEVARAM
CTSU Pre-Award - 363-PARK | Sponsor Reach out | Role | CTSU Finance | 2017-08-14 | 17 |  | N | 363-PARK
CTSU Pre-Award v2 - 364-KHAJA | Planning Meeting Completed | Role | CTSU Finance | 2017-08-14 | 17 |  | N | 364-KHAJA
CTSU Pre-Award v2 - 415-ROMANO | Budget Negotiations | Role | CTSU Finance | 2017-08-14 | 17 |  | N | 415-ROMANO
Calendar & Budget Retrofit - 00113034 | Initiate Updates | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00113034
Calendar & Budget Retrofit - 00113034 | Questions | Role | CTSU Finance | 2017-08-14 | 17 |  | N | 00113034
Calendar & Budget Retrofit - 00113034 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00113034
Calendar & Budget Retrofit - 00113560 | Questions | Role | CTSU Finance | 2017-08-14 | 1 | 2017-08-15 | N | 00113560
Calendar & Budget Retrofit - 00113560 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00113560
Calendar & Budget Retrofit - 00121246 | Initiate Updates | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00121246
Calendar & Budget Retrofit - 00121246 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00121246
Calendar & Budget Retrofit - 00126224 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00126224
Calendar & Budget Retrofit - 00126707 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00126707
Calendar & Budget Retrofit - 00128253 | Initiate Updates | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00128253
Calendar & Budget Retrofit - 00128253 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00128253
Calendar & Budget Retrofit - 00129652 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00129652
Calendar & Budget Retrofit - 00129716 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00129716
Calendar & Budget Retrofit - 00129820 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00129820
Calendar & Budget Retrofit - 00130575 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00130575
Calendar & Budget Retrofit - 00131837 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00131837
Calendar & Budget Retrofit - 00131953 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00131953
Calendar & Budget Retrofit - 00133290 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00133290
Calendar & Budget Retrofit - PLT-INF24-001 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-14 | 0 | 2017-08-14 | N | 00135388
Calendar Build - 8-AARONSON | Calendar Completed and Ready for CTSU Finance to Build Budget | Role | CTSU Finance | 2017-08-14 | 17 |  | N | 00132110
Calendaring : Initial Calendar Build - 358-SHELLHAAS | Acknowledge | Role | CTSU Finance | 2017-08-14 | 17 |  | N | 00133339
Pre-Award Financial - 255-LOK | Final Budget | Role | CTSU Finance | 2017-08-14 | 17 |  | N | 255-LOK
Pre-Award Financial - 298-SCHIOPU | Budget Negotiations | Role | CTSU Finance | 2017-08-14 | 17 |  | N | 298-SCHIOPU
Calendar & Budget Retrofit - 00091711 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-14 | 0 | 2017-08-14 | N | 00091711
Calendar & Budget Retrofit - 00098540 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-14 | 0 | 2017-08-14 | N | 00098540
Calendar & Budget Retrofit - 00123094 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-14 | 0 | 2017-08-14 | N | 00123094
Calendar & Budget Retrofit - 00129846 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-14 | 0 | 2017-08-14 | N | 00129846
Calendar & Budget Retrofit - 00130272 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-14 | 0 | 2017-08-14 | N | 00130272
Calendar & Budget Retrofit - 00131311 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-14 | 0 | 2017-08-14 | N | 00131311
Calendar & Budget Retrofit - 00131320 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-14 | 0 | 2017-08-14 | N | 00131320
Calendar & Budget Retrofit - 00133542 | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-14 | 0 | 2017-08-14 | N | 00133542
Calendar & Budget Retrofit - 6-TAYLOR | Received calendar from Niyati | User | Gladkowski, Ginger | 2017-08-14 | 0 | 2017-08-14 | N | 00132251
Calendaring : Initial Calendar Build - 409-NASR | Assign to Analyst | User | Greene, Paula | 2017-08-14 | 0 | 2017-08-14 | N | 409-NASR
CTSU Pre-Award - 341-STOFFEL | Budget Negotiations | User | Henry, Robin | 2017-08-14 | 7 | 2017-08-21 | N | 00134997
Pre-Award Financial - 278-CONJEEVARAM | PAF routed | User | Henry, Robin | 2017-08-14 | 7 | 2017-08-21 | N | 00133341
CTSU Pre-Award - 350-HIGGINS | PI approved Budget | User | VanderElzen, Liz | 2017-08-14 | 9 | 2017-08-23 | N | 00133054
CTSU Pre-Award - 351-HIGGINS | PI approved Budget | User | VanderElzen, Liz | 2017-08-14 | 10 | 2017-08-24 | N | 00134870
Pre-Award Financial - 179-LUGOGO | PI approved Budget | User | VanderElzen, Liz | 2017-08-14 | 17 |  | N | 179-LUGOGO
Pre-Award Financial - 70-LUGOGO | OnCore Budget Build | User | Yunk, Jason | 2017-08-14 | 17 |  | N | 70-LUGOGO
Calendaring : Initial Calendar Build - 409-NASR | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-08-14 | 7 | 2017-08-21 | N | 409-NASR
CTSU Pre-Award - 359-SMITH | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-15 | 16 |  | N | 359-SMITH
CTSU Pre-Award - 370-LOK | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-15 | 16 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-15 | 16 |  | N | 371-LOK
Pre-Award Financial - 142-FLAHERTY | Open to Accrual | Role | CTSU Administrator | 2017-08-15 | 16 |  | N | 142-FLAHERTY
Pre-Award Financial - 147-SCHIOPU | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-15 | 16 |  | N | 00131329
Pre-Award Financial - 170-SCHIOPU | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-15 | 16 |  | N | 00134035
CTSU Pre-Award - 337-MIAN | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-15 | 16 |  | N | 337-MIAN
CTSU Pre-Award - 338-MIAN | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-15 | 16 |  | N | 00133457
CTSU Pre-Award - 370-LOK | Sponsor Reach out | Role | CTSU Coordinator | 2017-08-15 | 0 | 2017-08-02 | N | 370-LOK
CTSU Pre-Award - 370-LOK | UFA Completed | Role | CTSU Coordinator | 2017-08-15 | 0 | 2017-08-01 | N | 370-LOK
CTSU Pre-Award - 371-LOK | Sponsor Reach out | Role | CTSU Coordinator | 2017-08-15 | 0 | 2017-08-02 | N | 371-LOK
CTSU Pre-Award - 371-LOK | UFA Completed | Role | CTSU Coordinator | 2017-08-15 | 0 | 2017-08-02 | N | 371-LOK
Calendar & Budget Retrofit - 00098540 | Initiate Updates | Role | CTSU Finance | 2017-08-15 | 16 |  | N | 00098540
Calendar & Budget Retrofit - 00113560 | Initiate Updates | Role | CTSU Finance | 2017-08-15 | 0 | 2017-08-14 | N | 00113560
Calendar & Budget Retrofit - 00123094 | Initiate Updates | Role | CTSU Finance | 2017-08-15 | 16 |  | N | 00123094
Calendar & Budget Retrofit - 00123094 | Questions | Role | CTSU Finance | 2017-08-15 | 16 |  | N | 00123094
Calendar & Budget Retrofit - 00126707 | Initiate Updates | Role | CTSU Finance | 2017-08-15 | 0 | 2017-08-14 | N | 00126707
Calendar & Budget Retrofit - 00126707 | Questions | Role | CTSU Finance | 2017-08-15 | 0 | 2017-08-14 | N | 00126707
Calendar & Budget Retrofit - 00128253 | Questions | Role | CTSU Finance | 2017-08-15 | 0 | 2017-08-15 | N | 00128253
Calendar & Budget Retrofit - 00130272 | Initiate Updates | Role | CTSU Finance | 2017-08-15 | 0 | 2017-08-14 | N | 00130272
Calendar & Budget Retrofit - 6-TAYLOR | Initiate Updates | Role | CTSU Finance | 2017-08-15 | 1 | 2017-08-16 | N | 00132251
Calendaring : Amendment Checklist & Process - 00132251 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-08-15 | 0 | 2017-08-15 | N | 00132251
Calendar & Budget Retrofit - 00129846 | Initiate Updates | User | Glorioso, Michelle | 2017-08-15 | 0 | 2017-08-14 | N | 00129846
Calendar & Budget Retrofit - 00129846 | Questions | User | Glorioso, Michelle | 2017-08-15 | 0 | 2017-08-14 | N | 00129846
Calendar & Budget Retrofit - 00131311 | Initiate Updates | User | Glorioso, Michelle | 2017-08-15 | 0 | 2017-08-14 | N | 00131311
Calendar & Budget Retrofit - 00131311 | Questions | User | Glorioso, Michelle | 2017-08-15 | 0 | 2017-08-14 | N | 00131311
Pre-Award Financial - 23-GUPTA | Budget Negotiations | User | Henry, Robin | 2017-08-15 | 0 | 2017-08-03 | N | 00134236
Pre-Award Financial - 86-AUCHUS | Planning Meeting Completed | User | Henry, Robin | 2017-08-15 | 0 | 2017-08-07 | N | 00132700
Pre-Award Financial - FONTANA-1 | Internal Budget Finished | User | Henry, Robin | 2017-08-15 | 0 | 2017-08-08 | N | 00133153
Spec. Update for 118070 (KLV) per office hours discussion (8.11.17) | Make Update(s) | User | LaVasseur, Kristen | 2017-08-15 | 0 | 2017-08-11 | N | 00118070
Spec. Update for 118070 (KLV) per office hours discussion (8.11.17) | Re-Complete Calendar | User | LaVasseur, Kristen | 2017-08-15 | 0 | 2017-08-11 | N | 00118070
Spec. Updates for 108077 (KLV) per review @ office hours on 8.11.17 | Make Update(s) | User | LaVasseur, Kristen | 2017-08-15 | 0 | 2017-08-11 | N | 00108077
Spec. Updates for 108077 (KLV) per review @ office hours on 8.11.17 | Re-Complete Calendar | User | LaVasseur, Kristen | 2017-08-15 | 0 | 2017-08-11 | N | 00108077
Pre-Award Financial - 70-LUGOGO | Calendar Released | User | Oliver, Amy | 2017-08-15 | 16 |  | N | 70-LUGOGO
Pre-Award Financial - 96-BESIRLI | Calendar Released | User | Oliver, Amy | 2017-08-15 | 0 | 2017-07-06 | N | 00129820
CTSU Pre-Award - 337-MIAN | Planning Meeting Completed | User | VanderElzen, Liz | 2017-08-15 | 0 | 2017-08-14 | N | 337-MIAN
CTSU Pre-Award - 338-MIAN | Planning Meeting Completed | User | VanderElzen, Liz | 2017-08-15 | 0 | 2017-08-14 | N | 00133457
Calendar & Budget Retrofit - 00129652 | Initiate Updates | User | Yunk, Jason | 2017-08-15 | 1 | 2017-08-16 | N | 00129652
Calendar & Budget Retrofit - 00129716 | Initiate Updates | User | Yunk, Jason | 2017-08-15 | 1 | 2017-08-16 | N | 00129716
Calendar & Budget Retrofit - 00129820 | Initiate Updates | User | Yunk, Jason | 2017-08-15 | 1 | 2017-08-16 | N | 00129820
Calendar & Budget Retrofit - 00130575 | Initiate Updates | User | Yunk, Jason | 2017-08-15 | 1 | 2017-08-16 | N | 00130575
Calendar & Budget Retrofit - 00131837 | Initiate Updates | User | Yunk, Jason | 2017-08-15 | 2 | 2017-08-17 | N | 00131837
Calendar & Budget Retrofit - 00131953 | Initiate Updates | User | Yunk, Jason | 2017-08-15 | 3 | 2017-08-18 | N | 00131953
Calendar & Budget Retrofit - 00133290 | Initiate Updates | User | Yunk, Jason | 2017-08-15 | 1 | 2017-08-16 | N | 00133290
Calendar & Budget Retrofit - PLT-INF24-001 | Initiate Updates | User | Yunk, Jason | 2017-08-15 | 1 | 2017-08-16 | N | 00135388
Pre-Award Financial - 278-CONJEEVARAM | OnCore Budget Build | User | Yunk, Jason | 2017-08-15 | 16 |  | N | 00133341
Pre-Award Financial - 49-MARTINEZ | OnCore Budget Build | User | Yunk, Jason | 2017-08-15 | 16 |  | N | 00132020
Calendaring : Initial Calendar Build - 00132700 | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-08-15 | 16 |  | N | 00132700
Calendaring : Initial Calendar Build - 00132700 | Make Updates | User | Zahs, Brian | 2017-08-15 | 16 |  | N | 00132700
Calendaring : Initial Calendar Build - 337-MIAN | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-08-15 | 16 |  | N | 337-MIAN
Calendaring : Initial Calendar Build - 337-MIAN | Make Updates | User | van Dijk, Tim | 2017-08-15 | 15 | 2017-08-30 | N | 337-MIAN
Calendaring : Initial Calendar Build - 338-MIAN | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-08-15 | 16 |  | N | 00133457
Calendaring : Initial Calendar Build - 338-MIAN | Make Updates | User | van Dijk, Tim | 2017-08-15 | 15 | 2017-08-30 | N | 00133457
CTSU Pre-Award v2 - 361-HASAN | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-16 | 15 |  | N | 361-HASAN
Calendar & Budget Retrofit - 00129583 | Initiate Updates | Role | CTSU Finance | 2017-08-16 | 0 | 2017-08-16 | N | 00129583
Pre-Award Financial - 255-LOK | PAF routed | Role | CTSU Finance | 2017-08-16 | 15 |  | N | 255-LOK
Pre-Award Financial - 278-CONJEEVARAM | Calendar Released | User | Oliver, Amy | 2017-08-16 | 15 |  | N | 00133341
Pre-Award Financial - 49-MARTINEZ | Calendar Released | User | Oliver, Amy | 2017-08-16 | 15 |  | N | 00132020
CTSU Pre-Award - 350-HIGGINS | Budget Negotiations | User | VanderElzen, Liz | 2017-08-16 | 14 | 2017-08-30 | N | 00133054
CTSU Pre-Award - 351-HIGGINS | Budget Negotiations | User | VanderElzen, Liz | 2017-08-16 | 14 | 2017-08-30 | N | 00134870
Pre-Award Financial - 179-LUGOGO | Budget Negotiations | User | VanderElzen, Liz | 2017-08-16 | 15 |  | N | 179-LUGOGO
Calendaring : Initial Calendar Build - 409-NASR | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-08-16 | 5 | 2017-08-21 | N | 409-NASR
Calendaring : Initial Calendar Build - 409-NASR | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-08-16 | 7 | 2017-08-23 | N | 409-NASR
Open to Accrual - 00121569 2 | Study Files Established | User | Brand, Sarah | 2017-08-17 | 0 | 2017-08-01 | N | 00121569
CTSU Pre-Award v2 - 403-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-17 | 0 | 2017-08-17 | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-17 | 0 | 2017-08-17 | N | 00134896
Pre-Award Financial - 11-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-17 | 0 | 2017-08-17 | N | 00134884
Pre-Award Financial - 147-SCHIOPU | Open to Accrual | Role | CTSU Administrator | 2017-08-17 | 14 |  | N | 00131329
Pre-Award Financial - 170-SCHIOPU | Open to Accrual | Role | CTSU Administrator | 2017-08-17 | 14 |  | N | 00134035
Pre-Award Financial - 96-BESIRLI | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-17 | 0 | 2017-08-08 | N | 00129820
CTSU Pre-Award - 359-SMITH | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-17 | 14 |  | N | 359-SMITH
CTSU Pre-Award v2 - 428-LAW | Intake Form Completed | Role | CTSU Coordinator | 2017-08-17 | 0 | 2017-08-17 | N | 00135072
CTSU Pre-Award - 313-CONJEEVARAM | PI approved Budget | Role | CTSU Finance | 2017-08-17 | 14 |  | N | 313-CONJEEVARAM
CTSU Pre-Award v2 - 364-KHAJA | Care Designations completed | Role | CTSU Finance | 2017-08-17 | 14 |  | N | 364-KHAJA
Calendar & Budget Retrofit - 00121246 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-17 | 1 | 2017-08-18 | N | 00121246
Calendar & Budget Retrofit - 00121246 | Review & Release Calendar | Role | CTSU Finance | 2017-08-17 | 0 | 2017-08-17 | N | 00121246
Calendar & Budget Retrofit - 00125425 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-17 | 0 | 2017-08-17 | N | 00125425
Calendar & Budget Retrofit - 00126707 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-17 | 1 | 2017-08-18 | N | 00126707
Calendar & Budget Retrofit - 00126707 | Review & Release Calendar | Role | CTSU Finance | 2017-08-17 | 0 | 2017-08-17 | N | 00126707
Calendar & Budget Retrofit - 00132020 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-17 | 0 | 2017-08-17 | N | 00132020
Calendaring : Initial Calendar Build - 00132700 | Acknowledge | Role | CTSU Finance | 2017-08-17 | 14 |  | N | 00132700
Calendaring : Initial Calendar Build - 227-STEIGERWALT 3 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-08-17 | 14 |  | N | 227-STEIGERWALT
Pre-Award Financial - 282-POP-BUSUI | Initiate Post-Award Task List | Role | CTSU Finance | 2017-08-17 | 14 |  | N | 00133290
Spec. Update for 118070 (KLV) per office hours discussion (8.11.17) | Acknowledge | Role | CTSU Finance | 2017-08-17 | 0 | 2017-08-11 | N | 00118070
Spec. Updates for 108077 (KLV) per review @ office hours on 8.11.17 | Acknowledge | Role | CTSU Finance | 2017-08-17 | 0 | 2017-08-11 | N | 00108077
Pre-Award Financial - 222-STEIGERWALT | Request Research Pharmacy Budget | User | Cohan, Lynn | 2017-08-17 | 0 | 2017-08-17 | N | 227-STEIGERWALT
Calendar & Budget Retrofit - 00129583 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-17 | 1 | 2017-08-18 | N | 00129583
Calendar & Budget Retrofit - 00129583 | Review & Release Calendar | User | Gladkowski, Ginger | 2017-08-17 | 0 | 2017-08-17 | N | 00129583
Calendaring : Initial Calendar Build - 00134884 | Assign to Analyst | User | Greene, Paula | 2017-08-17 | 1 | 2017-08-18 | N | 00134884
Calendaring : Initial Calendar Build - 00134884 | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-17 | 1 | 2017-08-18 | N | 00134884
Calendaring : Initial Calendar Build - 00134884 | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-17 | 1 | 2017-08-18 | N | 00134884
Calendaring : Initial Calendar Build - 403-HIGGINS | Assign to Analyst | User | Greene, Paula | 2017-08-17 | 1 | 2017-08-18 | N | 00134895
Calendaring : Initial Calendar Build - 403-HIGGINS | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-17 | 1 | 2017-08-18 | N | 00134895
Calendaring : Initial Calendar Build - 403-HIGGINS | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-17 | 1 | 2017-08-18 | N | 00134895
Calendaring : Initial Calendar Build - 404-HIGGINS | Assign to Analyst | User | Greene, Paula | 2017-08-17 | 1 | 2017-08-18 | N | 00134896
Calendaring : Initial Calendar Build - 404-HIGGINS | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-17 | 1 | 2017-08-18 | N | 00134896
Calendaring : Initial Calendar Build - 404-HIGGINS | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-17 | 1 | 2017-08-18 | N | 00134896
Pre-Award Financial - 110-SCHIOPU | Internal Budget Finished | User | Henry, Robin | 2017-08-17 | 0 | 2017-08-14 | N | 00134444
Calendaring : Specification Update Request(s) - 00127136 2 | Make Update(s) | User | Munasinghe, Sadeepa | 2017-08-17 | 14 |  | N | 00127136
Calendaring : Specification Update Request(s) - 00127136 2 | Re-Complete Calendar | User | Munasinghe, Sadeepa | 2017-08-17 | 14 |  | N | 00127136
Pre-Award Financial - 155-ORAL | PAN Released | User | Oliver, Amy | 2017-08-17 | 14 |  | N | 00130803
Pre-Award Financial - 282-POP-BUSUI | PAN Released | User | Oliver, Amy | 2017-08-17 | 14 |  | N | 00133290
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | ** Request(s) to Add Unscheduled Procedure(s) | User | Oliver, Amy | 2017-08-17 | 1 | 2017-08-18 | N | 00133290
CTSU Pre-Award - 359-SMITH | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-08-17 | 14 |  | N | 359-SMITH
CTSU Pre-Award - 359-SMITH | Request MCRU Budget | User | VanderElzen, Liz | 2017-08-17 | 14 |  | N | 359-SMITH
CTSU Pre-Award - 359-SMITH | Request Research Pharmacy Budget | User | VanderElzen, Liz | 2017-08-17 | 14 |  | N | 359-SMITH
Calendaring : Initial Calendar Build - 337-MIAN | Acknowledge | User | VanderElzen, Liz | 2017-08-17 | 14 |  | N | 337-MIAN
Calendaring : Initial Calendar Build - 338-MIAN | Acknowledge | User | VanderElzen, Liz | 2017-08-17 | 14 |  | N | 00133457
Pre-Award Financial - 251-COMER | Internal Budget Finished | User | VanderElzen, Liz | 2017-08-17 | 0 | 2017-08-10 | N | 00134232
Pre-Award Financial - 211-HIGGINS | OnCore Budget Build | User | Yunk, Jason | 2017-08-17 | 14 |  | N | 00128325
Calendaring : Amendment Checklist & Process - 00132251 | Assign to Analyst | User | Zahs, Brian | 2017-08-17 | 0 | 2017-08-15 | N | 00132251
Open to Accrual - 00121569 2 | Adequate Equipment and Supplies Available | User | Ziolkowski, Jaimie | 2017-08-17 | 0 | 2017-07-31 | N | 00121569
Open to Accrual - 00121569 2 | Provisions for Support and Services Finalized | User | Ziolkowski, Jaimie | 2017-08-17 | 0 | 2017-07-31 | N | 00121569
Open to Accrual - 00121569 2 | Study Team Roles/Responsibilities Finalized | User | Ziolkowski, Jaimie | 2017-08-17 | 0 | 2017-07-31 | N | 00121569
Calendaring : Initial Calendar Build - 162-PIPE | CRAO Approval Issue & Documented | User | van Dijk, Tim | 2017-08-17 | 0 | 2017-08-17 | N | 00131320
Calendaring : Initial Calendar Build - 409-NASR | Complete MCA / QCT | User | van Dijk, Tim | 2017-08-17 | 0 | 2017-08-15 | N | 409-NASR
Calendaring : Initial Calendar Build - 409-NASR | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-08-17 | 0 | 2017-08-15 | N | 409-NASR
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | Submit Update Request(s) |  |  | 2017-08-17 | 1 | 2017-08-18 | N | 00133290
CTSU Pre-Award v2 - 140-CHUNG | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-18 | 0 | 2017-08-18 | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-18 | 0 | 2017-08-18 | N | 00131840
Pre-Award Financial - 203-ELSE | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-18 | 0 | 2017-08-18 | N | 00132173
Pre-Award Financial - 70-LUGOGO | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-18 | 13 |  | N | 70-LUGOGO
CTSU Pre-Award - 332-BELLOLI | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-18 | 13 |  | N | 332-BELLOLI
CTSU Pre-Award v2 - 361-HASAN | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-18 | 13 |  | N | 361-HASAN
CTSU Pre-Award v2 - 430-HIGGINS | Intake Form Completed | Role | CTSU Coordinator | 2017-08-18 | 0 | 2017-08-18 | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | Intake Form Completed | Role | CTSU Coordinator | 2017-08-18 | 0 | 2017-08-18 | N | 432-JAYASUNDERA
CTSU Pre-Award - 332-BELLOLI | Planning Meeting Completed | Role | CTSU Finance | 2017-08-18 | 13 |  | N | 332-BELLOLI
CTSU Pre-Award v2 - 361-HASAN | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-18 | 13 |  | N | 361-HASAN
CTSU Pre-Award v2 - 361-HASAN | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-18 | 13 |  | N | 361-HASAN
Calendar & Budget Retrofit - 00098540 | Review & Release Calendar | Role | CTSU Finance | 2017-08-18 | 0 | 2017-08-18 | N | 00098540
Calendar & Budget Retrofit - 00113034 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-18 | 7 | 2017-08-25 | N | 00113034
Calendar & Budget Retrofit - 00113034 | Review & Release Calendar | Role | CTSU Finance | 2017-08-18 | 7 | 2017-08-25 | N | 00113034
Calendar & Budget Retrofit - 00113560 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-18 | 0 | 2017-08-18 | N | 00113560
Calendar & Budget Retrofit - 00113560 | Review & Release Calendar | Role | CTSU Finance | 2017-08-18 | 0 | 2017-08-17 | N | 00113560
Calendar & Budget Retrofit - 00123094 | Review & Release Calendar | Role | CTSU Finance | 2017-08-18 | 13 |  | N | 00123094
Calendar & Budget Retrofit - 00126224 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-18 | 0 | 2017-08-18 | N | 00126224
Calendar & Budget Retrofit - 00128253 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-18 | 0 | 2017-08-18 | N | 00128253
Calendar & Budget Retrofit - 00128253 | Review & Release Calendar | Role | CTSU Finance | 2017-08-18 | 0 | 2017-08-17 | N | 00128253
Calendar & Budget Retrofit - 00130272 | Review & Release Calendar | Role | CTSU Finance | 2017-08-18 | 0 | 2017-08-14 | N | 00130272
Calendar & Budget Retrofit - 6-TAYLOR | Review & Release Calendar | Role | CTSU Finance | 2017-08-18 | 0 | 2017-08-16 | N | 00132251
Pre-Award Financial - 263-DELMONTE | Final Budget | Role | CTSU Finance | 2017-08-18 | 13 |  | N | 263-DELMONTE
Open to Accrual - 4033CYTOKINETICS-GOUTMAN | Sponsor/Organizing Group Approval Granted for Initiation of Study | User | Duell, Jayna | 2017-08-18 | 13 |  | N | 00130639
Calendar & Budget Retrofit - 00091711 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-18 | 0 | 2017-08-18 | N | 00091711
Calendar & Budget Retrofit - 00098540 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-18 | 13 |  | N | 00098540
Calendar & Budget Retrofit - 00123094 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-18 | 13 |  | N | 00123094
Calendar & Budget Retrofit - 00129846 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-18 | 0 | 2017-08-18 | N | 00129846
Calendar & Budget Retrofit - 00130272 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-18 | 0 | 2017-08-18 | N | 00130272
Calendar & Budget Retrofit - 00131311 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-18 | 0 | 2017-08-18 | N | 00131311
Calendar & Budget Retrofit - 00131320 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-18 | 0 | 2017-08-18 | N | 00131320
Calendar & Budget Retrofit - 00133542 | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-18 | 0 | 2017-08-18 | N | 00133542
Calendar & Budget Retrofit - 6-TAYLOR | Notify Niyati Updated Calendar was Released | User | Gladkowski, Ginger | 2017-08-18 | 0 | 2017-08-18 | N | 00132251
Calendar & Budget Retrofit - 00129846 | Review & Release Calendar | User | Glorioso, Michelle | 2017-08-18 | 0 | 2017-08-18 | N | 00129846
Calendar & Budget Retrofit - 00131311 | Review & Release Calendar | User | Glorioso, Michelle | 2017-08-18 | 0 | 2017-08-18 | N | 00131311
Calendaring : Initial Calendar Build - 140-CHUNG | Assign to Analyst | User | Greene, Paula | 2017-08-18 | 3 | 2017-08-21 | N | 00133613
Calendaring : Initial Calendar Build - 140-CHUNG | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-18 | 3 | 2017-08-21 | N | 00133613
Calendaring : Initial Calendar Build - 140-CHUNG | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-18 | 0 | 2017-08-18 | N | 00133613
Calendaring : Initial Calendar Build - 203-ELSE | Assign to Analyst | User | Greene, Paula | 2017-08-18 | 0 | 2017-08-18 | N | 00132173
Calendaring : Initial Calendar Build - 203-ELSE | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-18 | 0 | 2017-08-18 | N | 00132173
Calendaring : Initial Calendar Build - 203-ELSE | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-18 | 0 | 2017-08-18 | N | 00132173
Calendaring : Initial Calendar Build - 325-AUCHUS | Assign to Analyst | User | Greene, Paula | 2017-08-18 | 3 | 2017-08-21 | N | 00131840
Calendaring : Initial Calendar Build - 325-AUCHUS | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-18 | 3 | 2017-08-21 | N | 00131840
Calendaring : Initial Calendar Build - 325-AUCHUS | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-18 | 3 | 2017-08-21 | N | 00131840
Calendaring : Initial Calendar Build - 416-MAO-DRAAYER | Assign to Analyst | User | Greene, Paula | 2017-08-18 | 0 | 2017-08-18 | N | 416-MAO-DRAAYER
Calendaring : Initial Calendar Build - 416-MAO-DRAAYER | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-18 | 0 | 2017-08-18 | N | 416-MAO-DRAAYER
Calendaring : Initial Calendar Build - 416-MAO-DRAAYER | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-18 | 0 | 2017-08-18 | N | 416-MAO-DRAAYER
Pre-Award Financial - 86-AUCHUS | Care Designations completed | User | Henry, Robin | 2017-08-18 | 0 | 2017-08-17 | N | 00132700
Pre-Award Financial - FONTANA-1 | PI approved Budget | User | Henry, Robin | 2017-08-18 | 0 | 2017-08-07 | N | 00133153
131463 Spec Update Request(s) - simplify labs & add unscheduled procedures | Make Update(s) | User | LaVasseur, Kristen | 2017-08-18 | 0 | 2017-08-11 | N | 00131463
131463 Spec Update Request(s) - simplify labs & add unscheduled procedures | Re-Complete Calendar | User | LaVasseur, Kristen | 2017-08-18 | 0 | 2017-08-11 | N | 00131463
Calendar & Budget Retrofit - 00129652 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00129652
Calendar & Budget Retrofit - 00129652 | Review & Release Calendar | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00129652
Calendar & Budget Retrofit - 00129716 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00129716
Calendar & Budget Retrofit - 00129716 | Review & Release Calendar | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00129716
Calendar & Budget Retrofit - 00129820 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00129820
Calendar & Budget Retrofit - 00129820 | Review & Release Calendar | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00129820
Calendar & Budget Retrofit - 00130575 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00130575
Calendar & Budget Retrofit - 00130575 | Review & Release Calendar | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00130575
Calendar & Budget Retrofit - 00131837 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00131837
Calendar & Budget Retrofit - 00131837 | Review & Release Calendar | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00131837
Calendar & Budget Retrofit - 00131953 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00131953
Calendar & Budget Retrofit - 00131953 | Review & Release Calendar | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00131953
Calendar & Budget Retrofit - 00133290 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00133290
Calendar & Budget Retrofit - 00133290 | Review & Release Calendar | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00133290
Calendar & Budget Retrofit - PLT-INF24-001 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00135388
Calendar & Budget Retrofit - PLT-INF24-001 | Review & Release Calendar | User | Oliver, Amy | 2017-08-18 | 0 | 2017-08-18 | N | 00135388
Pre-Award Financial - 211-HIGGINS | Calendar Released | User | Oliver, Amy | 2017-08-18 | 13 |  | N | 00128325
CTSU Pre-Award - 337-MIAN | Care Designations completed | User | VanderElzen, Liz | 2017-08-18 | 10 | 2017-08-28 | N | 337-MIAN
CTSU Pre-Award - 338-MIAN | Care Designations completed | User | VanderElzen, Liz | 2017-08-18 | 10 | 2017-08-28 | N | 00133457
Calendar & Budget Retrofit - 00125425 | Initiate Updates | User | Yunk, Jason | 2017-08-18 | 0 | 2017-08-18 | N | 00125425
Calendar & Budget Retrofit - 00132020 | Initiate Updates | User | Yunk, Jason | 2017-08-18 | 0 | 2017-08-18 | N | 00132020
Calendar & Budget Retrofit - 00132020 | Questions | User | Yunk, Jason | 2017-08-18 | 0 | 2017-08-18 | N | 00132020
Calendaring : Amendment Checklist & Process - 00132251 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Zahs, Brian | 2017-08-18 | 3 | 2017-08-21 | N | 00132251
Calendaring : Amendment Checklist & Process - 00132251 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Zahs, Brian | 2017-08-18 | 3 | 2017-08-21 | N | 00132251
Pre-Award Financial - 278-CONJEEVARAM | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-19 | 12 |  | N | 00133341
Pre-Award Financial - 49-MARTINEZ | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-19 | 12 |  | N | 00132020
CTSU Pre-Award v2 - 403-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-19 | 0 | 2017-08-18 | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-19 | 0 | 2017-08-18 | N | 00134896
Pre-Award Financial - 11-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-19 | 0 | 2017-08-18 | N | 00134884
CTSU Pre-Award - 313-CONJEEVARAM | Budget Negotiations | Role | CTSU Finance | 2017-08-19 | 12 |  | N | 313-CONJEEVARAM
CTSU Pre-Award - 332-BELLOLI | Care Designations completed | Role | CTSU Finance | 2017-08-19 | 12 |  | N | 332-BELLOLI
Pre-Award Financial - 261-LUGOGO | PAN Released | Role | CTSU Finance | 2017-08-19 | 12 |  | N | 261-LUGOGO
CTSU Pre-Award - 336-KHANNA | Final Budget | User | Henry, Robin | 2017-08-19 | 12 |  | N | 00133684
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | Assign to Analyst | User | LaVasseur, Kristen | 2017-08-19 | 0 | 2017-08-18 | N | 00133290
CTSU Pre-Award v2 - 403-HIGGINS | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-08-19 | 12 |  | N | 00134895
CTSU Pre-Award v2 - 403-HIGGINS | Request Research Pharmacy Budget | User | VanderElzen, Liz | 2017-08-19 | 12 |  | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-08-19 | 12 |  | N | 00134896
CTSU Pre-Award v2 - 404-HIGGINS | Request Research Pharmacy Budget | User | VanderElzen, Liz | 2017-08-19 | 12 |  | N | 00134896
Pre-Award Financial - 11-HIGGINS | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-08-19 | 2 | 2017-08-21 | N | 00134884
Pre-Award Financial - 11-HIGGINS | Request Research Pharmacy Budget | User | VanderElzen, Liz | 2017-08-19 | 9 | 2017-08-28 | N | 00134884
Calendaring : Specification Update Request(s) - 00127136 2 | Acknowledge | User | Yunk, Jason | 2017-08-19 | 12 |  | N | 00127136
Pre-Award Financial - 205-KHANNA | OnCore Budget Build | User | Yunk, Jason | 2017-08-19 | 12 |  | N | 00132200
Calendaring : Amendment Checklist & Process - 00132251 | ** Items/Services : Addition or Removal of Procedures / Events | User | Zahs, Brian | 2017-08-19 | 2 | 2017-08-21 | N | 00132251
Calendaring : Initial Calendar Build - 227-STEIGERWALT 3 | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-08-19 | 12 |  | N | 227-STEIGERWALT
Calendaring : Initial Calendar Build - 227-STEIGERWALT 3 | Make Updates | User | Zahs, Brian | 2017-08-19 | 12 |  | N | 227-STEIGERWALT
Pre-Award Financial - 70-LUGOGO | Open to Accrual | Role | CTSU Administrator | 2017-08-20 | 11 |  | N | 70-LUGOGO
CTSU Pre-Award v2 - 140-CHUNG | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-20 | 11 |  | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-20 | 4 | 2017-08-24 | N | 00131840
Pre-Award Financial - 203-ELSE | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-20 | 0 | 2017-08-11 | N | 00132173
131463 Spec Update Request(s) - simplify labs & add unscheduled procedures | Acknowledge | Role | CTSU Finance | 2017-08-20 | 11 |  | N | 00131463
CTSU Pre-Award - 348-CHEY | Billing Calendar Received | Role | CTSU Finance | 2017-08-20 | 11 |  | N | 348-CHEY
CTSU Pre-Award v2 - 140-CHUNG | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-20 | 11 |  | N | 00133613
CTSU Pre-Award v2 - 140-CHUNG | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-20 | 11 |  | N | 00133613
Pre-Award Financial - 263-DELMONTE | PAF routed | Role | CTSU Finance | 2017-08-20 | 11 |  | N | 263-DELMONTE
Pre-Award Financial - 110-SCHIOPU | PI approved Budget | User | Henry, Robin | 2017-08-20 | 0 | 2017-08-16 | N | 00134444
Pre-Award Financial - 203-ELSE | Created CTRF & "Notify ORSP" | User | Henry, Robin | 2017-08-20 | 3 | 2017-08-23 | N | 00132173
Pre-Award Financial - 203-ELSE | Request Research Pharmacy Budget | User | Henry, Robin | 2017-08-20 | 0 | 2017-08-14 | N | 00132173
Pre-Award Financial - FONTANA-1 | Budget Negotiations | User | Henry, Robin | 2017-08-20 | 0 | 2017-08-08 | N | 00133153
Pre-Award Financial - 205-KHANNA | Calendar Released | User | Oliver, Amy | 2017-08-20 | 11 |  | N | 00132200
Pre-Award Financial - 251-COMER | PI approved Budget | User | VanderElzen, Liz | 2017-08-20 | 0 | 2017-08-11 | N | 00134232
Calendaring : Amendment Checklist & Process - 00132251 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Zahs, Brian | 2017-08-20 | 1 | 2017-08-21 | N | 00132251
Calendaring : Amendment Checklist & Process - 00132251 | ** Visits : Addition or Removal of Time Points | User | Zahs, Brian | 2017-08-20 | 1 | 2017-08-21 | N | 00132251
Calendaring : Amendment Checklist & Process - 00132251 | Request Care Designations | User | Zahs, Brian | 2017-08-20 | 11 |  | N | 00132251
Calendaring : Amendment Checklist & Process - 00132251 | Update RSH Source in MBECT | User | Zahs, Brian | 2017-08-20 | 11 |  | N | 00132251
Calendaring : Initial Calendar Build - 00134884 | Complete MCA / QCT | User | van Dijk, Tim | 2017-08-20 | 4 | 2017-08-24 | N | 00134884
Calendaring : Initial Calendar Build - 00134884 | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-08-20 | 2 | 2017-08-22 | N | 00134884
Calendaring : Initial Calendar Build - 00134884 | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-08-20 | 4 | 2017-08-24 | N | 00134884
Calendaring : Initial Calendar Build - 403-HIGGINS | Complete MCA / QCT | User | van Dijk, Tim | 2017-08-20 | 4 | 2017-08-24 | N | 00134895
Calendaring : Initial Calendar Build - 403-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-08-20 | 2 | 2017-08-22 | N | 00134895
Calendaring : Initial Calendar Build - 403-HIGGINS | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-08-20 | 11 |  | N | 00134895
Calendaring : Initial Calendar Build - 404-HIGGINS | Complete MCA / QCT | User | van Dijk, Tim | 2017-08-20 | 4 | 2017-08-24 | N | 00134896
Calendaring : Initial Calendar Build - 404-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-08-20 | 2 | 2017-08-22 | N | 00134896
Calendaring : Initial Calendar Build - 404-HIGGINS | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-08-20 | 11 |  | N | 00134896
CTSU Pre-Award v2 - 380-LOK | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-21 | 10 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-21 | 10 |  | N | 381-HIGGINS
Pre-Award Financial - 211-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-21 | 10 |  | N | 00128325
Pre-Award Financial - 278-CONJEEVARAM | Open to Accrual | Role | CTSU Administrator | 2017-08-21 | 10 |  | N | 00133341
Pre-Award Financial - 49-MARTINEZ | Open to Accrual | Role | CTSU Administrator | 2017-08-21 | 10 |  | N | 00132020
CTSU Pre-Award v2 - 323-BOLLING | UFA Completed | Role | CTSU Coordinator | 2017-08-21 | 0 | 2017-08-21 | N | 323-BOLLING
CTSU Pre-Award v2 - 380-LOK | Sponsor Reach out | Role | CTSU Coordinator | 2017-08-21 | 10 |  | N | 380-LOK
CTSU Pre-Award v2 - 380-LOK | UFA Completed | Role | CTSU Coordinator | 2017-08-21 | 10 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator | 2017-08-21 | 0 | 2017-08-07 | N | 381-HIGGINS
CTSU Pre-Award v2 - 381-HIGGINS | UFA Completed | Role | CTSU Coordinator | 2017-08-21 | 0 | 2017-08-04 | N | 381-HIGGINS
CTSU Pre-Award v2 - 435-MOROI | Intake Form Completed | Role | CTSU Coordinator | 2017-08-21 | 0 | 2017-08-21 | N | 435-MOROI
CTSU Pre-Award v2 - 364-KHAJA | Internal Budget Finished | Role | CTSU Finance | 2017-08-21 | 10 |  | N | 364-KHAJA
CTSU Pre-Award v2 - 409-NASR | Billing Calendar Received | Role | CTSU Finance | 2017-08-21 | 10 |  | N | 409-NASR
Calendar & Budget Retrofit - 00089489 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00089489
Calendar & Budget Retrofit - 00108880 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00108880
Calendar & Budget Retrofit - 00111295 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00111295
Calendar & Budget Retrofit - 00125022 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00125022
Calendar & Budget Retrofit - 00125306 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00125306
Calendar & Budget Retrofit - 00125798 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00125798
Calendar & Budget Retrofit - 00126010 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00126010
Calendar & Budget Retrofit - 00126434 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00126434
Calendar & Budget Retrofit - 00127891 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 2 | 2017-08-23 | N | 00127891
Calendar & Budget Retrofit - 00128009 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00128009
Calendar & Budget Retrofit - 00128322 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-21 | 4 | 2017-08-25 | N | 00128322
Calendar & Budget Retrofit - 00128322 | Questions | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00128322
Calendar & Budget Retrofit - 00128322 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00128322
Calendar & Budget Retrofit - 00128322 | Review & Release Calendar | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00128322
Calendar & Budget Retrofit - 00129162 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00129162
Calendar & Budget Retrofit - 00129412 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00129412
Calendar & Budget Retrofit - 00130209 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00130209
Calendar & Budget Retrofit - 00130968 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 1 | 2017-08-22 | N | 00130968
Calendar & Budget Retrofit - 00131329 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00131329
Calendar & Budget Retrofit - 00131377 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 1 | 2017-08-22 | N | 00131377
Calendar & Budget Retrofit - 00132200 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 0 | 2017-08-21 | N | 00132200
Calendar & Budget Retrofit - 00134866 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 2 | 2017-08-23 | N | 00134866
Calendar & Budget Retrofit - 244-MODY | Received calendar from Niyati | Role | CTSU Finance | 2017-08-21 | 1 | 2017-08-22 | N | 244-MODY
Calendaring : Initial Calendar Build - 227-STEIGERWALT 3 | Acknowledge | Role | CTSU Finance | 2017-08-21 | 10 |  | N | 227-STEIGERWALT
Pre-Award Financial - 188-RUBENSTEIN | OnCore Budget Build | Role | CTSU Finance | 2017-08-21 | 10 |  | N | 188-RUBENSTEIN
CTSU Pre-Award - 336-KHANNA | PAF routed | User | Henry, Robin | 2017-08-21 | 10 |  | N | 00133684
Calendaring : Initial Calendar Build - 140-CHUNG | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-08-21 | 10 |  | N | 00133613
Calendaring : Initial Calendar Build - 140-CHUNG | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-08-21 | 10 |  | N | 00133613
Calendaring : Initial Calendar Build - 140-CHUNG | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-08-21 | 10 |  | N | 00133613
Calendaring : Initial Calendar Build - 203-ELSE | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-08-21 | 10 |  | N | 00132173
Calendaring : Initial Calendar Build - 203-ELSE | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-08-21 | 9 | 2017-08-30 | N | 00132173
Calendaring : Initial Calendar Build - 203-ELSE | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-08-21 | 10 |  | N | 00132173
Calendar & Budget Retrofit - 00128157 | Received calendar from Niyati | User | Oliver, Amy | 2017-08-21 | 0 | 2017-08-21 | N | 00128157
Calendaring : Specification Update Request(s) - 00130757 | ** Structural Edits | User | Yunk, Jason | 2017-08-21 | 0 | 2017-08-21 | N | 00130757
Pre-Award Financial - 46-HIGGINS | OnCore Budget Build | User | Yunk, Jason | 2017-08-21 | 10 |  | N | 46-HIGGINS
Pre-Award Financial - 56-RAO | OnCore Budget Build | User | Yunk, Jason | 2017-08-21 | 10 |  | N | 00133286
Calendaring : Initial Calendar Build - 416-MAO-DRAAYER | Complete MCA / QCT | User | Zahs, Brian | 2017-08-21 | 10 |  | N | 416-MAO-DRAAYER
Calendaring : Initial Calendar Build - 416-MAO-DRAAYER | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian | 2017-08-21 | 10 |  | N | 416-MAO-DRAAYER
Calendaring : Initial Calendar Build - 416-MAO-DRAAYER | Nimblify Build is Complete & Ready for Import | User | Zahs, Brian | 2017-08-21 | 10 |  | N | 416-MAO-DRAAYER
Calendaring : Specification Update Request(s) - 00130757 | Assign to Analyst | User | Zahs, Brian | 2017-08-21 | 10 |  | N | 00130757
Calendaring : Initial Calendar Build - 325-AUCHUS | Complete MCA / QCT | User | van Dijk, Tim | 2017-08-21 | 3 | 2017-08-24 | N | 00131840
Calendaring : Initial Calendar Build - 325-AUCHUS | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-08-21 | 3 | 2017-08-24 | N | 00131840
Calendaring : Initial Calendar Build - 325-AUCHUS | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-08-21 | 10 |  | N | 00131840
CTSU Pre-Award - 370-LOK | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-22 | 9 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-22 | 9 |  | N | 371-LOK
CTSU Pre-Award v2 - 323-BOLLING | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-22 | 9 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-22 | 9 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 323-BOLLING | Sponsor Reach out | Role | CTSU Coordinator | 2017-08-22 | 0 | 2017-08-22 | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | UFA Completed | Role | CTSU Coordinator | 2017-08-22 | 9 |  | N | 385-MCLAUGHLIN
Calendar & Budget Retrofit - 00125798 | Questions | Role | CTSU Finance | 2017-08-22 | 9 |  | N | 00125798
Calendar & Budget Retrofit - 00126434 | Initiate Updates | Role | CTSU Finance | 2017-08-22 | 0 | 2017-08-22 | N | 00126434
Calendar & Budget Retrofit - 00126434 | Questions | Role | CTSU Finance | 2017-08-22 | 0 | 2017-08-22 | N | 00126434
Calendar & Budget Retrofit - 00127891 | Initiate Updates | Role | CTSU Finance | 2017-08-22 | 1 | 2017-08-23 | N | 00127891
Calendar & Budget Retrofit - 00127891 | Questions | Role | CTSU Finance | 2017-08-22 | 1 | 2017-08-23 | N | 00127891
Calendar & Budget Retrofit - 00128009 | Initiate Updates | Role | CTSU Finance | 2017-08-22 | 0 | 2017-08-22 | N | 00128009
Calendar & Budget Retrofit - 00128009 | Questions | Role | CTSU Finance | 2017-08-22 | 0 | 2017-08-22 | N | 00128009
Calendar & Budget Retrofit - 00129412 | Initiate Updates | Role | CTSU Finance | 2017-08-22 | 0 | 2017-08-21 | N | 00129412
Calendar & Budget Retrofit - 00129412 | Questions | Role | CTSU Finance | 2017-08-22 | 0 | 2017-08-22 | N | 00129412
Calendar & Budget Retrofit - 00130209 | Initiate Updates | Role | CTSU Finance | 2017-08-22 | 1 | 2017-08-23 | N | 00130209
Calendar & Budget Retrofit - 00130209 | Questions | Role | CTSU Finance | 2017-08-22 | 1 | 2017-08-23 | N | 00130209
Calendar & Budget Retrofit - 00130968 | Initiate Updates | Role | CTSU Finance | 2017-08-22 | 0 | 2017-08-22 | N | 00130968
Calendar & Budget Retrofit - 00130968 | Questions | Role | CTSU Finance | 2017-08-22 | 0 | 2017-08-22 | N | 00130968
Calendar & Budget Retrofit - 00131377 | Initiate Updates | Role | CTSU Finance | 2017-08-22 | 0 | 2017-08-22 | N | 00131377
Calendar & Budget Retrofit - 00131377 | Questions | Role | CTSU Finance | 2017-08-22 | 0 | 2017-08-22 | N | 00131377
Calendar & Budget Retrofit - 00134866 | Initiate Updates | Role | CTSU Finance | 2017-08-22 | 1 | 2017-08-23 | N | 00134866
Calendar & Budget Retrofit - 00134866 | Questions | Role | CTSU Finance | 2017-08-22 | 1 | 2017-08-23 | N | 00134866
Calendar & Budget Retrofit - 244-MODY | Initiate Updates | Role | CTSU Finance | 2017-08-22 | 0 | 2017-08-22 | N | 244-MODY
Calendar & Budget Retrofit - 244-MODY | Questions | Role | CTSU Finance | 2017-08-22 | 0 | 2017-08-22 | N | 244-MODY
Pre-Award Financial - 188-RUBENSTEIN | Calendar Released | Role | CTSU Finance | 2017-08-22 | 9 |  | N | 188-RUBENSTEIN
Calendar & Budget Retrofit - 00128157 | Initiate Updates | User | Farmer, Amber | 2017-08-22 | 8 | 2017-08-30 | N | 00128157
Pre-Award Financial - 110-SCHIOPU | Budget Negotiations | User | Henry, Robin | 2017-08-22 | 0 | 2017-08-17 | N | 00134444
Pre-Award Financial - 86-AUCHUS | Internal Budget Finished | User | Henry, Robin | 2017-08-22 | 2 | 2017-08-24 | N | 00132700
Calendar & Budget Retrofit - 00128157 | Questions | User | Oliver, Amy | 2017-08-22 | 2 | 2017-08-24 | N | 00128157
Pre-Award Financial - 56-RAO | Calendar Released | User | Oliver, Amy | 2017-08-22 | 9 |  | N | 00133286
CTSU Pre-Award - 337-MIAN | Internal Budget Finished | User | VanderElzen, Liz | 2017-08-22 | 6 | 2017-08-28 | N | 337-MIAN
CTSU Pre-Award - 338-MIAN | Internal Budget Finished | User | VanderElzen, Liz | 2017-08-22 | 6 | 2017-08-28 | N | 00133457
Pre-Award Financial - 112-FLAHERTY | Final Budget | User | VanderElzen, Liz | 2017-08-22 | 9 |  | N | 112-FLAHERTY
Pre-Award Financial - 251-COMER | Budget Negotiations | User | VanderElzen, Liz | 2017-08-22 | 0 | 2017-08-15 | N | 00134232
CTSU Pre-Award - 336-KHANNA | OnCore Budget Build | User | Yunk, Jason | 2017-08-22 | 9 |  | N | 00133684
Calendar & Budget Retrofit - 00108880 | Initiate Updates | User | Yunk, Jason | 2017-08-22 | 0 | 2017-08-21 | N | 00108880
Calendar & Budget Retrofit - 00125022 | Initiate Updates | User | Yunk, Jason | 2017-08-22 | 0 | 2017-08-21 | N | 00125022
Calendar & Budget Retrofit - 00126010 | Initiate Updates | User | Yunk, Jason | 2017-08-22 | 0 | 2017-08-21 | N | 00126010
Calendar & Budget Retrofit - 00131329 | Initiate Updates | User | Yunk, Jason | 2017-08-22 | 0 | 2017-08-22 | N | 00131329
Calendar & Budget Retrofit - 00132200 | Initiate Updates | User | Yunk, Jason | 2017-08-22 | 0 | 2017-08-21 | N | 00132200
Calendar & Budget Retrofit - 00132200 | Questions | User | Yunk, Jason | 2017-08-22 | 0 | 2017-08-22 | N | 00132200
Pre-Award Financial - 46-HIGGINS | Calendar Released | User | Yunk, Jason | 2017-08-22 | 9 |  | N | 46-HIGGINS
Calendaring : Initial Calendar Build - 00129709 | CRAO Approval Issue & Documented | User | van Dijk, Tim | 2017-08-22 | 0 | 2017-08-22 | N | 00129709
Calendaring : Initial Calendar Build - 00134884 | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-08-22 | 2 | 2017-08-24 | N | 00134884
Calendaring : Initial Calendar Build - 00134884 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-08-22 | 2 | 2017-08-24 | N | 00134884
Calendaring : Initial Calendar Build - 403-HIGGINS | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-08-22 | 9 |  | N | 00134895
Calendaring : Initial Calendar Build - 403-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-08-22 | 9 |  | N | 00134895
Calendaring : Initial Calendar Build - 404-HIGGINS | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-08-22 | 9 |  | N | 00134896
Calendaring : Initial Calendar Build - 404-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-08-22 | 9 |  | N | 00134896
Pre-Award Financial - 205-KHANNA | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-23 | 8 |  | N | 00132200
Pre-Award Financial - 211-HIGGINS | Open to Accrual | Role | CTSU Administrator | 2017-08-23 | 8 |  | N | 00128325
CTSU Pre-Award v2 - 439-KHANNA | Intake Form Completed | Role | CTSU Coordinator | 2017-08-23 | 0 | 2017-08-23 | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | Intake Form Completed | Role | CTSU Coordinator | 2017-08-23 | 0 | 2017-08-23 | N | 440-LOK
Calendar & Budget Retrofit - 00101092 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-23 | 0 | 2017-08-23 | N | 00101092
Calendar & Budget Retrofit - 00107927 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-23 | 0 | 2017-08-23 | N | 00107927
Calendar & Budget Retrofit - 00111185 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-23 | 0 | 2017-08-23 | N | 00111185
Calendar & Budget Retrofit - 00125798 | Review & Release Calendar | Role | CTSU Finance | 2017-08-23 | 0 | 2017-08-23 | N | 00125798
Calendar & Budget Retrofit - 00129162 | Questions | Role | CTSU Finance | 2017-08-23 | 8 |  | N | 00129162
Calendaring : Initial Calendar Build - 409-NASR | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-08-23 | 8 |  | N | 409-NASR
Calendaring : Initial Calendar Build - 140-CHUNG | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-08-23 | 8 |  | N | 00133613
Calendaring : Initial Calendar Build - 140-CHUNG | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-08-23 | 8 |  | N | 00133613
Calendaring : Initial Calendar Build - 203-ELSE | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-08-23 | 8 |  | N | 00132173
Calendaring : Initial Calendar Build - 203-ELSE | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-08-23 | 8 |  | N | 00132173
CTSU Pre-Award - 336-KHANNA | Calendar Released | User | Oliver, Amy | 2017-08-23 | 8 |  | N | 00133684
Pre-Award Financial - 211-HIGGINS | Initiate Post-Award Task List | User | Oliver, Amy | 2017-08-23 | 8 |  | N | 00128325
Calendaring : Initial Calendar Build - 416-MAO-DRAAYER | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian | 2017-08-23 | 8 |  | N | 416-MAO-DRAAYER
Calendaring : Initial Calendar Build - 416-MAO-DRAAYER | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian | 2017-08-23 | 8 |  | N | 416-MAO-DRAAYER
Calendaring : Initial Calendar Build - 325-AUCHUS | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-08-23 | 8 |  | N | 00131840
Calendaring : Initial Calendar Build - 325-AUCHUS | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-08-23 | 8 |  | N | 00131840
CTSU Pre-Award v2 - 00132705 2 | IRB Application Submitted | User | Ball, Ron | 2017-08-24 | 7 |  | N | 00132705
Calendaring : Initial Calendar Build - 00125022 | CRAO Approval Issue & Documented | Role | CRAO | 2017-08-24 | 0 | 2017-08-24 | N | 00125022
CTSU Pre-Award v2 - 390-DAY | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-24 | 7 |  | N | 390-DAY
CTSU Pre-Award - 348-CHEY | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-24 | 7 |  | N | 348-CHEY
CTSU Pre-Award - 370-LOK | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-24 | 7 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-24 | 7 |  | N | 371-LOK
CTSU Pre-Award - 348-CHEY | Planning Meeting Completed | Role | CTSU Finance | 2017-08-24 | 7 |  | N | 348-CHEY
CTSU Pre-Award - 370-LOK | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-24 | 7 |  | N | 370-LOK
CTSU Pre-Award - 370-LOK | Request MCRU Budget | Role | CTSU Finance | 2017-08-24 | 7 |  | N | 370-LOK
CTSU Pre-Award - 370-LOK | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-24 | 7 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-24 | 7 |  | N | 371-LOK
CTSU Pre-Award - 371-LOK | Request MCRU Budget | Role | CTSU Finance | 2017-08-24 | 7 |  | N | 371-LOK
CTSU Pre-Award - 371-LOK | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-24 | 7 |  | N | 371-LOK
CTSU Pre-Award v2 - 364-KHAJA | PI approved Budget | Role | CTSU Finance | 2017-08-24 | 7 |  | N | 364-KHAJA
Calendar & Budget Retrofit - 00111185 | Initiate Updates | User | Farmer, Amber | 2017-08-24 | 0 | 2017-08-23 | N | 00111185
Calendar & Budget Retrofit - 00111185 | Questions | User | Farmer, Amber | 2017-08-24 | 6 | 2017-08-30 | N | 00111185
Calendaring : Initial Calendar Build - 23-GUPTA | Complete Calendar ( ie. Ready for Financials ) | User | Hodges, Lynda | 2017-08-24 | 0 | 2017-08-24 | N | 00134236
Calendaring : Initial Calendar Build - 23-GUPTA | Make Updates | User | Hodges, Lynda | 2017-08-24 | 0 | 2017-08-24 | N | 00134236
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | Make Update(s) | User | LaVasseur, Kristen | 2017-08-24 | 0 | 2017-08-18 | N | 00133290
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | Re-Complete Calendar | User | LaVasseur, Kristen | 2017-08-24 | 0 | 2017-08-18 | N | 00133290
CTSU Pre-Award v2 - 00132705 2 | Planning Meeting Completed | User | Miller, Diana | 2017-08-24 | 7 |  | N | 00132705
Calendar & Budget Retrofit - 00107927 | Questions | User | Oliver, Amy | 2017-08-24 | 7 |  | N | 00107927
Pre-Award Financial - 190-SCHIOPU | PAN Released | User | Oliver, Amy | 2017-08-24 | 7 |  | N | 00134443
Pre-Award Financial - 112-FLAHERTY | PAF routed | User | VanderElzen, Liz | 2017-08-24 | 7 |  | N | 112-FLAHERTY
Calendar & Budget Retrofit - 00101092 | Initiate Updates | User | Yunk, Jason | 2017-08-24 | 0 | 2017-08-23 | N | 00101092
Calendar & Budget Retrofit - 00107927 | Initiate Updates | User | Yunk, Jason | 2017-08-24 | 0 | 2017-08-23 | N | 00107927
Calendar Build - 8-AARONSON | QCT Checklist : completed in OnCore | User | Zahs, Brian | 2017-08-24 | 0 | 2017-08-24 | N | 00132110
Calendaring : Amendment Checklist & Process - 00082635 | AME Calendaring Process Initiated | User | Boyd, Collin | 2017-08-25 | 6 |  | N | 00082635
CTSU Pre-Award - 326-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-25 | 0 | 2017-08-25 | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-25 | 0 | 2017-08-25 | N | 327-HIGGINS
Pre-Award Financial - 188-RUBENSTEIN | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-25 | 6 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 205-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-25 | 0 | 2017-08-25 | N | 205-HIGGINS
Pre-Award Financial - 205-KHANNA | Open to Accrual | Role | CTSU Administrator | 2017-08-25 | 6 |  | N | 00132200
Pre-Award Financial - 46-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-25 | 6 |  | N | 46-HIGGINS
Pre-Award Financial - 56-RAO | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-25 | 6 |  | N | 00133286
CTSU Pre-Award v2 - 409-NASR | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-25 | 6 |  | N | 409-NASR
CTSU Pre-Award - 332-BELLOLI | Internal Budget Finished | Role | CTSU Finance | 2017-08-25 | 6 |  | N | 332-BELLOLI
CTSU Pre-Award - 375-JAMERSON | Feasibility w/Documents received | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-25 | N | 375-JAMERSON
CTSU Pre-Award v2 - 409-NASR | Planning Meeting Completed | Role | CTSU Finance | 2017-08-25 | 6 |  | N | 409-NASR
Calendar & Budget Retrofit - 00089489 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-25 | N | 00089489
Calendar & Budget Retrofit - 00089489 | Review & Release Calendar | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-23 | N | 00089489
Calendar & Budget Retrofit - 00111295 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-25 | N | 00111295
Calendar & Budget Retrofit - 00111295 | Review & Release Calendar | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-22 | N | 00111295
Calendar & Budget Retrofit - 00125306 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-25 | N | 00125306
Calendar & Budget Retrofit - 00125306 | Review & Release Calendar | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-25 | N | 00125306
Calendar & Budget Retrofit - 00125798 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-25 | N | 00125798
Calendar & Budget Retrofit - 00126434 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-23 | N | 00126434
Calendar & Budget Retrofit - 00126434 | Review & Release Calendar | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-22 | N | 00126434
Calendar & Budget Retrofit - 00127891 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-23 | N | 00127891
Calendar & Budget Retrofit - 00127891 | Review & Release Calendar | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-23 | N | 00127891
Calendar & Budget Retrofit - 00128009 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-23 | N | 00128009
Calendar & Budget Retrofit - 00128009 | Review & Release Calendar | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-22 | N | 00128009
Calendar & Budget Retrofit - 00129162 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-25 | N | 00129162
Calendar & Budget Retrofit - 00129162 | Review & Release Calendar | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-25 | N | 00129162
Calendar & Budget Retrofit - 00129412 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-23 | N | 00129412
Calendar & Budget Retrofit - 00129412 | Review & Release Calendar | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-22 | N | 00129412
Calendar & Budget Retrofit - 00130209 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-23 | N | 00130209
Calendar & Budget Retrofit - 00130209 | Review & Release Calendar | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-23 | N | 00130209
Calendar & Budget Retrofit - 00130968 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-23 | N | 00130968
Calendar & Budget Retrofit - 00130968 | Review & Release Calendar | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-22 | N | 00130968
Calendar & Budget Retrofit - 00131377 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-23 | N | 00131377
Calendar & Budget Retrofit - 00131377 | Review & Release Calendar | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-22 | N | 00131377
Calendar & Budget Retrofit - 00134866 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-23 | N | 00134866
Calendar & Budget Retrofit - 00134866 | Review & Release Calendar | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-23 | N | 00134866
Calendar & Budget Retrofit - 244-MODY | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-23 | N | 244-MODY
Calendar & Budget Retrofit - 244-MODY | Review & Release Calendar | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-22 | N | 244-MODY
Calendaring : Amendment Checklist & Process - 00120441 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-25 | N | 00120441
Calendaring : Amendment Checklist & Process - 00132251 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance | 2017-08-25 | 0 | 2017-08-22 | N | 00132251
Pre-Award Financial - 198-LUCKRITZ | Planning Meeting Request Sent | User | Earwood, Rebecca | 2017-08-25 | 0 | 2017-08-25 | N | 198-LUCKRITZ
Calendaring : Initial Calendar Build - 198-LUCKRITZ | Assign to Analyst | User | Greene, Paula | 2017-08-25 | 0 | 2017-08-25 | N | 198-LUCKRITZ
Calendaring : Initial Calendar Build - 198-LUCKRITZ | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-25 | 0 | 2017-08-25 | N | 198-LUCKRITZ
Calendaring : Initial Calendar Build - 198-LUCKRITZ | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-25 | 0 | 2017-08-25 | N | 198-LUCKRITZ
Calendaring : Initial Calendar Build - 205-HIGGINS | Assign to Analyst | User | Greene, Paula | 2017-08-25 | 0 | 2017-08-25 | N | 205-HIGGINS
Calendaring : Initial Calendar Build - 205-HIGGINS | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-25 | 0 | 2017-08-25 | N | 205-HIGGINS
Calendaring : Initial Calendar Build - 205-HIGGINS | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-25 | 0 | 2017-08-25 | N | 205-HIGGINS
Calendaring : Initial Calendar Build - 326-HIGGINS | Assign to Analyst | User | Greene, Paula | 2017-08-25 | 0 | 2017-08-25 | N | 326-HIGGINS
Calendaring : Initial Calendar Build - 326-HIGGINS | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-25 | 0 | 2017-08-25 | N | 326-HIGGINS
Calendaring : Initial Calendar Build - 326-HIGGINS | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-25 | 0 | 2017-08-25 | N | 326-HIGGINS
Calendaring : Initial Calendar Build - 327-HIGGINS | Assign to Analyst | User | Greene, Paula | 2017-08-25 | 0 | 2017-08-25 | N | 327-HIGGINS
Calendaring : Initial Calendar Build - 327-HIGGINS | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-25 | 0 | 2017-08-25 | N | 327-HIGGINS
Calendaring : Initial Calendar Build - 327-HIGGINS | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-25 | 0 | 2017-08-25 | N | 327-HIGGINS
Pre-Award Financial - 86-AUCHUS | PI approved Budget | User | Henry, Robin | 2017-08-25 | 0 | 2017-08-25 | N | 00132700
Pre-Award Financial - 198-LUCKRITZ | Feasibility approved/CRAO Notified | User | Naylor, Tracey | 2017-08-25 | 0 | 2017-08-25 | N | 198-LUCKRITZ
Calendar & Budget Retrofit - 00108880 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-25 | 0 | 2017-08-25 | N | 00108880
Calendar & Budget Retrofit - 00108880 | Review & Release Calendar | User | Oliver, Amy | 2017-08-25 | 0 | 2017-08-24 | N | 00108880
Calendar & Budget Retrofit - 00125022 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-25 | 0 | 2017-08-25 | N | 00125022
Calendar & Budget Retrofit - 00125022 | Review & Release Calendar | User | Oliver, Amy | 2017-08-25 | 0 | 2017-08-23 | N | 00125022
Calendar & Budget Retrofit - 00125425 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-25 | 0 | 2017-08-18 | N | 00125425
Calendar & Budget Retrofit - 00125425 | Review & Release Calendar | User | Oliver, Amy | 2017-08-25 | 0 | 2017-08-18 | N | 00125425
Calendar & Budget Retrofit - 00126010 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-25 | 0 | 2017-08-25 | N | 00126010
Calendar & Budget Retrofit - 00126010 | Review & Release Calendar | User | Oliver, Amy | 2017-08-25 | 0 | 2017-08-22 | N | 00126010
Calendar & Budget Retrofit - 00128157 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-25 | 6 |  | N | 00128157
Calendar & Budget Retrofit - 00128157 | Review & Release Calendar | User | Oliver, Amy | 2017-08-25 | 5 | 2017-08-30 | N | 00128157
Calendar & Budget Retrofit - 00131329 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-25 | 0 | 2017-08-25 | N | 00131329
Calendar & Budget Retrofit - 00131329 | Review & Release Calendar | User | Oliver, Amy | 2017-08-25 | 0 | 2017-08-23 | N | 00131329
Calendar & Budget Retrofit - 00132020 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-25 | 6 |  | N | 00132020
Calendar & Budget Retrofit - 00132020 | Review & Release Calendar | User | Oliver, Amy | 2017-08-25 | 6 |  | N | 00132020
Calendar & Budget Retrofit - 00132200 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-25 | 0 | 2017-08-25 | N | 00132200
Calendar & Budget Retrofit - 00132200 | Review & Release Calendar | User | Oliver, Amy | 2017-08-25 | 0 | 2017-08-23 | N | 00132200
CTSU Pre-Award - 337-MIAN | PI approved Budget | User | VanderElzen, Liz | 2017-08-25 | 3 | 2017-08-28 | N | 337-MIAN
CTSU Pre-Award - 338-MIAN | PI approved Budget | User | VanderElzen, Liz | 2017-08-25 | 3 | 2017-08-28 | N | 00133457
CTSU Pre-Award - 359-SMITH | Billing Calendar Received | User | VanderElzen, Liz | 2017-08-25 | 6 |  | N | 359-SMITH
Calendaring : Initial Calendar Build - 409-NASR | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-08-25 | 6 |  | N | 409-NASR
Calendaring : Initial Calendar Build - 409-NASR | Make Updates | User | van Dijk, Tim | 2017-08-25 | 6 |  | N | 409-NASR
CTSU Pre-Award - 336-KHANNA | PI Signoff in OnCore | Role | CTSU Administrator | 2017-08-26 | 5 |  | N | 00133684
CTSU Pre-Award v2 - 361-HASAN | Billing Calendar Received | Role | CTSU Finance | 2017-08-26 | 5 |  | N | 361-HASAN
CTSU Pre-Award v2 - 364-KHAJA | Budget Negotiations | Role | CTSU Finance | 2017-08-26 | 5 |  | N | 364-KHAJA
Calendaring : Initial Calendar Build - 23-GUPTA | Acknowledge | User | Henry, Robin | 2017-08-26 | 0 | 2017-08-25 | N | 00134236
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | Acknowledge | User | Yunk, Jason | 2017-08-26 | 0 | 2017-08-18 | N | 00133290
Calendaring : Specification Update Request(s) - 00130757 | Make Update(s) | User | Zahs, Brian | 2017-08-26 | 5 |  | N | 00130757
Calendaring : Specification Update Request(s) - 00130757 | Re-Complete Calendar | User | Zahs, Brian | 2017-08-26 | 5 |  | N | 00130757
Pre-Award Financial - 188-RUBENSTEIN | Open to Accrual | Role | CTSU Administrator | 2017-08-27 | 4 |  | N | 188-RUBENSTEIN
Pre-Award Financial - 46-HIGGINS | Open to Accrual | Role | CTSU Administrator | 2017-08-27 | 4 |  | N | 46-HIGGINS
Pre-Award Financial - 56-RAO | Open to Accrual | Role | CTSU Administrator | 2017-08-27 | 4 |  | N | 00133286
CTSU Pre-Award - 326-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-27 | 1 | 2017-08-28 | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-27 | 1 | 2017-08-28 | N | 327-HIGGINS
Pre-Award Financial - 205-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-27 | 1 | 2017-08-28 | N | 205-HIGGINS
CTSU Pre-Award - 326-HIGGINS | Billing Calendar Received | Role | CTSU Finance | 2017-08-27 | 4 |  | N | 326-HIGGINS
CTSU Pre-Award - 326-HIGGINS | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-27 | 4 |  | N | 326-HIGGINS
CTSU Pre-Award - 326-HIGGINS | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-27 | 4 |  | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-27 | 4 |  | N | 327-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Request MCRU Budget | Role | CTSU Finance | 2017-08-27 | 4 |  | N | 327-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-27 | 4 |  | N | 327-HIGGINS
CTSU Pre-Award - 348-CHEY | Care Designations completed | Role | CTSU Finance | 2017-08-27 | 4 |  | N | 348-CHEY
Calendaring : Initial Calendar Build - 409-NASR | Acknowledge | Role | CTSU Finance | 2017-08-27 | 4 |  | N | 409-NASR
Pre-Award Financial - 205-HIGGINS | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-27 | 4 |  | N | 205-HIGGINS
Pre-Award Financial - 205-HIGGINS | Request MCRU Budget | Role | CTSU Finance | 2017-08-27 | 4 |  | N | 205-HIGGINS
Pre-Award Financial - 205-HIGGINS | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-27 | 4 |  | N | 205-HIGGINS
Calendaring : Amendment Checklist & Process - 00120441 | Assign to Analyst | User | Greene, Paula | 2017-08-27 | 1 | 2017-08-28 | N | 00120441
Pre-Award Financial - 86-AUCHUS | Budget Negotiations | User | Henry, Robin | 2017-08-27 | 0 | 2017-08-25 | N | 00132700
Calendaring : Amendment Checklist & Process - 00082635 | Assign to Analyst | User | Hodges, Lynda | 2017-08-27 | 4 |  | N | 00082635
Calendar & Budget Retrofit - 00101092 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-27 | 4 |  | N | 00101092
Calendar & Budget Retrofit - 00101092 | Review & Release Calendar | User | Oliver, Amy | 2017-08-27 | 0 | 2017-08-23 | N | 00101092
Calendar & Budget Retrofit - 00107927 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-27 | 4 |  | N | 00107927
Calendar & Budget Retrofit - 00107927 | Review & Release Calendar | User | Oliver, Amy | 2017-08-27 | 4 |  | N | 00107927
Calendar & Budget Retrofit - 00111185 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-08-27 | 4 |  | N | 00111185
Calendar & Budget Retrofit - 00111185 | Review & Release Calendar | User | Oliver, Amy | 2017-08-27 | 4 |  | N | 00111185
Pre-Award Financial - 246-AS-SANIE | PAN Released | User | Oliver, Amy | 2017-08-27 | 4 |  | N | 246-AS-SANIE
CTSU Pre-Award - 337-MIAN | Budget Negotiations | User | VanderElzen, Liz | 2017-08-27 | 2 | 2017-08-29 | N | 337-MIAN
CTSU Pre-Award - 338-MIAN | Budget Negotiations | User | VanderElzen, Liz | 2017-08-27 | 2 | 2017-08-29 | N | 00133457
CTSU Pre-Award v2 - 403-HIGGINS | Billing Calendar Received | User | VanderElzen, Liz | 2017-08-27 | 4 |  | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | Billing Calendar Received | User | VanderElzen, Liz | 2017-08-27 | 4 |  | N | 00134896
Pre-Award Financial - 11-HIGGINS | Billing Calendar Received | User | VanderElzen, Liz | 2017-08-27 | 0 | 2017-08-24 | N | 00134884
Calendaring : Amendment Checklist & Process - 00132251 | Complete Calendar and Document Approval | User | Zahs, Brian | 2017-08-27 | 0 | 2017-08-23 | N | 00132251
CTSU Pre-Award - 336-KHANNA | Open to Accrual | Role | CTSU Administrator | 2017-08-28 | 3 |  | N | 00133684
CTSU Pre-Award v2 - 380-LOK | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-28 | 3 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-28 | 3 |  | N | 381-HIGGINS
CTSU Pre-Award v2 - 393-HYZY | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-28 | 3 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-28 | 3 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 393-HYZY | Sponsor Reach out | Role | CTSU Coordinator | 2017-08-28 | 3 |  | N | 393-HYZY
CTSU Pre-Award v2 - 393-HYZY | UFA Completed | Role | CTSU Coordinator | 2017-08-28 | 3 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | Sponsor Reach out | Role | CTSU Coordinator | 2017-08-28 | 0 | 2017-08-14 | N | 396-SCHIOPU
CTSU Pre-Award v2 - 396-SCHIOPU | UFA Completed | Role | CTSU Coordinator | 2017-08-28 | 0 | 2017-08-14 | N | 396-SCHIOPU
CTSU Pre-Award v2 - 397-HODISH | Sponsor Reach out | Role | CTSU Coordinator | 2017-08-28 | 0 | 2017-08-07 | N | 397-HODISH
CTSU Pre-Award v2 - 447-RAO | Intake Form Completed | Role | CTSU Coordinator | 2017-08-28 | 0 | 2017-08-28 | N | 447-RAO
CTSU Pre-Award - 332-BELLOLI | PI approved Budget | Role | CTSU Finance | 2017-08-28 | 3 |  | N | 332-BELLOLI
CTSU Pre-Award v2 - 140-CHUNG | Billing Calendar Received | Role | CTSU Finance | 2017-08-28 | 3 |  | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | Billing Calendar Received | Role | CTSU Finance | 2017-08-28 | 3 |  | N | 00131840
CTSU Pre-Award v2 - 409-NASR | Care Designations completed | Role | CTSU Finance | 2017-08-28 | 3 |  | N | 409-NASR
CTSU Pre-Award v2 - 415-ROMANO | Final Budget | Role | CTSU Finance | 2017-08-28 | 3 |  | N | 415-ROMANO
Calendar & Budget Retrofit - 00066077 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-28 | 0 | 2017-08-28 | N | 00066077
Calendar & Budget Retrofit - 00067625 | Questions | Role | CTSU Finance | 2017-08-28 | 3 |  | N | 00067625
Calendar & Budget Retrofit - 00067625 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-28 | 0 | 2017-08-28 | N | 00067625
Calendar & Budget Retrofit - 00082356 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-28 | 0 | 2017-08-28 | N | 00082356
Calendar & Budget Retrofit - 00088652 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-28 | 0 | 2017-08-28 | N | 00088652
Calendar & Budget Retrofit - 00089260 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-28 | 0 | 2017-08-28 | N | 00089260
Calendar & Budget Retrofit - 00089730 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-28 | 0 | 2017-08-28 | N | 00089730
Calendar & Budget Retrofit - 00101426 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-28 | 0 | 2017-08-28 | N | 00101426
Calendar & Budget Retrofit - 00128761 2 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-28 | 0 | 2017-08-28 | N | 00128761
Calendar & Budget Retrofit - 00129863 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-28 | 0 | 2017-08-28 | N | 00129863
Calendar & Budget Retrofit - 00130757 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-28 | 0 | 2017-08-28 | N | 00130757
Calendar & Budget Retrofit - 116-BRUMMETT | Received calendar from Niyati | Role | CTSU Finance | 2017-08-28 | 0 | 2017-08-28 | N | 00129418
Calendar & Budget Retrofit - 175-ORAL | Received calendar from Niyati | Role | CTSU Finance | 2017-08-28 | 0 | 2017-08-28 | N | 175-ORAL
Calendaring : Specification Update Request(s) - 00130757 | Acknowledge | Role | CTSU Finance | 2017-08-28 | 3 |  | N | 00130757
Pre-Award Financial - 298-SCHIOPU | Final Budget | Role | CTSU Finance | 2017-08-28 | 3 |  | N | 298-SCHIOPU
CTSU Pre-Award - 341-STOFFEL | Final Budget | User | Henry, Robin | 2017-08-28 | 0 | 2017-08-21 | N | 00134997
Pre-Award Financial - 203-ELSE | Billing Calendar Received | User | Henry, Robin | 2017-08-28 | 3 |  | N | 00132173
Pre-Award Financial - 278-CONJEEVARAM | PAN Released | User | Henry, Robin | 2017-08-28 | 3 |  | N | 00133341
Calendaring : Amendment Checklist & Process - 00082635 | ** Footnote Edits | User | Hodges, Lynda | 2017-08-28 | 3 |  | N | 00082635
Calendaring : Amendment Checklist & Process - 00082635 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Hodges, Lynda | 2017-08-28 | 3 |  | N | 00082635
Calendaring : Amendment Checklist & Process - 00082635 | ** Visit Tolerance Edits | User | Hodges, Lynda | 2017-08-28 | 3 |  | N | 00082635
Calendaring : Amendment Checklist & Process - 00082635 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Hodges, Lynda | 2017-08-28 | 3 |  | N | 00082635
Calendaring : Initial Calendar Build - 205-HIGGINS | Complete MCA / QCT | User | Hodges, Lynda | 2017-08-28 | 3 |  | N | 205-HIGGINS
Calendaring : Initial Calendar Build - 205-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) | User | Hodges, Lynda | 2017-08-28 | 1 | 2017-08-29 | N | 205-HIGGINS
Calendaring : Initial Calendar Build - 205-HIGGINS | Nimblify Build is Complete & Ready for Import | User | Hodges, Lynda | 2017-08-28 | 3 |  | N | 205-HIGGINS
Calendaring : Initial Calendar Build - 23-GUPTA | CRAO Approval Issue & Documented | User | Hodges, Lynda | 2017-08-28 | 0 | 2017-08-25 | N | 00134236
Calendaring : Initial Calendar Build - 198-LUCKRITZ | Complete MCA / QCT | User | Munasinghe, Sadeepa | 2017-08-28 | 3 |  | N | 198-LUCKRITZ
Calendaring : Initial Calendar Build - 198-LUCKRITZ | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa | 2017-08-28 | 3 |  | N | 198-LUCKRITZ
Calendaring : Initial Calendar Build - 198-LUCKRITZ | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa | 2017-08-28 | 3 |  | N | 198-LUCKRITZ
Pre-Award Financial - 278-CONJEEVARAM | Initiate Post-Award Task List | User | Oliver, Amy | 2017-08-28 | 3 |  | N | 00133341
Calendaring : Amendment Checklist & Process - 00120441 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Przykucki, Anne | 2017-08-28 | 1 | 2017-08-29 | N | 00120441
Calendaring : Specification Update Request(s) - 00127136 2 | ** Request for Clarification | User | Yunk, Jason | 2017-08-28 | 3 |  | N | 00127136
Calendaring : Initial Calendar Build - 327-HIGGINS | Complete MCA / QCT | User | Zahs, Brian | 2017-08-28 | 3 |  | N | 327-HIGGINS
Calendaring : Initial Calendar Build - 327-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian | 2017-08-28 | 3 |  | N | 327-HIGGINS
Calendaring : Initial Calendar Build - 327-HIGGINS | Nimblify Build is Complete & Ready for Import | User | Zahs, Brian | 2017-08-28 | 3 |  | N | 327-HIGGINS
Calendaring : Initial Calendar Build - 326-HIGGINS | Complete MCA / QCT | User | van Dijk, Tim | 2017-08-28 | 3 |  | N | 326-HIGGINS
Calendaring : Initial Calendar Build - 326-HIGGINS | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim | 2017-08-28 | 1 | 2017-08-29 | N | 326-HIGGINS
Calendaring : Initial Calendar Build - 326-HIGGINS | Nimblify Build is Complete & Ready for Import | User | van Dijk, Tim | 2017-08-28 | 3 |  | N | 326-HIGGINS
CTSU Pre-Award v2 - 323-BOLLING | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-29 | 2 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-29 | 2 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 403-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-29 | 0 | 2017-08-17 | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-29 | 0 | 2017-08-17 | N | 00134896
Calendar & Budget Retrofit - 00088652 | Initiate Updates | Role | CTSU Finance | 2017-08-29 | 1 | 2017-08-30 | N | 00088652
Calendar & Budget Retrofit - 116-BRUMMETT | Initiate Updates | Role | CTSU Finance | 2017-08-29 | 1 | 2017-08-30 | N | 00129418
Calendaring : Amendment Checklist & Process - 00119926 | AME Calendaring Process Initiated | Role | CTSU Finance | 2017-08-29 | 1 | 2017-08-30 | N | 00119926
Calendaring : Amendment Checklist & Process - 00132251 | Acknowledge | Role | CTSU Finance | 2017-08-29 | 0 | 2017-08-23 | N | 00132251
Calendar & Budget Retrofit - 00066077 | Initiate Updates | User | Farmer, Amber | 2017-08-29 | 2 |  | N | 00066077
Calendar & Budget Retrofit - 00066077 | Questions | User | Farmer, Amber | 2017-08-29 | 2 |  | N | 00066077
Calendar & Budget Retrofit - 00082356 | Initiate Updates | User | Farmer, Amber | 2017-08-29 | 1 | 2017-08-30 | N | 00082356
Calendar & Budget Retrofit - 00089260 | Initiate Updates | User | Farmer, Amber | 2017-08-29 | 0 | 2017-08-29 | N | 00089260
Calendar & Budget Retrofit - 00101426 | Initiate Updates | User | Farmer, Amber | 2017-08-29 | 1 | 2017-08-30 | N | 00101426
Calendar & Budget Retrofit - 00101426 | Questions | User | Farmer, Amber | 2017-08-29 | 0 | 2017-08-28 | N | 00101426
Calendar & Budget Retrofit - 00130757 | Initiate Updates | User | Farmer, Amber | 2017-08-29 | 1 | 2017-08-30 | N | 00130757
Calendar & Budget Retrofit - 00130757 | Questions | User | Farmer, Amber | 2017-08-29 | 0 | 2017-08-25 | N | 00130757
Calendaring : Initial Calendar Build - 332-BELLOLI | Assign to Analyst | User | Greene, Paula | 2017-08-29 | 0 | 2017-08-29 | N | 332-BELLOLI
Calendaring : Initial Calendar Build - 332-BELLOLI | Feasibility Approval Notice Received | User | Greene, Paula | 2017-08-29 | 0 | 2017-08-29 | N | 332-BELLOLI
Calendaring : Initial Calendar Build - 332-BELLOLI | Submit Calendar Build Request and Docs to Nimblify | User | Greene, Paula | 2017-08-29 | 0 | 2017-08-29 | N | 332-BELLOLI
Pre-Award Financial - 23-GUPTA | Final Budget | User | Henry, Robin | 2017-08-29 | 0 | 2017-08-14 | N | 00134236
Calendaring : Amendment Checklist & Process - 00082635 | ** Items/Services : Addition or Removal of Procedures / Events | User | Hodges, Lynda | 2017-08-29 | 2 |  | N | 00082635
Calendaring : Amendment Checklist & Process - 00120441 | ** Items/Services : Addition or Removal of Procedures / Events | User | Przykucki, Anne | 2017-08-29 | 2 |  | N | 00120441
CTSU Pre-Award - 337-MIAN | Final Budget | User | VanderElzen, Liz | 2017-08-29 | 2 |  | N | 337-MIAN
Calendaring : Initial Calendar Build - 00134884 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-08-29 | 2 |  | N | 00134884
Calendaring : Initial Calendar Build - 403-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-08-29 | 2 |  | N | 00134895
Calendaring : Initial Calendar Build - 404-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | VanderElzen, Liz | 2017-08-29 | 2 |  | N | 00134896
Calendaring : Initial Calendar Build - 227-STEIGERWALT 3 | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian | 2017-08-29 | 0 | 2017-08-29 | N | 227-STEIGERWALT
Calendaring : Initial Calendar Build - 227-STEIGERWALT 3 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian | 2017-08-29 | 0 | 2017-08-29 | N | 227-STEIGERWALT
Calendaring : Initial Calendar Build - 416-MAO-DRAAYER | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Boyd, Collin | 2017-08-30 | 1 |  | N | 416-MAO-DRAAYER
CTSU Pre-Award v2 - 410-PAULUS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-08-30 | 1 |  | N | 410-PAULUS
Pre-Award Financial - 201-MCCUNE | Open to Accrual | Role | CTSU Administrator | 2017-08-30 | 1 |  | N | 201-MCCUNE
CTSU Pre-Award v2 - 361-HASAN | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-30 | 1 |  | N | 361-HASAN
CTSU Pre-Award v2 - 380-LOK | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-30 | 1 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-30 | 1 |  | N | 381-HIGGINS
CTSU Pre-Award v2 - 410-PAULUS | Sponsor Reach out | Role | CTSU Coordinator | 2017-08-30 | 0 | 2017-08-17 | N | 410-PAULUS
CTSU Pre-Award - 309-MOROI | Final Budget | Role | CTSU Finance | 2017-08-30 | 0 | 2017-08-03 | N | 309-MOROI
CTSU Pre-Award - 332-BELLOLI | Budget Negotiations | Role | CTSU Finance | 2017-08-30 | 1 |  | N | 332-BELLOLI
CTSU Pre-Award v2 - 361-HASAN | Planning Meeting Completed | Role | CTSU Finance | 2017-08-30 | 1 |  | N | 361-HASAN
CTSU Pre-Award v2 - 380-LOK | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-30 | 1 |  | N | 380-LOK
CTSU Pre-Award v2 - 380-LOK | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-30 | 1 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-30 | 1 |  | N | 381-HIGGINS
CTSU Pre-Award v2 - 381-HIGGINS | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-30 | 1 |  | N | 381-HIGGINS
CTSU Pre-Award v2 - 415-ROMANO | PAF routed | Role | CTSU Finance | 2017-08-30 | 1 |  | N | 415-ROMANO
Calendar & Budget Retrofit - 00125836 | Received calendar from Niyati | Role | CTSU Finance | 2017-08-30 | 0 | 2017-08-30 | N | 00125836
Calendar & Budget Retrofit - 175-ORAL | Questions | Role | CTSU Finance | 2017-08-30 | 1 |  | N | 175-ORAL
Calendaring : Initial Calendar Build - 140-CHUNG | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-08-30 | 1 |  | N | 00133613
Calendaring : Initial Calendar Build - 203-ELSE | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-08-30 | 1 |  | N | 00132173
Calendaring : Initial Calendar Build - 325-AUCHUS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-08-30 | 1 |  | N | 00131840
Pre-Award Financial - 255-LOK | PAN Released | Role | CTSU Finance | 2017-08-30 | 1 |  | N | 255-LOK
Pre-Award Financial - 298-SCHIOPU | PAF routed | Role | CTSU Finance | 2017-08-30 | 1 |  | N | 298-SCHIOPU
CTSU Pre-Award - 341-STOFFEL | PAF routed | User | Henry, Robin | 2017-08-30 | 0 | 2017-08-22 | N | 00134997
Calendaring : Amendment Checklist & Process - 00082635 | ** Other | User | Hodges, Lynda | 2017-08-30 | 1 |  | N | 00082635
Calendaring : Amendment Checklist & Process - 00082635 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Hodges, Lynda | 2017-08-30 | 1 |  | N | 00082635
Calendaring : Amendment Checklist & Process - 00082635 | ** Visits : Addition or Removal of Time Points | User | Hodges, Lynda | 2017-08-30 | 1 |  | N | 00082635
Calendaring : Amendment Checklist & Process - 00082635 | Request Care Designations | User | Hodges, Lynda | 2017-08-30 | 1 |  | N | 00082635
Calendaring : Amendment Checklist & Process - 00082635 | Update RSH Source in MBECT | User | Hodges, Lynda | 2017-08-30 | 1 |  | N | 00082635
Calendaring : Initial Calendar Build - 205-HIGGINS | Attach Build Notes ( as Protocol Doc ) | User | Hodges, Lynda | 2017-08-30 | 1 |  | N | 205-HIGGINS
Calendaring : Initial Calendar Build - 205-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hodges, Lynda | 2017-08-30 | 1 |  | N | 205-HIGGINS
Calendaring : Initial Calendar Build - 198-LUCKRITZ | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa | 2017-08-30 | 1 |  | N | 198-LUCKRITZ
Calendaring : Initial Calendar Build - 198-LUCKRITZ | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa | 2017-08-30 | 1 |  | N | 198-LUCKRITZ
Calendaring : Amendment Checklist & Process - 00120441 | Request Care Designations | User | Przykucki, Anne | 2017-08-30 | 1 |  | N | 00120441
Calendaring : Amendment Checklist & Process - 00120441 | Update RSH Source in MBECT | User | Przykucki, Anne | 2017-08-30 | 1 |  | N | 00120441
CTSU Pre-Award - 350-HIGGINS | Final Budget | User | VanderElzen, Liz | 2017-08-30 | 1 |  | N | 00133054
CTSU Pre-Award - 351-HIGGINS | Final Budget | User | VanderElzen, Liz | 2017-08-30 | 1 |  | N | 00134870
Pre-Award Financial - 179-LUGOGO | Final Budget | User | VanderElzen, Liz | 2017-08-30 | 1 |  | N | 179-LUGOGO
Calendaring : Amendment Checklist & Process - 00094136 | AME Calendaring Process Initiated | User | Watson, Donna | 2017-08-30 | 0 | 2017-08-30 | N | 00094136
Calendaring : Initial Calendar Build - 327-HIGGINS | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian | 2017-08-30 | 1 |  | N | 327-HIGGINS
Calendaring : Initial Calendar Build - 327-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian | 2017-08-30 | 1 |  | N | 327-HIGGINS
Calendaring : Initial Calendar Build - 326-HIGGINS | Attach Build Notes ( as Protocol Doc ) | User | van Dijk, Tim | 2017-08-30 | 1 |  | N | 326-HIGGINS
Calendaring : Initial Calendar Build - 326-HIGGINS | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | van Dijk, Tim | 2017-08-30 | 1 |  | N | 326-HIGGINS
CTSU Pre-Award v2 - 390-DAY | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-08-31 | 0 |  | N | 390-DAY
CTSU Pre-Award - 359-SMITH | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-31 | 0 |  | N | 359-SMITH
CTSU Pre-Award - 359-SMITH | Planning Meeting Completed | Role | CTSU Coordinator | 2017-08-31 | 0 |  | N | 359-SMITH
CTSU Pre-Award v2 - 323-BOLLING | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-31 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-08-31 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 403-HIGGINS | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-31 | 0 |  | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | IRB Application Submitted | Role | CTSU Coordinator | 2017-08-31 | 0 |  | N | 00134896
CTSU Pre-Award - 348-CHEY | Internal Budget Finished | Role | CTSU Finance | 2017-08-31 | 0 |  | N | 348-CHEY
CTSU Pre-Award v2 - 323-BOLLING | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-31 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 323-BOLLING | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-31 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-08-31 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-08-31 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 415-ROMANO | OnCore Budget Build | Role | CTSU Finance | 2017-08-31 | 0 |  | N | 415-ROMANO
Pre-Award Financial - 298-SCHIOPU | Initiate Post-Award Task List | Role | CTSU Finance | 2017-08-31 | 0 |  | N | 298-SCHIOPU
CTSU Pre-Award v2 - 00132705 2 | Internal Budget Finished | User | Dahlgren, Molly | 2017-08-31 | 0 |  | N | 00132705
Pre-Award Financial - 23-GUPTA | PAF routed | User | Henry, Robin | 2017-08-31 | 0 | 2017-08-17 | N | 00134236
Calendaring : Amendment Checklist & Process - 00119926 | Assign to Analyst | User | Hodges, Lynda | 2017-08-31 | 0 | 2017-08-30 | N | 00119926
Open to Accrual - 00121569 2 | MiChart Verifications | User | Miller, Diana | 2017-08-31 | 0 |  | N | 00121569
Pre-Award Financial - 298-SCHIOPU | PAN Released | User | Oliver, Amy | 2017-08-31 | 0 |  | N | 298-SCHIOPU
CTSU Pre-Award - 337-MIAN | PAF routed | User | VanderElzen, Liz | 2017-08-31 | 0 |  | N | 337-MIAN
CTSU Pre-Award v2 - 403-HIGGINS | Planning Meeting Completed | User | VanderElzen, Liz | 2017-08-31 | 0 | 2017-08-30 | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | Planning Meeting Completed | User | VanderElzen, Liz | 2017-08-31 | 0 | 2017-08-30 | N | 00134896
Pre-Award Financial - 11-HIGGINS | Planning Meeting Completed | User | VanderElzen, Liz | 2017-08-31 | 0 | 2017-08-30 | N | 00134884
Open to Accrual - 00121569 2 | Contract Executed | User | Watson, Donna | 2017-08-31 | 0 | 2017-04-25 | N | 00121569
CTSU Post-Award - 00089260 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-08-31 | 0 |  | N | 00089260
CTSU Pre-Award - 341-STOFFEL | OnCore Budget Build | User | Yunk, Jason | 2017-08-31 | 0 |  | N | 00134997
Pre-Award Financial - 155-ORAL | OnCore Budget Build | User | Yunk, Jason | 2017-08-31 | 0 |  | N | 00130803
Pre-Award Financial - 298-SCHIOPU | OnCore Budget Build | User | Yunk, Jason | 2017-08-31 | 0 |  | N | 298-SCHIOPU
Open to Accrual - 00121569 2 | IRB Approval | User | Ziolkowski, Jaimie | 2017-08-31 | 0 |  | N | 00121569
Open to Accrual - 00121569 2 | Investigational Drug/Device Supplies Available | User | Ziolkowski, Jaimie | 2017-08-31 | 0 |  | N | 00121569
Calendaring : Initial Calendar Build - 00134884 | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-08-31 | 0 |  | N | 00134884
Calendaring : Initial Calendar Build - 00134884 | Make Updates | User | van Dijk, Tim | 2017-08-31 | 0 |  | N | 00134884
Calendaring : Initial Calendar Build - 403-HIGGINS | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-08-31 | 0 |  | N | 00134895
Calendaring : Initial Calendar Build - 403-HIGGINS | Make Updates | User | van Dijk, Tim | 2017-08-31 | 0 |  | N | 00134895
Calendaring : Initial Calendar Build - 404-HIGGINS | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-08-31 | 0 |  | N | 00134896
Calendaring : Initial Calendar Build - 404-HIGGINS | Make Updates | User | van Dijk, Tim | 2017-08-31 | 0 |  | N | 00134896
CTSU Pre-Award v2 - 140-CHUNG | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-01 | 0 |  | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-01 | 0 |  | N | 00131840
CTSU Post-Award - 00124920 | Next Schedule Reconciliation | Role | CTSU Finance | 2017-09-01 | 0 |  | N | 00124920
CTSU Pre-Award - 309-MOROI | PAF routed | Role | CTSU Finance | 2017-09-01 | 0 | 2017-08-03 | N | 309-MOROI
CTSU Pre-Award - 370-LOK | Billing Calendar Received | Role | CTSU Finance | 2017-09-01 | 0 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | Billing Calendar Received | Role | CTSU Finance | 2017-09-01 | 0 |  | N | 371-LOK
CTSU Pre-Award v2 - 140-CHUNG | Planning Meeting Completed | Role | CTSU Finance | 2017-09-01 | 0 |  | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | Planning Meeting Completed | Role | CTSU Finance | 2017-09-01 | 0 |  | N | 00131840
CTSU Pre-Award v2 - 409-NASR | Internal Budget Finished | Role | CTSU Finance | 2017-09-01 | 0 |  | N | 409-NASR
CTSU Pre-Award v2 - 415-ROMANO | Calendar Released | Role | CTSU Finance | 2017-09-01 | 0 |  | N | 415-ROMANO
Calendar & Budget Retrofit - 00088652 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-09-01 | 0 |  | N | 00088652
Calendar & Budget Retrofit - 00088652 | Review & Release Calendar | Role | CTSU Finance | 2017-09-01 | 0 | 2017-08-30 | N | 00088652
Calendar & Budget Retrofit - 00128761 2 | Review & Release Calendar | Role | CTSU Finance | 2017-09-01 | 0 |  | N | 00128761
Calendar & Budget Retrofit - 00129863 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-09-01 | 0 |  | N | 00129863
Calendar & Budget Retrofit - 116-BRUMMETT | Notify Niyati Updated Calendar was Released | Role | CTSU Finance | 2017-09-01 | 0 |  | N | 00129418
Calendar & Budget Retrofit - 116-BRUMMETT | Review & Release Calendar | Role | CTSU Finance | 2017-09-01 | 0 | 2017-08-28 | N | 00129418
Pre-Award Financial - 198-LUCKRITZ | Planning Meeting Completed | Role | CTSU Finance | 2017-09-01 | 0 | 2017-08-30 | N | 198-LUCKRITZ
Calendaring : Amendment Checklist & Process - 00094136 | Assign to Analyst | User | Greene, Paula | 2017-09-01 | 0 | 2017-08-28 | N | 00094136
Pre-Award Financial - 203-ELSE | Planning Meeting Completed | User | Henry, Robin | 2017-09-01 | 0 | 2017-08-29 | N | 00132173
Calendaring : Initial Calendar Build - 332-BELLOLI | Complete MCA / QCT | User | Hess, Aaron | 2017-09-01 | 0 |  | N | 332-BELLOLI
Calendaring : Initial Calendar Build - 332-BELLOLI | Complete SVS & Pricing List ( Built & Coded ) | User | Hess, Aaron | 2017-09-01 | 0 | 2017-08-30 | N | 332-BELLOLI
Calendaring : Initial Calendar Build - 332-BELLOLI | Nimblify Build is Complete & Ready for Import | User | Hess, Aaron | 2017-09-01 | 0 |  | N | 332-BELLOLI
Calendaring : Amendment Checklist & Process - 00119926 | ** Footnote Edits | User | Hodges, Lynda | 2017-09-01 | 0 | 2017-08-30 | N | 00119926
Calendaring : Amendment Checklist & Process - 00119926 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Hodges, Lynda | 2017-09-01 | 0 | 2017-08-30 | N | 00119926
Calendaring : Initial Calendar Build - 140-CHUNG | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-09-01 | 0 |  | N | 00133613
Calendaring : Initial Calendar Build - 140-CHUNG | Make Updates | User | Munasinghe, Sadeepa | 2017-09-01 | 0 |  | N | 00133613
Calendaring : Initial Calendar Build - 203-ELSE | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-09-01 | 0 |  | N | 00132173
Calendaring : Initial Calendar Build - 203-ELSE | Make Updates | User | Munasinghe, Sadeepa | 2017-09-01 | 0 |  | N | 00132173
CTSU Pre-Award - 341-STOFFEL | Calendar Released | User | Oliver, Amy | 2017-09-01 | 0 |  | N | 00134997
Calendar & Budget Retrofit - 00066077 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-09-01 | 0 |  | N | 00066077
Calendar & Budget Retrofit - 00066077 | Review & Release Calendar | User | Oliver, Amy | 2017-09-01 | 0 |  | N | 00066077
Calendar & Budget Retrofit - 00082356 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-09-01 | 0 |  | N | 00082356
Calendar & Budget Retrofit - 00082356 | Review & Release Calendar | User | Oliver, Amy | 2017-09-01 | 0 |  | N | 00082356
Calendar & Budget Retrofit - 00089260 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-09-01 | 0 |  | N | 00089260
Calendar & Budget Retrofit - 00089260 | Review & Release Calendar | User | Oliver, Amy | 2017-09-01 | 0 | 2017-08-29 | N | 00089260
Calendar & Budget Retrofit - 00101426 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-09-01 | 0 |  | N | 00101426
Calendar & Budget Retrofit - 00101426 | Review & Release Calendar | User | Oliver, Amy | 2017-09-01 | 0 | 2017-08-30 | N | 00101426
Calendar & Budget Retrofit - 00130757 | Notify Niyati Updated Calendar was Released | User | Oliver, Amy | 2017-09-01 | 0 |  | N | 00130757
Calendar & Budget Retrofit - 00130757 | Review & Release Calendar | User | Oliver, Amy | 2017-09-01 | 0 | 2017-08-30 | N | 00130757
Pre-Award Financial - 155-ORAL | Calendar Released | User | Oliver, Amy | 2017-09-01 | 0 |  | N | 00130803
Pre-Award Financial - 298-SCHIOPU | Calendar Released | User | Oliver, Amy | 2017-09-01 | 0 |  | N | 298-SCHIOPU
CTSU Pre-Award - 350-HIGGINS | PAF routed | User | VanderElzen, Liz | 2017-09-01 | 0 |  | N | 00133054
CTSU Pre-Award - 351-HIGGINS | PAF routed | User | VanderElzen, Liz | 2017-09-01 | 0 |  | N | 00134870
CTSU Pre-Award - 359-SMITH | Care Designations completed | User | VanderElzen, Liz | 2017-09-01 | 0 |  | N | 359-SMITH
Pre-Award Financial - 179-LUGOGO | PAF routed | User | VanderElzen, Liz | 2017-09-01 | 0 |  | N | 179-LUGOGO
CTSU Post-Award - 00129716 | Next Schedule Reconciliation | User | Yunk, Jason | 2017-09-01 | 0 |  | N | 00129716
CTSU Pre-Award - 337-MIAN | OnCore Budget Build | User | Yunk, Jason | 2017-09-01 | 0 |  | N | 337-MIAN
Calendaring : Initial Calendar Build - 416-MAO-DRAAYER | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-09-01 | 0 |  | N | 416-MAO-DRAAYER
Calendaring : Initial Calendar Build - 416-MAO-DRAAYER | Make Updates | User | Zahs, Brian | 2017-09-01 | 0 |  | N | 416-MAO-DRAAYER
Calendaring : Initial Calendar Build - 325-AUCHUS | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-09-01 | 0 |  | N | 00131840
Calendaring : Initial Calendar Build - 325-AUCHUS | Make Updates | User | van Dijk, Tim | 2017-09-01 | 0 |  | N | 00131840
CTSU Pre-Award v2 - 390-DAY | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-09-02 | 0 |  | N | 390-DAY
CTSU Pre-Award - 313-CONJEEVARAM | Final Budget | Role | CTSU Finance | 2017-09-02 | 0 |  | N | 313-CONJEEVARAM
CTSU Pre-Award v2 - 361-HASAN | Care Designations completed | Role | CTSU Finance | 2017-09-02 | 0 |  | N | 361-HASAN
CTSU Pre-Award v2 - 390-DAY | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-09-02 | 0 |  | N | 390-DAY
CTSU Pre-Award v2 - 390-DAY | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-09-02 | 0 |  | N | 390-DAY
Pre-Award Financial - 261-LUGOGO | OnCore Budget Build | Role | CTSU Finance | 2017-09-02 | 0 |  | N | 261-LUGOGO
Calendaring : Amendment Checklist & Process - 00119926 | ** Items/Services : Addition or Removal of Procedures / Events | User | Hodges, Lynda | 2017-09-02 | 0 |  | N | 00119926
Calendaring : Amendment Checklist & Process - 00119926 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Hodges, Lynda | 2017-09-02 | 0 | 2017-08-30 | N | 00119926
Calendaring : Amendment Checklist & Process - 00094136 | ** Footnote Edits | User | Munasinghe, Sadeepa | 2017-09-02 | 0 | 2017-08-28 | N | 00094136
Calendaring : Amendment Checklist & Process - 00094136 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Munasinghe, Sadeepa | 2017-09-02 | 0 | 2017-08-28 | N | 00094136
Calendaring : Amendment Checklist & Process - 00094136 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Munasinghe, Sadeepa | 2017-09-02 | 0 | 2017-08-28 | N | 00094136
CTSU Pre-Award - 337-MIAN | Calendar Released | User | Oliver, Amy | 2017-09-02 | 0 |  | N | 337-MIAN
Calendaring : Initial Calendar Build - 00134884 | Acknowledge | User | VanderElzen, Liz | 2017-09-02 | 0 |  | N | 00134884
Calendaring : Initial Calendar Build - 403-HIGGINS | Acknowledge | User | VanderElzen, Liz | 2017-09-02 | 0 |  | N | 00134895
Calendaring : Initial Calendar Build - 404-HIGGINS | Acknowledge | User | VanderElzen, Liz | 2017-09-02 | 0 |  | N | 00134896
CTSU Pre-Award - 350-HIGGINS | OnCore Budget Build | User | Yunk, Jason | 2017-09-02 | 0 |  | N | 00133054
CTSU Pre-Award - 351-HIGGINS | OnCore Budget Build | User | Yunk, Jason | 2017-09-02 | 0 |  | N | 00134870
CTSU Pre-Award - 326-HIGGINS | Care Designations completed | Role | CTSU Finance | 2017-09-03 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 348-CHEY | PI approved Budget | Role | CTSU Finance | 2017-09-03 | 0 |  | N | 348-CHEY
Calendaring : Initial Calendar Build - 140-CHUNG | Acknowledge | Role | CTSU Finance | 2017-09-03 | 0 |  | N | 00133613
Calendaring : Initial Calendar Build - 203-ELSE | Acknowledge | Role | CTSU Finance | 2017-09-03 | 0 |  | N | 00132173
Calendaring : Initial Calendar Build - 325-AUCHUS | Acknowledge | Role | CTSU Finance | 2017-09-03 | 0 |  | N | 00131840
Pre-Award Financial - 261-LUGOGO | Calendar Released | Role | CTSU Finance | 2017-09-03 | 0 |  | N | 261-LUGOGO
CTSU Pre-Award v2 - 00132705 2 | PI approved Budget | User | Dahlgren, Molly | 2017-09-03 | 0 |  | N | 00132705
Pre-Award Financial - FONTANA-1 | Final Budget | User | Henry, Robin | 2017-09-03 | 0 | 2017-08-17 | N | 00133153
Calendaring : Initial Calendar Build - 332-BELLOLI | Attach Build Notes ( as Protocol Doc ) | User | Hess, Aaron | 2017-09-03 | 0 |  | N | 332-BELLOLI
Calendaring : Initial Calendar Build - 332-BELLOLI | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hess, Aaron | 2017-09-03 | 0 |  | N | 332-BELLOLI
Calendaring : Amendment Checklist & Process - 00119926 | ** Other | User | Hodges, Lynda | 2017-09-03 | 0 | 2017-08-30 | N | 00119926
Calendaring : Amendment Checklist & Process - 00119926 | Request Care Designations | User | Hodges, Lynda | 2017-09-03 | 0 |  | N | 00119926
Calendaring : Amendment Checklist & Process - 00119926 | Update RSH Source in MBECT | User | Hodges, Lynda | 2017-09-03 | 0 |  | N | 00119926
Calendaring : Amendment Checklist & Process - 00094136 | ** Items/Services : Addition or Removal of Procedures / Events | User | Munasinghe, Sadeepa | 2017-09-03 | 0 | 2017-08-28 | N | 00094136
CTSU Pre-Award - 350-HIGGINS | Calendar Released | User | Oliver, Amy | 2017-09-03 | 0 |  | N | 00133054
CTSU Pre-Award - 351-HIGGINS | Calendar Released | User | Oliver, Amy | 2017-09-03 | 0 |  | N | 00134870
Pre-Award Financial - 263-DELMONTE | PAN Released | User | Oliver, Amy | 2017-09-03 | 0 |  | N | 263-DELMONTE
CTSU Pre-Award v2 - 403-HIGGINS | Care Designations completed | User | VanderElzen, Liz | 2017-09-03 | 0 |  | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | Care Designations completed | User | VanderElzen, Liz | 2017-09-03 | 0 |  | N | 00134896
Pre-Award Financial - 11-HIGGINS | Care Designations completed | User | VanderElzen, Liz | 2017-09-03 | 0 |  | N | 00134884
Calendaring : Initial Calendar Build - 416-MAO-DRAAYER | Acknowledge | User | Watson, Donna | 2017-09-03 | 0 |  | N | 416-MAO-DRAAYER
CTSU Pre-Award - 341-STOFFEL | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-04 | 0 |  | N | 00134997
CTSU Pre-Award v2 - 393-HYZY | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-09-04 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-09-04 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 415-ROMANO | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-04 | 0 |  | N | 415-ROMANO
Pre-Award Financial - 155-ORAL | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-04 | 0 |  | N | 00130803
Pre-Award Financial - 298-SCHIOPU | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-04 | 0 |  | N | 298-SCHIOPU
CTSU Pre-Award - 313-CONJEEVARAM | PAF routed | Role | CTSU Finance | 2017-09-04 | 0 |  | N | 313-CONJEEVARAM
CTSU Pre-Award - 326-HIGGINS | Request MCRU Budget | Role | CTSU Finance | 2017-09-04 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Billing Calendar Received | Role | CTSU Finance | 2017-09-04 | 0 |  | N | 327-HIGGINS
CTSU Pre-Award v2 - 140-CHUNG | Care Designations completed | Role | CTSU Finance | 2017-09-04 | 0 |  | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | Care Designations completed | Role | CTSU Finance | 2017-09-04 | 0 |  | N | 00131840
CTSU Pre-Award v2 - 409-NASR | PI approved Budget | Role | CTSU Finance | 2017-09-04 | 0 |  | N | 409-NASR
Calendaring : Amendment Checklist & Process - 00082635 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance | 2017-09-04 | 0 |  | N | 00082635
Calendaring : Amendment Checklist & Process - 00120441 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance | 2017-09-04 | 0 |  | N | 00120441
Pre-Award Financial - 203-ELSE | Care Designations completed | Role | CTSU Finance | 2017-09-04 | 0 |  | N | 00132173
Pre-Award Financial - 205-HIGGINS | Billing Calendar Received | Role | CTSU Finance | 2017-09-04 | 0 |  | N | 205-HIGGINS
CTSU Pre-Award - 336-KHANNA | Initiate Post-Award Task List | User | Henry, Robin | 2017-09-04 | 0 |  | N | 00133684
Calendaring : Amendment Checklist & Process - 00094136 | Update RSH Source in MBECT | User | Munasinghe, Sadeepa | 2017-09-04 | 0 |  | N | 00094136
CTSU Pre-Award - 336-KHANNA | PAN Released | User | Oliver, Amy | 2017-09-04 | 0 |  | N | 00133684
CTSU Pre-Award - 337-MIAN | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-05 | 0 |  | N | 337-MIAN
CTSU Pre-Award - 370-LOK | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-05 | 0 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-05 | 0 |  | N | 371-LOK
CTSU Pre-Award - 348-CHEY | Budget Negotiations | Role | CTSU Finance | 2017-09-05 | 0 |  | N | 348-CHEY
CTSU Pre-Award - 370-LOK | Planning Meeting Completed | Role | CTSU Finance | 2017-09-05 | 0 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | Planning Meeting Completed | Role | CTSU Finance | 2017-09-05 | 0 |  | N | 371-LOK
CTSU Pre-Award v2 - 00132705 2 | Budget Negotiations | User | Dahlgren, Molly | 2017-09-05 | 0 |  | N | 00132705
Pre-Award Financial - 110-SCHIOPU | Final Budget | User | Henry, Robin | 2017-09-05 | 0 |  | N | 00134444
Pre-Award Financial - FONTANA-1 | PAF routed | User | Henry, Robin | 2017-09-05 | 0 | 2017-08-21 | N | 00133153
Pre-Award Financial - 251-COMER | Final Budget | User | VanderElzen, Liz | 2017-09-05 | 0 |  | N | 00134232
CTSU Pre-Award - 313-CONJEEVARAM | OnCore Budget Build | User | Yunk, Jason | 2017-09-05 | 0 |  | N | 313-CONJEEVARAM
CTSU Pre-Award - 341-STOFFEL | Open to Accrual | Role | CTSU Administrator | 2017-09-06 | 0 |  | N | 00134997
CTSU Pre-Award - 350-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-06 | 0 |  | N | 00133054
CTSU Pre-Award - 351-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-06 | 0 |  | N | 00134870
CTSU Pre-Award v2 - 410-PAULUS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-09-06 | 0 |  | N | 410-PAULUS
CTSU Pre-Award v2 - 415-ROMANO | Open to Accrual | Role | CTSU Administrator | 2017-09-06 | 0 |  | N | 415-ROMANO
Pre-Award Financial - 155-ORAL | Open to Accrual | Role | CTSU Administrator | 2017-09-06 | 0 |  | N | 00130803
Pre-Award Financial - 261-LUGOGO | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-06 | 0 |  | N | 261-LUGOGO
Pre-Award Financial - 298-SCHIOPU | Open to Accrual | Role | CTSU Administrator | 2017-09-06 | 0 |  | N | 298-SCHIOPU
CTSU Pre-Award v2 - 393-HYZY | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-09-06 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-09-06 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 361-HASAN | Internal Budget Finished | Role | CTSU Finance | 2017-09-06 | 0 |  | N | 361-HASAN
CTSU Pre-Award v2 - 393-HYZY | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-09-06 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 393-HYZY | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-09-06 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-09-06 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 396-SCHIOPU | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-09-06 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 409-NASR | Budget Negotiations | Role | CTSU Finance | 2017-09-06 | 0 |  | N | 409-NASR
Calendaring : Initial Calendar Build - 198-LUCKRITZ | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-09-06 | 0 |  | N | 198-LUCKRITZ
Calendaring : Initial Calendar Build - 205-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-09-06 | 0 |  | N | 205-HIGGINS
Calendaring : Initial Calendar Build - 326-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-09-06 | 0 |  | N | 326-HIGGINS
Calendaring : Initial Calendar Build - 327-HIGGINS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-09-06 | 0 |  | N | 327-HIGGINS
Calendaring : Amendment Checklist & Process - 00082635 | Complete Calendar and Document Approval | User | Hodges, Lynda | 2017-09-06 | 0 |  | N | 00082635
CTSU Pre-Award - 313-CONJEEVARAM | Calendar Released | User | Oliver, Amy | 2017-09-06 | 0 |  | N | 313-CONJEEVARAM
Calendaring : Amendment Checklist & Process - 00120441 | Complete Calendar and Document Approval | User | Przykucki, Anne | 2017-09-06 | 0 |  | N | 00120441
CTSU Pre-Award - 337-MIAN | Open to Accrual | Role | CTSU Administrator | 2017-09-07 | 0 |  | N | 337-MIAN
CTSU Pre-Award v2 - 428-LAW | Feasibility w/Documents received | Role | CTSU Administrator | 2017-09-07 | 0 |  | N | 00135072
CTSU Pre-Award v2 - 380-LOK | Billing Calendar Received | Role | CTSU Finance | 2017-09-07 | 0 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | Billing Calendar Received | Role | CTSU Finance | 2017-09-07 | 0 |  | N | 381-HIGGINS
Pre-Award Financial - 112-FLAHERTY | PAN Released | Role | CTSU Finance | 2017-09-07 | 0 |  | N | 112-FLAHERTY
Pre-Award Financial - 110-SCHIOPU | PAF routed | User | Henry, Robin | 2017-09-07 | 0 |  | N | 00134444
CTSU Pre-Award - 359-SMITH | Internal Budget Finished | User | VanderElzen, Liz | 2017-09-07 | 0 |  | N | 359-SMITH
CTSU Pre-Award v2 - 403-HIGGINS | Internal Budget Finished | User | VanderElzen, Liz | 2017-09-07 | 0 |  | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | Internal Budget Finished | User | VanderElzen, Liz | 2017-09-07 | 0 |  | N | 00134896
Pre-Award Financial - 11-HIGGINS | Internal Budget Finished | User | VanderElzen, Liz | 2017-09-07 | 0 |  | N | 00134884
Pre-Award Financial - 251-COMER | PAF routed | User | VanderElzen, Liz | 2017-09-07 | 0 |  | N | 00134232
Open to Accrual - 00121569 2 | Project Award Notice (PAN) Received | User | Watson, Donna | 2017-09-07 | 0 |  | N | 00121569
Pre-Award Financial - 190-SCHIOPU | OnCore Budget Build | User | Yunk, Jason | 2017-09-07 | 0 |  | N | 00134443
Open to Accrual - 00121569 2 | Sponsor/Organizing Group Approval Granted for Initiation of Study | User | Ziolkowski, Jaimie | 2017-09-07 | 0 |  | N | 00121569
CTSU Pre-Award - 350-HIGGINS | Open to Accrual | Role | CTSU Administrator | 2017-09-08 | 0 |  | N | 00133054
CTSU Pre-Award - 351-HIGGINS | Open to Accrual | Role | CTSU Administrator | 2017-09-08 | 0 |  | N | 00134870
CTSU Pre-Award v2 - 430-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator | 2017-09-08 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | Feasibility w/Documents received | Role | CTSU Administrator | 2017-09-08 | 0 |  | N | 432-JAYASUNDERA
Pre-Award Financial - 261-LUGOGO | Open to Accrual | Role | CTSU Administrator | 2017-09-08 | 0 |  | N | 261-LUGOGO
CTSU Pre-Award - 326-HIGGINS | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-08 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-08 | 0 |  | N | 327-HIGGINS
CTSU Pre-Award v2 - 410-PAULUS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-09-08 | 0 |  | N | 410-PAULUS
CTSU Pre-Award v2 - 430-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator | 2017-09-08 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 430-HIGGINS | UFA Completed | Role | CTSU Coordinator | 2017-09-08 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | Sponsor Reach out | Role | CTSU Coordinator | 2017-09-08 | 0 |  | N | 432-JAYASUNDERA
CTSU Pre-Award v2 - 432-JAYASUNDERA | UFA Completed | Role | CTSU Coordinator | 2017-09-08 | 0 |  | N | 432-JAYASUNDERA
CTSU Pre-Award - 326-HIGGINS | Planning Meeting Completed | Role | CTSU Finance | 2017-09-08 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Planning Meeting Completed | Role | CTSU Finance | 2017-09-08 | 0 |  | N | 327-HIGGINS
CTSU Pre-Award - 370-LOK | Care Designations completed | Role | CTSU Finance | 2017-09-08 | 0 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | Care Designations completed | Role | CTSU Finance | 2017-09-08 | 0 |  | N | 371-LOK
CTSU Pre-Award v2 - 140-CHUNG | Internal Budget Finished | Role | CTSU Finance | 2017-09-08 | 0 |  | N | 00133613
CTSU Pre-Award v2 - 323-BOLLING | Billing Calendar Received | Role | CTSU Finance | 2017-09-08 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 325-AUCHUS | Internal Budget Finished | Role | CTSU Finance | 2017-09-08 | 0 |  | N | 00131840
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Billing Calendar Received | Role | CTSU Finance | 2017-09-08 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 410-PAULUS | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-09-08 | 0 |  | N | 410-PAULUS
CTSU Pre-Award v2 - 410-PAULUS | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-09-08 | 0 |  | N | 410-PAULUS
Calendaring : Amendment Checklist & Process - 00082635 | Acknowledge | Role | CTSU Finance | 2017-09-08 | 0 |  | N | 00082635
Calendaring : Amendment Checklist & Process - 00119926 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance | 2017-09-08 | 0 |  | N | 00119926
Calendaring : Amendment Checklist & Process - 00120441 | Acknowledge | Role | CTSU Finance | 2017-09-08 | 0 |  | N | 00120441
Pre-Award Financial - 203-ELSE | Internal Budget Finished | Role | CTSU Finance | 2017-09-08 | 0 |  | N | 00132173
Pre-Award Financial - 205-HIGGINS | Planning Meeting Completed | Role | CTSU Finance | 2017-09-08 | 0 |  | N | 205-HIGGINS
Calendaring : Initial Calendar Build - 205-HIGGINS | Complete Calendar ( ie. Ready for Financials ) | User | Hodges, Lynda | 2017-09-08 | 0 |  | N | 205-HIGGINS
Calendaring : Initial Calendar Build - 205-HIGGINS | Make Updates | User | Hodges, Lynda | 2017-09-08 | 0 |  | N | 205-HIGGINS
Calendaring : Initial Calendar Build - 198-LUCKRITZ | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa | 2017-09-08 | 0 |  | N | 198-LUCKRITZ
Calendaring : Initial Calendar Build - 198-LUCKRITZ | Make Updates | User | Munasinghe, Sadeepa | 2017-09-08 | 0 |  | N | 198-LUCKRITZ
Pre-Award Financial - 190-SCHIOPU | Calendar Released | User | Oliver, Amy | 2017-09-08 | 0 |  | N | 00134443
Calendaring : Initial Calendar Build - 327-HIGGINS | Complete Calendar ( ie. Ready for Financials ) | User | Zahs, Brian | 2017-09-08 | 0 |  | N | 327-HIGGINS
Calendaring : Initial Calendar Build - 327-HIGGINS | Make Updates | User | Zahs, Brian | 2017-09-08 | 0 |  | N | 327-HIGGINS
Calendaring : Initial Calendar Build - 326-HIGGINS | Complete Calendar ( ie. Ready for Financials ) | User | van Dijk, Tim | 2017-09-08 | 0 |  | N | 326-HIGGINS
Calendaring : Initial Calendar Build - 326-HIGGINS | Make Updates | User | van Dijk, Tim | 2017-09-08 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 313-CONJEEVARAM | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-09 | 0 |  | N | 313-CONJEEVARAM
CTSU Pre-Award v2 - 361-HASAN | PI approved Budget | Role | CTSU Finance | 2017-09-09 | 0 |  | N | 361-HASAN
CTSU Pre-Award v2 - 364-KHAJA | Final Budget | Role | CTSU Finance | 2017-09-09 | 0 |  | N | 364-KHAJA
CTSU Post-Award - 00127505 | Next Schedule Reconciliation | Role | CTSU Finance | 2017-09-10 | 0 |  | N | 00127505
CTSU Pre-Award v2 - 390-DAY | Billing Calendar Received | Role | CTSU Finance | 2017-09-10 | 0 |  | N | 390-DAY
Calendaring : Initial Calendar Build - 198-LUCKRITZ | Acknowledge | Role | CTSU Finance | 2017-09-10 | 0 |  | N | 198-LUCKRITZ
Calendaring : Initial Calendar Build - 205-HIGGINS | Acknowledge | Role | CTSU Finance | 2017-09-10 | 0 |  | N | 205-HIGGINS
Calendaring : Initial Calendar Build - 326-HIGGINS | Acknowledge | Role | CTSU Finance | 2017-09-10 | 0 |  | N | 326-HIGGINS
Calendaring : Initial Calendar Build - 327-HIGGINS | Acknowledge | Role | CTSU Finance | 2017-09-10 | 0 |  | N | 327-HIGGINS
Calendaring : Initial Calendar Build - 332-BELLOLI | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance | 2017-09-10 | 0 |  | N | 332-BELLOLI
Pre-Award Financial - 86-AUCHUS | Final Budget | User | Henry, Robin | 2017-09-10 | 0 |  | N | 00132700
Calendaring : Amendment Checklist & Process - 00119926 | Complete Calendar and Document Approval | User | Hodges, Lynda | 2017-09-10 | 0 |  | N | 00119926
CTSU Pre-Award - 338-MIAN | Final Budget | User | VanderElzen, Liz | 2017-09-10 | 0 |  | N | 00133457
CTSU Pre-Award - 359-SMITH | PI approved Budget | User | VanderElzen, Liz | 2017-09-10 | 0 |  | N | 359-SMITH
CTSU Pre-Award v2 - 403-HIGGINS | PI approved Budget | User | VanderElzen, Liz | 2017-09-10 | 0 |  | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | PI approved Budget | User | VanderElzen, Liz | 2017-09-10 | 0 |  | N | 00134896
Pre-Award Financial - 11-HIGGINS | PI approved Budget | User | VanderElzen, Liz | 2017-09-10 | 0 |  | N | 00134884
Pre-Award Financial - 246-AS-SANIE | OnCore Budget Build | User | Yunk, Jason | 2017-09-10 | 0 |  | N | 246-AS-SANIE
CTSU Pre-Award - 313-CONJEEVARAM | Open to Accrual | Role | CTSU Administrator | 2017-09-11 | 0 |  | N | 313-CONJEEVARAM
CTSU Pre-Award v2 - 435-MOROI | Feasibility w/Documents received | Role | CTSU Administrator | 2017-09-11 | 0 |  | N | 435-MOROI
Pre-Award Financial - 190-SCHIOPU | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-11 | 0 |  | N | 00134443
CTSU Pre-Award v2 - 380-LOK | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-11 | 0 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-11 | 0 |  | N | 381-HIGGINS
CTSU Pre-Award v2 - 435-MOROI | Sponsor Reach out | Role | CTSU Coordinator | 2017-09-11 | 0 |  | N | 435-MOROI
CTSU Pre-Award - 327-HIGGINS | Care Designations completed | Role | CTSU Finance | 2017-09-11 | 0 |  | N | 327-HIGGINS
CTSU Pre-Award v2 - 140-CHUNG | PI approved Budget | Role | CTSU Finance | 2017-09-11 | 0 |  | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | PI approved Budget | Role | CTSU Finance | 2017-09-11 | 0 |  | N | 00131840
CTSU Pre-Award v2 - 361-HASAN | Budget Negotiations | Role | CTSU Finance | 2017-09-11 | 0 |  | N | 361-HASAN
CTSU Pre-Award v2 - 364-KHAJA | PAF routed | Role | CTSU Finance | 2017-09-11 | 0 |  | N | 364-KHAJA
CTSU Pre-Award v2 - 380-LOK | Planning Meeting Completed | Role | CTSU Finance | 2017-09-11 | 0 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | Planning Meeting Completed | Role | CTSU Finance | 2017-09-11 | 0 |  | N | 381-HIGGINS
Pre-Award Financial - 203-ELSE | PI approved Budget | Role | CTSU Finance | 2017-09-11 | 0 |  | N | 00132173
Pre-Award Financial - 205-HIGGINS | Care Designations completed | Role | CTSU Finance | 2017-09-11 | 0 |  | N | 205-HIGGINS
Calendaring : Amendment Checklist & Process - 00094136 | Complete Calendar and Document Approval | User | Munasinghe, Sadeepa | 2017-09-11 | 0 |  | N | 00094136
Pre-Award Financial - 246-AS-SANIE | Calendar Released | User | Oliver, Amy | 2017-09-11 | 0 |  | N | 246-AS-SANIE
CTSU Pre-Award v2 - 323-BOLLING | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-12 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-12 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award - 370-LOK | Internal Budget Finished | Role | CTSU Finance | 2017-09-12 | 0 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | Internal Budget Finished | Role | CTSU Finance | 2017-09-12 | 0 |  | N | 371-LOK
CTSU Pre-Award v2 - 323-BOLLING | Planning Meeting Completed | Role | CTSU Finance | 2017-09-12 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 364-KHAJA | OnCore Budget Build | Role | CTSU Finance | 2017-09-12 | 0 |  | N | 364-KHAJA
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Planning Meeting Completed | Role | CTSU Finance | 2017-09-12 | 0 |  | N | 385-MCLAUGHLIN
Calendaring : Amendment Checklist & Process - 00119926 | Acknowledge | Role | CTSU Finance | 2017-09-12 | 0 |  | N | 00119926
Pre-Award Financial - 86-AUCHUS | PAF routed | User | Henry, Robin | 2017-09-12 | 0 |  | N | 00132700
Calendaring : Initial Calendar Build - 332-BELLOLI | Complete Calendar ( ie. Ready for Financials ) | User | Hess, Aaron | 2017-09-12 | 0 |  | N | 332-BELLOLI
Calendaring : Initial Calendar Build - 332-BELLOLI | Make Updates | User | Hess, Aaron | 2017-09-12 | 0 |  | N | 332-BELLOLI
CTSU Pre-Award - 338-MIAN | PAF routed | User | VanderElzen, Liz | 2017-09-12 | 0 |  | N | 00133457
CTSU Pre-Award - 359-SMITH | Budget Negotiations | User | VanderElzen, Liz | 2017-09-12 | 0 |  | N | 359-SMITH
CTSU Pre-Award v2 - 403-HIGGINS | Budget Negotiations | User | VanderElzen, Liz | 2017-09-12 | 0 |  | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | Budget Negotiations | User | VanderElzen, Liz | 2017-09-12 | 0 |  | N | 00134896
Pre-Award Financial - 11-HIGGINS | Budget Negotiations | User | VanderElzen, Liz | 2017-09-12 | 0 |  | N | 00134884
CTSU Pre-Award v2 - 439-KHANNA | Feasibility w/Documents received | Role | CTSU Administrator | 2017-09-13 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | Feasibility w/Documents received | Role | CTSU Administrator | 2017-09-13 | 0 |  | N | 440-LOK
Pre-Award Financial - 190-SCHIOPU | Open to Accrual | Role | CTSU Administrator | 2017-09-13 | 0 |  | N | 00134443
CTSU Pre-Award v2 - 439-KHANNA | Sponsor Reach out | Role | CTSU Coordinator | 2017-09-13 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 439-KHANNA | UFA Completed | Role | CTSU Coordinator | 2017-09-13 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | Sponsor Reach out | Role | CTSU Coordinator | 2017-09-13 | 0 |  | N | 440-LOK
CTSU Pre-Award v2 - 440-LOK | UFA Completed | Role | CTSU Coordinator | 2017-09-13 | 0 |  | N | 440-LOK
CTSU Pre-Award - 332-BELLOLI | Final Budget | Role | CTSU Finance | 2017-09-13 | 0 |  | N | 332-BELLOLI
CTSU Pre-Award - 341-STOFFEL | Initial Post-Award Task List | Role | CTSU Finance | 2017-09-13 | 0 |  | N | 00134997
CTSU Pre-Award v2 - 140-CHUNG | Budget Negotiations | Role | CTSU Finance | 2017-09-13 | 0 |  | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | Budget Negotiations | Role | CTSU Finance | 2017-09-13 | 0 |  | N | 00131840
CTSU Pre-Award v2 - 364-KHAJA | Calendar Released | Role | CTSU Finance | 2017-09-13 | 0 |  | N | 364-KHAJA
CTSU Pre-Award v2 - 415-ROMANO | Initiate Post-Award Task List | Role | CTSU Finance | 2017-09-13 | 0 |  | N | 415-ROMANO
CTSU Pre-Award v2 - 415-ROMANO | PAN Released | Role | CTSU Finance | 2017-09-13 | 0 |  | N | 415-ROMANO
Pre-Award Financial - 203-ELSE | Budget Negotiations | Role | CTSU Finance | 2017-09-13 | 0 |  | N | 00132173
Pre-Award Financial - 255-LOK | OnCore Budget Build | Role | CTSU Finance | 2017-09-13 | 0 |  | N | 255-LOK
Calendaring : Amendment Checklist & Process - 00094136 | Acknowledge | User | Munasinghe, Sadeepa | 2017-09-13 | 0 |  | N | 00094136
CTSU Pre-Award - 341-STOFFEL | PAN Released | User | Oliver, Amy | 2017-09-13 | 0 |  | N | 00134997
CTSU Pre-Award - 338-MIAN | OnCore Budget Build | User | Yunk, Jason | 2017-09-13 | 0 |  | N | 00133457
CTSU Pre-Award v2 - 428-LAW | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-09-14 | 0 |  | N | 00135072
CTSU Pre-Award v2 - 390-DAY | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-14 | 0 |  | N | 390-DAY
Pre-Award Financial - 246-AS-SANIE | PI Signoff in OnCore | Role | CTSU Coordinator | 2017-09-14 | 0 |  | N | 246-AS-SANIE
CTSU Pre-Award - 337-MIAN | Initiate Post-Award Task List | Role | CTSU Finance | 2017-09-14 | 0 |  | N | 337-MIAN
CTSU Pre-Award v2 - 380-LOK | Care Designations completed | Role | CTSU Finance | 2017-09-14 | 0 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | Care Designations completed | Role | CTSU Finance | 2017-09-14 | 0 |  | N | 381-HIGGINS
CTSU Pre-Award v2 - 390-DAY | Planning Meeting Completed | Role | CTSU Finance | 2017-09-14 | 0 |  | N | 390-DAY
CTSU Pre-Award v2 - 393-HYZY | Billing Calendar Received | Role | CTSU Finance | 2017-09-14 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | Billing Calendar Received | Role | CTSU Finance | 2017-09-14 | 0 |  | N | 396-SCHIOPU
Calendaring : Initial Calendar Build - 332-BELLOLI | Acknowledge | Role | CTSU Finance | 2017-09-14 | 0 |  | N | 332-BELLOLI
Pre-Award Financial - 255-LOK | Calendar Released | Role | CTSU Finance | 2017-09-14 | 0 |  | N | 255-LOK
CTSU Pre-Award - 337-MIAN | PAN Released | User | Oliver, Amy | 2017-09-14 | 0 |  | N | 337-MIAN
CTSU Pre-Award - 338-MIAN | Calendar Released | User | Oliver, Amy | 2017-09-14 | 0 |  | N | 00133457
Pre-Award Financial - 23-GUPTA | PAN Released | User | Oliver, Amy | 2017-09-14 | 0 |  | N | 00134236
CTSU Pre-Award v2 - 430-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-09-15 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-09-15 | 0 |  | N | 432-JAYASUNDERA
CTSU Pre-Award - 326-HIGGINS | Internal Budget Finished | Role | CTSU Finance | 2017-09-15 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Internal Budget Finished | Role | CTSU Finance | 2017-09-15 | 0 |  | N | 327-HIGGINS
CTSU Pre-Award - 332-BELLOLI | PAF routed | Role | CTSU Finance | 2017-09-15 | 0 |  | N | 332-BELLOLI
CTSU Pre-Award - 350-HIGGINS | Initiate Post-Award Task List | Role | CTSU Finance | 2017-09-15 | 0 |  | N | 00133054
CTSU Pre-Award - 351-HIGGINS | Initiate Post-Award Task List | Role | CTSU Finance | 2017-09-15 | 0 |  | N | 00134870
CTSU Pre-Award - 370-LOK | PI approved Budget | Role | CTSU Finance | 2017-09-15 | 0 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | PI approved Budget | Role | CTSU Finance | 2017-09-15 | 0 |  | N | 371-LOK
CTSU Pre-Award v2 - 323-BOLLING | Care Designations completed | Role | CTSU Finance | 2017-09-15 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Care Designations completed | Role | CTSU Finance | 2017-09-15 | 0 |  | N | 385-MCLAUGHLIN
Pre-Award Financial - 205-HIGGINS | Internal Budget Finished | Role | CTSU Finance | 2017-09-15 | 0 |  | N | 205-HIGGINS
Open to Accrual - 00118461 | Contract Executed | User | Dahlgren, Molly | 2017-09-15 | 0 |  | N | 00118461
CTSU Pre-Award - 350-HIGGINS | PAN Released | User | Oliver, Amy | 2017-09-15 | 0 |  | N | 00133054
CTSU Pre-Award - 351-HIGGINS | PAN Released | User | Oliver, Amy | 2017-09-15 | 0 |  | N | 00134870
Pre-Award Financial - 179-LUGOGO | PAN Released | User | VanderElzen, Liz | 2017-09-15 | 0 |  | N | 179-LUGOGO
CTSU Pre-Award v2 - 364-KHAJA | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-16 | 0 |  | N | 364-KHAJA
Pre-Award Financial - 246-AS-SANIE | Open to Accrual | Role | CTSU Administrator | 2017-09-16 | 0 |  | N | 246-AS-SANIE
CTSU Pre-Award v2 - 428-LAW | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-09-16 | 0 |  | N | 00135072
CTSU Pre-Award v2 - 410-PAULUS | Billing Calendar Received | Role | CTSU Finance | 2017-09-16 | 0 |  | N | 410-PAULUS
CTSU Pre-Award v2 - 428-LAW | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-09-16 | 0 |  | N | 00135072
CTSU Pre-Award v2 - 428-LAW | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-09-16 | 0 |  | N | 00135072
CTSU Pre-Award - 332-BELLOLI | OnCore Budget Build | User | Yunk, Jason | 2017-09-16 | 0 |  | N | 332-BELLOLI
CTSU Pre-Award - 338-MIAN | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-17 | 0 |  | N | 00133457
Pre-Award Financial - 255-LOK | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-17 | 0 |  | N | 255-LOK
CTSU Pre-Award v2 - 430-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-09-17 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-09-17 | 0 |  | N | 432-JAYASUNDERA
CTSU Pre-Award - 332-BELLOLI | Initiate Post-Award Task List | Role | CTSU Finance | 2017-09-17 | 0 |  | N | 332-BELLOLI
CTSU Pre-Award - 370-LOK | Budget Negotiations | Role | CTSU Finance | 2017-09-17 | 0 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | Budget Negotiations | Role | CTSU Finance | 2017-09-17 | 0 |  | N | 371-LOK
CTSU Pre-Award v2 - 390-DAY | Care Designations completed | Role | CTSU Finance | 2017-09-17 | 0 |  | N | 390-DAY
CTSU Pre-Award v2 - 430-HIGGINS | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-09-17 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 430-HIGGINS | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-09-17 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-09-17 | 0 |  | N | 432-JAYASUNDERA
CTSU Pre-Award v2 - 432-JAYASUNDERA | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-09-17 | 0 |  | N | 432-JAYASUNDERA
CTSU Pre-Award - 332-BELLOLI | Calendar Released | User | Oliver, Amy | 2017-09-17 | 0 |  | N | 332-BELLOLI
CTSU Pre-Award - 332-BELLOLI | PAN Released | User | Oliver, Amy | 2017-09-17 | 0 |  | N | 332-BELLOLI
Pre-Award Financial - 263-DELMONTE | OnCore Budget Build | User | Yunk, Jason | 2017-09-17 | 0 |  | N | 263-DELMONTE
CTSU Pre-Award v2 - 364-KHAJA | Open to Accrual | Role | CTSU Administrator | 2017-09-18 | 0 |  | N | 364-KHAJA
CTSU Pre-Award v2 - 435-MOROI | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-09-18 | 0 |  | N | 435-MOROI
CTSU Pre-Award v2 - 447-RAO | Feasibility w/Documents received | Role | CTSU Administrator | 2017-09-18 | 0 |  | N | 447-RAO
CTSU Pre-Award v2 - 393-HYZY | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-18 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-18 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award - 313-CONJEEVARAM | Initiate Post-Award Task List | Role | CTSU Finance | 2017-09-18 | 0 |  | N | 313-CONJEEVARAM
CTSU Pre-Award - 326-HIGGINS | PI approved Budget | Role | CTSU Finance | 2017-09-18 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | PI approved Budget | Role | CTSU Finance | 2017-09-18 | 0 |  | N | 327-HIGGINS
CTSU Pre-Award v2 - 380-LOK | Internal Budget Finished | Role | CTSU Finance | 2017-09-18 | 0 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | Internal Budget Finished | Role | CTSU Finance | 2017-09-18 | 0 |  | N | 381-HIGGINS
CTSU Pre-Award v2 - 393-HYZY | Planning Meeting Completed | Role | CTSU Finance | 2017-09-18 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | Planning Meeting Completed | Role | CTSU Finance | 2017-09-18 | 0 |  | N | 396-SCHIOPU
Pre-Award Financial - 205-HIGGINS | PI approved Budget | Role | CTSU Finance | 2017-09-18 | 0 |  | N | 205-HIGGINS
CTSU Pre-Award - 313-CONJEEVARAM | PAN Released | User | Oliver, Amy | 2017-09-18 | 0 |  | N | 313-CONJEEVARAM
Pre-Award Financial - 263-DELMONTE | Calendar Released | User | Oliver, Amy | 2017-09-18 | 0 |  | N | 263-DELMONTE
CTSU Pre-Award - 338-MIAN | Open to Accrual | Role | CTSU Administrator | 2017-09-19 | 0 |  | N | 00133457
Pre-Award Financial - 255-LOK | Open to Accrual | Role | CTSU Administrator | 2017-09-19 | 0 |  | N | 255-LOK
CTSU Pre-Award - 348-CHEY | Final Budget | Role | CTSU Finance | 2017-09-19 | 0 |  | N | 348-CHEY
CTSU Pre-Award v2 - 323-BOLLING | Internal Budget Finished | Role | CTSU Finance | 2017-09-19 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Internal Budget Finished | Role | CTSU Finance | 2017-09-19 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 00132705 2 | Final Budget | User | Dahlgren, Molly | 2017-09-19 | 0 |  | N | 00132705
Pre-Award Financial - FONTANA-1 | PAN Released | User | Oliver, Amy | 2017-09-19 | 0 |  | N | 00133153
CTSU Pre-Award v2 - 439-KHANNA | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-09-20 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-09-20 | 0 |  | N | 440-LOK
CTSU Pre-Award - 332-BELLOLI | PI Signoff in OnCore | Role | CTSU Coordinator | 2017-09-20 | 0 |  | N | 332-BELLOLI
CTSU Pre-Award v2 - 410-PAULUS | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-20 | 0 |  | N | 410-PAULUS
CTSU Pre-Award v2 - 435-MOROI | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-09-20 | 0 |  | N | 435-MOROI
CTSU Pre-Award - 326-HIGGINS | Budget Negotiations | Role | CTSU Finance | 2017-09-20 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Budget Negotiations | Role | CTSU Finance | 2017-09-20 | 0 |  | N | 327-HIGGINS
CTSU Pre-Award v2 - 409-NASR | Final Budget | Role | CTSU Finance | 2017-09-20 | 0 |  | N | 409-NASR
CTSU Pre-Award v2 - 410-PAULUS | Planning Meeting Completed | Role | CTSU Finance | 2017-09-20 | 0 |  | N | 410-PAULUS
Pre-Award Financial - 205-HIGGINS | Budget Negotiations | Role | CTSU Finance | 2017-09-20 | 0 |  | N | 205-HIGGINS
Pre-Award Financial - 263-DELMONTE | PI Signoff in OnCore | Role | CTSU Coordinator | 2017-09-21 | 0 |  | N | 263-DELMONTE
CTSU Pre-Award - 348-CHEY | PAF routed | Role | CTSU Finance | 2017-09-21 | 0 |  | N | 348-CHEY
CTSU Pre-Award v2 - 380-LOK | PI approved Budget | Role | CTSU Finance | 2017-09-21 | 0 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | PI approved Budget | Role | CTSU Finance | 2017-09-21 | 0 |  | N | 381-HIGGINS
CTSU Pre-Award v2 - 390-DAY | Internal Budget Finished | Role | CTSU Finance | 2017-09-21 | 0 |  | N | 390-DAY
CTSU Pre-Award v2 - 393-HYZY | Care Designations completed | Role | CTSU Finance | 2017-09-21 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | Care Designations completed | Role | CTSU Finance | 2017-09-21 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 00132705 2 | PAF routed | User | Dahlgren, Molly | 2017-09-21 | 0 |  | N | 00132705
Pre-Award Financial - 110-SCHIOPU | PAN Released | User | Oliver, Amy | 2017-09-21 | 0 |  | N | 00134444
Pre-Award Financial - 251-COMER | PAN Released | User | VanderElzen, Liz | 2017-09-21 | 0 |  | N | 00134232
Pre-Award Financial - 112-FLAHERTY | OnCore Budget Build | User | Yunk, Jason | 2017-09-21 | 0 |  | N | 112-FLAHERTY
CTSU Pre-Award - 332-BELLOLI | Open to Accrual | Role | CTSU Administrator | 2017-09-22 | 0 |  | N | 332-BELLOLI
CTSU Pre-Award v2 - 439-KHANNA | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-09-22 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-09-22 | 0 |  | N | 440-LOK
CTSU Pre-Award v2 - 323-BOLLING | PI approved Budget | Role | CTSU Finance | 2017-09-22 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | PI approved Budget | Role | CTSU Finance | 2017-09-22 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 409-NASR | PAF routed | Role | CTSU Finance | 2017-09-22 | 0 |  | N | 409-NASR
CTSU Pre-Award v2 - 439-KHANNA | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-09-22 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 439-KHANNA | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-09-22 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | Created CTRF & "Notify ORSP" | Role | CTSU Finance | 2017-09-22 | 0 |  | N | 440-LOK
CTSU Pre-Award v2 - 440-LOK | Request Research Pharmacy Budget | Role | CTSU Finance | 2017-09-22 | 0 |  | N | 440-LOK
CTSU Pre-Award v2 - 00132705 2 | OnCore Budget Build | User | Dahlgren, Molly | 2017-09-22 | 0 |  | N | 00132705
Open to Accrual - 00118461 | Project Award Notice (PAN) Received | User | Dahlgren, Molly | 2017-09-22 | 0 |  | N | 00118461
Open to Accrual - 00129709 | Adequate Equipment and Supplies Available | User | Duell, Jayna | 2017-09-22 | 0 |  | N | 00129709
Open to Accrual - 00129709 | IRB Approval | User | Duell, Jayna | 2017-09-22 | 0 |  | N | 00129709
Open to Accrual - 00129709 | Investigational Drug/Device Supplies Available | User | Duell, Jayna | 2017-09-22 | 0 |  | N | 00129709
Open to Accrual - 00129709 | Other Personnel Notified | User | Duell, Jayna | 2017-09-22 | 0 |  | N | 00129709
Open to Accrual - 00129709 | Provisions for Support and Services Finalized | User | Duell, Jayna | 2017-09-22 | 0 |  | N | 00129709
Open to Accrual - 00129709 | Sponsor/Organizing Group Approval Granted for Initiation of Study | User | Duell, Jayna | 2017-09-22 | 0 |  | N | 00129709
Open to Accrual - 00129709 | Study Files Established | User | Duell, Jayna | 2017-09-22 | 0 |  | N | 00129709
Open to Accrual - 00129709 | Study Team Roles/Responsibilities Finalized | User | Duell, Jayna | 2017-09-22 | 0 |  | N | 00129709
Pre-Award Financial - 112-FLAHERTY | Calendar Released | User | VanderElzen, Liz | 2017-09-22 | 0 |  | N | 112-FLAHERTY
CTSU Pre-Award - 348-CHEY | OnCore Budget Build | User | Yunk, Jason | 2017-09-22 | 0 |  | N | 348-CHEY
Pre-Award Financial - 263-DELMONTE | Open to Accrual | Role | CTSU Administrator | 2017-09-23 | 0 |  | N | 263-DELMONTE
CTSU Pre-Award v2 - 380-LOK | Budget Negotiations | Role | CTSU Finance | 2017-09-23 | 0 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | Budget Negotiations | Role | CTSU Finance | 2017-09-23 | 0 |  | N | 381-HIGGINS
CTSU Pre-Award v2 - 409-NASR | OnCore Budget Build | Role | CTSU Finance | 2017-09-23 | 0 |  | N | 409-NASR
CTSU Pre-Award v2 - 410-PAULUS | Care Designations completed | Role | CTSU Finance | 2017-09-23 | 0 |  | N | 410-PAULUS
CTSU Pre-Award v2 - 00132705 2 | Calendar Released | User | Dahlgren, Molly | 2017-09-23 | 0 |  | N | 00132705
CTSU Pre-Award - 348-CHEY | Calendar Released | User | Oliver, Amy | 2017-09-23 | 0 |  | N | 348-CHEY
CTSU Pre-Award v2 - 323-BOLLING | Budget Negotiations | Role | CTSU Finance | 2017-09-24 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Budget Negotiations | Role | CTSU Finance | 2017-09-24 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 390-DAY | PI approved Budget | Role | CTSU Finance | 2017-09-24 | 0 |  | N | 390-DAY
CTSU Pre-Award v2 - 409-NASR | Calendar Released | Role | CTSU Finance | 2017-09-24 | 0 |  | N | 409-NASR
CTSU Pre-Award v2 - 428-LAW | Billing Calendar Received | Role | CTSU Finance | 2017-09-24 | 0 |  | N | 00135072
CTSU Pre-Award v2 - 447-RAO | Feasibility approved/CRAO Notified | Role | CTSU Administrator | 2017-09-25 | 0 |  | N | 447-RAO
Pre-Award Financial - 112-FLAHERTY | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-25 | 0 |  | N | 112-FLAHERTY
CTSU Pre-Award v2 - 361-HASAN | Final Budget | Role | CTSU Finance | 2017-09-25 | 0 |  | N | 361-HASAN
CTSU Pre-Award v2 - 364-KHAJA | Initiate Post-Award Task List | Role | CTSU Finance | 2017-09-25 | 0 |  | N | 364-KHAJA
CTSU Pre-Award v2 - 364-KHAJA | PAN Released | Role | CTSU Finance | 2017-09-25 | 0 |  | N | 364-KHAJA
CTSU Pre-Award v2 - 393-HYZY | Internal Budget Finished | Role | CTSU Finance | 2017-09-25 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | Internal Budget Finished | Role | CTSU Finance | 2017-09-25 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 430-HIGGINS | Billing Calendar Received | Role | CTSU Finance | 2017-09-25 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | Billing Calendar Received | Role | CTSU Finance | 2017-09-25 | 0 |  | N | 432-JAYASUNDERA
CTSU Pre-Award - 348-CHEY | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-26 | 0 |  | N | 348-CHEY
CTSU Pre-Award - 338-MIAN | Initiate Post-Award Task List | Role | CTSU Finance | 2017-09-26 | 0 |  | N | 00133457
CTSU Pre-Award v2 - 390-DAY | Budget Negotiations | Role | CTSU Finance | 2017-09-26 | 0 |  | N | 390-DAY
Pre-Award Financial - 86-AUCHUS | PAN Released | Role | CTSU Finance | 2017-09-26 | 0 |  | N | 00132700
CTSU Pre-Award v2 - 00132705 2 | PI Signoff in OnCore | User | Miller, Diana | 2017-09-26 | 0 |  | N | 00132705
CTSU Pre-Award - 338-MIAN | PAN Released | User | Oliver, Amy | 2017-09-26 | 0 |  | N | 00133457
CTSU Pre-Award - 359-SMITH | Final Budget | User | VanderElzen, Liz | 2017-09-26 | 0 |  | N | 359-SMITH
CTSU Pre-Award v2 - 403-HIGGINS | Final Budget | User | VanderElzen, Liz | 2017-09-26 | 0 |  | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | Final Budget | User | VanderElzen, Liz | 2017-09-26 | 0 |  | N | 00134896
Pre-Award Financial - 11-HIGGINS | Final Budget | User | VanderElzen, Liz | 2017-09-26 | 0 |  | N | 00134884
CTSU Pre-Award v2 - 409-NASR | PI Signoff in OnCore | Role | CTSU Administrator | 2017-09-27 | 0 |  | N | 409-NASR
Pre-Award Financial - 112-FLAHERTY | Open to Accrual | Role | CTSU Administrator | 2017-09-27 | 0 |  | N | 112-FLAHERTY
CTSU Pre-Award v2 - 447-RAO | Planning Meeting Request Sent | Role | CTSU Coordinator | 2017-09-27 | 0 |  | N | 447-RAO
CTSU Pre-Award v2 - 140-CHUNG | Final Budget | Role | CTSU Finance | 2017-09-27 | 0 |  | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | Final Budget | Role | CTSU Finance | 2017-09-27 | 0 |  | N | 00131840
CTSU Pre-Award v2 - 361-HASAN | PAF routed | Role | CTSU Finance | 2017-09-27 | 0 |  | N | 361-HASAN
CTSU Pre-Award v2 - 410-PAULUS | Internal Budget Finished | Role | CTSU Finance | 2017-09-27 | 0 |  | N | 410-PAULUS
Pre-Award Financial - 203-ELSE | Final Budget | Role | CTSU Finance | 2017-09-27 | 0 |  | N | 00132173
CTSU Pre-Award v2 - 447-RAO | Created CTRF & "Notify ORSP" | User | VanderElzen, Liz | 2017-09-27 | 0 |  | N | 447-RAO
CTSU Pre-Award v2 - 447-RAO | Request Research Pharmacy Budget | User | VanderElzen, Liz | 2017-09-27 | 0 |  | N | 447-RAO
CTSU Pre-Award - 348-CHEY | Open to Accrual | Role | CTSU Administrator | 2017-09-28 | 0 |  | N | 348-CHEY
CTSU Pre-Award v2 - 00132705 2 | Open to Accrual | Role | CTSU Administrator | 2017-09-28 | 0 |  | N | 00132705
CTSU Pre-Award v2 - 428-LAW | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-28 | 0 |  | N | 00135072
CTSU Pre-Award v2 - 361-HASAN | OnCore Budget Build | Role | CTSU Finance | 2017-09-28 | 0 |  | N | 361-HASAN
CTSU Pre-Award v2 - 393-HYZY | PI approved Budget | Role | CTSU Finance | 2017-09-28 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | PI approved Budget | Role | CTSU Finance | 2017-09-28 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 428-LAW | Planning Meeting Completed | Role | CTSU Finance | 2017-09-28 | 0 |  | N | 00135072
CTSU Pre-Award - 359-SMITH | PAF routed | User | VanderElzen, Liz | 2017-09-28 | 0 |  | N | 359-SMITH
CTSU Pre-Award v2 - 403-HIGGINS | PAF routed | User | VanderElzen, Liz | 2017-09-28 | 0 |  | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | PAF routed | User | VanderElzen, Liz | 2017-09-28 | 0 |  | N | 00134896
CTSU Pre-Award v2 - 435-MOROI | Billing Calendar Received | User | VanderElzen, Liz | 2017-09-28 | 0 |  | N | 435-MOROI
Pre-Award Financial - 11-HIGGINS | PAF routed | User | VanderElzen, Liz | 2017-09-28 | 0 |  | N | 00134884
Pre-Award Financial - 23-GUPTA | OnCore Budget Build | User | Yunk, Jason | 2017-09-28 | 0 |  | N | 00134236
CTSU Pre-Award v2 - 409-NASR | Open to Accrual | Role | CTSU Administrator | 2017-09-29 | 0 |  | N | 409-NASR
CTSU Pre-Award v2 - 430-HIGGINS | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-29 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | IRB Application Submitted | Role | CTSU Coordinator | 2017-09-29 | 0 |  | N | 432-JAYASUNDERA
CTSU Pre-Award v2 - 140-CHUNG | PAF routed | Role | CTSU Finance | 2017-09-29 | 0 |  | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | PAF routed | Role | CTSU Finance | 2017-09-29 | 0 |  | N | 00131840
CTSU Pre-Award v2 - 361-HASAN | Calendar Released | Role | CTSU Finance | 2017-09-29 | 0 |  | N | 361-HASAN
CTSU Pre-Award v2 - 430-HIGGINS | Planning Meeting Completed | Role | CTSU Finance | 2017-09-29 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | Planning Meeting Completed | Role | CTSU Finance | 2017-09-29 | 0 |  | N | 432-JAYASUNDERA
Pre-Award Financial - 203-ELSE | PAF routed | Role | CTSU Finance | 2017-09-29 | 0 |  | N | 00132173
Open to Accrual - 00129709 | MiChart Verifications | User | Miller, Diana | 2017-09-29 | 0 |  | N | 00129709
Pre-Award Financial - 23-GUPTA | Calendar Released | User | Oliver, Amy | 2017-09-29 | 0 |  | N | 00134236
Open to Accrual - 00129709 | Budget Finalized | User | Rollins, Matthew | 2017-09-29 | 0 |  | N | 00129709
Open to Accrual - 00129709 | Project Award Notice (PAN) Received | User | Rollins, Matthew | 2017-09-29 | 0 |  | N | 00129709
CTSU Pre-Award - 359-SMITH | OnCore Budget Build | User | Yunk, Jason | 2017-09-29 | 0 |  | N | 359-SMITH
CTSU Pre-Award v2 - 403-HIGGINS | OnCore Budget Build | User | Yunk, Jason | 2017-09-29 | 0 |  | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | OnCore Budget Build | User | Yunk, Jason | 2017-09-29 | 0 |  | N | 00134896
Pre-Award Financial - 179-LUGOGO | OnCore Budget Build | User | Yunk, Jason | 2017-09-29 | 0 |  | N | 179-LUGOGO
CTSU Pre-Award v2 - 393-HYZY | Budget Negotiations | Role | CTSU Finance | 2017-09-30 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | Budget Negotiations | Role | CTSU Finance | 2017-09-30 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 410-PAULUS | PI approved Budget | Role | CTSU Finance | 2017-09-30 | 0 |  | N | 410-PAULUS
CTSU Pre-Award v2 - 439-KHANNA | Billing Calendar Received | Role | CTSU Finance | 2017-09-30 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | Billing Calendar Received | Role | CTSU Finance | 2017-09-30 | 0 |  | N | 440-LOK
CTSU Pre-Award - 359-SMITH | Calendar Released | User | Oliver, Amy | 2017-09-30 | 0 |  | N | 359-SMITH
CTSU Pre-Award v2 - 403-HIGGINS | Calendar Released | User | Oliver, Amy | 2017-09-30 | 0 |  | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | Calendar Released | User | Oliver, Amy | 2017-09-30 | 0 |  | N | 00134896
CTSU Pre-Award v2 - 140-CHUNG | OnCore Budget Build | User | Yunk, Jason | 2017-09-30 | 0 |  | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | OnCore Budget Build | User | Yunk, Jason | 2017-09-30 | 0 |  | N | 00131840
Pre-Award Financial - 179-LUGOGO | Calendar Released | User | Yunk, Jason | 2017-09-30 | 0 |  | N | 179-LUGOGO
CTSU Pre-Award - 370-LOK | Final Budget | Role | CTSU Finance | 2017-10-01 | 0 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | Final Budget | Role | CTSU Finance | 2017-10-01 | 0 |  | N | 371-LOK
CTSU Pre-Award v2 - 428-LAW | Care Designations completed | Role | CTSU Finance | 2017-10-01 | 0 |  | N | 00135072
CTSU Pre-Award v2 - 140-CHUNG | Calendar Released | User | Oliver, Amy | 2017-10-01 | 0 |  | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | Calendar Released | User | Oliver, Amy | 2017-10-01 | 0 |  | N | 00131840
CTSU Pre-Award v2 - 361-HASAN | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-02 | 0 |  | N | 361-HASAN
Pre-Award Financial - 23-GUPTA | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-02 | 0 |  | N | 00134236
CTSU Pre-Award v2 - 435-MOROI | IRB Application Submitted | Role | CTSU Coordinator | 2017-10-02 | 0 |  | N | 435-MOROI
CTSU Pre-Award v2 - 410-PAULUS | Budget Negotiations | Role | CTSU Finance | 2017-10-02 | 0 |  | N | 410-PAULUS
CTSU Pre-Award v2 - 430-HIGGINS | Care Designations completed | Role | CTSU Finance | 2017-10-02 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | Care Designations completed | Role | CTSU Finance | 2017-10-02 | 0 |  | N | 432-JAYASUNDERA
CTSU Pre-Award v2 - 435-MOROI | Planning Meeting Completed | User | VanderElzen, Liz | 2017-10-02 | 0 |  | N | 435-MOROI
CTSU Pre-Award - 359-SMITH | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-03 | 0 |  | N | 359-SMITH
CTSU Pre-Award v2 - 403-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-03 | 0 |  | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-03 | 0 |  | N | 00134896
Pre-Award Financial - 179-LUGOGO | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-03 | 0 |  | N | 179-LUGOGO
CTSU Pre-Award - 370-LOK | PAF routed | Role | CTSU Finance | 2017-10-03 | 0 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | PAF routed | Role | CTSU Finance | 2017-10-03 | 0 |  | N | 371-LOK
Pre-Award Financial - FONTANA-1 | OnCore Budget Build | User | Yunk, Jason | 2017-10-03 | 0 |  | N | 00133153
CTSU Pre-Award v2 - 140-CHUNG | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-04 | 0 |  | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-04 | 0 |  | N | 00131840
CTSU Pre-Award v2 - 361-HASAN | Open to Accrual | Role | CTSU Administrator | 2017-10-04 | 0 |  | N | 361-HASAN
Pre-Award Financial - 23-GUPTA | Open to Accrual | Role | CTSU Administrator | 2017-10-04 | 0 |  | N | 00134236
CTSU Pre-Award v2 - 439-KHANNA | IRB Application Submitted | Role | CTSU Coordinator | 2017-10-04 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | IRB Application Submitted | Role | CTSU Coordinator | 2017-10-04 | 0 |  | N | 440-LOK
CTSU Pre-Award - 326-HIGGINS | Final Budget | Role | CTSU Finance | 2017-10-04 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Final Budget | Role | CTSU Finance | 2017-10-04 | 0 |  | N | 327-HIGGINS
CTSU Pre-Award v2 - 439-KHANNA | Planning Meeting Completed | Role | CTSU Finance | 2017-10-04 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | Planning Meeting Completed | Role | CTSU Finance | 2017-10-04 | 0 |  | N | 440-LOK
Pre-Award Financial - 205-HIGGINS | Final Budget | Role | CTSU Finance | 2017-10-04 | 0 |  | N | 205-HIGGINS
Pre-Award Financial - FONTANA-1 | Calendar Released | User | Oliver, Amy | 2017-10-04 | 0 |  | N | 00133153
CTSU Pre-Award - 370-LOK | OnCore Budget Build | User | Yunk, Jason | 2017-10-04 | 0 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | OnCore Budget Build | User | Yunk, Jason | 2017-10-04 | 0 |  | N | 371-LOK
CTSU Pre-Award - 359-SMITH | Open to Accrual | Role | CTSU Administrator | 2017-10-05 | 0 |  | N | 359-SMITH
CTSU Pre-Award v2 - 403-HIGGINS | Open to Accrual | Role | CTSU Administrator | 2017-10-05 | 0 |  | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | Open to Accrual | Role | CTSU Administrator | 2017-10-05 | 0 |  | N | 00134896
Pre-Award Financial - 179-LUGOGO | Open to Accrual | Role | CTSU Administrator | 2017-10-05 | 0 |  | N | 179-LUGOGO
CTSU Pre-Award - 348-CHEY | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-05 | 0 |  | N | 348-CHEY
CTSU Pre-Award v2 - 428-LAW | Internal Budget Finished | Role | CTSU Finance | 2017-10-05 | 0 |  | N | 00135072
CTSU Pre-Award v2 - 00132705 2 | PAN Released | User | Dahlgren, Molly | 2017-10-05 | 0 |  | N | 00132705
Pre-Award Financial - 110-SCHIOPU | OnCore Budget Build | User | Henry, Robin | 2017-10-05 | 0 |  | N | 00134444
CTSU Pre-Award - 348-CHEY | PAN Released | User | Oliver, Amy | 2017-10-05 | 0 |  | N | 348-CHEY
CTSU Pre-Award - 370-LOK | Calendar Released | User | Oliver, Amy | 2017-10-05 | 0 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | Calendar Released | User | Oliver, Amy | 2017-10-05 | 0 |  | N | 371-LOK
CTSU Pre-Award v2 - 435-MOROI | Care Designations completed | User | VanderElzen, Liz | 2017-10-05 | 0 |  | N | 435-MOROI
CTSU Pre-Award v2 - 447-RAO | Billing Calendar Received | User | VanderElzen, Liz | 2017-10-05 | 0 |  | N | 447-RAO
Pre-Award Financial - 251-COMER | OnCore Budget Build | User | Yunk, Jason | 2017-10-05 | 0 |  | N | 00134232
CTSU Pre-Award v2 - 140-CHUNG | Open to Accrual | Role | CTSU Administrator | 2017-10-06 | 0 |  | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | Open to Accrual | Role | CTSU Administrator | 2017-10-06 | 0 |  | N | 00131840
CTSU Pre-Award - 326-HIGGINS | PAF routed | Role | CTSU Finance | 2017-10-06 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | PAF routed | Role | CTSU Finance | 2017-10-06 | 0 |  | N | 327-HIGGINS
CTSU Pre-Award v2 - 409-NASR | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-06 | 0 |  | N | 409-NASR
CTSU Pre-Award v2 - 409-NASR | PAN Released | Role | CTSU Finance | 2017-10-06 | 0 |  | N | 409-NASR
CTSU Pre-Award v2 - 430-HIGGINS | Internal Budget Finished | Role | CTSU Finance | 2017-10-06 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | Internal Budget Finished | Role | CTSU Finance | 2017-10-06 | 0 |  | N | 432-JAYASUNDERA
Pre-Award Financial - 205-HIGGINS | PAF routed | Role | CTSU Finance | 2017-10-06 | 0 |  | N | 205-HIGGINS
Pre-Award Financial - 251-COMER | Calendar Released | Role | CTSU Finance | 2017-10-06 | 0 |  | N | 00134232
Pre-Award Financial - 110-SCHIOPU | Calendar Released | User | Oliver, Amy | 2017-10-06 | 0 |  | N | 00134444
Pre-Award Financial - FONTANA-1 | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-07 | 0 |  | N | 00133153
CTSU Pre-Award v2 - 380-LOK | Final Budget | Role | CTSU Finance | 2017-10-07 | 0 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | Final Budget | Role | CTSU Finance | 2017-10-07 | 0 |  | N | 381-HIGGINS
CTSU Pre-Award v2 - 439-KHANNA | Care Designations completed | Role | CTSU Finance | 2017-10-07 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | Care Designations completed | Role | CTSU Finance | 2017-10-07 | 0 |  | N | 440-LOK
CTSU Pre-Award - 326-HIGGINS | OnCore Budget Build | User | Yunk, Jason | 2017-10-07 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | OnCore Budget Build | User | Yunk, Jason | 2017-10-07 | 0 |  | N | 327-HIGGINS
CTSU Pre-Award - 370-LOK | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-08 | 0 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-08 | 0 |  | N | 371-LOK
CTSU Pre-Award v2 - 323-BOLLING | Final Budget | Role | CTSU Finance | 2017-10-08 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Final Budget | Role | CTSU Finance | 2017-10-08 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 428-LAW | PI approved Budget | Role | CTSU Finance | 2017-10-08 | 0 |  | N | 00135072
CTSU Pre-Award - 326-HIGGINS | Calendar Released | User | Oliver, Amy | 2017-10-08 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Calendar Released | User | Oliver, Amy | 2017-10-08 | 0 |  | N | 327-HIGGINS
Pre-Award Financial - 110-SCHIOPU | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-09 | 0 |  | N | 00134444
Pre-Award Financial - 251-COMER | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-09 | 0 |  | N | 00134232
Pre-Award Financial - FONTANA-1 | Open to Accrual | Role | CTSU Administrator | 2017-10-09 | 0 |  | N | 00133153
CTSU Pre-Award v2 - 447-RAO | IRB Application Submitted | Role | CTSU Coordinator | 2017-10-09 | 0 |  | N | 447-RAO
CTSU Pre-Award v2 - 380-LOK | PAF routed | Role | CTSU Finance | 2017-10-09 | 0 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | PAF routed | Role | CTSU Finance | 2017-10-09 | 0 |  | N | 381-HIGGINS
CTSU Pre-Award v2 - 430-HIGGINS | PI approved Budget | Role | CTSU Finance | 2017-10-09 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | PI approved Budget | Role | CTSU Finance | 2017-10-09 | 0 |  | N | 432-JAYASUNDERA
CTSU Pre-Award v2 - 435-MOROI | Internal Budget Finished | User | VanderElzen, Liz | 2017-10-09 | 0 |  | N | 435-MOROI
CTSU Pre-Award v2 - 447-RAO | Planning Meeting Completed | User | VanderElzen, Liz | 2017-10-09 | 0 |  | N | 447-RAO
CTSU Pre-Award - 370-LOK | Open to Accrual | Role | CTSU Administrator | 2017-10-10 | 0 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | Open to Accrual | Role | CTSU Administrator | 2017-10-10 | 0 |  | N | 371-LOK
CTSU Pre-Award v2 - 323-BOLLING | PAF routed | Role | CTSU Finance | 2017-10-10 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | PAF routed | Role | CTSU Finance | 2017-10-10 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 390-DAY | Final Budget | Role | CTSU Finance | 2017-10-10 | 0 |  | N | 390-DAY
CTSU Pre-Award v2 - 428-LAW | Budget Negotiations | Role | CTSU Finance | 2017-10-10 | 0 |  | N | 00135072
Pre-Award Financial - 86-AUCHUS | OnCore Budget Build | Role | CTSU Finance | 2017-10-10 | 0 |  | N | 00132700
CTSU Pre-Award v2 - 380-LOK | OnCore Budget Build | User | Yunk, Jason | 2017-10-10 | 0 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | OnCore Budget Build | User | Yunk, Jason | 2017-10-10 | 0 |  | N | 381-HIGGINS
CTSU Pre-Award - 326-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-11 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-11 | 0 |  | N | 327-HIGGINS
Pre-Award Financial - 110-SCHIOPU | Open to Accrual | Role | CTSU Administrator | 2017-10-11 | 0 |  | N | 00134444
Pre-Award Financial - 251-COMER | Open to Accrual | Role | CTSU Administrator | 2017-10-11 | 0 |  | N | 00134232
CTSU Pre-Award v2 - 323-BOLLING | OnCore Budget Build | Role | CTSU Finance | 2017-10-11 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 361-HASAN | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-11 | 0 |  | N | 361-HASAN
CTSU Pre-Award v2 - 361-HASAN | PAN Released | Role | CTSU Finance | 2017-10-11 | 0 |  | N | 361-HASAN
CTSU Pre-Award v2 - 385-MCLAUGHLIN | OnCore Budget Build | Role | CTSU Finance | 2017-10-11 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 430-HIGGINS | Budget Negotiations | Role | CTSU Finance | 2017-10-11 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | Budget Negotiations | Role | CTSU Finance | 2017-10-11 | 0 |  | N | 432-JAYASUNDERA
CTSU Pre-Award v2 - 439-KHANNA | Internal Budget Finished | Role | CTSU Finance | 2017-10-11 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | Internal Budget Finished | Role | CTSU Finance | 2017-10-11 | 0 |  | N | 440-LOK
Pre-Award Financial - 86-AUCHUS | Calendar Released | Role | CTSU Finance | 2017-10-11 | 0 |  | N | 00132700
CTSU Pre-Award v2 - 380-LOK | Calendar Released | User | Oliver, Amy | 2017-10-11 | 0 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | Calendar Released | User | Oliver, Amy | 2017-10-11 | 0 |  | N | 381-HIGGINS
CTSU Pre-Award - 359-SMITH | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-12 | 0 |  | N | 359-SMITH
CTSU Pre-Award v2 - 323-BOLLING | Calendar Released | Role | CTSU Finance | 2017-10-12 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Calendar Released | Role | CTSU Finance | 2017-10-12 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 390-DAY | PAF routed | Role | CTSU Finance | 2017-10-12 | 0 |  | N | 390-DAY
CTSU Pre-Award v2 - 403-HIGGINS | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-12 | 0 |  | N | 00134895
CTSU Pre-Award - 359-SMITH | PAN Released | User | Oliver, Amy | 2017-10-12 | 0 |  | N | 359-SMITH
CTSU Pre-Award v2 - 403-HIGGINS | PAN Released | User | Oliver, Amy | 2017-10-12 | 0 |  | N | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | PAN Released | User | Oliver, Amy | 2017-10-12 | 0 |  | N | 00134896
CTSU Pre-Award v2 - 404-HIGGINS | Initiate Post-Award Task List | User | VanderElzen, Liz | 2017-10-12 | 0 |  | N | 00134896
CTSU Pre-Award v2 - 435-MOROI | PI approved Budget | User | VanderElzen, Liz | 2017-10-12 | 0 |  | N | 435-MOROI
CTSU Pre-Award v2 - 447-RAO | Care Designations completed | User | VanderElzen, Liz | 2017-10-12 | 0 |  | N | 447-RAO
Pre-Award Financial - 11-HIGGINS | PAN Released | User | VanderElzen, Liz | 2017-10-12 | 0 |  | N | 00134884
CTSU Pre-Award - 326-HIGGINS | Open to Accrual | Role | CTSU Administrator | 2017-10-13 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Open to Accrual | Role | CTSU Administrator | 2017-10-13 | 0 |  | N | 327-HIGGINS
CTSU Pre-Award v2 - 140-CHUNG | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-13 | 0 |  | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-13 | 0 |  | N | 00131840
CTSU Pre-Award v2 - 390-DAY | OnCore Budget Build | Role | CTSU Finance | 2017-10-13 | 0 |  | N | 390-DAY
Pre-Award Financial - 203-ELSE | PAN Released | Role | CTSU Finance | 2017-10-13 | 0 |  | N | 00132173
CTSU Pre-Award v2 - 140-CHUNG | PAN Released | User | Oliver, Amy | 2017-10-13 | 0 |  | N | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | PAN Released | User | Oliver, Amy | 2017-10-13 | 0 |  | N | 00131840
CTSU Pre-Award v2 - 380-LOK | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-14 | 0 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-14 | 0 |  | N | 381-HIGGINS
Pre-Award Financial - 86-AUCHUS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-14 | 0 |  | N | 00132700
CTSU Pre-Award v2 - 390-DAY | Calendar Released | Role | CTSU Finance | 2017-10-14 | 0 |  | N | 390-DAY
CTSU Pre-Award v2 - 393-HYZY | Final Budget | Role | CTSU Finance | 2017-10-14 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | Final Budget | Role | CTSU Finance | 2017-10-14 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 439-KHANNA | PI approved Budget | Role | CTSU Finance | 2017-10-14 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | PI approved Budget | Role | CTSU Finance | 2017-10-14 | 0 |  | N | 440-LOK
CTSU Pre-Award v2 - 323-BOLLING | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-15 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-15 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 380-LOK | Open to Accrual | Role | CTSU Administrator | 2017-10-16 | 0 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | Open to Accrual | Role | CTSU Administrator | 2017-10-16 | 0 |  | N | 381-HIGGINS
Pre-Award Financial - 86-AUCHUS | Open to Accrual | Role | CTSU Administrator | 2017-10-16 | 0 |  | N | 00132700
CTSU Pre-Award v2 - 393-HYZY | PAF routed | Role | CTSU Finance | 2017-10-16 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | PAF routed | Role | CTSU Finance | 2017-10-16 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 410-PAULUS | Final Budget | Role | CTSU Finance | 2017-10-16 | 0 |  | N | 410-PAULUS
CTSU Pre-Award v2 - 439-KHANNA | Budget Negotiations | Role | CTSU Finance | 2017-10-16 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | Budget Negotiations | Role | CTSU Finance | 2017-10-16 | 0 |  | N | 440-LOK
CTSU Pre-Award v2 - 447-RAO | Internal Budget Finished | User | VanderElzen, Liz | 2017-10-16 | 0 |  | N | 447-RAO
CTSU Pre-Award v2 - 323-BOLLING | Open to Accrual | Role | CTSU Administrator | 2017-10-17 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Open to Accrual | Role | CTSU Administrator | 2017-10-17 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 390-DAY | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-17 | 0 |  | N | 390-DAY
CTSU Pre-Award - 370-LOK | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-17 | 0 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-17 | 0 |  | N | 371-LOK
CTSU Pre-Award v2 - 393-HYZY | OnCore Budget Build | Role | CTSU Finance | 2017-10-17 | 0 |  | N | 393-HYZY
CTSU Pre-Award - 370-LOK | PAN Released | User | Oliver, Amy | 2017-10-17 | 0 |  | N | 370-LOK
CTSU Pre-Award - 371-LOK | PAN Released | User | Oliver, Amy | 2017-10-17 | 0 |  | N | 371-LOK
CTSU Pre-Award v2 - 396-SCHIOPU | OnCore Budget Build | User | Yunk, Jason | 2017-10-17 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 393-HYZY | Calendar Released | Role | CTSU Finance | 2017-10-18 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 410-PAULUS | PAF routed | Role | CTSU Finance | 2017-10-18 | 0 |  | N | 410-PAULUS
CTSU Pre-Award v2 - 396-SCHIOPU | Calendar Released | User | Oliver, Amy | 2017-10-18 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 390-DAY | Open to Accrual | Role | CTSU Administrator | 2017-10-19 | 0 |  | N | 390-DAY
CTSU Pre-Award v2 - 447-RAO | PI approved Budget | User | VanderElzen, Liz | 2017-10-19 | 0 |  | N | 447-RAO
CTSU Pre-Award v2 - 410-PAULUS | OnCore Budget Build | User | Yunk, Jason | 2017-10-19 | 0 |  | N | 410-PAULUS
CTSU Pre-Award - 326-HIGGINS | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-20 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-20 | 0 |  | N | 327-HIGGINS
Pre-Award Financial - 205-HIGGINS | PAN Released | Role | CTSU Finance | 2017-10-20 | 0 |  | N | 205-HIGGINS
CTSU Pre-Award - 326-HIGGINS | PAN Released | User | Oliver, Amy | 2017-10-20 | 0 |  | N | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | PAN Released | User | Oliver, Amy | 2017-10-20 | 0 |  | N | 327-HIGGINS
CTSU Pre-Award v2 - 410-PAULUS | Calendar Released | User | Oliver, Amy | 2017-10-20 | 0 |  | N | 410-PAULUS
CTSU Pre-Award v2 - 393-HYZY | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-21 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-21 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 447-RAO | Budget Negotiations | User | VanderElzen, Liz | 2017-10-21 | 0 |  | N | 447-RAO
CTSU Pre-Award v2 - 393-HYZY | Open to Accrual | Role | CTSU Administrator | 2017-10-23 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | Open to Accrual | Role | CTSU Administrator | 2017-10-23 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 410-PAULUS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-23 | 0 |  | N | 410-PAULUS
CTSU Pre-Award v2 - 380-LOK | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-23 | 0 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-23 | 0 |  | N | 381-HIGGINS
CTSU Pre-Award v2 - 380-LOK | PAN Released | User | Oliver, Amy | 2017-10-23 | 0 |  | N | 380-LOK
CTSU Pre-Award v2 - 381-HIGGINS | PAN Released | User | Oliver, Amy | 2017-10-23 | 0 |  | N | 381-HIGGINS
CTSU Pre-Award v2 - 323-BOLLING | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-24 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 323-BOLLING | PAN Released | Role | CTSU Finance | 2017-10-24 | 0 |  | N | 323-BOLLING
CTSU Pre-Award v2 - 385-MCLAUGHLIN | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-24 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 385-MCLAUGHLIN | PAN Released | Role | CTSU Finance | 2017-10-24 | 0 |  | N | 385-MCLAUGHLIN
CTSU Pre-Award v2 - 428-LAW | Final Budget | Role | CTSU Finance | 2017-10-24 | 0 |  | N | 00135072
CTSU Pre-Award v2 - 410-PAULUS | Open to Accrual | Role | CTSU Administrator | 2017-10-25 | 0 |  | N | 410-PAULUS
CTSU Pre-Award v2 - 430-HIGGINS | Final Budget | Role | CTSU Finance | 2017-10-25 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | Final Budget | Role | CTSU Finance | 2017-10-25 | 0 |  | N | 432-JAYASUNDERA
CTSU Pre-Award v2 - 390-DAY | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-26 | 0 |  | N | 390-DAY
CTSU Pre-Award v2 - 390-DAY | PAN Released | Role | CTSU Finance | 2017-10-26 | 0 |  | N | 390-DAY
CTSU Pre-Award v2 - 428-LAW | PAF routed | Role | CTSU Finance | 2017-10-26 | 0 |  | N | 00135072
Pre-Award Financial - 11-HIGGINS | OnCore Budget Build | Role | CTSU Finance | 2017-10-26 | 0 |  | N | 00134884
CTSU Pre-Award v2 - 430-HIGGINS | PAF routed | Role | CTSU Finance | 2017-10-27 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | PAF routed | Role | CTSU Finance | 2017-10-27 | 0 |  | N | 432-JAYASUNDERA
Pre-Award Financial - 11-HIGGINS | Calendar Released | Role | CTSU Finance | 2017-10-27 | 0 |  | N | 00134884
Pre-Award Financial - 203-ELSE | OnCore Budget Build | Role | CTSU Finance | 2017-10-27 | 0 |  | N | 00132173
CTSU Pre-Award v2 - 428-LAW | OnCore Budget Build | User | Yunk, Jason | 2017-10-27 | 0 |  | N | 00135072
Pre-Award Financial - 203-ELSE | Calendar Released | Role | CTSU Finance | 2017-10-28 | 0 |  | N | 00132173
CTSU Pre-Award v2 - 428-LAW | Calendar Released | User | Oliver, Amy | 2017-10-28 | 0 |  | N | 00135072
CTSU Pre-Award v2 - 435-MOROI | Final Budget | User | VanderElzen, Liz | 2017-10-28 | 0 |  | N | 435-MOROI
CTSU Pre-Award v2 - 430-HIGGINS | OnCore Budget Build | User | Yunk, Jason | 2017-10-28 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | OnCore Budget Build | User | Yunk, Jason | 2017-10-28 | 0 |  | N | 432-JAYASUNDERA
CTSU Pre-Award v2 - 430-HIGGINS | Calendar Released | User | Oliver, Amy | 2017-10-29 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | Calendar Released | User | Oliver, Amy | 2017-10-29 | 0 |  | N | 432-JAYASUNDERA
Pre-Award Financial - 11-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-30 | 0 |  | N | 00134884
CTSU Pre-Award v2 - 393-HYZY | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-30 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 393-HYZY | PAN Released | Role | CTSU Finance | 2017-10-30 | 0 |  | N | 393-HYZY
CTSU Pre-Award v2 - 396-SCHIOPU | Initiate Post-Award Task List | Role | CTSU Finance | 2017-10-30 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 439-KHANNA | Final Budget | Role | CTSU Finance | 2017-10-30 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | Final Budget | Role | CTSU Finance | 2017-10-30 | 0 |  | N | 440-LOK
CTSU Pre-Award v2 - 396-SCHIOPU | PAN Released | User | Oliver, Amy | 2017-10-30 | 0 |  | N | 396-SCHIOPU
CTSU Pre-Award v2 - 428-LAW | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-31 | 0 |  | N | 00135072
Pre-Award Financial - 203-ELSE | PI Signoff in OnCore | Role | CTSU Administrator | 2017-10-31 | 0 |  | N | 00132173
CTSU Pre-Award v2 - 435-MOROI | OnCore Budget Build | User | Yunk, Jason | 2017-10-31 | 0 |  | N | 435-MOROI
CTSU Pre-Award v2 - 430-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-11-01 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | PI Signoff in OnCore | Role | CTSU Administrator | 2017-11-01 | 0 |  | N | 432-JAYASUNDERA
Pre-Award Financial - 11-HIGGINS | Open to Accrual | Role | CTSU Administrator | 2017-11-01 | 0 |  | N | 00134884
CTSU Pre-Award v2 - 410-PAULUS | Initiate Post-Award Task List | Role | CTSU Finance | 2017-11-01 | 0 |  | N | 410-PAULUS
CTSU Pre-Award v2 - 439-KHANNA | PAF routed | Role | CTSU Finance | 2017-11-01 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | PAF routed | Role | CTSU Finance | 2017-11-01 | 0 |  | N | 440-LOK
CTSU Pre-Award v2 - 410-PAULUS | PAN Released | User | Oliver, Amy | 2017-11-01 | 0 |  | N | 410-PAULUS
CTSU Pre-Award v2 - 435-MOROI | Calendar Released | User | Oliver, Amy | 2017-11-01 | 0 |  | N | 435-MOROI
CTSU Pre-Award v2 - 428-LAW | Open to Accrual | Role | CTSU Administrator | 2017-11-02 | 0 |  | N | 00135072
Pre-Award Financial - 203-ELSE | Open to Accrual | Role | CTSU Administrator | 2017-11-02 | 0 |  | N | 00132173
CTSU Pre-Award v2 - 439-KHANNA | OnCore Budget Build | User | Yunk, Jason | 2017-11-02 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | OnCore Budget Build | User | Yunk, Jason | 2017-11-02 | 0 |  | N | 440-LOK
CTSU Pre-Award v2 - 430-HIGGINS | Open to Accrual | Role | CTSU Administrator | 2017-11-03 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | Open to Accrual | Role | CTSU Administrator | 2017-11-03 | 0 |  | N | 432-JAYASUNDERA
Pre-Award Financial - 205-HIGGINS | OnCore Budget Build | Role | CTSU Finance | 2017-11-03 | 0 |  | N | 205-HIGGINS
CTSU Pre-Award v2 - 439-KHANNA | Calendar Released | User | Oliver, Amy | 2017-11-03 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | Calendar Released | User | Oliver, Amy | 2017-11-03 | 0 |  | N | 440-LOK
CTSU Pre-Award v2 - 435-MOROI | PI Signoff in OnCore | Role | CTSU Administrator | 2017-11-04 | 0 |  | N | 435-MOROI
Pre-Award Financial - 205-HIGGINS | Calendar Released | Role | CTSU Finance | 2017-11-04 | 0 |  | N | 205-HIGGINS
CTSU Pre-Award v2 - 447-RAO | Final Budget | User | VanderElzen, Liz | 2017-11-04 | 0 |  | N | 447-RAO
CTSU Pre-Award v2 - 435-MOROI | Open to Accrual | Role | CTSU Administrator | 2017-11-06 | 0 |  | N | 435-MOROI
CTSU Pre-Award v2 - 439-KHANNA | PI Signoff in OnCore | Role | CTSU Administrator | 2017-11-06 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | PI Signoff in OnCore | Role | CTSU Administrator | 2017-11-06 | 0 |  | N | 440-LOK
CTSU Pre-Award v2 - 447-RAO | PAF routed | User | VanderElzen, Liz | 2017-11-06 | 0 |  | N | 447-RAO
Pre-Award Financial - 205-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator | 2017-11-07 | 0 |  | N | 205-HIGGINS
CTSU Pre-Award v2 - 447-RAO | OnCore Budget Build | User | Yunk, Jason | 2017-11-07 | 0 |  | N | 447-RAO
CTSU Pre-Award v2 - 439-KHANNA | Open to Accrual | Role | CTSU Administrator | 2017-11-08 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | Open to Accrual | Role | CTSU Administrator | 2017-11-08 | 0 |  | N | 440-LOK
CTSU Pre-Award v2 - 447-RAO | Calendar Released | User | Oliver, Amy | 2017-11-08 | 0 |  | N | 447-RAO
Pre-Award Financial - 205-HIGGINS | Open to Accrual | Role | CTSU Administrator | 2017-11-09 | 0 |  | N | 205-HIGGINS
CTSU Pre-Award v2 - 428-LAW | Initiate Post-Award Task List | Role | CTSU Finance | 2017-11-09 | 0 |  | N | 00135072
CTSU Pre-Award v2 - 428-LAW | PAN Released | User | Oliver, Amy | 2017-11-09 | 0 |  | N | 00135072
CTSU Pre-Award v2 - 430-HIGGINS | Initiate Post-Award Task List | Role | CTSU Finance | 2017-11-10 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | Initiate Post-Award Task List | Role | CTSU Finance | 2017-11-10 | 0 |  | N | 432-JAYASUNDERA
CTSU Pre-Award v2 - 430-HIGGINS | PAN Released | User | Oliver, Amy | 2017-11-10 | 0 |  | N | 430-HIGGINS
CTSU Pre-Award v2 - 432-JAYASUNDERA | PAN Released | User | Oliver, Amy | 2017-11-10 | 0 |  | N | 432-JAYASUNDERA
CTSU Pre-Award v2 - 447-RAO | PI Signoff in OnCore | Role | CTSU Administrator | 2017-11-11 | 0 |  | N | 447-RAO
CTSU Pre-Award v2 - 447-RAO | Open to Accrual | Role | CTSU Administrator | 2017-11-13 | 0 |  | N | 447-RAO
CTSU Pre-Award v2 - 435-MOROI | Initiate Post-Award Task List | Role | CTSU Finance | 2017-11-13 | 0 |  | N | 435-MOROI
CTSU Pre-Award v2 - 435-MOROI | PAN Released | User | Oliver, Amy | 2017-11-13 | 0 |  | N | 435-MOROI
CTSU Pre-Award v2 - 439-KHANNA | Initiate Post-Award Task List | Role | CTSU Finance | 2017-11-15 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | Initiate Post-Award Task List | Role | CTSU Finance | 2017-11-15 | 0 |  | N | 440-LOK
CTSU Pre-Award v2 - 439-KHANNA | PAN Released | User | Oliver, Amy | 2017-11-15 | 0 |  | N | 439-KHANNA
CTSU Pre-Award v2 - 440-LOK | PAN Released | User | Oliver, Amy | 2017-11-15 | 0 |  | N | 440-LOK
CTSU Pre-Award v2 - 447-RAO | Initiate Post-Award Task List | Role | CTSU Finance | 2017-11-20 | 0 |  | N | 447-RAO
CTSU Pre-Award v2 - 447-RAO | PAN Released | User | Oliver, Amy | 2017-11-20 | 0 |  | N | 447-RAO
Calendar Build - 52-AARONSON | Approved care designations | User | Benton, Archie |  |  |  | N | 00128761
Core Sponsor Documents for Study Feasibility & Start Up - General - 2 | Care Designations | User | Benton, Archie |  |  |  | N | 00127913
Core Sponsor Documents for Study Feasibility & Start Up - General - 192-ALAM | Informed Consent | User | Bonham, Tess |  |  |  | N | 192-ALAM
Core Sponsor Documents for Study Feasibility & Start Up - General - 192-ALAM | Investigational Drug Brochure / Investigator's Brochure | User | Bonham, Tess |  |  |  | N | 192-ALAM
Open to Accrual - 192-ALAM | Adequate Equipment and Supplies Available | User | Bonham, Tess |  |  |  | N | 192-ALAM
Open to Accrual - 192-ALAM | IRB Approval | User | Bonham, Tess |  |  |  | N | 192-ALAM
Open to Accrual - 192-ALAM | Investigational Drug/Device Supplies Available | User | Bonham, Tess |  |  |  | N | 192-ALAM
Open to Accrual - 192-ALAM | MiChart Verifications | User | Bonham, Tess |  |  |  | N | 192-ALAM
Open to Accrual - 192-ALAM | Other Personnel Notified | User | Bonham, Tess |  |  |  | N | 192-ALAM
Open to Accrual - 192-ALAM | Provisions for Support and Services Finalized | User | Bonham, Tess |  |  |  | N | 192-ALAM
Open to Accrual - 192-ALAM | Sponsor/Organizing Group Approval Granted for Initiation of Study | User | Bonham, Tess |  |  |  | N | 192-ALAM
Open to Accrual - 192-ALAM | Study Files Established | User | Bonham, Tess |  |  |  | N | 192-ALAM
Open to Accrual - 192-ALAM | Study Team Roles/Responsibilities Finalized | User | Bonham, Tess |  |  |  | N | 192-ALAM
Open to Accrual - 00121569 2 | FDA Approval | User | Brand, Sarah |  |  | NA | Y | 00121569
Amendment 00072647 | ** Footnote Edits | Role | CRAO |  |  |  | N | 00122489
Amendment 00072647 | ** Items/Services : Addition or Removal of Procedures / Events | Role | CRAO |  |  |  | N | 00122489
Amendment 00072647 | ** Items/Services : Updates to Activity for Existing Procedures / Events | Role | CRAO |  |  |  | N | 00122489
Amendment 00072647 | ** Other | Role | CRAO |  |  |  | N | 00122489
Amendment 00072647 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | Role | CRAO |  |  |  | N | 00122489
Amendment 00072647 | ** Visit Tolerance Edits | Role | CRAO |  |  |  | N | 00122489
Amendment 00072647 | ** Visits : Addition or Removal of Time Points | Role | CRAO |  |  |  | N | 00122489
Amendment 00072647 | Assign to Analyst | Role | CRAO |  |  |  | N | 00122489
Amendment 00072647 | Complete Calendar and Document Approval | Role | CRAO |  |  |  | N | 00122489
Amendment 00072647 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | Role | CRAO |  |  |  | N | 00122489
Amendment 00072647 | Request Care Designations | Role | CRAO |  |  |  | N | 00122489
Amendment 00072647 | Update RSH Source in MBECT | Role | CRAO |  |  |  | N | 00122489
BC : Initial Build - PLT-INF24-001 | CRAO Approval Issue & Documented | Role | CRAO |  |  |  | N | 00135388
BC : Initial Build - PLT-INF24-001 | Complete SVS & Pricing List ( Built & Coded ) | Role | CRAO |  |  | NA | Y | 00135388
BC : Initial Build - PLT-INF24-001 | Make Updates | Role | CRAO |  |  | NA | Y | 00135388
Calendaring : Amendment Checklist & Process - 00068856 | ** Footnote Edits | Role | CRAO |  |  | NA | Y | 00068856
Calendaring : Amendment Checklist & Process - 00068856 | ** Items/Services : Addition or Removal of Procedures / Events | Role | CRAO |  |  | NA | Y | 00068856
Calendaring : Amendment Checklist & Process - 00068856 | ** Other | Role | CRAO |  |  | NA | Y | 00068856
Calendaring : Amendment Checklist & Process - 00068856 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | Role | CRAO |  |  | NA | Y | 00068856
Calendaring : Amendment Checklist & Process - 00068856 | ** Visit Tolerance Edits | Role | CRAO |  |  | NA | Y | 00068856
Calendaring : Amendment Checklist & Process - 00068856 | ** Visits : Addition or Removal of Time Points | Role | CRAO |  |  | NA | Y | 00068856
Calendaring : Amendment Checklist & Process - 00068856 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | Role | CRAO |  |  | NA | Y | 00068856
Calendaring : Amendment Checklist & Process - 00068856 | Request Care Designations | Role | CRAO |  |  | NA | Y | 00068856
Calendaring : Amendment Checklist & Process - 00068856 | Update RSH Source in MBECT | Role | CRAO |  |  | NA | Y | 00068856
Calendaring : Amendment Checklist & Process - 00080998 | ** Items/Services : Addition or Removal of Procedures / Events | Role | CRAO |  |  | NA | Y | 00080998
Calendaring : Amendment Checklist & Process - 00080998 | ** Other | Role | CRAO |  |  | NA | Y | 00080998
Calendaring : Amendment Checklist & Process - 00080998 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | Role | CRAO |  |  | NA | Y | 00080998
Calendaring : Amendment Checklist & Process - 00080998 | ** Visit Tolerance Edits | Role | CRAO |  |  | NA | Y | 00080998
Calendaring : Amendment Checklist & Process - 00080998 | ** Visits : Addition or Removal of Time Points | Role | CRAO |  |  | NA | Y | 00080998
Calendaring : Amendment Checklist & Process - 00080998 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | Role | CRAO |  |  | NA | Y | 00080998
Calendaring : Amendment Checklist & Process - 00080998 | Request Care Designations | Role | CRAO |  |  | NA | Y | 00080998
Calendaring : Amendment Checklist & Process - 00080998 | Update RSH Source in MBECT | Role | CRAO |  |  | NA | Y | 00080998
Calendaring : Amendment Checklist & Process - 00101092 | ** Visits : Addition or Removal of Time Points | Role | CRAO |  |  | NA | Y | 00101092
Calendaring : Amendment Checklist & Process - 00101092 | Request Care Designations | Role | CRAO |  |  | NA | Y | 00101092
Calendaring : Amendment Checklist & Process - 00106894 | ** Items/Services : Addition or Removal of Procedures / Events | Role | CRAO |  |  | NA | Y | 00106894
Calendaring : Amendment Checklist & Process - 00106894 | ** Other | Role | CRAO |  |  | NA | Y | 00106894
Calendaring : Amendment Checklist & Process - 00106894 | ** Visit Tolerance Edits | Role | CRAO |  |  | NA | Y | 00106894
Calendaring : Amendment Checklist & Process - 00106894 | ** Visits : Addition or Removal of Time Points | Role | CRAO |  |  | NA | Y | 00106894
Calendaring : Amendment Checklist & Process - 00106894 | Request Care Designations | Role | CRAO |  |  | NA | Y | 00106894
Calendaring : Amendment Checklist & Process - 00106894 | Update RSH Source in MBECT | Role | CRAO |  |  | NA | Y | 00106894
Calendaring : Amendment Checklist & Process - 00110881 | ** Other | Role | CRAO |  |  | NA | Y | 00110881
Calendaring : Amendment Checklist & Process - 00110881 | ** Visit Tolerance Edits | Role | CRAO |  |  | NA | Y | 00110881
Calendaring : Amendment Checklist & Process - 00110881 | ** Visits : Addition or Removal of Time Points | Role | CRAO |  |  | NA | Y | 00110881
Calendaring : Amendment Checklist & Process - 00110881 | Request Care Designations | Role | CRAO |  |  | NA | Y | 00110881
Calendaring : Amendment Checklist & Process - 00115982 | ** Items/Services : Addition or Removal of Procedures / Events | Role | CRAO |  |  | NA | Y | 00115982
Calendaring : Amendment Checklist & Process - 00115982 | ** Other | Role | CRAO |  |  | NA | Y | 00115982
Calendaring : Amendment Checklist & Process - 00115982 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | Role | CRAO |  |  | NA | Y | 00115982
Calendaring : Amendment Checklist & Process - 00115982 | ** Visit Tolerance Edits | Role | CRAO |  |  | NA | Y | 00115982
Calendaring : Amendment Checklist & Process - 00115982 | ** Visits : Addition or Removal of Time Points | Role | CRAO |  |  | NA | Y | 00115982
Calendaring : Amendment Checklist & Process - 00115982 | Request Care Designations | Role | CRAO |  |  | NA | Y | 00115982
Calendaring : Amendment Checklist & Process - 00115982 | Update RSH Source in MBECT | Role | CRAO |  |  | NA | Y | 00115982
Calendaring : Amendment Checklist & Process - 00119399 | ** Items/Services : Addition or Removal of Procedures / Events | Role | CRAO |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 | ** Items/Services : Updates to Activity for Existing Procedures / Events | Role | CRAO |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 | ** Other | Role | CRAO |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | Role | CRAO |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 | ** Visit Tolerance Edits | Role | CRAO |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 | ** Visits : Addition or Removal of Time Points | Role | CRAO |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 | Request Care Designations | Role | CRAO |  |  | NA | Y | 00119399
Calendaring : Initial Build - 00126224 | Feasibility Approval Notice Received | Role | CRAO |  |  | 2017-01-23 | N | 00126224
Calendaring : Initial Build - 00126224 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  | 2017-02-13 | N | 00126224
Calendaring : Initial Calendar Build - | CRAO Approval Issue & Documented | Role | CRAO |  |  |  | N | 103-GAGNIER
Calendaring : Initial Calendar Build - | Complete Calendar ( ie. Ready for Financials ) | Role | CRAO |  |  | NA | Y | 103-GAGNIER
Calendaring : Initial Calendar Build - | Import + Michiganize & Export Billing Grid for Determining Care Designations | Role | CRAO |  |  | NA | Y | 103-GAGNIER
Calendaring : Initial Calendar Build - | Make Updates | Role | CRAO |  |  | NA | Y | 103-GAGNIER
Calendaring : Initial Calendar Build - 00109407 | Complete SVS & Pricing List ( Built & Coded ) | Role | CRAO |  |  | NA | Y | 00109407
Calendaring : Initial Calendar Build - 00113042 | CRAO Approval Issue & Documented | Role | CRAO |  |  | NA | Y | 00113042
Calendaring : Initial Calendar Build - 00113042 | Complete SVS & Pricing List ( Built & Coded ) | Role | CRAO |  |  | NA | Y | 00113042
Calendaring : Initial Calendar Build - 00113042 | Make Updates | Role | CRAO |  |  | NA | Y | 00113042
Calendaring : Initial Calendar Build - 00118070 | Attach Build Notes ( as Protocol Doc ) | Role | CRAO |  |  |  | N | 00118070
Calendaring : Initial Calendar Build - 00118070 | CRAO Approval Issue & Documented | Role | CRAO |  |  |  | N | 00118070
Calendaring : Initial Calendar Build - 00118070 | Complete Calendar ( ie. Ready for Financials ) | Role | CRAO |  |  |  | N | 00118070
Calendaring : Initial Calendar Build - 00118070 | Complete MCA / QCT | Role | CRAO |  |  |  | N | 00118070
Calendaring : Initial Calendar Build - 00118070 | Complete SVS & Pricing List ( Built & Coded ) | Role | CRAO |  |  |  | N | 00118070
Calendaring : Initial Calendar Build - 00118070 | Feasibility Approval Notice Received | Role | CRAO |  |  | 2017-04-18 | N | 00118070
Calendaring : Initial Calendar Build - 00118070 | Import + Michiganize & Export Billing Grid for Determining Care Designations | Role | CRAO |  |  |  | N | 00118070
Calendaring : Initial Calendar Build - 00118070 | Make Updates | Role | CRAO |  |  |  | N | 00118070
Calendaring : Initial Calendar Build - 00118070 | Nimblify Build is Complete & Ready for Import | Role | CRAO |  |  | 2017-04-18 | N | 00118070
Calendaring : Initial Calendar Build - 00118461 | CRAO Approval Issue & Documented | Role | CRAO |  |  | NA | Y | 00118461
Calendaring : Initial Calendar Build - 00118461 | Complete SVS & Pricing List ( Built & Coded ) | Role | CRAO |  |  | NA | Y | 00118461
Calendaring : Initial Calendar Build - 00120786 | CRAO Approval Issue & Documented | Role | CRAO |  |  | 2017-01-20 | N | 00120786
Calendaring : Initial Calendar Build - 00121569 2 | Feasibility Approval Notice Received | Role | CRAO |  |  | 2017-03-01 | N | 00121569
Calendaring : Initial Calendar Build - 00121569 2 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  | 2017-03-02 | N | 00121569
Calendaring : Initial Calendar Build - 00123069 | Attach Build Notes ( as Protocol Doc ) | Role | CRAO |  |  | NA | Y | 00123069
Calendaring : Initial Calendar Build - 00123069 | CRAO Approval Issue & Documented | Role | CRAO |  |  | NA | Y | 00123069
Calendaring : Initial Calendar Build - 00123069 | Complete Calendar ( ie. Ready for Financials ) | Role | CRAO |  |  | NA | Y | 00123069
Calendaring : Initial Calendar Build - 00123069 | Complete MCA / QCT | Role | CRAO |  |  | NA | Y | 00123069
Calendaring : Initial Calendar Build - 00123069 | Complete SVS & Pricing List ( Built & Coded ) | Role | CRAO |  |  | NA | Y | 00123069
Calendaring : Initial Calendar Build - 00123069 | Feasibility Approval Notice Received | Role | CRAO |  |  | NA | Y | 00123069
Calendaring : Initial Calendar Build - 00123069 | Import + Michiganize & Export Billing Grid for Determining Care Designations | Role | CRAO |  |  | NA | Y | 00123069
Calendaring : Initial Calendar Build - 00123069 | Make Updates | Role | CRAO |  |  | NA | Y | 00123069
Calendaring : Initial Calendar Build - 00123069 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  | NA | Y | 00123069
Calendaring : Initial Calendar Build - 00124839 | Complete SVS & Pricing List ( Built & Coded ) | Role | CRAO |  |  | NA | Y | 00124839
Calendaring : Initial Calendar Build - 00125022 | Feasibility Approval Notice Received | Role | CRAO |  |  | NA | Y | 00125022
Calendaring : Initial Calendar Build - 00125022 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  | NA | Y | 00125022
Calendaring : Initial Calendar Build - 00125599 | CRAO Approval Issue & Documented | Role | CRAO |  |  | NA | Y | 00125599
Calendaring : Initial Calendar Build - 00125599 | Complete SVS & Pricing List ( Built & Coded ) | Role | CRAO |  |  | NA | Y | 00125599
Calendaring : Initial Calendar Build - 00125599 | Make Updates | Role | CRAO |  |  | NA | Y | 00125599
Calendaring : Initial Calendar Build - 00125836 | Attach Build Notes ( as Protocol Doc ) | Role | CRAO |  |  | NA | Y | 00125836
Calendaring : Initial Calendar Build - 00125836 | Complete MCA / QCT | Role | CRAO |  |  | NA | Y | 00125836
Calendaring : Initial Calendar Build - 00125836 | Feasibility Approval Notice Received | Role | CRAO |  |  | NA | Y | 00125836
Calendaring : Initial Calendar Build - 00125836 | Import + Michiganize & Export Billing Grid for Determining Care Designations | Role | CRAO |  |  | NA | Y | 00125836
Calendaring : Initial Calendar Build - 00125836 | Nimblify Build is Complete & Ready for Import | Role | CRAO |  |  | NA | Y | 00125836
Calendaring : Initial Calendar Build - 00125836 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  | NA | Y | 00125836
Calendaring : Initial Calendar Build - 00126135 | Complete SVS & Pricing List ( Built & Coded ) | Role | CRAO |  |  | NA | Y | 00126135
Calendaring : Initial Calendar Build - 00126135 | Feasibility Approval Notice Received | Role | CRAO |  |  | NA | Y | 00126135
Calendaring : Initial Calendar Build - 00126135 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  | NA | Y | 00126135
Calendaring : Initial Calendar Build - 00126215 | Attach Build Notes ( as Protocol Doc ) | Role | CRAO |  |  |  | N | 00126215
Calendaring : Initial Calendar Build - 00126215 | CRAO Approval Issue & Documented | Role | CRAO |  |  |  | N | 00126215
Calendaring : Initial Calendar Build - 00126215 | Complete Calendar ( ie. Ready for Financials ) | Role | CRAO |  |  |  | N | 00126215
Calendaring : Initial Calendar Build - 00126215 | Complete MCA / QCT | Role | CRAO |  |  |  | N | 00126215
Calendaring : Initial Calendar Build - 00126215 | Complete SVS & Pricing List ( Built & Coded ) | Role | CRAO |  |  |  | N | 00126215
Calendaring : Initial Calendar Build - 00126215 | Feasibility Approval Notice Received | Role | CRAO |  |  | 2017-02-22 | N | 00126215
Calendaring : Initial Calendar Build - 00126215 | Import + Michiganize & Export Billing Grid for Determining Care Designations | Role | CRAO |  |  |  | N | 00126215
Calendaring : Initial Calendar Build - 00126215 | Make Updates | Role | CRAO |  |  |  | N | 00126215
Calendaring : Initial Calendar Build - 00126215 | Nimblify Build is Complete & Ready for Import | Role | CRAO |  |  |  | N | 00126215
Calendaring : Initial Calendar Build - 00126215 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  | 2017-03-21 | N | 00126215
Calendaring : Initial Calendar Build - 00127356 | Feasibility Approval Notice Received | Role | CRAO |  |  |  | N | 00127356
Calendaring : Initial Calendar Build - 00127356 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  |  | N | 00127356
Calendaring : Initial Calendar Build - 00127505 | CRAO Approval Issue & Documented | Role | CRAO |  |  |  | N | 00127505
Calendaring : Initial Calendar Build - 00127505 | Feasibility Approval Notice Received | Role | CRAO |  |  |  | N | 00127505
Calendaring : Initial Calendar Build - 00127505 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  |  | N | 00127505
Calendaring : Initial Calendar Build - 00128301 | Feasibility Approval Notice Received | Role | CRAO |  |  | 2017-04-12 | N | 00128301
Calendaring : Initial Calendar Build - 00129709 | Feasibility Approval Notice Received | Role | CRAO |  |  | NA | Y | 00129709
Calendaring : Initial Calendar Build - 00129709 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  | NA | Y | 00129709
Calendaring : Initial Calendar Build - 00129943 | CRAO Approval Issue & Documented | Role | CRAO |  |  |  | N | 00129943
Calendaring : Initial Calendar Build - 147 | CRAO Approval Issue & Documented | Role | CRAO |  |  |  | N | 00128322
Calendaring : Initial Calendar Build - 147 | Feasibility Approval Notice Received | Role | CRAO |  |  | 2017-03-01 | N | 00128322
Calendaring : Initial Calendar Build - 190-SCHIOPU | Feasibility Approval Notice Received | Role | CRAO |  |  | 2017-06-29 | N | 00134443
Calendaring : Initial Calendar Build - 225-ROSENBLUM | Complete SVS & Pricing List ( Built & Coded ) | Role | CRAO |  |  | NA | Y | 00124224
Calendaring : Initial Calendar Build - 227-STEIGERWALT 3 | Feasibility Approval Notice Received | Role | CRAO |  |  | 2017-08-10 | N | 227-STEIGERWALT
Calendaring : Initial Calendar Build - 24-PARIKH | Make Updates | Role | CRAO |  |  | NA | Y | 00128493
Calendaring : Initial Calendar Build - 24-PARIKH | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  |  | N | 00128493
Calendaring : Initial Calendar Build - 27-WALKOVICH | Feasibility Approval Notice Received | Role | CRAO |  |  | 2017-03-02 | N | 00127988
Calendaring : Initial Calendar Build - 27-WALKOVICH | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  | 2017-03-22 | N | 00127988
Calendaring : Initial Calendar Build - 314-PARK | Assign to Analyst | Role | CRAO |  |  |  | N | 314-PARK
Calendaring : Initial Calendar Build - 314-PARK | Attach Build Notes ( as Protocol Doc ) | Role | CRAO |  |  |  | N | 314-PARK
Calendaring : Initial Calendar Build - 314-PARK | CRAO Approval Issue & Documented | Role | CRAO |  |  |  | N | 314-PARK
Calendaring : Initial Calendar Build - 314-PARK | Complete Calendar ( ie. Ready for Financials ) | Role | CRAO |  |  |  | N | 314-PARK
Calendaring : Initial Calendar Build - 314-PARK | Complete MCA / QCT | Role | CRAO |  |  |  | N | 314-PARK
Calendaring : Initial Calendar Build - 314-PARK | Complete SVS & Pricing List ( Built & Coded ) | Role | CRAO |  |  |  | N | 314-PARK
Calendaring : Initial Calendar Build - 314-PARK | Feasibility Approval Notice Received | Role | CRAO |  |  |  | N | 314-PARK
Calendaring : Initial Calendar Build - 314-PARK | Import + Michiganize & Export Billing Grid for Determining Care Designations | Role | CRAO |  |  |  | N | 314-PARK
Calendaring : Initial Calendar Build - 314-PARK | Make Updates | Role | CRAO |  |  |  | N | 314-PARK
Calendaring : Initial Calendar Build - 314-PARK | Nimblify Build is Complete & Ready for Import | Role | CRAO |  |  |  | N | 314-PARK
Calendaring : Initial Calendar Build - 314-PARK | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  |  | N | 314-PARK
Calendaring : Initial Calendar Build - 357-GRANT 2 | CRAO Approval Issue & Documented | Role | CRAO |  |  |  | N | 00119336
Calendaring : Initial Calendar Build - 384-MODY | Feasibility Approval Notice Received | Role | CRAO |  |  | 2017-08-10 | N | 00134459
Calendaring : Initial Calendar Build - 97-KALES | CRAO Approval Issue & Documented | Role | CRAO |  |  |  | N | 97-KALES
Calendaring : Initial Calendar Build - CIP-1403 | Attach Build Notes ( as Protocol Doc ) | Role | CRAO |  |  |  | N | 00128253
Calendaring : Initial Calendar Build - CIP-1403 | CRAO Approval Issue & Documented | Role | CRAO |  |  |  | N | 00128253
Calendaring : Initial Calendar Build - CIP-1403 | Feasibility Approval Notice Received | Role | CRAO |  |  | NA | Y | 00128253
Calendaring : Initial Calendar Build - CIP-1403 | Nimblify Build is Complete & Ready for Import | Role | CRAO |  |  | 2017-04-28 | N | 00128253
Calendaring : Initial Calendar Build - P-3058HELFRICH | CRAO Approval Issue & Documented | Role | CRAO |  |  |  | N | 00129897
Calendaring : Migration - 000127913 | Attach Build Notes and MBECT Calendar Reference ( as Protocol Docs ) | Role | CRAO |  |  | NA | Y | 00127913
Calendaring : Migration - 000127913 | Nimblify Build is Complete & Ready for Import | Role | CRAO |  |  | 2017-04-17 | N | 00127913
Calendaring : Migration - 00070592 | Acknowledge | Role | CRAO |  |  |  | N | PROTOCOL-SHELL-001
Calendaring : Migration - 00070592 | Assign to Analyst | Role | CRAO |  |  |  | N | PROTOCOL-SHELL-001
Calendaring : Migration - 00070592 | Attach Build Notes and MBECT Calendar Reference ( as Protocol Docs ) | Role | CRAO |  |  |  | N | PROTOCOL-SHELL-001
Calendaring : Migration - 00070592 | Complete Calendar ( ie. Flag as Ready for Financials ) | Role | CRAO |  |  |  | N | PROTOCOL-SHELL-001
Calendaring : Migration - 00070592 | Import + Michiganize, including Entry of Care Designations & Comments per Current Approved MBECT Calendar | Role | CRAO |  |  |  | N | PROTOCOL-SHELL-001
Calendaring : Migration - 00070592 | Nimblify Build is Complete & Ready for Import | Role | CRAO |  |  |  | N | PROTOCOL-SHELL-001
Calendaring : Migration - 00070592 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  |  | N | PROTOCOL-SHELL-001
Calendaring : Migration - 00076393 | Acknowledge | Role | CRAO |  |  |  | N | 00076393
Calendaring : Migration - 00076393 | Assign to Analyst | Role | CRAO |  |  |  | N | 00076393
Calendaring : Migration - 00076393 | Attach Build Notes and MBECT Calendar Reference ( as Protocol Docs ) | Role | CRAO |  |  |  | N | 00076393
Calendaring : Migration - 00076393 | Complete Calendar ( ie. Flag as Ready for Financials ) | Role | CRAO |  |  |  | N | 00076393
Calendaring : Migration - 00076393 | Import + Michiganize, including Entry of Care Designations & Comments per Current Approved MBECT Calendar | Role | CRAO |  |  |  | N | 00076393
Calendaring : Migration - 00076393 | Nimblify Build is Complete & Ready for Import | Role | CRAO |  |  |  | N | 00076393
Calendaring : Migration - 00076393 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  | 2017-03-03 | N | 00076393
Calendaring : Migration - 00081004 | Nimblify Build is Complete & Ready for Import | Role | CRAO |  |  | 2017-03-16 | N | 00081004
Calendaring : Migration - 00089664 | Nimblify Build is Complete & Ready for Import | Role | CRAO |  |  | NA | Y | 00089664
Calendaring : Migration - 00089664 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  | NA | Y | 00089664
Calendaring : Migration - 00100501 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  | 2017-04-21 | N | 00100501
Calendaring : Migration - 00105810 | Nimblify Build is Complete & Ready for Import | Role | CRAO |  |  | 2017-03-15 | N | 00105810
Calendaring : Migration - 00105810 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  | 2017-03-03 | N | 00105810
Calendaring : Migration - 00125493 | Acknowledge | Role | CRAO |  |  |  | N | 00125493
Calendaring : Migration - 00125493 | Attach Build Notes and MBECT Calendar Reference ( as Protocol Docs ) | Role | CRAO |  |  |  | N | 00125493
Calendaring : Migration - 00125493 | Complete Calendar ( ie. Flag as Ready for Financials ) | Role | CRAO |  |  |  | N | 00125493
Calendaring : Migration - 00125493 | Import + Michiganize, including Entry of Care Designations & Comments per Current Approved MBECT Calendar | Role | CRAO |  |  |  | N | 00125493
Calendaring : Migration - 00125493 | Nimblify Build is Complete & Ready for Import | Role | CRAO |  |  | 2017-02-09 | N | 00125493
Calendaring : Migration - 00125493 | Submit Calendar Build Request and Docs to Nimblify | Role | CRAO |  |  | 2017-02-09 | N | 00125493
Calendaring : Specification Update Request(s) - 00091655 | Assign to Analyst | Role | CRAO |  |  | NA | Y | 00091655
Calendaring : Specification Update Request(s) - 00091655 | Make Update(s) | Role | CRAO |  |  | NA | Y | 00091655
Calendaring : Specification Update Request(s) - 00091655 | Re-Complete Calendar | Role | CRAO |  |  | NA | Y | 00091655
Calendaring : Specification Update Request(s) - 00127913 | Assign to Analyst | Role | CRAO |  |  | NA | Y | 00127913
Calendaring : Specification Update Request(s) - 00127913 | Make Update(s) | Role | CRAO |  |  | NA | Y | 00127913
Calendaring : Specification Update Request(s) - 00127913 | Re-Complete Calendar | Role | CRAO |  |  | NA | Y | 00127913
CTSU Pre-Award - 309-MOROI | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 309-MOROI | Feasibility w/Documents received | Role | CTSU Administrator |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 309-MOROI | Open to Accrual | Role | CTSU Administrator |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 309-MOROI | PI Signoff in OnCore | Role | CTSU Administrator |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 314-PARK | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 314-PARK
CTSU Pre-Award - 331-FLAHERTY | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | Feasibility w/Documents received | Role | CTSU Administrator |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | Open to Accrual | Role | CTSU Administrator |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 342-HUMES | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 342-HUMES
CTSU Pre-Award - 346-BAPTIST | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | Feasibility w/Documents received | Role | CTSU Administrator |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | PI Signoff in OnCore | Role | CTSU Administrator |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 347-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | Open to Accrual | Role | CTSU Administrator |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 348-CHEY | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Feasibility w/Documents received | Role | CTSU Administrator |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | PI Signoff in OnCore | Role | CTSU Administrator |  |  |  | N | 348-CHEY
CTSU Pre-Award - 354-PAGANI | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 363-PARK | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 363-PARK
CTSU Pre-Award - 375-JAMERSON | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 375-JAMERSON
CTSU Pre-Award v2 - 00134459 | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | Feasibility w/Documents received | Role | CTSU Administrator |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | PI Signoff in OnCore | Role | CTSU Administrator |  |  |  | N | 00134459
CTSU Pre-Award v2 - 397-HODISH | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | Feasibility w/Documents received | Role | CTSU Administrator |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | Open to Accrual | Role | CTSU Administrator |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | PI Signoff in OnCore | Role | CTSU Administrator |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 409-NASR | Feasibility w/Documents received | Role | CTSU Administrator |  |  | NA | Y | 409-NASR
CTSU Pre-Award v2 - 412-NASR | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | Feasibility w/Documents received | Role | CTSU Administrator |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | PI Signoff in OnCore | Role | CTSU Administrator |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 419-PIPE 2 | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | Feasibility w/Documents received | Role | CTSU Administrator |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | PI Signoff in OnCore | Role | CTSU Administrator |  |  |  | N | 00130583
CTSU Pre-Award v2 - 427-KOSCHMANN | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | Feasibility w/Documents received | Role | CTSU Administrator |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | PI Signoff in OnCore | Role | CTSU Administrator |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 8-AARONSON | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | Feasibility w/Documents received | Role | CTSU Administrator |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | PI Signoff in OnCore | Role | CTSU Administrator |  |  |  | N | 00132110
Open to Accrual - 00117851 | MiChart Verifications | Role | CTSU Administrator |  |  | 2017-06-19 | N | 00117851
Open to Accrual - 00120231 | MiChart Verifications | Role | CTSU Administrator |  |  | 2017-07-12 | N | 00120231
Open to Accrual - 00122153 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Administrator |  |  | 2017-04-21 | N | 00122153
Open to Accrual - 00122815 | MiChart Verifications | Role | CTSU Administrator |  |  | 2017-06-09 | N | 00122815
Open to Accrual - 00123069 | MiChart Verifications | Role | CTSU Administrator |  |  | 2017-08-09 | N | 00123069
Open to Accrual - 00123632 | MiChart Verifications | Role | CTSU Administrator |  |  | 2017-05-31 | N | 00123632
Open to Accrual - 00125798 | MiChart Verifications | Role | CTSU Administrator |  |  |  | N | 00125798
Open to Accrual - 00128253 | MiChart Verifications | Role | CTSU Administrator |  |  | 2017-07-05 | N | 00128253
Open to Accrual - 00128322 | MiChart Verifications | Role | CTSU Administrator |  |  | 2017-08-22 | N | 00128322
Open to Accrual - 00128322 | Project Award Notice (PAN) Received | Role | CTSU Administrator |  |  | 2017-08-24 | N | 00128322
Open to Accrual - 00128761 | MiChart Verifications | Role | CTSU Administrator |  |  | 2017-08-22 | N | 00128761
Open to Accrual - 00129716 | FDA Approval | Role | CTSU Administrator |  |  | NA | Y | 00129716
Pre-Award Financial - 00121967 2 | Open to Accrual | Role | CTSU Administrator |  |  | 2016-12-08 | N | 00121967
Pre-Award Financial - 00123237 | Open to Accrual | Role | CTSU Administrator |  |  | NA | Y | 00123237
Pre-Award Financial - 00124712 | Open to Accrual | Role | CTSU Administrator |  |  | NA | Y | 00124712
Pre-Award Financial - 00124712 | PI Signoff in OnCore | Role | CTSU Administrator |  |  | NA | Y | 00124712
Pre-Award Financial - 00126215 | Open to Accrual | Role | CTSU Administrator |  |  | NA | Y | 00126215
Pre-Award Financial - 00126215 | PI Signoff in OnCore | Role | CTSU Administrator |  |  | NA | Y | 00126215
Pre-Award Financial - 00126224 | Open to Accrual | Role | CTSU Administrator |  |  | NA | Y | 00126224
Pre-Award Financial - 00127988 | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 00127988
Pre-Award Financial - 111-HIGGINS | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | Feasibility w/Documents received | Role | CTSU Administrator |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | Open to Accrual | Role | CTSU Administrator |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | PI Signoff in OnCore | Role | CTSU Administrator |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 131-LUGOGO | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | Feasibility w/Documents received | Role | CTSU Administrator |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | Open to Accrual | Role | CTSU Administrator |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | PI Signoff in OnCore | Role | CTSU Administrator |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 155-ORAL | Feasibility w/Documents received | Role | CTSU Administrator |  |  | NA | Y | 00130803
Pre-Award Financial - 187-MCLAUGHLIN | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 192-ALAM | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 192-ALAM
Pre-Award Financial - 194-MCLAUGHLIN | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 198-LUCKRITZ | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 198-LUCKRITZ
Pre-Award Financial - 201-MCCUNE | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | Feasibility w/Documents received | Role | CTSU Administrator |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | PI Signoff in OnCore | Role | CTSU Administrator |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 222-STEIGERWALT | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 234-MCLAUGHLIN | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 236-NASR | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 00131580
Pre-Award Financial - 238-GUNNERSON | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 241-SILVER | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 00132956
Pre-Award Financial - 258-SHEEHAN | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 268-NEUMAR | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 305-PELOSI | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 305-PELOSI
Pre-Award Financial - 44-MCUNE | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Feasibility w/Documents received | Role | CTSU Administrator |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | PI Signoff in OnCore | Role | CTSU Administrator |  |  |  | N | 44-MCUNE
Pre-Award Financial - 69-KHANNA | UFA Completed | Role | CTSU Administrator |  |  | NA | Y | 69-KHANNA
Pre-Award Financial - FONTANA-3 | Feasibility approved/CRAO Notified | Role | CTSU Administrator |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | Feasibility w/Documents received | Role | CTSU Administrator |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | Open to Accrual | Role | CTSU Administrator |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | PI Signoff in OnCore | Role | CTSU Administrator |  |  | NA | Y | FONTANA-3
Pre-Award Financial - HUM00091711 | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 00091711
Pre-Award Financial - HUM00129276 | Open to Accrual | Role | CTSU Administrator |  |  |  | N | 00129276
CTSU Pre-Award - 309-MOROI | IRB Application Submitted | Role | CTSU Coordinator |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 309-MOROI | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 309-MOROI | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 309-MOROI | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 314-PARK | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 314-PARK
CTSU Pre-Award - 326-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 326-HIGGINS
CTSU Pre-Award - 326-HIGGINS | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 326-HIGGINS
CTSU Pre-Award - 327-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 327-HIGGINS
CTSU Pre-Award - 327-HIGGINS | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 327-HIGGINS
CTSU Pre-Award - 331-FLAHERTY | IRB Application Submitted | Role | CTSU Coordinator |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | PI Signoff in OnCore | Role | CTSU Coordinator |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 336-KHANNA | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00133684
CTSU Pre-Award - 337-MIAN | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 337-MIAN
CTSU Pre-Award - 337-MIAN | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 337-MIAN
CTSU Pre-Award - 338-MIAN | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00133457
CTSU Pre-Award - 338-MIAN | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00133457
CTSU Pre-Award - 341-STOFFEL | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00134997
CTSU Pre-Award - 341-STOFFEL | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00134997
CTSU Pre-Award - 342-HUMES | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 342-HUMES
CTSU Pre-Award - 346-BAPTIST | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 346-BAPTIST
CTSU Pre-Award - 347-HIGGINS | IRB Application Submitted | Role | CTSU Coordinator |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 348-CHEY | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Intake Form Completed | Role | CTSU Coordinator |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Sponsor Reach out | Role | CTSU Coordinator |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | UFA Completed | Role | CTSU Coordinator |  |  |  | N | 348-CHEY
CTSU Pre-Award - 350-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00133054
CTSU Pre-Award - 350-HIGGINS | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00133054
CTSU Pre-Award - 351-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00134870
CTSU Pre-Award - 351-HIGGINS | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00134870
CTSU Pre-Award - 354-PAGANI | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 363-PARK | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 363-PARK
CTSU Pre-Award - 375-JAMERSON | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 375-JAMERSON
CTSU Pre-Award v2 - 00132705 2 | Sponsor Reach out | Role | CTSU Coordinator |  |  |  | N | 00132705
CTSU Pre-Award v2 - 00134459 | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00134459
CTSU Pre-Award v2 - 00134459 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00134459
CTSU Pre-Award v2 - 140-CHUNG | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00133613
CTSU Pre-Award v2 - 140-CHUNG | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00133613
CTSU Pre-Award v2 - 325-AUCHUS | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00131840
CTSU Pre-Award v2 - 325-AUCHUS | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00131840
CTSU Pre-Award v2 - 364-KHAJA | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 364-KHAJA
CTSU Pre-Award v2 - 364-KHAJA | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 364-KHAJA
CTSU Pre-Award v2 - 37-SILVER | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 37-SILVER
CTSU Pre-Award v2 - 37-SILVER | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 37-SILVER
CTSU Pre-Award v2 - 390-DAY | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 390-DAY
CTSU Pre-Award v2 - 390-DAY | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 390-DAY
CTSU Pre-Award v2 - 397-HODISH | IRB Application Submitted | Role | CTSU Coordinator |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 403-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00134895
CTSU Pre-Award v2 - 403-HIGGINS | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00134895
CTSU Pre-Award v2 - 404-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00134896
CTSU Pre-Award v2 - 404-HIGGINS | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00134896
CTSU Pre-Award v2 - 409-NASR | Intake Form Completed | Role | CTSU Coordinator |  |  | NA | Y | 409-NASR
CTSU Pre-Award v2 - 409-NASR | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 409-NASR
CTSU Pre-Award v2 - 409-NASR | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 409-NASR
CTSU Pre-Award v2 - 410-PAULUS | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 410-PAULUS
CTSU Pre-Award v2 - 412-NASR | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 415-ROMANO | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 415-ROMANO
CTSU Pre-Award v2 - 415-ROMANO | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 415-ROMANO
CTSU Pre-Award v2 - 419-PIPE 2 | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00130583
CTSU Pre-Award v2 - 427-KOSCHMANN | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | Sponsor Reach out | Role | CTSU Coordinator |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | UFA Completed | Role | CTSU Coordinator |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 428-LAW | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00135072
CTSU Pre-Award v2 - 428-LAW | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00135072
CTSU Pre-Award v2 - 435-MOROI | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 435-MOROI
CTSU Pre-Award v2 - 447-RAO | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 447-RAO
CTSU Pre-Award v2 - 447-RAO | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 447-RAO
CTSU Pre-Award v2 - 8-AARONSON | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | Intake Form Completed | Role | CTSU Coordinator |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | Sponsor Reach out | Role | CTSU Coordinator |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | UFA Completed | Role | CTSU Coordinator |  |  |  | N | 00132110
Core Sponsor Documents for Study Feasibility & Start Up - General - 2 | Informed Consent | Role | CTSU Coordinator |  |  |  | N | 00127913
Core Sponsor Documents for Study Feasibility & Start Up - General - 2 | Initial contact with sponsor | Role | CTSU Coordinator |  |  |  | N | 00127913
Core Sponsor Documents for Study Feasibility & Start Up - General - 2 | Investigational Drug Brochure / Investigator's Brochure | Role | CTSU Coordinator |  |  |  | N | 00127913
Core Sponsor Documents for Study Feasibility & Start Up - General - 2 | Protocol (and any approved Amendments) | Role | CTSU Coordinator |  |  |  | N | 00127913
Core Sponsor Documents for Study Feasibility & Start Up - General - 2 | Sponsor Budget | Role | CTSU Coordinator |  |  |  | N | 00127913
Core Sponsor Documents for Study Feasibility & Start Up - General - 2 | Sponsor Contract | Role | CTSU Coordinator |  |  |  | N | 00127913
Core Sponsor Documents for Study Feasibility & Start Up - General - 2 | U-M Planning Questionnaire | Role | CTSU Coordinator |  |  |  | N | 00127913
Core Sponsor Documents for Study Feasibility & Start Up - General - 00123635 | Informed Consent | Role | CTSU Coordinator |  |  | 2017-01-13 | N | 00123635
Core Sponsor Documents for Study Feasibility & Start Up - General - 00123635 | Initial contact with sponsor | Role | CTSU Coordinator |  |  |  | N | 00123635
Core Sponsor Documents for Study Feasibility & Start Up - General - 00123635 | Investigational Drug Brochure / Investigator's Brochure | Role | CTSU Coordinator |  |  |  | N | 00123635
Core Sponsor Documents for Study Feasibility & Start Up - General - 00123635 | Protocol (and any approved Amendments) | Role | CTSU Coordinator |  |  | 2017-01-13 | N | 00123635
Core Sponsor Documents for Study Feasibility & Start Up - General - 00123635 | Sponsor Budget | Role | CTSU Coordinator |  |  |  | N | 00123635
Core Sponsor Documents for Study Feasibility & Start Up - General - 00123635 | Sponsor Contract | Role | CTSU Coordinator |  |  |  | N | 00123635
Core Sponsor Documents for Study Feasibility & Start Up - General - 00123635 | U-M Planning Questionnaire | Role | CTSU Coordinator |  |  |  | N | 00123635
Core Sponsor Documents for Study Feasibility & Start Up - General - 00126224 | Informed Consent | Role | CTSU Coordinator |  |  |  | N | 00126224
Core Sponsor Documents for Study Feasibility & Start Up - General - 00126224 | Initial contact with sponsor | Role | CTSU Coordinator |  |  |  | N | 00126224
Core Sponsor Documents for Study Feasibility & Start Up - General - 00126224 | Investigational Drug Brochure / Investigator's Brochure | Role | CTSU Coordinator |  |  |  | N | 00126224
Core Sponsor Documents for Study Feasibility & Start Up - General - 00126224 | Protocol (and any approved Amendments) | Role | CTSU Coordinator |  |  |  | N | 00126224
Core Sponsor Documents for Study Feasibility & Start Up - General - 00126224 | Sponsor Budget | Role | CTSU Coordinator |  |  |  | N | 00126224
Core Sponsor Documents for Study Feasibility & Start Up - General - 00126224 | Sponsor Contract | Role | CTSU Coordinator |  |  |  | N | 00126224
Core Sponsor Documents for Study Feasibility & Start Up - General - 00126224 | U-M Planning Questionnaire | Role | CTSU Coordinator |  |  |  | N | 00126224
Core Sponsor Documents for Study Feasibility & Start Up - General - 192-ALAM | U-M Planning Questionnaire | Role | CTSU Coordinator |  |  | NA | Y | 192-ALAM
Core Sponsor Documents for Study Feasibility & Start Up - General - 238-GUNNERSON | Informed Consent | Role | CTSU Coordinator |  |  |  | N | 238-GUNNERSON
Core Sponsor Documents for Study Feasibility & Start Up - General - 238-GUNNERSON | Initial contact with sponsor | Role | CTSU Coordinator |  |  |  | N | 238-GUNNERSON
Core Sponsor Documents for Study Feasibility & Start Up - General - 238-GUNNERSON | Investigational Drug Brochure / Investigator's Brochure | Role | CTSU Coordinator |  |  |  | N | 238-GUNNERSON
Core Sponsor Documents for Study Feasibility & Start Up - General - 238-GUNNERSON | Protocol (and any approved Amendments) | Role | CTSU Coordinator |  |  |  | N | 238-GUNNERSON
Core Sponsor Documents for Study Feasibility & Start Up - General - 238-GUNNERSON | Sponsor Budget | Role | CTSU Coordinator |  |  |  | N | 238-GUNNERSON
Core Sponsor Documents for Study Feasibility & Start Up - General - 238-GUNNERSON | Sponsor Contract | Role | CTSU Coordinator |  |  |  | N | 238-GUNNERSON
Core Sponsor Documents for Study Feasibility & Start Up - General - 238-GUNNERSON | U-M Planning Questionnaire | Role | CTSU Coordinator |  |  |  | N | 238-GUNNERSON
Core Sponsor Documents for Study Feasibility & Start Up - General - 239-KORLEY | Informed Consent | Role | CTSU Coordinator |  |  | NA | Y | 00129045
Core Sponsor Documents for Study Feasibility & Start Up - General - 239-KORLEY | Initial contact with sponsor | Role | CTSU Coordinator |  |  | NA | Y | 00129045
Core Sponsor Documents for Study Feasibility & Start Up - General - 239-KORLEY | Investigational Drug Brochure / Investigator's Brochure | Role | CTSU Coordinator |  |  | NA | Y | 00129045
Core Sponsor Documents for Study Feasibility & Start Up - General - 239-KORLEY | Protocol (and any approved Amendments) | Role | CTSU Coordinator |  |  | NA | Y | 00129045
Core Sponsor Documents for Study Feasibility & Start Up - General - 239-KORLEY | Sponsor Budget | Role | CTSU Coordinator |  |  | NA | Y | 00129045
Core Sponsor Documents for Study Feasibility & Start Up - General - 239-KORLEY | Sponsor Contract | Role | CTSU Coordinator |  |  | NA | Y | 00129045
Core Sponsor Documents for Study Feasibility & Start Up - General - 239-KORLEY | U-M Planning Questionnaire | Role | CTSU Coordinator |  |  | NA | Y | 00129045
Core Sponsor Documents for Study Feasibility & Start Up - General - 73-ALAM 2 | Informed Consent | Role | CTSU Coordinator |  |  |  | N | 73-ALAM
Core Sponsor Documents for Study Feasibility & Start Up - General - 73-ALAM 2 | Investigational Drug Brochure / Investigator's Brochure | Role | CTSU Coordinator |  |  |  | N | 73-ALAM
Core Sponsor Documents for Study Feasibility & Start Up - General - 73-ALAM 2 | Protocol (and any approved Amendments) | Role | CTSU Coordinator |  |  |  | N | 73-ALAM
Core Sponsor Documents for Study Feasibility & Start Up - General - 73-ALAM 2 | Sponsor Budget | Role | CTSU Coordinator |  |  |  | N | 73-ALAM
Core Sponsor Documents for Study Feasibility & Start Up - General - 73-ALAM 2 | Sponsor Contract | Role | CTSU Coordinator |  |  |  | N | 73-ALAM
Core Sponsor Documents for Study Feasibility & Start Up - General - 73-ALAM 2 | U-M Planning Questionnaire | Role | CTSU Coordinator |  |  |  | N | 73-ALAM
Open to Accrual - 00117851 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00117851
Open to Accrual - 00117851 | Contract Executed | Role | CTSU Coordinator |  |  |  | N | 00117851
Open to Accrual - 00117851 | FDA Approval | Role | CTSU Coordinator |  |  | 2017-06-12 | N | 00117851
Open to Accrual - 00117851 | IRB Approval | Role | CTSU Coordinator |  |  | 2017-06-12 | N | 00117851
Open to Accrual - 00117851 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00117851
Open to Accrual - 00117851 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-06-12 | N | 00117851
Open to Accrual - 00117851 | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  |  | N | 00117851
Open to Accrual - 00117851 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-06-12 | N | 00117851
Open to Accrual - 00117851 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  |  | N | 00117851
Open to Accrual - 00117851 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-06-12 | N | 00117851
Open to Accrual - 00117851 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-06-12 | N | 00117851
Open to Accrual - 00118070 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00118070
Open to Accrual - 00120187 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-08-21 | N | 00120187
Open to Accrual - 00120187 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00120187
Open to Accrual - 00120187 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-08-21 | N | 00120187
Open to Accrual - 00120187 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-08-21 | N | 00120187
Open to Accrual - 00120187 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-08-21 | N | 00120187
Open to Accrual - 00120187 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-04-28 | N | 00120187
Open to Accrual - 00120187 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-08-21 | N | 00120187
Open to Accrual - 00120187 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-08-21 | N | 00120187
Open to Accrual - 00120189 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-06-20 | N | 00120189
Open to Accrual - 00120189 | Contract Executed | Role | CTSU Coordinator |  |  | 2017-06-15 | N | 00120189
Open to Accrual - 00120189 | FDA Approval | Role | CTSU Coordinator |  |  |  | N | 00120189
Open to Accrual - 00120189 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-06-20 | N | 00120189
Open to Accrual - 00120189 | MiChart Verifications | Role | CTSU Coordinator |  |  | 2017-06-22 | N | 00120189
Open to Accrual - 00120189 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-06-20 | N | 00120189
Open to Accrual - 00120189 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-06-20 | N | 00120189
Open to Accrual - 00120189 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-05-19 | N | 00120189
Open to Accrual - 00120189 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-06-20 | N | 00120189
Open to Accrual - 00120189 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-06-20 | N | 00120189
Open to Accrual - 00120231 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-07-11 | N | 00120231
Open to Accrual - 00120231 | FDA Approval | Role | CTSU Coordinator |  |  | 2017-07-11 | N | 00120231
Open to Accrual - 00120231 | IRB Approval | Role | CTSU Coordinator |  |  | 2017-07-11 | N | 00120231
Open to Accrual - 00120231 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-07-11 | N | 00120231
Open to Accrual - 00120231 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-07-11 | N | 00120231
Open to Accrual - 00120231 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-07-11 | N | 00120231
Open to Accrual - 00120231 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-07-11 | N | 00120231
Open to Accrual - 00120231 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-07-11 | N | 00120231
Open to Accrual - 00120231 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-07-11 | N | 00120231
Open to Accrual - 00120349 | FDA Approval | Role | CTSU Coordinator |  |  |  | N | 00120349
Open to Accrual - 00121967 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00121967
Open to Accrual - 00121967 | IRB Approval | Role | CTSU Coordinator |  |  | 2016-12-08 | N | 00121967
Open to Accrual - 00122152 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122152
Open to Accrual - 00122152 | Contract Executed | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122152
Open to Accrual - 00122152 | FDA Approval | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122152
Open to Accrual - 00122152 | IRB Approval | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122152
Open to Accrual - 00122152 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122152
Open to Accrual - 00122152 | MiChart Verifications | Role | CTSU Coordinator |  |  | 2017-05-03 | N | 00122152
Open to Accrual - 00122152 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122152
Open to Accrual - 00122152 | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122152
Open to Accrual - 00122152 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122152
Open to Accrual - 00122152 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122152
Open to Accrual - 00122152 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122152
Open to Accrual - 00122152 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122152
Open to Accrual - 00122153 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122153
Open to Accrual - 00122153 | FDA Approval | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122153
Open to Accrual - 00122153 | IRB Approval | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122153
Open to Accrual - 00122153 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122153
Open to Accrual - 00122153 | MiChart Verifications | Role | CTSU Coordinator |  |  | 2017-06-08 | N | 00122153
Open to Accrual - 00122153 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122153
Open to Accrual - 00122153 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122153
Open to Accrual - 00122153 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122153
Open to Accrual - 00122153 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-04-21 | N | 00122153
Open to Accrual - 00122489 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00122489
Open to Accrual - 00122815 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-05-02 | N | 00122815
Open to Accrual - 00122815 | FDA Approval | Role | CTSU Coordinator |  |  | 2017-05-02 | N | 00122815
Open to Accrual - 00122815 | IRB Approval | Role | CTSU Coordinator |  |  | 2017-05-02 | N | 00122815
Open to Accrual - 00122815 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-05-02 | N | 00122815
Open to Accrual - 00122815 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-05-02 | N | 00122815
Open to Accrual - 00122815 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-05-02 | N | 00122815
Open to Accrual - 00122815 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-05-02 | N | 00122815
Open to Accrual - 00122815 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-05-02 | N | 00122815
Open to Accrual - 00122815 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-05-02 | N | 00122815
Open to Accrual - 00123069 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-07-31 | N | 00123069
Open to Accrual - 00123069 | FDA Approval | Role | CTSU Coordinator |  |  | 2017-07-31 | N | 00123069
Open to Accrual - 00123069 | IRB Approval | Role | CTSU Coordinator |  |  | 2017-07-31 | N | 00123069
Open to Accrual - 00123069 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00123069
Open to Accrual - 00123069 | Other Personnel Notified | Role | CTSU Coordinator |  |  |  | N | 00123069
Open to Accrual - 00123069 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-07-31 | N | 00123069
Open to Accrual - 00123069 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  |  | N | 00123069
Open to Accrual - 00123069 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-07-31 | N | 00123069
Open to Accrual - 00123069 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-07-31 | N | 00123069
Open to Accrual - 00123632 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00123632
Open to Accrual - 00123632 | FDA Approval | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00123632
Open to Accrual - 00123632 | IRB Approval | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00123632
Open to Accrual - 00123632 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00123632
Open to Accrual - 00123632 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00123632
Open to Accrual - 00123632 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00123632
Open to Accrual - 00123632 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00123632
Open to Accrual - 00123632 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00123632
Open to Accrual - 00123632 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00123632
Open to Accrual - 00123861 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-05-18 | N | 00123861
Open to Accrual - 00123861 | Contract Executed | Role | CTSU Coordinator |  |  | 2017-03-30 | N | 00123861
Open to Accrual - 00123861 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00123861
Open to Accrual - 00123861 | IRB Approval | Role | CTSU Coordinator |  |  | 2017-03-23 | N | 00123861
Open to Accrual - 00123861 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-05-18 | N | 00123861
Open to Accrual - 00123861 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-05-18 | N | 00123861
Open to Accrual - 00123861 | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  | 2017-04-07 | N | 00123861
Open to Accrual - 00123861 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-05-18 | N | 00123861
Open to Accrual - 00123861 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-05-18 | N | 00123861
Open to Accrual - 00123861 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-05-18 | N | 00123861
Open to Accrual - 00123861 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-05-18 | N | 00123861
Open to Accrual - 00124839 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00124839
Open to Accrual - 00124839 | Contract Executed | Role | CTSU Coordinator |  |  | 2017-06-02 | N | 00124839
Open to Accrual - 00124839 | FDA Approval | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00124839
Open to Accrual - 00124839 | IRB Approval | Role | CTSU Coordinator |  |  | 2017-05-02 | N | 00124839
Open to Accrual - 00124839 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00124839
Open to Accrual - 00124839 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00124839
Open to Accrual - 00124839 | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  | 2017-06-02 | N | 00124839
Open to Accrual - 00124839 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00124839
Open to Accrual - 00124839 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00124839
Open to Accrual - 00124839 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-05-22 | N | 00124839
Open to Accrual - 00125425 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-07-10 | N | 00125425
Open to Accrual - 00125425 | Contract Executed | Role | CTSU Coordinator |  |  | 2017-06-01 | N | 00125425
Open to Accrual - 00125425 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00125425
Open to Accrual - 00125425 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-07-11 | N | 00125425
Open to Accrual - 00125425 | MiChart Verifications | Role | CTSU Coordinator |  |  | 2017-06-22 | N | 00125425
Open to Accrual - 00125425 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-07-10 | N | 00125425
Open to Accrual - 00125425 | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  | 2017-06-13 | N | 00125425
Open to Accrual - 00125425 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-07-10 | N | 00125425
Open to Accrual - 00125425 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-07-10 | N | 00125425
Open to Accrual - 00125425 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-07-10 | N | 00125425
Open to Accrual - 00125566 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-07-28 | N | 00125566
Open to Accrual - 00125566 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00125566
Open to Accrual - 00125566 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-07-28 | N | 00125566
Open to Accrual - 00125566 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-07-28 | N | 00125566
Open to Accrual - 00125566 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-07-28 | N | 00125566
Open to Accrual - 00125566 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-07-28 | N | 00125566
Open to Accrual - 00125566 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-07-28 | N | 00125566
Open to Accrual - 00125566 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-07-28 | N | 00125566
Open to Accrual - 00125786 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-07-07 | N | 00125786
Open to Accrual - 00125786 | Contract Executed | Role | CTSU Coordinator |  |  | 2017-06-22 | N | 00125786
Open to Accrual - 00125786 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00125786
Open to Accrual - 00125786 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-07-07 | N | 00125786
Open to Accrual - 00125786 | MiChart Verifications | Role | CTSU Coordinator |  |  | 2017-07-09 | N | 00125786
Open to Accrual - 00125786 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-07-07 | N | 00125786
Open to Accrual - 00125786 | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  | 2017-07-06 | N | 00125786
Open to Accrual - 00125786 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-07-07 | N | 00125786
Open to Accrual - 00125786 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-07-07 | N | 00125786
Open to Accrual - 00125786 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-07-07 | N | 00125786
Open to Accrual - 00125786 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-07-07 | N | 00125786
Open to Accrual - 00125794 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-06-26 | N | 00125794
Open to Accrual - 00125794 | Contract Executed | Role | CTSU Coordinator |  |  | 2017-06-14 | N | 00125794
Open to Accrual - 00125794 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00125794
Open to Accrual - 00125794 | IRB Approval | Role | CTSU Coordinator |  |  | 2017-06-08 | N | 00125794
Open to Accrual - 00125794 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-06-26 | N | 00125794
Open to Accrual - 00125794 | MiChart Verifications | Role | CTSU Coordinator |  |  | 2017-06-23 | N | 00125794
Open to Accrual - 00125794 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-06-26 | N | 00125794
Open to Accrual - 00125794 | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  |  | N | 00125794
Open to Accrual - 00125794 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-06-26 | N | 00125794
Open to Accrual - 00125794 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-06-26 | N | 00125794
Open to Accrual - 00125794 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-06-26 | N | 00125794
Open to Accrual - 00125794 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-06-26 | N | 00125794
Open to Accrual - 00125798 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00125798
Open to Accrual - 00125798 | FDA Approval | Role | CTSU Coordinator |  |  |  | N | 00125798
Open to Accrual - 00125798 | IRB Approval | Role | CTSU Coordinator |  |  |  | N | 00125798
Open to Accrual - 00125798 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00125798
Open to Accrual - 00125798 | Other Personnel Notified | Role | CTSU Coordinator |  |  |  | N | 00125798
Open to Accrual - 00125798 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  |  | N | 00125798
Open to Accrual - 00125798 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  |  | N | 00125798
Open to Accrual - 00125798 | Study Files Established | Role | CTSU Coordinator |  |  |  | N | 00125798
Open to Accrual - 00125798 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  |  | N | 00125798
Open to Accrual - 00126010 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00126010
Open to Accrual - 00126010 | Contract Executed | Role | CTSU Coordinator |  |  | 2017-07-19 | N | 00126010
Open to Accrual - 00126010 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00126010
Open to Accrual - 00126010 | IRB Approval | Role | CTSU Coordinator |  |  | 2017-08-09 | N | 00126010
Open to Accrual - 00126010 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00126010
Open to Accrual - 00126010 | MiChart Verifications | Role | CTSU Coordinator |  |  |  | N | 00126010
Open to Accrual - 00126010 | Other Personnel Notified | Role | CTSU Coordinator |  |  |  | N | 00126010
Open to Accrual - 00126010 | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  |  | N | 00126010
Open to Accrual - 00126010 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  |  | N | 00126010
Open to Accrual - 00126010 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  |  | N | 00126010
Open to Accrual - 00126010 | Study Files Established | Role | CTSU Coordinator |  |  |  | N | 00126010
Open to Accrual - 00126010 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  |  | N | 00126010
Open to Accrual - 00127496 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00127496
Open to Accrual - 00127496 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00127496
Open to Accrual - 00127496 | IRB Approval | Role | CTSU Coordinator |  |  |  | N | 00127496
Open to Accrual - 00127496 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00127496
Open to Accrual - 00127496 | MiChart Verifications | Role | CTSU Coordinator |  |  |  | N | 00127496
Open to Accrual - 00127496 | Other Personnel Notified | Role | CTSU Coordinator |  |  |  | N | 00127496
Open to Accrual - 00127496 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  |  | N | 00127496
Open to Accrual - 00127496 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  |  | N | 00127496
Open to Accrual - 00127496 | Study Files Established | Role | CTSU Coordinator |  |  |  | N | 00127496
Open to Accrual - 00127496 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  |  | N | 00127496
Open to Accrual - 00127537 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-06-26 | N | 00127537
Open to Accrual - 00127537 | Contract Executed | Role | CTSU Coordinator |  |  | 2017-06-13 | N | 00127537
Open to Accrual - 00127537 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00127537
Open to Accrual - 00127537 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-06-26 | N | 00127537
Open to Accrual - 00127537 | MiChart Verifications | Role | CTSU Coordinator |  |  | 2017-06-23 | N | 00127537
Open to Accrual - 00127537 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-06-26 | N | 00127537
Open to Accrual - 00127537 | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  | 2017-06-13 | N | 00127537
Open to Accrual - 00127537 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-06-26 | N | 00127537
Open to Accrual - 00127537 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-06-26 | N | 00127537
Open to Accrual - 00127537 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-06-26 | N | 00127537
Open to Accrual - 00127537 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-06-26 | N | 00127537
Open to Accrual - 00127891 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-08-14 | N | 00127891
Open to Accrual - 00127891 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00127891
Open to Accrual - 00127891 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-08-14 | N | 00127891
Open to Accrual - 00127891 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-08-14 | N | 00127891
Open to Accrual - 00127891 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-08-14 | N | 00127891
Open to Accrual - 00127891 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-04-28 | N | 00127891
Open to Accrual - 00127891 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-08-14 | N | 00127891
Open to Accrual - 00127891 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-08-14 | N | 00127891
Open to Accrual - 00128061 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00128061
Open to Accrual - 00128061 | Contract Executed | Role | CTSU Coordinator |  |  | 2017-05-24 | N | 00128061
Open to Accrual - 00128061 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00128061
Open to Accrual - 00128061 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00128061
Open to Accrual - 00128061 | MiChart Verifications | Role | CTSU Coordinator |  |  |  | N | 00128061
Open to Accrual - 00128061 | Other Personnel Notified | Role | CTSU Coordinator |  |  |  | N | 00128061
Open to Accrual - 00128061 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  |  | N | 00128061
Open to Accrual - 00128061 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  |  | N | 00128061
Open to Accrual - 00128061 | Study Files Established | Role | CTSU Coordinator |  |  |  | N | 00128061
Open to Accrual - 00128061 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  |  | N | 00128061
Open to Accrual - 00128253 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-07-05 | N | 00128253
Open to Accrual - 00128253 | FDA Approval | Role | CTSU Coordinator |  |  | 2017-07-05 | N | 00128253
Open to Accrual - 00128253 | IRB Approval | Role | CTSU Coordinator |  |  | 2017-07-05 | N | 00128253
Open to Accrual - 00128253 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-07-05 | N | 00128253
Open to Accrual - 00128253 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-07-05 | N | 00128253
Open to Accrual - 00128253 | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  | 2017-07-06 | N | 00128253
Open to Accrual - 00128253 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-07-05 | N | 00128253
Open to Accrual - 00128253 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-07-05 | N | 00128253
Open to Accrual - 00128253 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-07-05 | N | 00128253
Open to Accrual - 00128253 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-07-05 | N | 00128253
Open to Accrual - 00128301 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00128301
Open to Accrual - 00128301 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00128301
Open to Accrual - 00128301 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00128301
Open to Accrual - 00128301 | MiChart Verifications | Role | CTSU Coordinator |  |  |  | N | 00128301
Open to Accrual - 00128301 | Other Personnel Notified | Role | CTSU Coordinator |  |  |  | N | 00128301
Open to Accrual - 00128301 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  |  | N | 00128301
Open to Accrual - 00128301 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  |  | N | 00128301
Open to Accrual - 00128301 | Study Files Established | Role | CTSU Coordinator |  |  |  | N | 00128301
Open to Accrual - 00128301 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  |  | N | 00128301
Open to Accrual - 00128322 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128322
Open to Accrual - 00128322 | FDA Approval | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128322
Open to Accrual - 00128322 | IRB Approval | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128322
Open to Accrual - 00128322 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128322
Open to Accrual - 00128322 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128322
Open to Accrual - 00128322 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128322
Open to Accrual - 00128322 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128322
Open to Accrual - 00128322 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128322
Open to Accrual - 00128322 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128322
Open to Accrual - 00128493 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00128493
Open to Accrual - 00128493 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00128493
Open to Accrual - 00128493 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00128493
Open to Accrual - 00128493 | MiChart Verifications | Role | CTSU Coordinator |  |  |  | N | 00128493
Open to Accrual - 00128493 | Other Personnel Notified | Role | CTSU Coordinator |  |  |  | N | 00128493
Open to Accrual - 00128493 | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  |  | N | 00128493
Open to Accrual - 00128493 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  |  | N | 00128493
Open to Accrual - 00128493 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  |  | N | 00128493
Open to Accrual - 00128493 | Study Files Established | Role | CTSU Coordinator |  |  |  | N | 00128493
Open to Accrual - 00128493 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  |  | N | 00128493
Open to Accrual - 00128761 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128761
Open to Accrual - 00128761 | Contract Executed | Role | CTSU Coordinator |  |  | 2017-08-17 | N | 00128761
Open to Accrual - 00128761 | FDA Approval | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128761
Open to Accrual - 00128761 | IRB Approval | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128761
Open to Accrual - 00128761 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128761
Open to Accrual - 00128761 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128761
Open to Accrual - 00128761 | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  | 2017-08-17 | N | 00128761
Open to Accrual - 00128761 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128761
Open to Accrual - 00128761 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128761
Open to Accrual - 00128761 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128761
Open to Accrual - 00128761 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-08-22 | N | 00128761
Open to Accrual - 00129427 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00129427
Open to Accrual - 00129427 | Contract Executed | Role | CTSU Coordinator |  |  |  | N | 00129427
Open to Accrual - 00129427 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00129427
Open to Accrual - 00129427 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  |  | N | 00129427
Open to Accrual - 00129427 | MiChart Verifications | Role | CTSU Coordinator |  |  |  | N | 00129427
Open to Accrual - 00129427 | Other Personnel Notified | Role | CTSU Coordinator |  |  |  | N | 00129427
Open to Accrual - 00129427 | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  |  | N | 00129427
Open to Accrual - 00129427 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  |  | N | 00129427
Open to Accrual - 00129427 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  |  | N | 00129427
Open to Accrual - 00129427 | Study Files Established | Role | CTSU Coordinator |  |  |  | N | 00129427
Open to Accrual - 00129427 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  |  | N | 00129427
Open to Accrual - 00129709 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00129709
Open to Accrual - 00129820 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00129820
Open to Accrual - 00129851 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-06-06 | N | 00129851
Open to Accrual - 00129851 | Contract Executed | Role | CTSU Coordinator |  |  | 2017-05-31 | N | 00129851
Open to Accrual - 00129851 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00129851
Open to Accrual - 00129851 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-06-06 | N | 00129851
Open to Accrual - 00129851 | MiChart Verifications | Role | CTSU Coordinator |  |  | 2017-06-06 | N | 00129851
Open to Accrual - 00129851 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-06-06 | N | 00129851
Open to Accrual - 00129851 | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  | 2017-06-06 | N | 00129851
Open to Accrual - 00129851 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-06-06 | N | 00129851
Open to Accrual - 00129851 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-06-06 | N | 00129851
Open to Accrual - 00129851 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-06-06 | N | 00129851
Open to Accrual - 00129851 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-06-06 | N | 00129851
Open to Accrual - 00131377 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-07-26 | N | 00131377
Open to Accrual - 00131377 | Contract Executed | Role | CTSU Coordinator |  |  | NA | Y | 00131377
Open to Accrual - 00131377 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00131377
Open to Accrual - 00131377 | IRB Approval | Role | CTSU Coordinator |  |  | 2017-07-12 | N | 00131377
Open to Accrual - 00131377 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-07-26 | N | 00131377
Open to Accrual - 00131377 | MiChart Verifications | Role | CTSU Coordinator |  |  | 2017-07-26 | N | 00131377
Open to Accrual - 00131377 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-07-26 | N | 00131377
Open to Accrual - 00131377 | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  |  | N | 00131377
Open to Accrual - 00131377 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-07-26 | N | 00131377
Open to Accrual - 00131377 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-08-02 | N | 00131377
Open to Accrual - 00131377 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-07-26 | N | 00131377
Open to Accrual - 00131377 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-07-26 | N | 00131377
Open to Accrual - 192-ALAM | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 192-ALAM
Open to Accrual - 239-KORLEY | Contract Executed | Role | CTSU Coordinator |  |  | NA | Y | 00129045
Open to Accrual - 239-KORLEY | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00129045
Open to Accrual - 239-KORLEY | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  | NA | Y | 00129045
Open to Accrual - 239-KORLEY | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | NA | Y | 00129045
Open to Accrual - 268-NEUMAR | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | NA | Y | 268-NEUMAR
Open to Accrual - 314-PARK | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  |  | N | 314-PARK
Open to Accrual - 314-PARK | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 314-PARK
Open to Accrual - 314-PARK | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  |  | N | 314-PARK
Open to Accrual - 314-PARK | MiChart Verifications | Role | CTSU Coordinator |  |  |  | N | 314-PARK
Open to Accrual - 314-PARK | Other Personnel Notified | Role | CTSU Coordinator |  |  |  | N | 314-PARK
Open to Accrual - 314-PARK | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  |  | N | 314-PARK
Open to Accrual - 314-PARK | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  |  | N | 314-PARK
Open to Accrual - 314-PARK | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  |  | N | 314-PARK
Open to Accrual - 363-PARK | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  |  | N | 363-PARK
Open to Accrual - 363-PARK | Contract Executed | Role | CTSU Coordinator |  |  |  | N | 363-PARK
Open to Accrual - 363-PARK | FDA Approval | Role | CTSU Coordinator |  |  |  | N | 363-PARK
Open to Accrual - 363-PARK | IRB Approval | Role | CTSU Coordinator |  |  |  | N | 363-PARK
Open to Accrual - 363-PARK | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  |  | N | 363-PARK
Open to Accrual - 363-PARK | MiChart Verifications | Role | CTSU Coordinator |  |  |  | N | 363-PARK
Open to Accrual - 363-PARK | Other Personnel Notified | Role | CTSU Coordinator |  |  |  | N | 363-PARK
Open to Accrual - 363-PARK | Project Award Notice (PAN) Received | Role | CTSU Coordinator |  |  |  | N | 363-PARK
Open to Accrual - 363-PARK | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  |  | N | 363-PARK
Open to Accrual - 363-PARK | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  |  | N | 363-PARK
Open to Accrual - 363-PARK | Study Files Established | Role | CTSU Coordinator |  |  |  | N | 363-PARK
Open to Accrual - 363-PARK | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  |  | N | 363-PARK
Open to Accrual - HUM00129276 | Adequate Equipment and Supplies Available | Role | CTSU Coordinator |  |  | 2017-08-30 | N | 00129276
Open to Accrual - HUM00129276 | FDA Approval | Role | CTSU Coordinator |  |  | NA | Y | 00129276
Open to Accrual - HUM00129276 | Investigational Drug/Device Supplies Available | Role | CTSU Coordinator |  |  | 2017-08-30 | N | 00129276
Open to Accrual - HUM00129276 | Other Personnel Notified | Role | CTSU Coordinator |  |  | 2017-08-30 | N | 00129276
Open to Accrual - HUM00129276 | Provisions for Support and Services Finalized | Role | CTSU Coordinator |  |  | 2017-08-30 | N | 00129276
Open to Accrual - HUM00129276 | Sponsor/Organizing Group Approval Granted for Initiation of Study | Role | CTSU Coordinator |  |  | 2017-08-15 | N | 00129276
Open to Accrual - HUM00129276 | Study Files Established | Role | CTSU Coordinator |  |  | 2017-08-30 | N | 00129276
Open to Accrual - HUM00129276 | Study Team Roles/Responsibilities Finalized | Role | CTSU Coordinator |  |  | 2017-08-30 | N | 00129276
Pre-Award Financial - 00108880 | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00108880
Pre-Award Financial - 00108880 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00108880
Pre-Award Financial - 00108880 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00108880
Pre-Award Financial - 00121967 2 | PI Signoff in OnCore | Role | CTSU Coordinator |  |  | 2016-12-08 | N | 00121967
Pre-Award Financial - 00122254 | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00122254
Pre-Award Financial - 00122254 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00122254
Pre-Award Financial - 00122254 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00122254
Pre-Award Financial - 00123237 | PI Signoff in OnCore | Role | CTSU Coordinator |  |  | NA | Y | 00123237
Pre-Award Financial - 00123861 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00123861
Pre-Award Financial - 00123861 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00123861
Pre-Award Financial - 00124712 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00124712
Pre-Award Financial - 00124712 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00124712
Pre-Award Financial - 00124920 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00124920
Pre-Award Financial - 00124920 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00124920
Pre-Award Financial - 00125022 | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00125022
Pre-Award Financial - 00125022 | Intake Form Completed | Role | CTSU Coordinator |  |  | NA | Y | 00125022
Pre-Award Financial - 00125022 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00125022
Pre-Award Financial - 00125022 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00125022
Pre-Award Financial - 00125425 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00125425
Pre-Award Financial - 00125425 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00125425
Pre-Award Financial - 00125566 | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  | NA | Y | 00125566
Pre-Award Financial - 00125566 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00125566
Pre-Award Financial - 00125566 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00125566
Pre-Award Financial - 00125786 | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  | NA | Y | 00125786
Pre-Award Financial - 00125786 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00125786
Pre-Award Financial - 00125786 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00125786
Pre-Award Financial - 00125794 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00125794
Pre-Award Financial - 00125794 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00125794
Pre-Award Financial - 00126010 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00126010
Pre-Award Financial - 00126010 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00126010
Pre-Award Financial - 00126215 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00126215
Pre-Award Financial - 00126215 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00126215
Pre-Award Financial - 00126224 | PI Signoff in OnCore | Role | CTSU Coordinator |  |  | NA | Y | 00126224
Pre-Award Financial - 00127136 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00127136
Pre-Award Financial - 00127136 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00127136
Pre-Award Financial - 00127356 | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00127356
Pre-Award Financial - 00127356 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00127356
Pre-Award Financial - 00127356 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00127356
Pre-Award Financial - 00127505 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00127505
Pre-Award Financial - 00127505 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00127505
Pre-Award Financial - 00127537 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00127537
Pre-Award Financial - 00127537 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00127537
Pre-Award Financial - 00127988 | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 00127988
Pre-Award Financial - 00128157 | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00128157
Pre-Award Financial - 00128157 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00128157
Pre-Award Financial - 00128157 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00128157
Pre-Award Financial - 00128173 | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00128173
Pre-Award Financial - 00128173 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00128173
Pre-Award Financial - 00128173 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00128173
Pre-Award Financial - 00128531 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00128531
Pre-Award Financial - 00128531 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00128531
Pre-Award Financial - 00128743 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00128743
Pre-Award Financial - 00128743 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00128743
Pre-Award Financial - 00129427 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00129427
Pre-Award Financial - 00129427 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00129427
Pre-Award Financial - 00129851 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00129851
Pre-Award Financial - 00130575 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00130575
Pre-Award Financial - 00130575 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00130575
Pre-Award Financial - 00130793 | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00130793
Pre-Award Financial - 10-JAYASUNDERA | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 10-JAYASUNDERA
Pre-Award Financial - 10-JAYASUNDERA | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 10-JAYASUNDERA
Pre-Award Financial - 11-HIGGINS | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00134884
Pre-Award Financial - 110-SCHIOPU | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00134444
Pre-Award Financial - 110-SCHIOPU | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00134444
Pre-Award Financial - 111-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 112-FLAHERTY | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 112-FLAHERTY
Pre-Award Financial - 12-HIGGINS | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 12-HIGGINS
Pre-Award Financial - 131-LUGOGO | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 142-FLAHERTY | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 142-FLAHERTY
Pre-Award Financial - 147-SCHIOPU | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00131329
Pre-Award Financial - 147-SCHIOPU | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00131329
Pre-Award Financial - 155-ORAL | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00130803
Pre-Award Financial - 155-ORAL | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  | NA | Y | 00130803
Pre-Award Financial - 155-ORAL | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00130803
Pre-Award Financial - 155-ORAL | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00130803
Pre-Award Financial - 179-LUGOGO | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 179-LUGOGO
Pre-Award Financial - 179-LUGOGO | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 179-LUGOGO
Pre-Award Financial - 180-HOFF | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00129450
Pre-Award Financial - 180-HOFF | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00129450
Pre-Award Financial - 187-MCLAUGHLIN | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 188-RUBENSTEIN | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 188-RUBENSTEIN
Pre-Award Financial - 190-SCHIOPU | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00134443
Pre-Award Financial - 192-ALAM | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 192-ALAM
Pre-Award Financial - 194-MCLAUGHLIN | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 198-LUCKRITZ | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 198-LUCKRITZ
Pre-Award Financial - 2-MARSH | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 2-MARSH
Pre-Award Financial - 201-MCCUNE | IRB Application Submitted | Role | CTSU Coordinator |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 203-ELSE | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00132173
Pre-Award Financial - 205-HIGGINS | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 205-HIGGINS
Pre-Award Financial - 205-KHANNA | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  | NA | Y | 00132200
Pre-Award Financial - 205-KHANNA | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00132200
Pre-Award Financial - 205-KHANNA | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00132200
Pre-Award Financial - 211-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00128325
Pre-Award Financial - 211-HIGGINS | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00128325
Pre-Award Financial - 222-STEIGERWALT | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 23-GUPTA | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00134236
Pre-Award Financial - 23-GUPTA | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00134236
Pre-Award Financial - 234-MCLAUGHLIN | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 235-SUGAR | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 235-SUGAR
Pre-Award Financial - 235-SUGAR | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 235-SUGAR
Pre-Award Financial - 236-NASR | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 00131580
Pre-Award Financial - 238-GUNNERSON | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 241-SILVER | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 00132956
Pre-Award Financial - 242-AS-SANIE | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 242-AS-SANIE
Pre-Award Financial - 246-AS-SANIE | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 246-AS-SANIE
Pre-Award Financial - 251-COMER | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00134232
Pre-Award Financial - 251-COMER | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00134232
Pre-Award Financial - 255-LOK | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 255-LOK
Pre-Award Financial - 258-SHEEHAN | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 261-LUGOGO | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 261-LUGOGO
Pre-Award Financial - 263-DELMONTE | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 263-DELMONTE
Pre-Award Financial - 268-NEUMAR | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 278-CONJEEVARAM | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00133341
Pre-Award Financial - 282-POP-BUSUI | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00133290
Pre-Award Financial - 282-POP-BUSUI | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00133290
Pre-Award Financial - 30-FLAHERTY | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 30-FLAHERTY
Pre-Award Financial - 305-PELOSI | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 305-PELOSI
Pre-Award Financial - 33-FLAHERTY | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00129716
Pre-Award Financial - 33-FLAHERTY | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00129716
Pre-Award Financial - 34-MARSH | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 34-MARSH
Pre-Award Financial - 44-MCUNE | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Intake Form Completed | Role | CTSU Coordinator |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Sponsor Reach out | Role | CTSU Coordinator |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | UFA Completed | Role | CTSU Coordinator |  |  |  | N | 44-MCUNE
Pre-Award Financial - 46-HIGGINS | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 46-HIGGINS
Pre-Award Financial - 46-HIGGINS | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  | NA | Y | 46-HIGGINS
Pre-Award Financial - 46-HIGGINS | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 46-HIGGINS
Pre-Award Financial - 46-HIGGINS | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 46-HIGGINS
Pre-Award Financial - 49-MARTINEZ | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00132020
Pre-Award Financial - 56-RAO | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00133286
Pre-Award Financial - 69-KHANNA | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 69-KHANNA
Pre-Award Financial - 69-KHANNA | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  | NA | Y | 69-KHANNA
Pre-Award Financial - 70-LUGOGO | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 70-LUGOGO
Pre-Award Financial - 70-LUGOGO | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 70-LUGOGO
Pre-Award Financial - 71-RICE | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00134857
Pre-Award Financial - 71-RICE | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00134857
Pre-Award Financial - 71-RICE | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00134857
Pre-Award Financial - 76-KHANNA | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  | NA | Y | 00131837
Pre-Award Financial - 76-KHANNA | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00131837
Pre-Award Financial - 76-KHANNA | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00131837
Pre-Award Financial - 77-CONJEEVARAM | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 77-CONJEEVARAM
Pre-Award Financial - 77-CONJEEVARAM | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 77-CONJEEVARAM
Pre-Award Financial - 77-CONJEEVARAM | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 77-CONJEEVARAM
Pre-Award Financial - 81-HIGGINS | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 81-HIGGINS
Pre-Award Financial - 86-AUCHUS | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00132700
Pre-Award Financial - 9-JAYASUNDERA | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 9-JAYASUNDERA
Pre-Award Financial - 91-ELSE | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 91-ELSE
Pre-Award Financial - 91-ELSE | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 91-ELSE
Pre-Award Financial - 92-AUCHUS | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 92-AUCHUS
Pre-Award Financial - 96-BESIRLI | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00129820
Pre-Award Financial - 96-BESIRLI | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00129820
Pre-Award Financial - FONTANA-3 | Planning Meeting Request Sent | Role | CTSU Coordinator |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | FONTANA-3
Pre-Award Financial - HUM00091711 | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 00091711
Pre-Award Financial - HUM00129276 | PI Signoff in OnCore | Role | CTSU Coordinator |  |  |  | N | 00129276
Pre-Award Financial - PLT-INF24-001 | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | 00135388
Pre-Award Financial - PLT-INF24-001 | Sponsor Reach out | Role | CTSU Coordinator |  |  | NA | Y | 00135388
Pre-Award Financial - PLT-INF24-001 | UFA Completed | Role | CTSU Coordinator |  |  | NA | Y | 00135388
Pre-Award Financial - SCHIOPU-1 | IRB Application Submitted | Role | CTSU Coordinator |  |  |  | N | SCHIOPU-1
Pre-Award Financial - SLS-III | IRB Application Submitted | Role | CTSU Coordinator |  |  | 2017-07-06 | N | 00131953
131463 Spec Update Request(s) - simplify labs & add unscheduled procedures | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00131463
131463 Spec Update Request(s) - simplify labs & add unscheduled procedures | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00131463
131463 Spec Update Request(s) - simplify labs & add unscheduled procedures | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00131463
131463 Spec Update Request(s) - simplify labs & add unscheduled procedures | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00131463
Amendment 00072647 | AME Calendaring Process Initiated | Role | CTSU Finance |  |  | 2017-08-21 | N | 00122489
Amendment 00072647 | Acknowledge | Role | CTSU Finance |  |  |  | N | 00122489
Amendment 00072647 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance |  |  |  | N | 00122489
BC : Initial Build - PLT-INF24-001 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  | NA | Y | 00135388
CTSU Post-Award - 00107755 | Comments | Role | CTSU Finance |  |  |  | N | 00107755
CTSU Post-Award - 00113391 | Comments | Role | CTSU Finance |  |  |  | N | 00113391
CTSU Post-Award - 00119175 | Comments | Role | CTSU Finance |  |  |  | N | 00119175
CTSU Post-Award - 00124920 | Comments | Role | CTSU Finance |  |  |  | N | 00124920
CTSU Post-Award - 00127505 | Comments | Role | CTSU Finance |  |  |  | N | 00127505
CTSU Pre-Award - 309-MOROI | Billing Calendar Received | Role | CTSU Finance |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 309-MOROI | Budget Negotiations | Role | CTSU Finance |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 309-MOROI | Care Designations completed | Role | CTSU Finance |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 309-MOROI | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 309-MOROI | Initiate Post-Award Task List | Role | CTSU Finance |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 309-MOROI | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 309-MOROI | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 309-MOROI | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 314-PARK | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | Calendar Released | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | Care Designations completed | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | Feasibility w/Documents received | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | Final Budget | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | PAF routed | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | PAN Released | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | PI approved Budget | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 314-PARK | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 314-PARK
CTSU Pre-Award - 331-FLAHERTY | Billing Calendar Received | Role | CTSU Finance |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | Budget Negotiations | Role | CTSU Finance |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | Care Designations completed | Role | CTSU Finance |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | Final Budget | Role | CTSU Finance |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | Initiate Post-Award Task List | Role | CTSU Finance |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | Internal Budget Finished | Role | CTSU Finance |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | PAF routed | Role | CTSU Finance |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | PI approved Budget | Role | CTSU Finance |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 337-MIAN | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 337-MIAN
CTSU Pre-Award - 338-MIAN | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00133457
CTSU Pre-Award - 341-STOFFEL | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00134997
CTSU Pre-Award - 342-HUMES | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | Calendar Released | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | Care Designations completed | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | Feasibility w/Documents received | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | Final Budget | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | PAF routed | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | PAN Released | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | PI approved Budget | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 342-HUMES
CTSU Pre-Award - 342-HUMES | Sponsor Reach out | Role | CTSU Finance |  |  | NA | Y | 342-HUMES
CTSU Pre-Award - 342-HUMES | UFA Completed | Role | CTSU Finance |  |  | NA | Y | 342-HUMES
CTSU Pre-Award - 346-BAPTIST | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | Care Designations completed | Role | CTSU Finance |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | Final Budget | Role | CTSU Finance |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | PAF routed | Role | CTSU Finance |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | PI approved Budget | Role | CTSU Finance |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 347-HIGGINS | Billing Calendar Received | Role | CTSU Finance |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | Budget Negotiations | Role | CTSU Finance |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | Care Designations completed | Role | CTSU Finance |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | Final Budget | Role | CTSU Finance |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | Initiate Post-Award Task List | Role | CTSU Finance |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | Internal Budget Finished | Role | CTSU Finance |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | PAF routed | Role | CTSU Finance |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | PI approved Budget | Role | CTSU Finance |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 348-CHEY | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Care Designations completed | Role | CTSU Finance |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Final Budget | Role | CTSU Finance |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | PAF routed | Role | CTSU Finance |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | PI approved Budget | Role | CTSU Finance |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 348-CHEY
CTSU Pre-Award - 350-HIGGINS | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00133054
CTSU Pre-Award - 354-PAGANI | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | Calendar Released | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | Care Designations completed | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | Feasibility w/Documents received | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | Final Budget | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | PAF routed | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | PAN Released | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | PI approved Budget | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 354-PAGANI | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 354-PAGANI
CTSU Pre-Award - 363-PARK | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | Calendar Released | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | Care Designations completed | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | Feasibility w/Documents received | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | Final Budget | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | PAF routed | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | PAN Released | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | PI approved Budget | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 363-PARK | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 363-PARK
CTSU Pre-Award - 375-JAMERSON | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award - 375-JAMERSON | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award - 375-JAMERSON | Calendar Released | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award - 375-JAMERSON | Care Designations completed | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award - 375-JAMERSON | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award - 375-JAMERSON | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award - 375-JAMERSON | Final Budget | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award - 375-JAMERSON | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award - 375-JAMERSON | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award - 375-JAMERSON | PAF routed | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award - 375-JAMERSON | PAN Released | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award - 375-JAMERSON | PI approved Budget | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award - 375-JAMERSON | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award - 375-JAMERSON | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award - 375-JAMERSON | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award - 375-JAMERSON | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 375-JAMERSON
CTSU Pre-Award v2 - 00132705 2 | Initiate Post-Award Task List | Role | CTSU Finance |  |  | NA | Y | 00132705
CTSU Pre-Award v2 - 00132705 2 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00132705
CTSU Pre-Award v2 - 00134459 | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | Calendar Released | Role | CTSU Finance |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | Care Designations completed | Role | CTSU Finance |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | Final Budget | Role | CTSU Finance |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | PAF routed | Role | CTSU Finance |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | PAN Released | Role | CTSU Finance |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | PI approved Budget | Role | CTSU Finance |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 00134459
CTSU Pre-Award v2 - 00134459 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 00134459
CTSU Pre-Award v2 - 325-AUCHUS | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 00131840
CTSU Pre-Award v2 - 325-AUCHUS | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00131840
CTSU Pre-Award v2 - 397-HODISH | Billing Calendar Received | Role | CTSU Finance |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | Budget Negotiations | Role | CTSU Finance |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | Care Designations completed | Role | CTSU Finance |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | Final Budget | Role | CTSU Finance |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | Initiate Post-Award Task List | Role | CTSU Finance |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | Internal Budget Finished | Role | CTSU Finance |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | PAF routed | Role | CTSU Finance |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | PI approved Budget | Role | CTSU Finance |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 412-NASR | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | Calendar Released | Role | CTSU Finance |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | Care Designations completed | Role | CTSU Finance |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | Final Budget | Role | CTSU Finance |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | PAF routed | Role | CTSU Finance |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | PAN Released | Role | CTSU Finance |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | PI approved Budget | Role | CTSU Finance |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 415-ROMANO | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 415-ROMANO
CTSU Pre-Award v2 - 419-PIPE 2 | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | Calendar Released | Role | CTSU Finance |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | Care Designations completed | Role | CTSU Finance |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | Final Budget | Role | CTSU Finance |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | PAF routed | Role | CTSU Finance |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | PAN Released | Role | CTSU Finance |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | PI approved Budget | Role | CTSU Finance |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 00130583
CTSU Pre-Award v2 - 419-PIPE 2 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 00130583
CTSU Pre-Award v2 - 427-KOSCHMANN | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | Calendar Released | Role | CTSU Finance |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | Care Designations completed | Role | CTSU Finance |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | Final Budget | Role | CTSU Finance |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | PAF routed | Role | CTSU Finance |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | PAN Released | Role | CTSU Finance |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | PI approved Budget | Role | CTSU Finance |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 427-KOSCHMANN | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 427-KOSCHMANN
CTSU Pre-Award v2 - 435-MOROI | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 435-MOROI
CTSU Pre-Award v2 - 435-MOROI | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 435-MOROI
CTSU Pre-Award v2 - 8-AARONSON | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | Calendar Released | Role | CTSU Finance |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | Care Designations completed | Role | CTSU Finance |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | Final Budget | Role | CTSU Finance |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | PAF routed | Role | CTSU Finance |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | PAN Released | Role | CTSU Finance |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | PI approved Budget | Role | CTSU Finance |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 00132110
CTSU Pre-Award v2 - 8-AARONSON | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 00132110
Calendar & Budget Retrofit - 00067625 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00067625
Calendar & Budget Retrofit - 00067625 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance |  |  | NA | Y | 00067625
Calendar & Budget Retrofit - 00067625 | Review & Release Calendar | Role | CTSU Finance |  |  | NA | Y | 00067625
Calendar & Budget Retrofit - 00088652 | Questions | Role | CTSU Finance |  |  | NA | Y | 00088652
Calendar & Budget Retrofit - 00089489 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00089489
Calendar & Budget Retrofit - 00089489 | Questions | Role | CTSU Finance |  |  | NA | Y | 00089489
Calendar & Budget Retrofit - 00089730 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00089730
Calendar & Budget Retrofit - 00089730 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance |  |  | NA | Y | 00089730
Calendar & Budget Retrofit - 00089730 | Questions | Role | CTSU Finance |  |  | NA | Y | 00089730
Calendar & Budget Retrofit - 00089730 | Review & Release Calendar | Role | CTSU Finance |  |  | NA | Y | 00089730
Calendar & Budget Retrofit - 00091711 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00091711
Calendar & Budget Retrofit - 00091711 | Questions | Role | CTSU Finance |  |  | NA | Y | 00091711
Calendar & Budget Retrofit - 00091711 | Review & Release Calendar | Role | CTSU Finance |  |  | NA | Y | 00091711
Calendar & Budget Retrofit - 00098540 | Questions | Role | CTSU Finance |  |  | NA | Y | 00098540
Calendar & Budget Retrofit - 00111295 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00111295
Calendar & Budget Retrofit - 00111295 | Questions | Role | CTSU Finance |  |  | NA | Y | 00111295
Calendar & Budget Retrofit - 00113535 | Questions | Role | CTSU Finance |  |  | NA | Y | 00113535
Calendar & Budget Retrofit - 00120231 | Questions | Role | CTSU Finance |  |  | NA | Y | 00120231
Calendar & Budget Retrofit - 00121246 | Questions | Role | CTSU Finance |  |  | NA | Y | 00121246
Calendar & Budget Retrofit - 00125306 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00125306
Calendar & Budget Retrofit - 00125306 | Questions | Role | CTSU Finance |  |  |  | N | 00125306
Calendar & Budget Retrofit - 00125798 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00125798
Calendar & Budget Retrofit - 00125836 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00125836
Calendar & Budget Retrofit - 00125836 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance |  |  | NA | Y | 00125836
Calendar & Budget Retrofit - 00125836 | Questions | Role | CTSU Finance |  |  | NA | Y | 00125836
Calendar & Budget Retrofit - 00125836 | Review & Release Calendar | Role | CTSU Finance |  |  | NA | Y | 00125836
Calendar & Budget Retrofit - 00126224 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00126224
Calendar & Budget Retrofit - 00126224 | Questions | Role | CTSU Finance |  |  | NA | Y | 00126224
Calendar & Budget Retrofit - 00126224 | Review & Release Calendar | Role | CTSU Finance |  |  | NA | Y | 00126224
Calendar & Budget Retrofit - 00127988 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00127988
Calendar & Budget Retrofit - 00127988 | Questions | Role | CTSU Finance |  |  | NA | Y | 00127988
Calendar & Budget Retrofit - 00127988 | Review & Release Calendar | Role | CTSU Finance |  |  | NA | Y | 00127988
Calendar & Budget Retrofit - 00128322 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00128322
Calendar & Budget Retrofit - 00128761 2 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00128761
Calendar & Budget Retrofit - 00128761 2 | Notify Niyati Updated Calendar was Released | Role | CTSU Finance |  |  | NA | Y | 00128761
Calendar & Budget Retrofit - 00128761 2 | Questions | Role | CTSU Finance |  |  | NA | Y | 00128761
Calendar & Budget Retrofit - 00129162 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00129162
Calendar & Budget Retrofit - 00129583 | Questions | Role | CTSU Finance |  |  | NA | Y | 00129583
Calendar & Budget Retrofit - 00129583 | Received calendar from Niyati | Role | CTSU Finance |  |  | NA | Y | 00129583
Calendar & Budget Retrofit - 00129863 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00129863
Calendar & Budget Retrofit - 00129863 | Questions | Role | CTSU Finance |  |  | NA | Y | 00129863
Calendar & Budget Retrofit - 00129863 | Review & Release Calendar | Role | CTSU Finance |  |  | NA | Y | 00129863
Calendar & Budget Retrofit - 00129943 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00129943
Calendar & Budget Retrofit - 00129943 | Questions | Role | CTSU Finance |  |  | NA | Y | 00129943
Calendar & Budget Retrofit - 00129943 | Review & Release Calendar | Role | CTSU Finance |  |  | NA | Y | 00129943
Calendar & Budget Retrofit - 00130272 | Questions | Role | CTSU Finance |  |  | NA | Y | 00130272
Calendar & Budget Retrofit - 00131320 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00131320
Calendar & Budget Retrofit - 00131320 | Questions | Role | CTSU Finance |  |  | NA | Y | 00131320
Calendar & Budget Retrofit - 00131320 | Review & Release Calendar | Role | CTSU Finance |  |  | NA | Y | 00131320
Calendar & Budget Retrofit - 00131580 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00131580
Calendar & Budget Retrofit - 00131580 | Questions | Role | CTSU Finance |  |  | NA | Y | 00131580
Calendar & Budget Retrofit - 00131580 | Review & Release Calendar | Role | CTSU Finance |  |  | NA | Y | 00131580
Calendar & Budget Retrofit - 00133542 | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 00133542
Calendar & Budget Retrofit - 00133542 | Questions | Role | CTSU Finance |  |  | NA | Y | 00133542
Calendar & Budget Retrofit - 00133542 | Review & Release Calendar | Role | CTSU Finance |  |  | NA | Y | 00133542
Calendar & Budget Retrofit - 116-BRUMMETT | Questions | Role | CTSU Finance |  |  | NA | Y | 00129418
Calendar & Budget Retrofit - 175-ORAL | Initiate Updates | Role | CTSU Finance |  |  | NA | Y | 175-ORAL
Calendar & Budget Retrofit - 175-ORAL | Notify Niyati Updated Calendar was Released | Role | CTSU Finance |  |  | NA | Y | 175-ORAL
Calendar & Budget Retrofit - 175-ORAL | Review & Release Calendar | Role | CTSU Finance |  |  | NA | Y | 175-ORAL
Calendar & Budget Retrofit - 6-TAYLOR | Questions | Role | CTSU Finance |  |  | NA | Y | 00132251
Calendar Build - 00124859 | * N/A for MANUAL ENTRY STUDIES W. FULL MBECT BC * // Care Designations +/- finance / study-team feedback submitted to CRAO for OnCore entry | Role | CTSU Finance |  |  | NA | Y | 00124859
Calendar Build - 50-HUMMEL | Calendar Completed and Ready for CTSU Finance to Build Budget | Role | CTSU Finance |  |  | NA | Y | 00129162
Calendar Build - 50-HUMMEL | Care Designations +/- finance / study-team feedback submitted to CRAO for OnCore entry | Role | CTSU Finance |  |  | NA | Y | 00129162
Calendar Build - 52-AARONSON | Care Designations +/- finance / study-team feedback submitted to CRAO for OnCore entry | Role | CTSU Finance |  |  | 2017-05-01 | N | 00128761
Calendaring : Amendment Checklist & Process - 00066077 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance |  |  | NA | Y | 00066077
Calendaring : Amendment Checklist & Process - 00068856 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance |  |  | NA | Y | 00068856
Calendaring : Amendment Checklist & Process - 00080998 | Acknowledge | Role | CTSU Finance |  |  | NA | Y | 00080998
Calendaring : Amendment Checklist & Process - 00080998 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance |  |  | NA | Y | 00080998
Calendaring : Amendment Checklist & Process - 00094136 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance |  |  |  | N | 00094136
Calendaring : Amendment Checklist & Process - 00101092 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance |  |  | NA | Y | 00101092
Calendaring : Amendment Checklist & Process - 00104658 | Acknowledge | Role | CTSU Finance |  |  | NA | Y | 00104658
Calendaring : Amendment Checklist & Process - 00104658 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance |  |  | NA | Y | 00104658
Calendaring : Amendment Checklist & Process - 00106894 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance |  |  | NA | Y | 00106894
Calendaring : Amendment Checklist & Process - 00113560 | Acknowledge | Role | CTSU Finance |  |  | NA | Y | 00113560
Calendaring : Amendment Checklist & Process - 00113560 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance |  |  | NA | Y | 00113560
Calendaring : Amendment Checklist & Process - 00119399 | AME Calendaring Process Initiated | Role | CTSU Finance |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 2 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00123635 | Provide PI-Determined Care Designations ( +/- Feedback ) | Role | CTSU Finance |  |  | NA | Y | 00123635
Calendaring : Initial Build - 00126224 | Acknowledge | Role | CTSU Finance |  |  | 2017-05-10 | N | 00126224
Calendaring : Initial Build - 00126224 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  | 2017-03-13 | N | 00126224
Calendaring : Initial Calendar Build - | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  | NA | Y | 103-GAGNIER
Calendaring : Initial Calendar Build - 00113042 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  | NA | Y | 00113042
Calendaring : Initial Calendar Build - 00118070 | Acknowledge | Role | CTSU Finance |  |  | 2017-06-08 | N | 00118070
Calendaring : Initial Calendar Build - 00118070 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  | 2017-06-08 | N | 00118070
Calendaring : Initial Calendar Build - 00123069 | Acknowledge | Role | CTSU Finance |  |  | 2017-05-08 | N | 00123069
Calendaring : Initial Calendar Build - 00123069 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  | NA | Y | 00123069
Calendaring : Initial Calendar Build - 00125599 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  | NA | Y | 00125599
Calendaring : Initial Calendar Build - 00126215 | Acknowledge | Role | CTSU Finance |  |  |  | N | 00126215
Calendaring : Initial Calendar Build - 00126215 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  |  | N | 00126215
Calendaring : Initial Calendar Build - 225-ROSENBLUM | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  | NA | Y | 00124224
Calendaring : Initial Calendar Build - 230-ROGERS | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  | NA | Y | 00130272
Calendaring : Initial Calendar Build - 239-KORLEY | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  | NA | Y | 00129045
Calendaring : Initial Calendar Build - 24-PARIKH | Acknowledge | Role | CTSU Finance |  |  | NA | Y | 00128493
Calendaring : Initial Calendar Build - 24-PARIKH | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  | 2017-04-25 | N | 00128493
Calendaring : Initial Calendar Build - 241-SILVER | Acknowledge | Role | CTSU Finance |  |  | NA | Y | 00132956
Calendaring : Initial Calendar Build - 241-SILVER | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  | NA | Y | 00132956
Calendaring : Initial Calendar Build - 287-HUTCHINSON | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  | NA | Y | 00119926
Calendaring : Initial Calendar Build - 295-ARNEDT | Acknowledge | Role | CTSU Finance |  |  | 2017-08-07 | N | 00130209
Calendaring : Initial Calendar Build - 295-ARNEDT | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  | 2017-07-27 | N | 00130209
Calendaring : Initial Calendar Build - 314-PARK | Acknowledge | Role | CTSU Finance |  |  |  | N | 314-PARK
Calendaring : Initial Calendar Build - 384-MODY | Acknowledge | Role | CTSU Finance |  |  |  | N | 00134459
Calendaring : Initial Calendar Build - 384-MODY | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  |  | N | 00134459
Calendaring : Initial Calendar Build - CIP-1403 | Acknowledge | Role | CTSU Finance |  |  | 2017-05-08 | N | 00128253
Calendaring : Initial Calendar Build - CIP-1403 | Care Designations-Bolling/TMVR | Role | CTSU Finance |  |  | 2017-05-08 | N | 00128253
Calendaring : Initial Calendar Build - CIP-1403 | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | Role | CTSU Finance |  |  | 2017-05-08 | N | 00128253
Calendaring : Migration - 00087702 | Acknowledge | Role | CTSU Finance |  |  |  | N | 00087702
Calendaring : Migration - 00100501 | Acknowledge | Role | CTSU Finance |  |  |  | N | 00100501
Calendaring : Specification Update Request(s) - 00091655 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00091655
Calendaring : Specification Update Request(s) - 00091655 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00091655
Calendaring : Specification Update Request(s) - 00091655 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00091655
Calendaring : Specification Update Request(s) - 00091655 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00091655
Calendaring : Specification Update Request(s) - 00091655 | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00091655
Calendaring : Specification Update Request(s) - 00091655 | Acknowledge | Role | CTSU Finance |  |  | NA | Y | 00091655
Calendaring : Specification Update Request(s) - 00091655 | Submit Update Request(s) | Role | CTSU Finance |  |  | NA | Y | 00091655
Calendaring : Specification Update Request(s) - 00113560 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00113560
Calendaring : Specification Update Request(s) - 00113560 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00113560
Calendaring : Specification Update Request(s) - 00113560 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00113560
Calendaring : Specification Update Request(s) - 00113560 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00113560
Calendaring : Specification Update Request(s) - 00113560 | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance |  |  | NA | Y | 00113560
Calendaring : Specification Update Request(s) - 00113560 | Acknowledge | Role | CTSU Finance |  |  | NA | Y | 00113560
Calendaring : Specification Update Request(s) - 00117851 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00117851
Calendaring : Specification Update Request(s) - 00117851 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00117851
Calendaring : Specification Update Request(s) - 00117851 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00117851
Calendaring : Specification Update Request(s) - 00117851 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00117851
Calendaring : Specification Update Request(s) - 00117851 | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance |  |  | NA | Y | 00117851
Calendaring : Specification Update Request(s) - 00122815 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00122815
Calendaring : Specification Update Request(s) - 00122815 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00122815
Calendaring : Specification Update Request(s) - 00122815 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00122815
Calendaring : Specification Update Request(s) - 00122815 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00122815
Calendaring : Specification Update Request(s) - 00122815 | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance |  |  | NA | Y | 00122815
Calendaring : Specification Update Request(s) - 00125798 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00125798
Calendaring : Specification Update Request(s) - 00125798 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00125798
Calendaring : Specification Update Request(s) - 00125798 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00125798
Calendaring : Specification Update Request(s) - 00125798 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00125798
Calendaring : Specification Update Request(s) - 00125798 | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00125798
Calendaring : Specification Update Request(s) - 00126707 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00126707
Calendaring : Specification Update Request(s) - 00126707 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00126707
Calendaring : Specification Update Request(s) - 00126707 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00126707
Calendaring : Specification Update Request(s) - 00126707 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00126707
Calendaring : Specification Update Request(s) - 00126707 | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance |  |  | NA | Y | 00126707
Calendaring : Specification Update Request(s) - 00126707 | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00126707
Calendaring : Specification Update Request(s) - 00127136 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00127136
Calendaring : Specification Update Request(s) - 00127136 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00127136
Calendaring : Specification Update Request(s) - 00127136 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00127136
Calendaring : Specification Update Request(s) - 00127136 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00127136
Calendaring : Specification Update Request(s) - 00127136 | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00127136
Calendaring : Specification Update Request(s) - 00127136 2 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00127136
Calendaring : Specification Update Request(s) - 00127136 2 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00127136
Calendaring : Specification Update Request(s) - 00127136 2 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00127136
Calendaring : Specification Update Request(s) - 00127136 2 | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance |  |  | NA | Y | 00127136
Calendaring : Specification Update Request(s) - 00127136 2 | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00127136
Calendaring : Specification Update Request(s) - 00127505 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00127505
Calendaring : Specification Update Request(s) - 00127505 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00127505
Calendaring : Specification Update Request(s) - 00127505 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00127505
Calendaring : Specification Update Request(s) - 00127505 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00127505
Calendaring : Specification Update Request(s) - 00127505 | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00127505
Calendaring : Specification Update Request(s) - 00127913 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00127913
Calendaring : Specification Update Request(s) - 00127913 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00127913
Calendaring : Specification Update Request(s) - 00127913 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00127913
Calendaring : Specification Update Request(s) - 00127913 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00127913
Calendaring : Specification Update Request(s) - 00127913 | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00127913
Calendaring : Specification Update Request(s) - 00127913 | Acknowledge | Role | CTSU Finance |  |  | NA | Y | 00127913
Calendaring : Specification Update Request(s) - 00127913 | Submit Update Request(s) | Role | CTSU Finance |  |  | NA | Y | 00127913
Calendaring : Specification Update Request(s) - 00128253 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00128253
Calendaring : Specification Update Request(s) - 00128253 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00128253
Calendaring : Specification Update Request(s) - 00128253 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00128253
Calendaring : Specification Update Request(s) - 00128253 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00128253
Calendaring : Specification Update Request(s) - 00128253 | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00128253
Calendaring : Specification Update Request(s) - 00128322 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00128322
Calendaring : Specification Update Request(s) - 00128322 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00128322
Calendaring : Specification Update Request(s) - 00128322 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00128322
Calendaring : Specification Update Request(s) - 00128322 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00128322
Calendaring : Specification Update Request(s) - 00128322 | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00128322
Calendaring : Specification Update Request(s) - 00128322 | Acknowledge | Role | CTSU Finance |  |  | NA | Y | 00128322
Calendaring : Specification Update Request(s) - 00128322 2 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00128322
Calendaring : Specification Update Request(s) - 00128322 2 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00128322
Calendaring : Specification Update Request(s) - 00128322 2 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00128322
Calendaring : Specification Update Request(s) - 00128322 2 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00128322
Calendaring : Specification Update Request(s) - 00128322 2 | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00128322
Calendaring : Specification Update Request(s) - 00128531 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00128531
Calendaring : Specification Update Request(s) - 00128531 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00128531
Calendaring : Specification Update Request(s) - 00128531 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00128531
Calendaring : Specification Update Request(s) - 00128531 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00128531
Calendaring : Specification Update Request(s) - 00128531 | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance |  |  | NA | Y | 00128531
Calendaring : Specification Update Request(s) - 00128531 | Submit Update Request(s) | Role | CTSU Finance |  |  | NA | Y | 00128531
Calendaring : Specification Update Request(s) - 00130575 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00130575
Calendaring : Specification Update Request(s) - 00130575 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00130575
Calendaring : Specification Update Request(s) - 00130575 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00130575
Calendaring : Specification Update Request(s) - 00130575 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00130575
Calendaring : Specification Update Request(s) - 00130757 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00130757
Calendaring : Specification Update Request(s) - 00130757 | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00130757
Calendaring : Specification Update Request(s) - 00130757 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00130757
Calendaring : Specification Update Request(s) - 00130757 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00130757
Calendaring : Specification Update Request(s) - 00130757 | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance |  |  | NA | Y | 00130757
Calendaring : Specification Update Request(s) - 00130757 | Submit Update Request(s) | Role | CTSU Finance |  |  | NA | Y | 00130757
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00066077
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00066077
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00066077
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance |  |  | NA | Y | 00066077
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00066077
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | Acknowledge | Role | CTSU Finance |  |  | 2017-05-02 | N | 00066077
Open to Accrual - 00117851 | Budget Finalized | Role | CTSU Finance |  |  | 2017-06-12 | N | 00117851
Open to Accrual - 00118070 | Budget Finalized | Role | CTSU Finance |  |  | NA | Y | 00118070
Open to Accrual - 00120187 | Budget Finalized | Role | CTSU Finance |  |  | NA | Y | 00120187
Open to Accrual - 00120189 | Budget Finalized | Role | CTSU Finance |  |  |  | N | 00120189
Open to Accrual - 00120231 | Budget Finalized | Role | CTSU Finance |  |  | 2017-06-13 | N | 00120231
Open to Accrual - 00120231 | Contract Executed | Role | CTSU Finance |  |  | 2017-06-13 | N | 00120231
Open to Accrual - 00120231 | Project Award Notice (PAN) Received | Role | CTSU Finance |  |  | 2017-06-13 | N | 00120231
Open to Accrual - 00120349 | Budget Finalized | Role | CTSU Finance |  |  |  | N | 00120349
Open to Accrual - 00122152 | Budget Finalized | Role | CTSU Finance |  |  | 2017-05-03 | N | 00122152
Open to Accrual - 00122153 | Budget Finalized | Role | CTSU Finance |  |  | 2017-04-21 | N | 00122153
Open to Accrual - 00122153 | Contract Executed | Role | CTSU Finance |  |  | 2017-04-21 | N | 00122153
Open to Accrual - 00122153 | Project Award Notice (PAN) Received | Role | CTSU Finance |  |  | 2017-04-21 | N | 00122153
Open to Accrual - 00122815 | Budget Finalized | Role | CTSU Finance |  |  | 2017-05-25 | N | 00122815
Open to Accrual - 00122815 | Contract Executed | Role | CTSU Finance |  |  | 2017-05-25 | N | 00122815
Open to Accrual - 00122815 | Project Award Notice (PAN) Received | Role | CTSU Finance |  |  | 2017-05-25 | N | 00122815
Open to Accrual - 00123069 | Budget Finalized | Role | CTSU Finance |  |  | 2017-08-09 | N | 00123069
Open to Accrual - 00123069 | Contract Executed | Role | CTSU Finance |  |  |  | N | 00123069
Open to Accrual - 00123069 | Project Award Notice (PAN) Received | Role | CTSU Finance |  |  |  | N | 00123069
Open to Accrual - 00123632 | Budget Finalized | Role | CTSU Finance |  |  | 2017-05-25 | N | 00123632
Open to Accrual - 00123632 | Contract Executed | Role | CTSU Finance |  |  | 2017-05-25 | N | 00123632
Open to Accrual - 00123632 | Project Award Notice (PAN) Received | Role | CTSU Finance |  |  | 2017-05-25 | N | 00123632
Open to Accrual - 00123861 | Budget Finalized | Role | CTSU Finance |  |  | 2017-03-24 | N | 00123861
Open to Accrual - 00125425 | Budget Finalized | Role | CTSU Finance |  |  | 2017-04-18 | N | 00125425
Open to Accrual - 00125786 | Budget Finalized | Role | CTSU Finance |  |  | 2017-05-12 | N | 00125786
Open to Accrual - 00125794 | Budget Finalized | Role | CTSU Finance |  |  | 2017-05-05 | N | 00125794
Open to Accrual - 00125798 | Budget Finalized | Role | CTSU Finance |  |  |  | N | 00125798
Open to Accrual - 00125798 | Contract Executed | Role | CTSU Finance |  |  |  | N | 00125798
Open to Accrual - 00125798 | Project Award Notice (PAN) Received | Role | CTSU Finance |  |  |  | N | 00125798
Open to Accrual - 00126010 | Budget Finalized | Role | CTSU Finance |  |  | 2017-07-19 | N | 00126010
Open to Accrual - 00127537 | Budget Finalized | Role | CTSU Finance |  |  | 2017-05-05 | N | 00127537
Open to Accrual - 00128061 | Budget Finalized | Role | CTSU Finance |  |  | NA | Y | 00128061
Open to Accrual - 00128253 | Budget Finalized | Role | CTSU Finance |  |  | 2017-07-06 | N | 00128253
Open to Accrual - 00128253 | Contract Executed | Role | CTSU Finance |  |  | 2017-07-06 | N | 00128253
Open to Accrual - 00128322 | Budget Finalized | Role | CTSU Finance |  |  | 2017-08-22 | N | 00128322
Open to Accrual - 00128322 | Contract Executed | Role | CTSU Finance |  |  | 2017-08-24 | N | 00128322
Open to Accrual - 00128761 | Budget Finalized | Role | CTSU Finance |  |  | 2017-08-17 | N | 00128761
Open to Accrual - 00129427 | Budget Finalized | Role | CTSU Finance |  |  |  | N | 00129427
Open to Accrual - 00129851 | Budget Finalized | Role | CTSU Finance |  |  | 2017-04-05 | N | 00129851
Open to Accrual - 00131377 | Budget Finalized | Role | CTSU Finance |  |  |  | N | 00131377
Open to Accrual - 239-KORLEY | Budget Finalized | Role | CTSU Finance |  |  | NA | Y | 00129045
Open to Accrual - 268-NEUMAR | Budget Finalized | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Open to Accrual - 268-NEUMAR | Contract Executed | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Open to Accrual - 268-NEUMAR | Project Award Notice (PAN) Received | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Open to Accrual - 363-PARK | Budget Finalized | Role | CTSU Finance |  |  |  | N | 363-PARK
Pre-Award Financial - 00108880 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00108880
Pre-Award Financial - 00108880 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00108880
Pre-Award Financial - 00118070 | Budget Negotiations | Role | CTSU Finance |  |  | NA | Y | 00118070
Pre-Award Financial - 00118070 | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 00118070
Pre-Award Financial - 00118070 | Feasibility w/Documents received | Role | CTSU Finance |  |  | NA | Y | 00118070
Pre-Award Financial - 00118070 | Internal Budget Finished | Role | CTSU Finance |  |  | NA | Y | 00118070
Pre-Award Financial - 00118070 | OnCore Budget Build | Role | CTSU Finance |  |  | 2017-06-09 | N | 00118070
Pre-Award Financial - 00118070 | PAF routed | Role | CTSU Finance |  |  | NA | Y | 00118070
Pre-Award Financial - 00118070 | PI approved Budget | Role | CTSU Finance |  |  | NA | Y | 00118070
Pre-Award Financial - 00118070 | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 00118070
Pre-Award Financial - 00118070 | Planning Meeting Request Sent | Role | CTSU Finance |  |  | NA | Y | 00118070
Pre-Award Financial - 00118070 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00118070
Pre-Award Financial - 00118070 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00118070
Pre-Award Financial - 00118070 | Sponsor Reach out | Role | CTSU Finance |  |  | NA | Y | 00118070
Pre-Award Financial - 00118070 | UFA Completed | Role | CTSU Finance |  |  | NA | Y | 00118070
Pre-Award Financial - 00121967 2 | Billing Calendar Received | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | Budget Negotiations | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | Calendar Released | Role | CTSU Finance |  |  | 2017-04-28 | N | 00121967
Pre-Award Financial - 00121967 2 | Care Designations completed | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | Feasibility w/Documents received | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | Final Budget | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | Intake Form Completed | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | Internal Budget Finished | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | OnCore Budget Build | Role | CTSU Finance |  |  | 2017-04-28 | N | 00121967
Pre-Award Financial - 00121967 2 | PAF routed | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | PAN Released | Role | CTSU Finance |  |  | 2017-02-22 | N | 00121967
Pre-Award Financial - 00121967 2 | PI approved Budget | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | Planning Meeting Request Sent | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | Sponsor Reach out | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00121967 2 | UFA Completed | Role | CTSU Finance |  |  | NA | Y | 00121967
Pre-Award Financial - 00122254 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00122254
Pre-Award Financial - 00122254 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00122254
Pre-Award Financial - 00123237 | Billing Calendar Received | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | Budget Negotiations | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | Calendar Released | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | Care Designations completed | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | Feasibility w/Documents received | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | Final Budget | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | Intake Form Completed | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | Internal Budget Finished | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | OnCore Budget Build | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | PAF routed | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | PAN Released | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | PI approved Budget | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | Planning Meeting Request Sent | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | Sponsor Reach out | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123237 | UFA Completed | Role | CTSU Finance |  |  | NA | Y | 00123237
Pre-Award Financial - 00123861 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00123861
Pre-Award Financial - 00123861 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00123861
Pre-Award Financial - 00124712 | Billing Calendar Received | Role | CTSU Finance |  |  | NA | Y | 00124712
Pre-Award Financial - 00124712 | Budget Negotiations | Role | CTSU Finance |  |  | NA | Y | 00124712
Pre-Award Financial - 00124712 | Calendar Released | Role | CTSU Finance |  |  | NA | Y | 00124712
Pre-Award Financial - 00124712 | Care Designations completed | Role | CTSU Finance |  |  | NA | Y | 00124712
Pre-Award Financial - 00124712 | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 00124712
Pre-Award Financial - 00124712 | Final Budget | Role | CTSU Finance |  |  | NA | Y | 00124712
Pre-Award Financial - 00124712 | OnCore Budget Build | Role | CTSU Finance |  |  | NA | Y | 00124712
Pre-Award Financial - 00124712 | PAF routed | Role | CTSU Finance |  |  | NA | Y | 00124712
Pre-Award Financial - 00124712 | PAN Released | Role | CTSU Finance |  |  | NA | Y | 00124712
Pre-Award Financial - 00124712 | PI approved Budget | Role | CTSU Finance |  |  | NA | Y | 00124712
Pre-Award Financial - 00124712 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00124712
Pre-Award Financial - 00124920 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00124920
Pre-Award Financial - 00124920 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00124920
Pre-Award Financial - 00125022 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00125022
Pre-Award Financial - 00125022 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00125022
Pre-Award Financial - 00125425 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00125425
Pre-Award Financial - 00125425 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00125425
Pre-Award Financial - 00125566 | Billing Calendar Received | Role | CTSU Finance |  |  | NA | Y | 00125566
Pre-Award Financial - 00125566 | Internal Budget Finished | Role | CTSU Finance |  |  | NA | Y | 00125566
Pre-Award Financial - 00125566 | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 00125566
Pre-Award Financial - 00125566 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00125566
Pre-Award Financial - 00125566 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00125566
Pre-Award Financial - 00125786 | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 00125786
Pre-Award Financial - 00125786 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00125786
Pre-Award Financial - 00125786 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00125786
Pre-Award Financial - 00125794 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00125794
Pre-Award Financial - 00125794 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00125794
Pre-Award Financial - 00126010 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00126010
Pre-Award Financial - 00126215 | Billing Calendar Received | Role | CTSU Finance |  |  | NA | Y | 00126215
Pre-Award Financial - 00126215 | Budget Negotiations | Role | CTSU Finance |  |  | NA | Y | 00126215
Pre-Award Financial - 00126215 | Calendar Released | Role | CTSU Finance |  |  | NA | Y | 00126215
Pre-Award Financial - 00126215 | Care Designations completed | Role | CTSU Finance |  |  | NA | Y | 00126215
Pre-Award Financial - 00126215 | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 00126215
Pre-Award Financial - 00126215 | Final Budget | Role | CTSU Finance |  |  | NA | Y | 00126215
Pre-Award Financial - 00126215 | Internal Budget Finished | Role | CTSU Finance |  |  | NA | Y | 00126215
Pre-Award Financial - 00126215 | OnCore Budget Build | Role | CTSU Finance |  |  | NA | Y | 00126215
Pre-Award Financial - 00126215 | PAF routed | Role | CTSU Finance |  |  | NA | Y | 00126215
Pre-Award Financial - 00126215 | PAN Released | Role | CTSU Finance |  |  | NA | Y | 00126215
Pre-Award Financial - 00126215 | PI approved Budget | Role | CTSU Finance |  |  | NA | Y | 00126215
Pre-Award Financial - 00126215 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00126215
Pre-Award Financial - 00126215 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00126215
Pre-Award Financial - 00126224 | Billing Calendar Received | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | Budget Negotiations | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | Calendar Released | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | Care Designations completed | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | Feasibility w/Documents received | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | Final Budget | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | Intake Form Completed | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | Internal Budget Finished | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | OnCore Budget Build | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | PAF routed | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | PAN Released | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | PI approved Budget | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 00126224
Pre-Award Financial - 00126224 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | Sponsor Reach out | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00126224 | UFA Completed | Role | CTSU Finance |  |  | NA | Y | 00126224
Pre-Award Financial - 00127136 | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00127136
Pre-Award Financial - 00127136 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00127136
Pre-Award Financial - 00127136 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00127136
Pre-Award Financial - 00127356 | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00127356
Pre-Award Financial - 00127356 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00127356
Pre-Award Financial - 00127356 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00127356
Pre-Award Financial - 00127505 | Initiate Post-Award Task List | Role | CTSU Finance |  |  | 2017-08-10 | N | 00127505
Pre-Award Financial - 00127505 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00127505
Pre-Award Financial - 00127505 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00127505
Pre-Award Financial - 00127537 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00127537
Pre-Award Financial - 00127537 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00127537
Pre-Award Financial - 00127988 | Billing Calendar Received | Role | CTSU Finance |  |  | 2017-04-20 | N | 00127988
Pre-Award Financial - 00127988 | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 00127988
Pre-Award Financial - 00127988 | Calendar Released | Role | CTSU Finance |  |  |  | N | 00127988
Pre-Award Financial - 00127988 | Care Designations completed | Role | CTSU Finance |  |  | 2017-05-08 | N | 00127988
Pre-Award Financial - 00127988 | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | 2017-05-10 | N | 00127988
Pre-Award Financial - 00127988 | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  | 2017-02-28 | N | 00127988
Pre-Award Financial - 00127988 | Feasibility w/Documents received | Role | CTSU Finance |  |  | NA | Y | 00127988
Pre-Award Financial - 00127988 | Final Budget | Role | CTSU Finance |  |  |  | N | 00127988
Pre-Award Financial - 00127988 | Intake Form Completed | Role | CTSU Finance |  |  | NA | Y | 00127988
Pre-Award Financial - 00127988 | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 00127988
Pre-Award Financial - 00127988 | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 00127988
Pre-Award Financial - 00127988 | PAF routed | Role | CTSU Finance |  |  |  | N | 00127988
Pre-Award Financial - 00127988 | PAN Released | Role | CTSU Finance |  |  |  | N | 00127988
Pre-Award Financial - 00127988 | PI approved Budget | Role | CTSU Finance |  |  |  | N | 00127988
Pre-Award Financial - 00127988 | Planning Meeting Completed | Role | CTSU Finance |  |  | 2017-05-04 | N | 00127988
Pre-Award Financial - 00127988 | Planning Meeting Request Sent | Role | CTSU Finance |  |  | NA | Y | 00127988
Pre-Award Financial - 00127988 | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 00127988
Pre-Award Financial - 00127988 | Sponsor Reach out | Role | CTSU Finance |  |  | NA | Y | 00127988
Pre-Award Financial - 00127988 | UFA Completed | Role | CTSU Finance |  |  | NA | Y | 00127988
Pre-Award Financial - 00128157 | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00128157
Pre-Award Financial - 00128157 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00128157
Pre-Award Financial - 00128157 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00128157
Pre-Award Financial - 00128173 | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00128173
Pre-Award Financial - 00128173 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00128173
Pre-Award Financial - 00128173 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00128173
Pre-Award Financial - 00128531 | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00128531
Pre-Award Financial - 00128531 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00128531
Pre-Award Financial - 00128531 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00128531
Pre-Award Financial - 00128743 | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00128743
Pre-Award Financial - 00128743 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00128743
Pre-Award Financial - 00128743 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00128743
Pre-Award Financial - 00129427 | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 00129427
Pre-Award Financial - 00129652 | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00129652
Pre-Award Financial - 00129851 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00129851
Pre-Award Financial - 00129851 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00129851
Pre-Award Financial - 00130575 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00130575
Pre-Award Financial - 00130575 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00130575
Pre-Award Financial - 00130793 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00130793
Pre-Award Financial - 10-JAYASUNDERA | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 10-JAYASUNDERA
Pre-Award Financial - 11-HIGGINS | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00134884
Pre-Award Financial - 110-SCHIOPU | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00134444
Pre-Award Financial - 110-SCHIOPU | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00134444
Pre-Award Financial - 111-HIGGINS | Billing Calendar Received | Role | CTSU Finance |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | Budget Negotiations | Role | CTSU Finance |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | Calendar Released | Role | CTSU Finance |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | Care Designations completed | Role | CTSU Finance |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | Final Budget | Role | CTSU Finance |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | Internal Budget Finished | Role | CTSU Finance |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | OnCore Budget Build | Role | CTSU Finance |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | PAF routed | Role | CTSU Finance |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | PAN Released | Role | CTSU Finance |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | PI approved Budget | Role | CTSU Finance |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 111-HIGGINS | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 111-HIGGINS
Pre-Award Financial - 112-FLAHERTY | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 112-FLAHERTY
Pre-Award Financial - 12-HIGGINS | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 12-HIGGINS
Pre-Award Financial - 131-LUGOGO | Billing Calendar Received | Role | CTSU Finance |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | Budget Negotiations | Role | CTSU Finance |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | Calendar Released | Role | CTSU Finance |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | Care Designations completed | Role | CTSU Finance |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | Final Budget | Role | CTSU Finance |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | Internal Budget Finished | Role | CTSU Finance |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | OnCore Budget Build | Role | CTSU Finance |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | PAF routed | Role | CTSU Finance |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | PAN Released | Role | CTSU Finance |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | PI approved Budget | Role | CTSU Finance |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 131-LUGOGO | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 131-LUGOGO
Pre-Award Financial - 142-FLAHERTY | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 142-FLAHERTY
Pre-Award Financial - 147-SCHIOPU | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00131329
Pre-Award Financial - 155-ORAL | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 00130803
Pre-Award Financial - 155-ORAL | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00130803
Pre-Award Financial - 155-ORAL | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00130803
Pre-Award Financial - 170-SCHIOPU | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00134035
Pre-Award Financial - 179-LUGOGO | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 179-LUGOGO
Pre-Award Financial - 187-MCLAUGHLIN | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | Calendar Released | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | Care Designations completed | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | Feasibility w/Documents received | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | Final Budget | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | Intake Form Completed | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | PAF routed | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | PAN Released | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | PI approved Budget | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | Sponsor Reach out | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 187-MCLAUGHLIN | UFA Completed | Role | CTSU Finance |  |  |  | N | 187-MCLAUGHLIN
Pre-Award Financial - 188-RUBENSTEIN | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 188-RUBENSTEIN
Pre-Award Financial - 192-ALAM | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | Calendar Released | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | Care Designations completed | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | Feasibility w/Documents received | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | Final Budget | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | PAF routed | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | PAN Released | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | PI approved Budget | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | Sponsor Reach out | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 192-ALAM | UFA Completed | Role | CTSU Finance |  |  |  | N | 192-ALAM
Pre-Award Financial - 194-MCLAUGHLIN | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | Calendar Released | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | Care Designations completed | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | Feasibility w/Documents received | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | Final Budget | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | PAF routed | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | PAN Released | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | PI approved Budget | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 194-MCLAUGHLIN | Sponsor Reach out | Role | CTSU Finance |  |  |  | N | 194-MCLAUGHLIN
Pre-Award Financial - 198-LUCKRITZ | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 198-LUCKRITZ
Pre-Award Financial - 198-LUCKRITZ | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 198-LUCKRITZ
Pre-Award Financial - 198-LUCKRITZ | Calendar Released | Role | CTSU Finance |  |  |  | N | 198-LUCKRITZ
Pre-Award Financial - 198-LUCKRITZ | Care Designations completed | Role | CTSU Finance |  |  |  | N | 198-LUCKRITZ
Pre-Award Financial - 198-LUCKRITZ | Feasibility w/Documents received | Role | CTSU Finance |  |  | 2017-08-24 | N | 198-LUCKRITZ
Pre-Award Financial - 198-LUCKRITZ | Final Budget | Role | CTSU Finance |  |  |  | N | 198-LUCKRITZ
Pre-Award Financial - 198-LUCKRITZ | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 198-LUCKRITZ
Pre-Award Financial - 198-LUCKRITZ | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 198-LUCKRITZ
Pre-Award Financial - 198-LUCKRITZ | PAF routed | Role | CTSU Finance |  |  |  | N | 198-LUCKRITZ
Pre-Award Financial - 198-LUCKRITZ | PAN Released | Role | CTSU Finance |  |  |  | N | 198-LUCKRITZ
Pre-Award Financial - 198-LUCKRITZ | PI approved Budget | Role | CTSU Finance |  |  |  | N | 198-LUCKRITZ
Pre-Award Financial - 198-LUCKRITZ | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 198-LUCKRITZ
Pre-Award Financial - 198-LUCKRITZ | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 198-LUCKRITZ
Pre-Award Financial - 198-LUCKRITZ | Sponsor Reach out | Role | CTSU Finance |  |  |  | N | 198-LUCKRITZ
Pre-Award Financial - 2-MARSH | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 2-MARSH
Pre-Award Financial - 201-MCCUNE | Billing Calendar Received | Role | CTSU Finance |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | Budget Negotiations | Role | CTSU Finance |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | Calendar Released | Role | CTSU Finance |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | Care Designations completed | Role | CTSU Finance |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | Final Budget | Role | CTSU Finance |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | Initiate Post-Award Task List | Role | CTSU Finance |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | Internal Budget Finished | Role | CTSU Finance |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | OnCore Budget Build | Role | CTSU Finance |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | PAF routed | Role | CTSU Finance |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | PAN Released | Role | CTSU Finance |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | PI approved Budget | Role | CTSU Finance |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 201-MCCUNE | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 201-MCCUNE
Pre-Award Financial - 203-ELSE | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00132173
Pre-Award Financial - 203-ELSE | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00132173
Pre-Award Financial - 205-HIGGINS | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 205-HIGGINS
Pre-Award Financial - 205-KHANNA | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 00132200
Pre-Award Financial - 205-KHANNA | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 00132200
Pre-Award Financial - 205-KHANNA | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00132200
Pre-Award Financial - 211-HIGGINS | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 00128325
Pre-Award Financial - 211-HIGGINS | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00128325
Pre-Award Financial - 222-STEIGERWALT | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 222-STEIGERWALT | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 222-STEIGERWALT | Calendar Released | Role | CTSU Finance |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 222-STEIGERWALT | Care Designations completed | Role | CTSU Finance |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 222-STEIGERWALT | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 222-STEIGERWALT | Final Budget | Role | CTSU Finance |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 222-STEIGERWALT | Intake Form Completed | Role | CTSU Finance |  |  | NA | Y | 227-STEIGERWALT
Pre-Award Financial - 222-STEIGERWALT | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 222-STEIGERWALT | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 222-STEIGERWALT | PAF routed | Role | CTSU Finance |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 222-STEIGERWALT | PAN Released | Role | CTSU Finance |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 222-STEIGERWALT | PI approved Budget | Role | CTSU Finance |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 222-STEIGERWALT | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 222-STEIGERWALT | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 222-STEIGERWALT | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 227-STEIGERWALT
Pre-Award Financial - 222-STEIGERWALT | Sponsor Reach out | Role | CTSU Finance |  |  | NA | Y | 227-STEIGERWALT
Pre-Award Financial - 234-MCLAUGHLIN | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | Calendar Released | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | Care Designations completed | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | Feasibility w/Documents received | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | Final Budget | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | PAF routed | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | PAN Released | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | PI approved Budget | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 234-MCLAUGHLIN | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 234-MCLAUGHLIN
Pre-Award Financial - 236-NASR | Billing Calendar Received | Role | CTSU Finance |  |  | 2017-06-20 | N | 00131580
Pre-Award Financial - 236-NASR | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 00131580
Pre-Award Financial - 236-NASR | Calendar Released | Role | CTSU Finance |  |  |  | N | 00131580
Pre-Award Financial - 236-NASR | Care Designations completed | Role | CTSU Finance |  |  | 2017-07-11 | N | 00131580
Pre-Award Financial - 236-NASR | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 00131580
Pre-Award Financial - 236-NASR | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  | NA | Y | 00131580
Pre-Award Financial - 236-NASR | Feasibility w/Documents received | Role | CTSU Finance |  |  | NA | Y | 00131580
Pre-Award Financial - 236-NASR | Final Budget | Role | CTSU Finance |  |  |  | N | 00131580
Pre-Award Financial - 236-NASR | Intake Form Completed | Role | CTSU Finance |  |  | NA | Y | 00131580
Pre-Award Financial - 236-NASR | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 00131580
Pre-Award Financial - 236-NASR | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 00131580
Pre-Award Financial - 236-NASR | PAF routed | Role | CTSU Finance |  |  |  | N | 00131580
Pre-Award Financial - 236-NASR | PAN Released | Role | CTSU Finance |  |  |  | N | 00131580
Pre-Award Financial - 236-NASR | PI approved Budget | Role | CTSU Finance |  |  |  | N | 00131580
Pre-Award Financial - 236-NASR | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 00131580
Pre-Award Financial - 236-NASR | Planning Meeting Request Sent | Role | CTSU Finance |  |  | NA | Y | 00131580
Pre-Award Financial - 236-NASR | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00131580
Pre-Award Financial - 236-NASR | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00131580
Pre-Award Financial - 236-NASR | Sponsor Reach out | Role | CTSU Finance |  |  | NA | Y | 00131580
Pre-Award Financial - 236-NASR | UFA Completed | Role | CTSU Finance |  |  | NA | Y | 00131580
Pre-Award Financial - 238-GUNNERSON | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | Calendar Released | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | Care Designations completed | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | Feasibility w/Documents received | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | Final Budget | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | Intake Form Completed | Role | CTSU Finance |  |  | 2017-05-30 | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | PAF routed | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | PAN Released | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | PI approved Budget | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | Sponsor Reach out | Role | CTSU Finance |  |  | 2017-08-15 | N | 238-GUNNERSON
Pre-Award Financial - 238-GUNNERSON | UFA Completed | Role | CTSU Finance |  |  | 2017-07-11 | N | 238-GUNNERSON
Pre-Award Financial - 239-KORLEY | Budget Negotiations | Role | CTSU Finance |  |  | NA | Y | 00129045
Pre-Award Financial - 239-KORLEY | Calendar Released | Role | CTSU Finance |  |  |  | N | 00129045
Pre-Award Financial - 239-KORLEY | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 00129045
Pre-Award Financial - 239-KORLEY | Final Budget | Role | CTSU Finance |  |  | NA | Y | 00129045
Pre-Award Financial - 239-KORLEY | Internal Budget Finished | Role | CTSU Finance |  |  | NA | Y | 00129045
Pre-Award Financial - 239-KORLEY | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 00129045
Pre-Award Financial - 239-KORLEY | PAF routed | Role | CTSU Finance |  |  | NA | Y | 00129045
Pre-Award Financial - 239-KORLEY | PAN Released | Role | CTSU Finance |  |  | NA | Y | 00129045
Pre-Award Financial - 239-KORLEY | PI approved Budget | Role | CTSU Finance |  |  | NA | Y | 00129045
Pre-Award Financial - 239-KORLEY | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 00129045
Pre-Award Financial - 239-KORLEY | Planning Meeting Request Sent | Role | CTSU Finance |  |  | NA | Y | 00129045
Pre-Award Financial - 239-KORLEY | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00129045
Pre-Award Financial - 239-KORLEY | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00129045
Pre-Award Financial - 239-KORLEY | Sponsor Reach out | Role | CTSU Finance |  |  | NA | Y | 00129045
Pre-Award Financial - 239-KORLEY | UFA Completed | Role | CTSU Finance |  |  | NA | Y | 00129045
Pre-Award Financial - 241-SILVER | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | Calendar Released | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | Care Designations completed | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | Feasibility w/Documents received | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | Final Budget | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | PAF routed | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | PAN Released | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | PI approved Budget | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 00132956
Pre-Award Financial - 241-SILVER | Sponsor Reach out | Role | CTSU Finance |  |  | NA | Y | 00132956
Pre-Award Financial - 241-SILVER | UFA Completed | Role | CTSU Finance |  |  | NA | Y | 00132956
Pre-Award Financial - 242-AS-SANIE | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 242-AS-SANIE
Pre-Award Financial - 246-AS-SANIE | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 246-AS-SANIE
Pre-Award Financial - 251-COMER | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00134232
Pre-Award Financial - 251-COMER | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00134232
Pre-Award Financial - 255-LOK | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 255-LOK
Pre-Award Financial - 258-SHEEHAN | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | Calendar Released | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | Care Designations completed | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | Feasibility w/Documents received | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | Final Budget | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | Intake Form Completed | Role | CTSU Finance |  |  | 2017-06-08 | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | PAF routed | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | PAN Released | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | PI approved Budget | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | Sponsor Reach out | Role | CTSU Finance |  |  | 2017-06-29 | N | 258-SHEEHAN
Pre-Award Financial - 258-SHEEHAN | UFA Completed | Role | CTSU Finance |  |  | 2017-06-14 | N | 258-SHEEHAN
Pre-Award Financial - 261-LUGOGO | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 261-LUGOGO
Pre-Award Financial - 263-DELMONTE | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 263-DELMONTE
Pre-Award Financial - 268-NEUMAR | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | Calendar Released | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | Care Designations completed | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | Feasibility w/Documents received | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | Final Budget | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | Intake Form Completed | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | PAF routed | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | PAN Released | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | PI approved Budget | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | Sponsor Reach out | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 268-NEUMAR | UFA Completed | Role | CTSU Finance |  |  |  | N | 268-NEUMAR
Pre-Award Financial - 282-POP-BUSUI | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00133290
Pre-Award Financial - 30-FLAHERTY | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 30-FLAHERTY
Pre-Award Financial - 305-PELOSI | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | Calendar Released | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | Care Designations completed | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | Feasibility w/Documents received | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | Final Budget | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | PAF routed | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | PAN Released | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | PI approved Budget | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 305-PELOSI
Pre-Award Financial - 305-PELOSI | Sponsor Reach out | Role | CTSU Finance |  |  | NA | Y | 305-PELOSI
Pre-Award Financial - 33-FLAHERTY | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00129716
Pre-Award Financial - 33-FLAHERTY | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00129716
Pre-Award Financial - 34-MARSH | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 34-MARSH
Pre-Award Financial - 44-MCUNE | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Care Designations completed | Role | CTSU Finance |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Final Budget | Role | CTSU Finance |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | PAF routed | Role | CTSU Finance |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | PI approved Budget | Role | CTSU Finance |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 44-MCUNE
Pre-Award Financial - 46-HIGGINS | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 46-HIGGINS
Pre-Award Financial - 70-LUGOGO | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 70-LUGOGO
Pre-Award Financial - 71-RICE | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00134857
Pre-Award Financial - 71-RICE | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00134857
Pre-Award Financial - 71-RICE | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00134857
Pre-Award Financial - 76-KHANNA | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | 00131837
Pre-Award Financial - 76-KHANNA | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | 00131837
Pre-Award Financial - 76-KHANNA | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00131837
Pre-Award Financial - 76-KHANNA | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00131837
Pre-Award Financial - 77-CONJEEVARAM | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 77-CONJEEVARAM
Pre-Award Financial - 81-HIGGINS | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 81-HIGGINS
Pre-Award Financial - 86-AUCHUS | Initial Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00132700
Pre-Award Financial - 86-AUCHUS | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00132700
Pre-Award Financial - 87-ORAL | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 00130757
Pre-Award Financial - 87-ORAL | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00130757
Pre-Award Financial - 9-JAYASUNDERA | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 9-JAYASUNDERA
Pre-Award Financial - 91-ELSE | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 91-ELSE
Pre-Award Financial - 92-AUCHUS | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | 92-AUCHUS
Pre-Award Financial - 96-BESIRLI | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00129820
Pre-Award Financial - 96-BESIRLI | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00129820
Pre-Award Financial - FONTANA-3 | Billing Calendar Received | Role | CTSU Finance |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | Budget Negotiations | Role | CTSU Finance |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | Calendar Released | Role | CTSU Finance |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | Care Designations completed | Role | CTSU Finance |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | Final Budget | Role | CTSU Finance |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | Internal Budget Finished | Role | CTSU Finance |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | OnCore Budget Build | Role | CTSU Finance |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | PAF routed | Role | CTSU Finance |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | PAN Released | Role | CTSU Finance |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | PI approved Budget | Role | CTSU Finance |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | Planning Meeting Completed | Role | CTSU Finance |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | FONTANA-3
Pre-Award Financial - FONTANA-3 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | FONTANA-3
Pre-Award Financial - HUM00091711 | Billing Calendar Received | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | Calendar Released | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | Care Designations completed | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | Feasibility w/Documents received | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | Final Budget | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | Intake Form Completed | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | PAF routed | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | PAN Released | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | PI approved Budget | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | Planning Meeting Completed | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | Planning Meeting Request Sent | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | Request MCRU Budget | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | Sponsor Reach out | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00091711 | UFA Completed | Role | CTSU Finance |  |  |  | N | 00091711
Pre-Award Financial - HUM00129276 | Budget Negotiations | Role | CTSU Finance |  |  |  | N | 00129276
Pre-Award Financial - HUM00129276 | Calendar Released | Role | CTSU Finance |  |  |  | N | 00129276
Pre-Award Financial - HUM00129276 | Created CTRF & "Notify ORSP" | Role | CTSU Finance |  |  | 2017-05-08 | N | 00129276
Pre-Award Financial - HUM00129276 | Feasibility approved/CRAO Notified | Role | CTSU Finance |  |  | 2017-05-08 | N | 00129276
Pre-Award Financial - HUM00129276 | Feasibility w/Documents received | Role | CTSU Finance |  |  | NA | Y | 00129276
Pre-Award Financial - HUM00129276 | Final Budget | Role | CTSU Finance |  |  |  | N | 00129276
Pre-Award Financial - HUM00129276 | Intake Form Completed | Role | CTSU Finance |  |  | NA | Y | 00129276
Pre-Award Financial - HUM00129276 | Internal Budget Finished | Role | CTSU Finance |  |  |  | N | 00129276
Pre-Award Financial - HUM00129276 | OnCore Budget Build | Role | CTSU Finance |  |  |  | N | 00129276
Pre-Award Financial - HUM00129276 | PAF routed | Role | CTSU Finance |  |  |  | N | 00129276
Pre-Award Financial - HUM00129276 | PAN Released | Role | CTSU Finance |  |  |  | N | 00129276
Pre-Award Financial - HUM00129276 | PI approved Budget | Role | CTSU Finance |  |  |  | N | 00129276
Pre-Award Financial - HUM00129276 | Planning Meeting Request Sent | Role | CTSU Finance |  |  | 2017-05-08 | N | 00129276
Pre-Award Financial - HUM00129276 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00129276
Pre-Award Financial - HUM00129276 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | 2017-05-08 | N | 00129276
Pre-Award Financial - HUM00129276 | Sponsor Reach out | Role | CTSU Finance |  |  | NA | Y | 00129276
Pre-Award Financial - HUM00129276 | UFA Completed | Role | CTSU Finance |  |  | NA | Y | 00129276
Pre-Award Financial - PLT-INF24-001 | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00135388
Pre-Award Financial - PLT-INF24-001 | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00135388
Pre-Award Financial - SCHIOPU-1 | Initiate Post-Award Task List | Role | CTSU Finance |  |  |  | N | SCHIOPU-1
Pre-Award Financial - SLS-III | Request MCRU Budget | Role | CTSU Finance |  |  | NA | Y | 00131953
Pre-Award Financial - SLS-III | Request Research Pharmacy Budget | Role | CTSU Finance |  |  | NA | Y | 00131953
Spec Update Req. 120786 (KLV) Adding 2-WPostDose time point that was missed | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00120786
Spec Update Req. 120786 (KLV) Adding 2-WPostDose time point that was missed | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00120786
Spec Update Req. 120786 (KLV) Adding 2-WPostDose time point that was missed | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00120786
Spec Update Req. 120786 (KLV) Adding 2-WPostDose time point that was missed | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00120786
Spec Update Req. 120786 (KLV) Adding 2-WPostDose time point that was missed | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance |  |  | NA | Y | 00120786
Spec. Update for 118070 (KLV) per office hours discussion (8.11.17) | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00118070
Spec. Update for 118070 (KLV) per office hours discussion (8.11.17) | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00118070
Spec. Update for 118070 (KLV) per office hours discussion (8.11.17) | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00118070
Spec. Update for 118070 (KLV) per office hours discussion (8.11.17) | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance |  |  | NA | Y | 00118070
Spec. Update for 118070 (KLV) per office hours discussion (8.11.17) | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00118070
Spec. Updates for 108077 (KLV) per review @ office hours on 8.11.17 | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00108077
Spec. Updates for 108077 (KLV) per review @ office hours on 8.11.17 | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00108077
Spec. Updates for 108077 (KLV) per review @ office hours on 8.11.17 | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00108077
Spec. Updates for 108077 (KLV) per review @ office hours on 8.11.17 | ** Request(s) to Add Unscheduled Procedure(s) | Role | CTSU Finance |  |  | NA | Y | 00108077
Spec. Updates for 108077 (KLV) per review @ office hours on 8.11.17 | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00108077
Spec. Updates for 121569 (KLV) : add unsched. procedures & clarify SF details | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00121569
Spec. Updates for 121569 (KLV) : add unsched. procedures & clarify SF details | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00121569
Spec. Updates for 121569 (KLV) : add unsched. procedures & clarify SF details | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00121569
Spec. Updates for 121569 (KLV) : add unsched. procedures & clarify SF details | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00121569
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | ** Footnote Request(s) | Role | CTSU Finance |  |  | NA | Y | 00133290
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | ** Other Request(s) | Role | CTSU Finance |  |  | NA | Y | 00133290
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | ** Request for Clarification | Role | CTSU Finance |  |  | NA | Y | 00133290
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | ** Request to Rename for Clarity | Role | CTSU Finance |  |  | NA | Y | 00133290
Spec. Updates for 133290 (KLV, 8.18.17) : adding unscheduled procedures per contract | ** Structural Edits | Role | CTSU Finance |  |  | NA | Y | 00133290
Open to Accrual - 00121967 | Adequate Equipment and Supplies Available | User | Chen, Tina |  |  | NA | Y | 00121967
Open to Accrual - 00121967 | Investigational Drug/Device Supplies Available | User | Chen, Tina |  |  | NA | Y | 00121967
Open to Accrual - 00121967 | MiChart Verifications | User | Chen, Tina |  |  | NA | Y | 00121967
Open to Accrual - 00121967 | Other Personnel Notified | User | Chen, Tina |  |  | NA | Y | 00121967
Open to Accrual - 00121967 | Provisions for Support and Services Finalized | User | Chen, Tina |  |  | NA | Y | 00121967
Open to Accrual - 00121967 | Sponsor/Organizing Group Approval Granted for Initiation of Study | User | Chen, Tina |  |  | NA | Y | 00121967
Open to Accrual - 00121967 | Study Files Established | User | Chen, Tina |  |  | NA | Y | 00121967
Open to Accrual - 00121967 | Study Team Roles/Responsibilities Finalized | User | Chen, Tina |  |  | NA | Y | 00121967
Open to Accrual - 00122489 | Adequate Equipment and Supplies Available | User | Chen, Tina |  |  | 2017-05-18 | N | 00122489
Open to Accrual - 00122489 | IRB Approval | User | Chen, Tina |  |  | 2017-04-27 | N | 00122489
Open to Accrual - 00122489 | Investigational Drug/Device Supplies Available | User | Chen, Tina |  |  | 2017-05-18 | N | 00122489
Open to Accrual - 00122489 | MiChart Verifications | User | Chen, Tina |  |  | 2017-06-08 | N | 00122489
Open to Accrual - 00122489 | Other Personnel Notified | User | Chen, Tina |  |  | 2017-05-18 | N | 00122489
Open to Accrual - 00122489 | Provisions for Support and Services Finalized | User | Chen, Tina |  |  | 2017-05-18 | N | 00122489
Open to Accrual - 00122489 | Sponsor/Organizing Group Approval Granted for Initiation of Study | User | Chen, Tina |  |  | 2017-05-18 | N | 00122489
Open to Accrual - 00122489 | Study Files Established | User | Chen, Tina |  |  | 2017-05-18 | N | 00122489
Open to Accrual - 00122489 | Study Team Roles/Responsibilities Finalized | User | Chen, Tina |  |  | 2017-05-18 | N | 00122489
Open to Accrual - 314-PARK | IRB Approval | User | Chen, Tina |  |  |  | N | 314-PARK
Open to Accrual - 314-PARK | Study Files Established | User | Chen, Tina |  |  |  | N | 314-PARK
Calendar Build - 50-HUMMEL | Care Designations -Corvia Reduced LAP | User | Cohan, Lynn |  |  | 2017-05-09 | N | 00129162
CTSU Pre-Award v2 - 00132705 2 | Billing Calendar Received | User | Dahlgren, Molly |  |  |  | N | 00132705
CTSU Pre-Award v2 - 00132705 2 | Care Designations completed | User | Dahlgren, Molly |  |  |  | N | 00132705
CTSU Pre-Award v2 - 00132705 2 | Created CTRF & "Notify ORSP" | User | Dahlgren, Molly |  |  |  | N | 00132705
CTSU Pre-Award v2 - 00132705 2 | UFA Completed | User | Dahlgren, Molly |  |  |  | N | 00132705
Open to Accrual - 00124839 | Budget Finalized | User | Dahlgren, Molly |  |  | 2017-06-22 | N | 00124839
Calendar Build - 00121967 | Calendar Completed and Ready for CTSU Finance to Build Budget | User | Dickelman, James |  |  | 2017-06-01 | N | 00121967
Calendar Build - 00122489 | Calendar Completed and Ready for CTSU Finance to Build Budget | User | Dickelman, James |  |  | 2017-06-01 | N | 00122489
Open to Accrual - 00118070 | Project Award Notice (PAN) Received | User | Dickelman, James |  |  | 2017-05-18 | N | 00118070
Open to Accrual - 00121967 | Budget Finalized | User | Dickelman, James |  |  | NA | Y | 00121967
Open to Accrual - 00121967 | Contract Executed | User | Dickelman, James |  |  | NA | Y | 00121967
Open to Accrual - 00121967 | Project Award Notice (PAN) Received | User | Dickelman, James |  |  | NA | Y | 00121967
Open to Accrual - 00122489 | Budget Finalized | User | Dickelman, James |  |  | 2017-06-01 | N | 00122489
Open to Accrual - 00122489 | Contract Executed | User | Dickelman, James |  |  | 2017-06-01 | N | 00122489
Open to Accrual - 00122489 | Project Award Notice (PAN) Received | User | Dickelman, James |  |  | 2017-06-01 | N | 00122489
Open to Accrual - 192-ALAM | Project Award Notice (PAN) Received | User | Dickelman, James |  |  |  | N | 192-ALAM
Open to Accrual - 314-PARK | Contract Executed | User | Dickelman, James |  |  |  | N | 314-PARK
Open to Accrual - 314-PARK | Project Award Notice (PAN) Received | User | Dickelman, James |  |  |  | N | 314-PARK
Pre-Award Financial - 00118070 | Billing Calendar Received | User | Dickelman, James |  |  | NA | Y | 00118070
Pre-Award Financial - 00118070 | Calendar Released | User | Dickelman, James |  |  | 2017-06-09 | N | 00118070
Pre-Award Financial - 00118070 | Care Designations completed | User | Dickelman, James |  |  | NA | Y | 00118070
Pre-Award Financial - 00118070 | Final Budget | User | Dickelman, James |  |  | NA | Y | 00118070
Pre-Award Financial - 00118070 | PAN Released | User | Dickelman, James |  |  | 2017-05-11 | N | 00118070
Open to Accrual - 4033CYTOKINETICS-GOUTMAN | FDA Approval | User | Duell, Jayna |  |  | NA | Y | 00130639
Open to Accrual - 4033CYTOKINETICS-GOUTMAN | SIV occurred | User | Duell, Jayna |  |  | 2017-08-17 | N | 00130639
CTSU Pre-Award v2 - 412-NASR | Sponsor Reach out | User | Earwood, Rebecca |  |  |  | N | 412-NASR
CTSU Pre-Award v2 - 412-NASR | UFA Completed | User | Earwood, Rebecca |  |  | 2017-08-11 | N | 412-NASR
Pre-Award Financial - 198-LUCKRITZ | Created CTRF & "Notify ORSP" | User | Earwood, Rebecca |  |  | 2017-08-25 | N | 198-LUCKRITZ
Open to Accrual - 239-KORLEY | Adequate Equipment and Supplies Available | User | Falk, Hayley |  |  |  | N | 00129045
Open to Accrual - 239-KORLEY | IRB Approval | User | Falk, Hayley |  |  |  | N | 00129045
Open to Accrual - 239-KORLEY | Investigational Drug/Device Supplies Available | User | Falk, Hayley |  |  |  | N | 00129045
Open to Accrual - 239-KORLEY | MiChart Verifications | User | Falk, Hayley |  |  |  | N | 00129045
Open to Accrual - 239-KORLEY | Other Personnel Notified | User | Falk, Hayley |  |  |  | N | 00129045
Open to Accrual - 239-KORLEY | Provisions for Support and Services Finalized | User | Falk, Hayley |  |  |  | N | 00129045
Open to Accrual - 239-KORLEY | Study Files Established | User | Falk, Hayley |  |  |  | N | 00129045
Open to Accrual - 239-KORLEY | Study Team Roles/Responsibilities Finalized | User | Falk, Hayley |  |  |  | N | 00129045
Pre-Award Financial - 239-KORLEY | PI Signoff in OnCore | User | Falk, Hayley |  |  |  | N | 00129045
Calendar & Budget Retrofit - 00082356 | Questions | User | Farmer, Amber |  |  | NA | Y | 00082356
Calendar & Budget Retrofit - 00089260 | Questions | User | Farmer, Amber |  |  | NA | Y | 00089260
Open to Accrual - 00120786 | Budget Finalized | User | Fitzpatrick, Patti |  |  | 2017-08-09 | N | 00120786
Open to Accrual - 00120786 | Project Award Notice (PAN) Received | User | Fitzpatrick, Patti |  |  | 2017-07-07 | N | 00120786
Open to Accrual - 268-NEUMAR | Adequate Equipment and Supplies Available | User | Fowler, Jennifer |  |  |  | N | 268-NEUMAR
Open to Accrual - 268-NEUMAR | FDA Approval | User | Fowler, Jennifer |  |  |  | N | 268-NEUMAR
Open to Accrual - 268-NEUMAR | IRB Approval | User | Fowler, Jennifer |  |  |  | N | 268-NEUMAR
Open to Accrual - 268-NEUMAR | MiChart Verifications | User | Fowler, Jennifer |  |  |  | N | 268-NEUMAR
Open to Accrual - 268-NEUMAR | Other Personnel Notified | User | Fowler, Jennifer |  |  |  | N | 268-NEUMAR
Open to Accrual - 268-NEUMAR | Provisions for Support and Services Finalized | User | Fowler, Jennifer |  |  |  | N | 268-NEUMAR
Open to Accrual - 268-NEUMAR | Sponsor/Organizing Group Approval Granted for Initiation of Study | User | Fowler, Jennifer |  |  |  | N | 268-NEUMAR
Open to Accrual - 268-NEUMAR | Study Files Established | User | Fowler, Jennifer |  |  |  | N | 268-NEUMAR
Open to Accrual - 268-NEUMAR | Study Team Roles/Responsibilities Finalized | User | Fowler, Jennifer |  |  |  | N | 268-NEUMAR
Calendar Build - 00124859 | Calendar Completed and Ready for CTSU Finance to Build Budget | User | Gladkowski, Ginger |  |  | 2017-03-09 | N | 00124859
Calendar & Budget Retrofit - 00124702 | Questions | User | Gorowski, Teresa |  |  | NA | Y | 00124702
Calendar & Budget Retrofit - 00124722 | Questions | User | Gorowski, Teresa |  |  | NA | Y | 00124722
Calendar & Budget Retrofit - 00131463 | Questions | User | Gorowski, Teresa |  |  | NA | Y | 00131463
CTSU Pre-Award v2 - 00132705 2 | Intake Form Completed | User | Harper, Tamara |  |  |  | N | 00132705
CTSU Pre-Award - 336-KHANNA | Request MCRU Budget | User | Henry, Robin |  |  | NA | Y | 00133684
Pre-Award Financial - 170-SCHIOPU | Request MCRU Budget | User | Henry, Robin |  |  | NA | Y | 00134035
Pre-Award Financial - 190-SCHIOPU | Request MCRU Budget | User | Henry, Robin |  |  | NA | Y | 00134443
Pre-Award Financial - 211-HIGGINS | Budget Negotiations | User | Henry, Robin |  |  | NA | Y | 00128325
Pre-Award Financial - 211-HIGGINS | PAN Released | User | Henry, Robin |  |  | NA | Y | 00128325
Pre-Award Financial - 211-HIGGINS | Request MCRU Budget | User | Henry, Robin |  |  | NA | Y | 00128325
Pre-Award Financial - 23-GUPTA | Request MCRU Budget | User | Henry, Robin |  |  | NA | Y | 00134236
Pre-Award Financial - 278-CONJEEVARAM | Request MCRU Budget | User | Henry, Robin |  |  | NA | Y | 00133341
Pre-Award Financial - 56-RAO | Request MCRU Budget | User | Henry, Robin |  |  | NA | Y | 00133286
Pre-Award Financial - FONTANA-1 | Request MCRU Budget | User | Henry, Robin |  |  | NA | Y | 00133153
Calendar Build - 50-HUMMEL | Care designations entered ( per PI determinations) | User | Hess, Aaron |  |  |  | N | 00129162
Calendar Build - 50-HUMMEL | Feedback incorporated / resolved | User | Hess, Aaron |  |  |  | N | 00129162
Calendar Build - 50-HUMMEL | ‘Build Notes’ documentation ( w. CRAO comments, as needed ) attached ( as protocol doc ) +/- other supplemental documentation | User | Hess, Aaron |  |  | 2017-05-05 | N | 00129162
Calendar Build - 52-AARONSON | Calendar Build Request sent to Nimblify | User | Hess, Aaron |  |  | 2017-04-03 | N | 00128761
Calendar Build - 52-AARONSON | Calendar Completed and Ready for CTSU Finance to Build Budget | User | Hess, Aaron |  |  | 2017-05-04 | N | 00128761
Calendar Build - 52-AARONSON | Care designations entered ( per PI determinations) | User | Hess, Aaron |  |  | 2017-05-04 | N | 00128761
Calendar Build - 52-AARONSON | QCT Checklist : completed in OnCore | User | Hess, Aaron |  |  | 2017-05-04 | N | 00128761
Calendar Build - 52-AARONSON | Specification has been Imported / Michiganized and is ready for Finance / Study team review, feedback and determination of care designations | User | Hess, Aaron |  |  | 2017-04-17 | N | 00128761
Calendar Build - 52-AARONSON | ‘Build Notes’ documentation ( w. CRAO comments, as needed ) attached ( as protocol doc ) +/- other supplemental documentation | User | Hess, Aaron |  |  | 2017-04-17 | N | 00128761
Calendaring : Initial Calendar Build - | Complete SVS & Pricing List ( Built & Coded ) | User | Hess, Aaron |  |  | NA | Y | 103-GAGNIER
Calendaring : Initial Calendar Build - 00109407 | CRAO Approval Issue & Documented | User | Hess, Aaron |  |  |  | N | 00109407
Calendaring : Initial Calendar Build - 00109407 | Complete MCA / QCT | User | Hess, Aaron |  |  | NA | Y | 00109407
Calendaring : Initial Calendar Build - 00118070 | Assign to Analyst | User | Hess, Aaron |  |  | 2017-04-18 | N | 00118070
Calendaring : Initial Calendar Build - 00118070 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron |  |  | 2017-04-06 | N | 00118070
Calendaring : Initial Calendar Build - 00124202 | CRAO Approval Issue & Documented | User | Hess, Aaron |  |  |  | N | 00124202
Calendaring : Initial Calendar Build - 00124839 | CRAO Approval Issue & Documented | User | Hess, Aaron |  |  |  | N | 00124839
Calendaring : Initial Calendar Build - 00128743 | Feasibility Approval Notice Received 04/17/17 | User | Hess, Aaron |  |  | 2017-04-17 | N | 00128743
Calendaring : Initial Calendar Build - 00131837 | Complete MCA / QCT | User | Hess, Aaron |  |  | NA | Y | 00131837
Calendaring : Initial Calendar Build - 190-SCHIOPU | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron |  |  | 2017-06-30 | N | 00134443
Calendaring : Initial Calendar Build - 205-KHANNA | CRAO Approval Issue & Documented | User | Hess, Aaron |  |  |  | N | 00132200
Calendaring : Initial Calendar Build - 227-STEIGERWALT 3 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron |  |  | 2017-08-10 | N | 227-STEIGERWALT
Calendaring : Initial Calendar Build - 295-ARNEDT | Feasibility Approval Notice Received | User | Hess, Aaron |  |  | 2017-06-27 | N | 00130209
Calendaring : Initial Calendar Build - 295-ARNEDT | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron |  |  | 2017-06-27 | N | 00130209
Calendaring : Initial Calendar Build - 332-BELLOLI | CRAO Approval Issue & Documented | User | Hess, Aaron |  |  |  | N | 332-BELLOLI
Calendaring : Initial Calendar Build - 384-MODY | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron |  |  | 2017-08-10 | N | 00134459
Calendaring : Initial Calendar Build - CIP-1403 | Complete Calendar ( ie. Ready for Financials ) | User | Hess, Aaron |  |  | 2017-05-02 | N | 00128253
Calendaring : Initial Calendar Build - CIP-1403 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Hess, Aaron |  |  | 2017-04-28 | N | 00128253
Calendaring : Initial Calendar Build - CIP-1403 | Make Updates | User | Hess, Aaron |  |  | 2017-05-01 | N | 00128253
Calendaring : Initial Calendar Build - FENNER-1 | CRAO Approval Issue & Documented | User | Hess, Aaron |  |  |  | N | FENNER-1
Calendaring : Migration - 000127913 | Acknowledge | User | Hess, Aaron |  |  | 2017-05-08 | N | 00127913
Calendaring : Migration - 000127913 | Assign to Analyst | User | Hess, Aaron |  |  | 2017-04-17 | N | 00127913
Calendaring : Migration - 000127913 | Complete Calendar ( ie. Flag as Ready for Financials ) | User | Hess, Aaron |  |  | 2017-05-04 | N | 00127913
Calendaring : Migration - 000127913 | Import + Michiganize, including Entry of Care Designations & Comments per Current Approved MBECT Calendar | User | Hess, Aaron |  |  | 2017-04-17 | N | 00127913
Calendaring : Migration - 00081004 | Submit Calendar Build Request and Docs to Nimblify | User | Hess, Aaron |  |  | 2017-03-06 | N | 00081004
Calendaring : Amendment Checklist & Process - 00115982 | Diane Hilfinger | User | Hilfinger, Diane |  |  | 2017-06-28 | N | 00115982
Calendaring : Amendment Checklist & Process - 00105691 | ** Items/Services : Addition or Removal of Procedures / Events | User | Hodges, Lynda |  |  | NA | Y | 00105691
Calendaring : Amendment Checklist & Process - 00105691 | ** Other | User | Hodges, Lynda |  |  | NA | Y | 00105691
Calendaring : Amendment Checklist & Process - 00105691 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Hodges, Lynda |  |  | NA | Y | 00105691
Calendaring : Amendment Checklist & Process - 00105691 | ** Visit Tolerance Edits | User | Hodges, Lynda |  |  | NA | Y | 00105691
Calendaring : Amendment Checklist & Process - 00105691 | ** Visits : Addition or Removal of Time Points | User | Hodges, Lynda |  |  | NA | Y | 00105691
Calendaring : Amendment Checklist & Process - 00105691 | Request Care Designations | User | Hodges, Lynda |  |  | NA | Y | 00105691
Calendaring : Amendment Checklist & Process - 00105691 | Update RSH Source in MBECT | User | Hodges, Lynda |  |  | NA | Y | 00105691
Calendaring : Amendment Checklist & Process - 00108139 | ** Other | User | Hodges, Lynda |  |  | NA | Y | 00108139
Calendaring : Amendment Checklist & Process - 00108139 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Hodges, Lynda |  |  | NA | Y | 00108139
Calendaring : Amendment Checklist & Process - 00108139 | ** Visit Tolerance Edits | User | Hodges, Lynda |  |  | NA | Y | 00108139
Calendaring : Amendment Checklist & Process - 00108139 | Update RSH Source in MBECT | User | Hodges, Lynda |  |  | NA | Y | 00108139
Calendaring : Amendment Checklist & Process - 00110881 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Hodges, Lynda |  |  | NA | Y | 00110881
Calendaring : Amendment Checklist & Process - 00119399 2 | ** Footnote Edits | User | Hodges, Lynda |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 2 | ** Items/Services : Addition or Removal of Procedures / Events | User | Hodges, Lynda |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 2 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Hodges, Lynda |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 2 | ** Other | User | Hodges, Lynda |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 2 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Hodges, Lynda |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 2 | ** Visit Tolerance Edits | User | Hodges, Lynda |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 2 | ** Visits : Addition or Removal of Time Points | User | Hodges, Lynda |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 2 | Complete Calendar and Document Approval | User | Hodges, Lynda |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 2 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Hodges, Lynda |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 2 | Request Care Designations | User | Hodges, Lynda |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119399 2 | Update RSH Source in MBECT | User | Hodges, Lynda |  |  | NA | Y | 00119399
Calendaring : Amendment Checklist & Process - 00119926 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Hodges, Lynda |  |  | NA | Y | 00119926
Calendaring : Amendment Checklist & Process - 00119926 | ** Visit Tolerance Edits | User | Hodges, Lynda |  |  | NA | Y | 00119926
Calendaring : Amendment Checklist & Process - 00119926 | ** Visits : Addition or Removal of Time Points | User | Hodges, Lynda |  |  | NA | Y | 00119926
Calendaring : Amendment Checklist & Process - 00122815 | ** Items/Services : Addition or Removal of Procedures / Events | User | Hodges, Lynda |  |  | NA | Y | 00122815
Calendaring : Amendment Checklist & Process - 00122815 | ** Other | User | Hodges, Lynda |  |  | NA | Y | 00122815
Calendaring : Amendment Checklist & Process - 00122815 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Hodges, Lynda |  |  | NA | Y | 00122815
Calendaring : Amendment Checklist & Process - 00122815 | ** Visit Tolerance Edits | User | Hodges, Lynda |  |  | NA | Y | 00122815
Calendaring : Amendment Checklist & Process - 00122815 | Update RSH Source in MBECT | User | Hodges, Lynda |  |  | NA | Y | 00122815
Calendaring : Amendment Checklist & Process - 00123231 | ** Footnote Edits | User | Hodges, Lynda |  |  | NA | Y | 00123231
Calendaring : Amendment Checklist & Process - 00123231 | ** Items/Services : Addition or Removal of Procedures / Events | User | Hodges, Lynda |  |  | NA | Y | 00123231
Calendaring : Amendment Checklist & Process - 00123231 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Hodges, Lynda |  |  | NA | Y | 00123231
Calendaring : Amendment Checklist & Process - 00123231 | ** Other | User | Hodges, Lynda |  |  | NA | Y | 00123231
Calendaring : Amendment Checklist & Process - 00123231 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Hodges, Lynda |  |  | NA | Y | 00123231
Calendaring : Amendment Checklist & Process - 00123231 | ** Visit Tolerance Edits | User | Hodges, Lynda |  |  | NA | Y | 00123231
Calendaring : Amendment Checklist & Process - 00123231 | ** Visits : Addition or Removal of Time Points | User | Hodges, Lynda |  |  | NA | Y | 00123231
Calendaring : Amendment Checklist & Process - 00123231 | Complete Calendar and Document Approval | User | Hodges, Lynda |  |  | NA | Y | 00123231
Calendaring : Amendment Checklist & Process - 00123231 | Request Care Designations | User | Hodges, Lynda |  |  | NA | Y | 00123231
Calendaring : Amendment Checklist & Process - 00123231 | Update RSH Source in MBECT | User | Hodges, Lynda |  |  | NA | Y | 00123231
Calendaring : Initial Calendar Build - 147 | Complete SVS & Pricing List ( Built & Coded ) | User | Hodges, Lynda |  |  | 2017-03-23 | N | 00128322
Calendaring : Initial Calendar Build - 205-HIGGINS | CRAO Approval Issue & Documented | User | Hodges, Lynda |  |  |  | N | 205-HIGGINS
Calendaring : Initial Calendar Build - 351-HIGGINS | CRAO Approval Issue & Documented | User | Hodges, Lynda |  |  |  | N | 00134870
Calendaring : Initial Calendar Build - 351-HIGGINS | Make Updates | User | Hodges, Lynda |  |  | NA | Y | 00134870
Calendaring : Initial Calendar Build - 358-SHELLHAAS | CRAO Approval Issue & Documented | User | Hodges, Lynda |  |  |  | N | 00133339
Open to Accrual - 00123861 | MiChart Verifications | User | Huffman, Kate |  |  | 2017-05-18 | N | 00123861
Open to Accrual - 00124920 | FDA Approval | User | Huffman, Kate |  |  | NA | Y | 00124920
Open to Accrual - 00120349 | Adequate Equipment and Supplies Available | User | Kruse, Dawn |  |  | 2017-07-18 | N | 00120349
Open to Accrual - 00120349 | Investigational Drug/Device Supplies Available | User | Kruse, Dawn |  |  | 2017-07-18 | N | 00120349
Open to Accrual - 00120349 | Other Personnel Notified | User | Kruse, Dawn |  |  | 2017-07-18 | N | 00120349
Open to Accrual - 00120349 | Provisions for Support and Services Finalized | User | Kruse, Dawn |  |  | 2017-07-18 | N | 00120349
Open to Accrual - 00120349 | Sponsor/Organizing Group Approval Granted for Initiation of Study | User | Kruse, Dawn |  |  | 2017-07-18 | N | 00120349
Open to Accrual - 00120349 | Study Files Established | User | Kruse, Dawn |  |  | 2017-07-18 | N | 00120349
Open to Accrual - 00120349 | Study Team Roles/Responsibilities Finalized | User | Kruse, Dawn |  |  | 2017-07-18 | N | 00120349
Calendar Build - 00121967 | CRAO Approval issued / documented | User | LaVasseur, Kristen |  |  | 2017-03-14 | N | 00121967
Calendar Build - 00121967 | Care designations entered ( per PI determinations / current approved MBECT BC ) | User | LaVasseur, Kristen |  |  | 2017-03-14 | N | 00121967
Calendar Build - 00121967 | Specification has been Imported / Michiganized | User | LaVasseur, Kristen |  |  | 2017-03-14 | N | 00121967
Calendar Build - 00121967 | ‘Build Notes’ documentation ( w. CRAO comments, as needed ) attached ( as protocol doc ) +/- other supplemental documentation | User | LaVasseur, Kristen |  |  | 2017-03-14 | N | 00121967
Calendar Build - 00122489 | CRAO Approval issued / documented | User | LaVasseur, Kristen |  |  | 2017-03-14 | N | 00122489
Calendar Build - 00122489 | Specification has been Imported / Michiganized and is ready for Finance / Study team review, feedback and determination of care designations | User | LaVasseur, Kristen |  |  | 2017-03-12 | N | 00122489
Calendar Build - 00122489 | ‘Build Notes’ documentation ( w. CRAO comments, as needed ) attached ( as protocol doc ) +/- other supplemental documentation | User | LaVasseur, Kristen |  |  | 2017-03-12 | N | 00122489
Calendar Build - 00124859 | CRAO Approval issued / documented | User | LaVasseur, Kristen |  |  | 2017-03-09 | N | 00124859
Calendar Build - 00124859 | Care designations entered ( per PI determinations) | User | LaVasseur, Kristen |  |  | 2017-03-09 | N | 00124859
Calendar Build - 00124859 | Specification has been Imported / Michiganized and is ready for Finance / Study team review, feedback and determination of care designations | User | LaVasseur, Kristen |  |  | 2017-03-09 | N | 00124859
Calendar Build - 00124859 | ‘Build Notes’ documentation ( w. CRAO comments, as needed ) attached ( as protocol doc ) +/- other supplemental documentation | User | LaVasseur, Kristen |  |  | 2017-03-09 | N | 00124859
Calendaring : Initial Build - 00126224 | Attach Build Notes ( as Protocol Doc ) | User | LaVasseur, Kristen |  |  | 2017-05-04 | N | 00126224
Calendaring : Initial Build - 00126224 | Complete Calendar ( ie. Ready for Financials ) | User | LaVasseur, Kristen |  |  | 2017-05-04 | N | 00126224
Calendaring : Initial Build - 00126224 | Complete SVS & Pricing List ( Built & Coded ) | User | LaVasseur, Kristen |  |  | 2017-02-19 | N | 00126224
Calendaring : Initial Build - 00126224 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | LaVasseur, Kristen |  |  | 2017-02-19 | N | 00126224
Calendaring : Initial Build - 00126224 | Make Updates | User | LaVasseur, Kristen |  |  | NA | Y | 00126224
Calendaring : Initial Build - 00126224 | Nimblify Build is Complete & Ready for Import | User | LaVasseur, Kristen |  |  | 2017-02-19 | N | 00126224
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | ** Other Request(s) | User | LaVasseur, Kristen |  |  | 2017-04-12 | N | 00066077
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | Assign to Analyst | User | LaVasseur, Kristen |  |  | 2017-04-12 | N | 00066077
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | Make Update(s) | User | LaVasseur, Kristen |  |  | 2017-04-12 | N | 00066077
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | Submit Update Request(s) | User | LaVasseur, Kristen |  |  | 2017-04-12 | N | 00066077
CTSU Pre-Award v2 - 00132705 2 | Feasibility approved/CRAO Notified | User | Miller, Diana |  |  |  | N | 00132705
CTSU Pre-Award v2 - 00132705 2 | Feasibility w/Documents received | User | Miller, Diana |  |  |  | N | 00132705
CTSU Pre-Award v2 - 00132705 2 | Planning Meeting Request Sent | User | Miller, Diana |  |  |  | N | 00132705
Open to Accrual - 00124839 | MiChart Verifications | User | Miller, Diana |  |  | 2017-06-22 | N | 00124839
Calendaring : Amendment Checklist & Process - 00094136 | ** Other | User | Munasinghe, Sadeepa |  |  | NA | Y | 00094136
Calendaring : Amendment Checklist & Process - 00094136 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Munasinghe, Sadeepa |  |  | NA | Y | 00094136
Calendaring : Amendment Checklist & Process - 00094136 | ** Visit Tolerance Edits | User | Munasinghe, Sadeepa |  |  | NA | Y | 00094136
Calendaring : Amendment Checklist & Process - 00094136 | ** Visits : Addition or Removal of Time Points | User | Munasinghe, Sadeepa |  |  | NA | Y | 00094136
Calendaring : Amendment Checklist & Process - 00094136 | Request Care Designations | User | Munasinghe, Sadeepa |  |  | NA | Y | 00094136
Calendaring : Amendment Checklist & Process - 00121569 2 | ** Footnote Edits | User | Munasinghe, Sadeepa |  |  | NA | Y | 00121569
Calendaring : Amendment Checklist & Process - 00121569 2 | ** Items/Services : Addition or Removal of Procedures / Events | User | Munasinghe, Sadeepa |  |  | NA | Y | 00121569
Calendaring : Amendment Checklist & Process - 00121569 2 | ** Other | User | Munasinghe, Sadeepa |  |  | NA | Y | 00121569
Calendaring : Amendment Checklist & Process - 00121569 2 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Munasinghe, Sadeepa |  |  | NA | Y | 00121569
Calendaring : Amendment Checklist & Process - 00121569 2 | ** Visit Tolerance Edits | User | Munasinghe, Sadeepa |  |  | NA | Y | 00121569
Calendaring : Amendment Checklist & Process - 00121569 2 | Request Care Designations | User | Munasinghe, Sadeepa |  |  | NA | Y | 00121569
Calendaring : Amendment Checklist & Process - 00121569 2 | Update RSH Source in MBECT | User | Munasinghe, Sadeepa |  |  | NA | Y | 00121569
Calendaring : Initial Calendar Build - 00108880 | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  |  | N | 00108880
Calendaring : Initial Calendar Build - 00121569 2 | Assign to Analyst | User | Munasinghe, Sadeepa |  |  | 2017-05-19 | N | 00121569
Calendaring : Initial Calendar Build - 00121569 2 | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa |  |  | 2017-06-30 | N | 00121569
Calendaring : Initial Calendar Build - 00121569 2 | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  |  | N | 00121569
Calendaring : Initial Calendar Build - 00121569 2 | Complete MCA / QCT | User | Munasinghe, Sadeepa |  |  | 2017-06-30 | N | 00121569
Calendaring : Initial Calendar Build - 00121569 2 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa |  |  | 2017-07-10 | N | 00121569
Calendaring : Initial Calendar Build - 00121569 2 | Make Updates | User | Munasinghe, Sadeepa |  |  | NA | Y | 00121569
Calendaring : Initial Calendar Build - 00121569 2 | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa |  |  | 2017-06-30 | N | 00121569
Calendaring : Initial Calendar Build - 00126707 | Make Updates | User | Munasinghe, Sadeepa |  |  | NA | Y | 00126707
Calendaring : Initial Calendar Build - 00131837 | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  | 2017-08-15 | N | 00131837
Calendaring : Initial Calendar Build - 00131904 | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  | 2017-08-18 | N | 00131904
Calendaring : Initial Calendar Build - 00132363 | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  |  | N | 00132363
Calendaring : Initial Calendar Build - 110-SCHIOPU | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  |  | N | 00134444
Calendaring : Initial Calendar Build - 116-BRUMMETT | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  |  | N | 00129418
Calendaring : Initial Calendar Build - 116-BRUMMETT | Make Updates | User | Munasinghe, Sadeepa |  |  | NA | Y | 00129418
Calendaring : Initial Calendar Build - 140-CHUNG | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  |  | N | 00133613
Calendaring : Initial Calendar Build - 147-SCHIOPU | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  | 2017-08-03 | N | 00131329
Calendaring : Initial Calendar Build - 147-SCHIOPU | Make Updates | User | Munasinghe, Sadeepa |  |  | NA | Y | 00131329
Calendaring : Initial Calendar Build - 158-PIPE | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  | 2017-07-31 | N | 00131463
Calendaring : Initial Calendar Build - 158-PIPE | Make Updates | User | Munasinghe, Sadeepa |  |  | NA | Y | 00131463
Calendaring : Initial Calendar Build - 192-ALAM | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  |  | N | 192-ALAM
Calendaring : Initial Calendar Build - 198-LUCKRITZ | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  |  | N | 198-LUCKRITZ
Calendaring : Initial Calendar Build - 203-ELSE | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  |  | N | 00132173
Calendaring : Initial Calendar Build - 243-MODY | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  |  | N | 00130968
Calendaring : Initial Calendar Build - 295-ARNEDT | Assign to Analyst | User | Munasinghe, Sadeepa |  |  | 2017-06-27 | N | 00130209
Calendaring : Initial Calendar Build - 295-ARNEDT | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa |  |  | 2017-07-18 | N | 00130209
Calendaring : Initial Calendar Build - 295-ARNEDT | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa |  |  | 2017-08-07 | N | 00130209
Calendaring : Initial Calendar Build - 295-ARNEDT | Complete MCA / QCT | User | Munasinghe, Sadeepa |  |  | 2017-06-29 | N | 00130209
Calendaring : Initial Calendar Build - 295-ARNEDT | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa |  |  | 2017-06-29 | N | 00130209
Calendaring : Initial Calendar Build - 295-ARNEDT | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa |  |  | 2017-07-18 | N | 00130209
Calendaring : Initial Calendar Build - 295-ARNEDT | Make Updates | User | Munasinghe, Sadeepa |  |  | 2017-08-07 | N | 00130209
Calendaring : Initial Calendar Build - 295-ARNEDT | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa |  |  | 2017-07-11 | N | 00130209
Calendaring : Initial Calendar Build - 336-KHANNA | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  |  | N | 00133684
Calendaring : Initial Calendar Build - 336-KHANNA | Make Updates | User | Munasinghe, Sadeepa |  |  | NA | Y | 00133684
Calendaring : Initial Calendar Build - 350-HIGGINS | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  |  | N | 00133054
Calendaring : Initial Calendar Build - 350-HIGGINS | Make Updates | User | Munasinghe, Sadeepa |  |  | NA | Y | 00133054
Calendaring : Initial Calendar Build - 357-GRANT 2 | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa |  |  | NA | Y | 00119336
Calendaring : Initial Calendar Build - 357-GRANT 2 | Make Updates | User | Munasinghe, Sadeepa |  |  | NA | Y | 00119336
Calendaring : Initial Calendar Build - 384-MODY | Assign to Analyst | User | Munasinghe, Sadeepa |  |  | 2017-08-10 | N | 00134459
Calendaring : Initial Calendar Build - 384-MODY | Attach Build Notes ( as Protocol Doc ) | User | Munasinghe, Sadeepa |  |  | 2017-08-22 | N | 00134459
Calendaring : Initial Calendar Build - 384-MODY | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  |  | N | 00134459
Calendaring : Initial Calendar Build - 384-MODY | Complete Calendar ( ie. Ready for Financials ) | User | Munasinghe, Sadeepa |  |  |  | N | 00134459
Calendaring : Initial Calendar Build - 384-MODY | Complete MCA / QCT | User | Munasinghe, Sadeepa |  |  | 2017-08-22 | N | 00134459
Calendaring : Initial Calendar Build - 384-MODY | Complete SVS & Pricing List ( Built & Coded ) | User | Munasinghe, Sadeepa |  |  | 2017-08-21 | N | 00134459
Calendaring : Initial Calendar Build - 384-MODY | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Munasinghe, Sadeepa |  |  |  | N | 00134459
Calendaring : Initial Calendar Build - 384-MODY | Make Updates | User | Munasinghe, Sadeepa |  |  |  | N | 00134459
Calendaring : Initial Calendar Build - 384-MODY | Nimblify Build is Complete & Ready for Import | User | Munasinghe, Sadeepa |  |  | 2017-08-22 | N | 00134459
Calendaring : Initial Calendar Build - 94-AUCHUS | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  | 2017-08-09 | N | 00129652
Calendaring : Initial Calendar Build - 94-AUCHUS | Make Updates | User | Munasinghe, Sadeepa |  |  | NA | Y | 00129652
Calendaring : Initial Calendar Build - P-3073HELFRICH | CRAO Approval Issue & Documented | User | Munasinghe, Sadeepa |  |  |  | N | 00128488
Calendaring : Initial Calendar Build - P-3073HELFRICH | Make Updates | User | Munasinghe, Sadeepa |  |  | NA | Y | 00128488
Calendaring : Specification Update Request(s) - 00126707 | Re-Complete Calendar | User | Munasinghe, Sadeepa |  |  | NA | Y | 00126707
Calendaring : Initial Calendar Build - 314-PARK | Update Designations in Excel per PI and Submit ( +/ - Feedback ) to CRAO | User | Munsey, Barbara |  |  |  | N | 314-PARK
Core Sponsor Documents for Study Feasibility & Start Up - General - 73-ALAM 2 | Initial contact with sponsor | User | Munsey, Barbara |  |  | 2017-07-13 | N | 73-ALAM
Open to Accrual - 192-ALAM | Budget Finalized | User | Munsey, Barbara |  |  |  | N | 192-ALAM
Open to Accrual - 192-ALAM | Contract Executed | User | Munsey, Barbara |  |  |  | N | 192-ALAM
Open to Accrual - 314-PARK | Budget Finalized | User | Munsey, Barbara |  |  |  | N | 314-PARK
Pre-Award Financial - 00118070 | Open to Accrual | User | Munsey, Barbara |  |  |  | N | 00118070
Pre-Award Financial - 239-KORLEY | Open to Accrual | User | Munsey, Barbara |  |  |  | N | 00129045
Calendar Build - 52-AARONSON | MBECT SVS ( MBECT Single-Visit-Shell ) : built & coded | User | Myers, Brigette |  |  | 2017-04-06 | N | 00128761
CTSU Pre-Award v2 - 00134459 | Intake Form Completed | User | Naylor, Tracey |  |  | 2017-08-01 | N | 00134459
CTSU Pre-Award v2 - 412-NASR | Intake Form Completed | User | Naylor, Tracey |  |  | 2017-08-10 | N | 412-NASR
CTSU Pre-Award v2 - 419-PIPE 2 | Intake Form Completed | User | Naylor, Tracey |  |  | 2017-08-16 | N | 00130583
CTSU Pre-Award v2 - 427-KOSCHMANN | Intake Form Completed | User | Naylor, Tracey |  |  | 2017-08-16 | N | 427-KOSCHMANN
Open to Accrual - 00120187 | Contract Executed | User | Naylor, Tracey |  |  | 2017-01-10 | N | 00120187
Open to Accrual - 00120187 | IRB Approval | User | Naylor, Tracey |  |  | 2017-03-31 | N | 00120187
Open to Accrual - 00120187 | MiChart Verifications | User | Naylor, Tracey |  |  | 2017-08-22 | N | 00120187
Open to Accrual - 00120187 | Project Award Notice (PAN) Received | User | Naylor, Tracey |  |  | 2017-05-15 | N | 00120187
Open to Accrual - 00120189 | IRB Approval | User | Naylor, Tracey |  |  | 2017-04-18 | N | 00120189
Open to Accrual - 00120189 | Notification from Study Team | User | Naylor, Tracey |  |  | 2017-06-20 | N | 00120189
Open to Accrual - 00120189 | Project Award Notice (PAN) Received | User | Naylor, Tracey |  |  | 2017-06-13 | N | 00120189
Open to Accrual - 00120349 | Contract Executed | User | Naylor, Tracey |  |  | 2017-06-19 | N | 00120349
Open to Accrual - 00120349 | IRB Approval | User | Naylor, Tracey |  |  | 2017-04-17 | N | 00120349
Open to Accrual - 00120349 | MiChart Verifications | User | Naylor, Tracey |  |  | 2017-08-03 | N | 00120349
Open to Accrual - 00120349 | Project Award Notice (PAN) Received | User | Naylor, Tracey |  |  | 2017-05-18 | N | 00120349
Open to Accrual - 00127496 | Budget Finalized | User | Naylor, Tracey |  |  | 2017-05-12 | N | 00127496
Open to Accrual - 00127496 | Contract Executed | User | Naylor, Tracey |  |  | 2017-06-23 | N | 00127496
Open to Accrual - 00127496 | Project Award Notice (PAN) Received | User | Naylor, Tracey |  |  | 2017-07-21 | N | 00127496
Open to Accrual - 00127891 | Budget Finalized | User | Naylor, Tracey |  |  | 2017-08-04 | N | 00127891
Open to Accrual - 00127891 | Contract Executed | User | Naylor, Tracey |  |  | 2017-08-10 | N | 00127891
Open to Accrual - 00127891 | IRB Approval | User | Naylor, Tracey |  |  | 2017-06-12 | N | 00127891
Open to Accrual - 00127891 | MiChart Verifications | User | Naylor, Tracey |  |  | 2017-08-14 | N | 00127891
Open to Accrual - 00127891 | Project Award Notice (PAN) Received | User | Naylor, Tracey |  |  | 2017-08-15 | N | 00127891
Open to Accrual - 00128061 | IRB Approval | User | Naylor, Tracey |  |  | 2017-07-27 | N | 00128061
Open to Accrual - 00128061 | Project Award Notice (PAN) Received | User | Naylor, Tracey |  |  | 2017-08-17 | N | 00128061
Open to Accrual - 00128301 | Budget Finalized | User | Naylor, Tracey |  |  | 2017-06-07 | N | 00128301
Open to Accrual - 00128301 | Contract Executed | User | Naylor, Tracey |  |  | 2017-06-26 | N | 00128301
Open to Accrual - 00128301 | IRB Approval | User | Naylor, Tracey |  |  | 2017-06-29 | N | 00128301
Open to Accrual - 00128301 | Project Award Notice (PAN) Received | User | Naylor, Tracey |  |  | 2017-07-11 | N | 00128301
Open to Accrual - 00128493 | Budget Finalized | User | Naylor, Tracey |  |  | 2017-04-28 | N | 00128493
Open to Accrual - 00128493 | Contract Executed | User | Naylor, Tracey |  |  | 2017-08-04 | N | 00128493
Open to Accrual - 00128493 | IRB Approval | User | Naylor, Tracey |  |  | 2017-06-08 | N | 00128493
Open to Accrual - HUM00129276 | Budget Finalized | User | Naylor, Tracey |  |  | 2017-07-21 | N | 00129276
Open to Accrual - HUM00129276 | Contract Executed | User | Naylor, Tracey |  |  | 2017-08-24 | N | 00129276
Open to Accrual - HUM00129276 | IRB Approval | User | Naylor, Tracey |  |  | 2017-07-13 | N | 00129276
Open to Accrual - HUM00129276 | MiChart Verifications | User | Naylor, Tracey |  |  | 2017-08-30 | N | 00129276
Open to Accrual - HUM00129276 | Project Award Notice (PAN) Received | User | Naylor, Tracey |  |  | 2017-08-24 | N | 00129276
Open to Accrual - 00118070 | Adequate Equipment and Supplies Available | User | Nelson, Kristine |  |  | 2017-05-18 | N | 00118070
Open to Accrual - 00118070 | Contract Executed | User | Nelson, Kristine |  |  | 2017-05-18 | N | 00118070
Open to Accrual - 00118070 | IRB Approval | User | Nelson, Kristine |  |  | 2017-04-24 | N | 00118070
Open to Accrual - 00118070 | Investigational Drug/Device Supplies Available | User | Nelson, Kristine |  |  | 2017-05-18 | N | 00118070
Open to Accrual - 00118070 | MiChart Verifications | User | Nelson, Kristine |  |  | 2017-05-18 | N | 00118070
Open to Accrual - 00118070 | Other Personnel Notified | User | Nelson, Kristine |  |  | 2017-05-18 | N | 00118070
Open to Accrual - 00118070 | Provisions for Support and Services Finalized | User | Nelson, Kristine |  |  | 2017-05-18 | N | 00118070
Open to Accrual - 00118070 | Sponsor/Organizing Group Approval Granted for Initiation of Study | User | Nelson, Kristine |  |  | 2017-05-18 | N | 00118070
Open to Accrual - 00118070 | Study Files Established | User | Nelson, Kristine |  |  | 2017-05-18 | N | 00118070
Open to Accrual - 00118070 | Study Team Roles/Responsibilities Finalized | User | Nelson, Kristine |  |  | 2017-05-18 | N | 00118070
Pre-Award Financial - 00118070 | PI Signoff in OnCore | User | Nelson, Kristine |  |  |  | N | 00118070
CTSU Pre-Award - 309-MOROI | Calendar Released | User | Oliver, Amy |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 309-MOROI | PAN Released | User | Oliver, Amy |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 331-FLAHERTY | Calendar Released | User | Oliver, Amy |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 331-FLAHERTY | PAN Released | User | Oliver, Amy |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 346-BAPTIST | Calendar Released | User | Oliver, Amy |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 346-BAPTIST | PAN Released | User | Oliver, Amy |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 347-HIGGINS | Calendar Released | User | Oliver, Amy |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 347-HIGGINS | PAN Released | User | Oliver, Amy |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 348-CHEY | Calendar Released | User | Oliver, Amy |  |  |  | N | 348-CHEY
CTSU Pre-Award - 348-CHEY | PAN Released | User | Oliver, Amy |  |  |  | N | 348-CHEY
CTSU Pre-Award v2 - 397-HODISH | Calendar Released | User | Oliver, Amy |  |  | NA | Y | 397-HODISH
CTSU Pre-Award v2 - 397-HODISH | PAN Released | User | Oliver, Amy |  |  | NA | Y | 397-HODISH
Calendar & Budget Retrofit - 00101092 | Questions | User | Oliver, Amy |  |  | NA | Y | 00101092
Calendaring : Amendment Checklist & Process - 00119399 2 | Acknowledge | User | Oliver, Amy |  |  | NA | Y | 00119399
Pre-Award Financial - 00122254 | Initiate Post-Award Task List | User | Oliver, Amy |  |  |  | N | 00122254
Pre-Award Financial - 00124920 | Initiate Post-Award Task List | User | Oliver, Amy |  |  | 2017-08-01 | N | 00124920
Pre-Award Financial - 00125022 | Initiate Post-Award Task List | User | Oliver, Amy |  |  |  | N | 00125022
Pre-Award Financial - 00129427 | Initiate Post-Award Task List | User | Oliver, Amy |  |  |  | N | 00129427
Pre-Award Financial - 00130575 | Initiate Post-Award Task List | User | Oliver, Amy |  |  |  | N | 00130575
Pre-Award Financial - 00130793 | Initiate Post-Award Task List | User | Oliver, Amy |  |  |  | N | 00130793
Pre-Award Financial - 155-ORAL | Budget Negotiations | User | Oliver, Amy |  |  | NA | Y | 00130803
Pre-Award Financial - 155-ORAL | Final Budget | User | Oliver, Amy |  |  | NA | Y | 00130803
Pre-Award Financial - 155-ORAL | Initiate Post-Award Task List | User | Oliver, Amy |  |  |  | N | 00130803
Pre-Award Financial - 155-ORAL | Internal Budget Finished | User | Oliver, Amy |  |  | NA | Y | 00130803
Pre-Award Financial - 155-ORAL | PI approved Budget | User | Oliver, Amy |  |  | NA | Y | 00130803
Pre-Award Financial - 180-HOFF | Created CTRF & "Notify ORSP" | User | Oliver, Amy |  |  | NA | Y | 00129450
Pre-Award Financial - 180-HOFF | Initiate Post-Award Task List | User | Oliver, Amy |  |  |  | N | 00129450
Pre-Award Financial - 180-HOFF | Request MCRU Budget | User | Oliver, Amy |  |  | NA | Y | 00129450
Pre-Award Financial - 180-HOFF | Request Research Pharmacy Budget | User | Oliver, Amy |  |  | NA | Y | 00129450
Pre-Award Financial - 190-SCHIOPU | Initiate Post-Award Task List | User | Oliver, Amy |  |  |  | N | 00134443
Pre-Award Financial - 211-HIGGINS | PAF routed | User | Oliver, Amy |  |  | NA | Y | 00128325
Pre-Award Financial - 23-GUPTA | Initiate Post-Award Task List | User | Oliver, Amy |  |  |  | N | 00134236
Pre-Award Financial - 44-MCUNE | Calendar Released | User | Oliver, Amy |  |  |  | N | 44-MCUNE
Pre-Award Financial - 44-MCUNE | PAN Released | User | Oliver, Amy |  |  |  | N | 44-MCUNE
Pre-Award Financial - 49-MARTINEZ | Initiate Post-Award Task List | User | Oliver, Amy |  |  |  | N | 00132020
Pre-Award Financial - 56-RAO | Initiate Post-Award Task List | User | Oliver, Amy |  |  |  | N | 00133286
Pre-Award Financial - 69-KHANNA | Budget Negotiations | User | Oliver, Amy |  |  | 2017-03-28 | N | 69-KHANNA
Pre-Award Financial - 69-KHANNA | Created CTRF & "Notify ORSP" | User | Oliver, Amy |  |  | NA | Y | 69-KHANNA
Pre-Award Financial - 69-KHANNA | Final Budget | User | Oliver, Amy |  |  | NA | Y | 69-KHANNA
Pre-Award Financial - 69-KHANNA | Initiate Post-Award Task List | User | Oliver, Amy |  |  |  | N | 69-KHANNA
Pre-Award Financial - 69-KHANNA | Internal Budget Finished | User | Oliver, Amy |  |  | NA | Y | 69-KHANNA
Pre-Award Financial - 69-KHANNA | PI approved Budget | User | Oliver, Amy |  |  | NA | Y | 69-KHANNA
Pre-Award Financial - 69-KHANNA | Planning Meeting Completed | User | Oliver, Amy |  |  | NA | Y | 69-KHANNA
Pre-Award Financial - 69-KHANNA | Request MCRU Budget | User | Oliver, Amy |  |  | NA | Y | 69-KHANNA
Pre-Award Financial - 69-KHANNA | Request Research Pharmacy Budget | User | Oliver, Amy |  |  | NA | Y | 69-KHANNA
Pre-Award Financial - FONTANA-1 | Initiate Post-Award Task List | User | Oliver, Amy |  |  |  | N | 00133153
Pre-Award Financial - PLT-INF24-001 | Initiate Post-Award Task List | User | Oliver, Amy |  |  |  | N | 00135388
Pre-Award Financial - SLS-III | Initiate Post-Award Task List | User | Oliver, Amy |  |  |  | N | 00131953
Calendaring : Amendment Checklist & Process - 00066077 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Przykucki, Anne |  |  | NA | Y | 00066077
Calendaring : Amendment Checklist & Process - 00066077 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Przykucki, Anne |  |  | NA | Y | 00066077
Calendaring : Amendment Checklist & Process - 00066077 | ** Visit Tolerance Edits | User | Przykucki, Anne |  |  | NA | Y | 00066077
Calendaring : Amendment Checklist & Process - 00066077 | ** Visits : Addition or Removal of Time Points | User | Przykucki, Anne |  |  | NA | Y | 00066077
Calendaring : Amendment Checklist & Process - 00066077 | Request Care Designations | User | Przykucki, Anne |  |  | NA | Y | 00066077
Calendaring : Amendment Checklist & Process - 00101092 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Przykucki, Anne |  |  | NA | Y | 00101092
Calendaring : Amendment Checklist & Process - 00113560 | ** Footnote Edits | User | Przykucki, Anne |  |  | NA | Y | 00113560
Calendaring : Amendment Checklist & Process - 00113560 | ** Items/Services : Addition or Removal of Procedures / Events | User | Przykucki, Anne |  |  | NA | Y | 00113560
Calendaring : Amendment Checklist & Process - 00113560 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Przykucki, Anne |  |  | NA | Y | 00113560
Calendaring : Amendment Checklist & Process - 00113560 | ** Other | User | Przykucki, Anne |  |  | NA | Y | 00113560
Calendaring : Amendment Checklist & Process - 00113560 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Przykucki, Anne |  |  | NA | Y | 00113560
Calendaring : Amendment Checklist & Process - 00113560 | ** Visit Tolerance Edits | User | Przykucki, Anne |  |  | NA | Y | 00113560
Calendaring : Amendment Checklist & Process - 00113560 | ** Visits : Addition or Removal of Time Points | User | Przykucki, Anne |  |  | NA | Y | 00113560
Calendaring : Amendment Checklist & Process - 00113560 | Request Care Designations | User | Przykucki, Anne |  |  | NA | Y | 00113560
Calendaring : Amendment Checklist & Process - 00113560 | Update RSH Source in MBECT | User | Przykucki, Anne |  |  | NA | Y | 00113560
Calendaring : Amendment Checklist & Process - 00120441 | ** Footnote Edits | User | Przykucki, Anne |  |  | NA | Y | 00120441
Calendaring : Amendment Checklist & Process - 00120441 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Przykucki, Anne |  |  | NA | Y | 00120441
Calendaring : Amendment Checklist & Process - 00120441 | ** Other | User | Przykucki, Anne |  |  | NA | Y | 00120441
Calendaring : Amendment Checklist & Process - 00120441 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Przykucki, Anne |  |  | NA | Y | 00120441
Calendaring : Amendment Checklist & Process - 00120441 | ** Visit Tolerance Edits | User | Przykucki, Anne |  |  | NA | Y | 00120441
Calendaring : Amendment Checklist & Process - 00120441 | ** Visits : Addition or Removal of Time Points | User | Przykucki, Anne |  |  | NA | Y | 00120441
Calendaring : Amendment Checklist & Process - 00123635 | ** Other | User | Przykucki, Anne |  |  | NA | Y | 00123635
Calendaring : Amendment Checklist & Process - 00123635 | Request Care Designations | User | Przykucki, Anne |  |  | NA | Y | 00123635
Calendaring : Initial Calendar Build - 56-RAO | CRAO Approval Issue & Documented | User | Przykucki, Anne |  |  |  | N | 00133286
Calendaring : Initial Calendar Build - 56-RAO | Make Updates | User | Przykucki, Anne |  |  | NA | Y | 00133286
Calendaring : Initial Calendar Build - CY5022 | CRAO Approval Issue & Documented | User | Przykucki, Anne |  |  |  | N | 00132631
Calendaring : Initial Calendar Build - CY5022 | Make Updates | User | Przykucki, Anne |  |  | NA | Y | 00132631
Calendaring : Specification Update Request(s) - 00113560 | Re-Complete Calendar | User | Przykucki, Anne |  |  | NA | Y | 00113560
Calendaring : Amendment Checklist & Process - 00080998 | AME Calendaring Process Initiated | User | Radenbaugh, Pauline |  |  | 2017-05-12 | N | 00080998
Calendaring : Amendment Checklist & Process - 00104658 | ** Footnote Edits | User | Radenbaugh, Pauline |  |  | NA | Y | 00104658
Calendaring : Amendment Checklist & Process - 00104658 | ** Items/Services : Addition or Removal of Procedures / Events | User | Radenbaugh, Pauline |  |  | NA | Y | 00104658
Calendaring : Amendment Checklist & Process - 00104658 | ** Items/Services : Updates to Activity for Existing Procedures / Events | User | Radenbaugh, Pauline |  |  | NA | Y | 00104658
Calendaring : Amendment Checklist & Process - 00104658 | ** Other | User | Radenbaugh, Pauline |  |  | NA | Y | 00104658
Calendaring : Amendment Checklist & Process - 00104658 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Radenbaugh, Pauline |  |  | NA | Y | 00104658
Calendaring : Amendment Checklist & Process - 00104658 | ** Visit Tolerance Edits | User | Radenbaugh, Pauline |  |  | NA | Y | 00104658
Calendaring : Amendment Checklist & Process - 00104658 | ** Visits : Addition or Removal of Time Points | User | Radenbaugh, Pauline |  |  | NA | Y | 00104658
Calendaring : Amendment Checklist & Process - 00104658 | Complete Calendar and Document Approval | User | Radenbaugh, Pauline |  |  | NA | Y | 00104658
Calendaring : Amendment Checklist & Process - 00104658 | Confirm Materials and Required Details ( Summary & Supporting Documents ) | User | Radenbaugh, Pauline |  |  | NA | Y | 00104658
Calendaring : Amendment Checklist & Process - 00104658 | Request Care Designations | User | Radenbaugh, Pauline |  |  | NA | Y | 00104658
Calendaring : Amendment Checklist & Process - 00104658 | Update RSH Source in MBECT | User | Radenbaugh, Pauline |  |  | NA | Y | 00104658
Calendaring : Amendment Checklist & Process - 00107954 | ** Footnote Edits | User | Radenbaugh, Pauline |  |  | NA | Y | 00107954
Calendaring : Amendment Checklist & Process - 00107954 | ** Other | User | Radenbaugh, Pauline |  |  | NA | Y | 00107954
Calendaring : Amendment Checklist & Process - 00107954 | ** Structural Specification Edits : Arms / Segments / Logic / etc. | User | Radenbaugh, Pauline |  |  | NA | Y | 00107954
Calendaring : Amendment Checklist & Process - 00107954 | ** Visit Tolerance Edits | User | Radenbaugh, Pauline |  |  | NA | Y | 00107954
Calendaring : Amendment Checklist & Process - 00107954 | Update RSH Source in MBECT | User | Radenbaugh, Pauline |  |  | NA | Y | 00107954
Calendaring : Amendment Checklist & Process - 00113391 | ** Other | User | Radenbaugh, Pauline |  |  | NA | Y | 00113391
Calendaring : Amendment Checklist & Process - 00113391 | Update RSH Source in MBECT | User | Radenbaugh, Pauline |  |  | NA | Y | 00113391
Calendaring : Initial Calendar Build - 00122957 | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  | NA | Y | 00124722
Calendaring : Initial Calendar Build - 00126010 | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 00126010
Calendaring : Initial Calendar Build - 00127356 | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 00127356
Calendaring : Initial Calendar Build - 00127505 | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline |  |  | 2017-04-25 | N | 00127505
Calendaring : Initial Calendar Build - 00127505 | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline |  |  | 2017-04-25 | N | 00127505
Calendaring : Initial Calendar Build - 00127505 | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline |  |  | 2017-04-25 | N | 00127505
Calendaring : Initial Calendar Build - 00128157 | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 00128157
Calendaring : Initial Calendar Build - 00128173 | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 00128173
Calendaring : Initial Calendar Build - 00128301 | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  | 2017-05-16 | N | 00128301
Calendaring : Initial Calendar Build - 00128743 | Assign to Analyst | User | Radenbaugh, Pauline |  |  | 2017-04-18 | N | 00128743
Calendaring : Initial Calendar Build - 00128743 | Complete MCA / QCT | User | Radenbaugh, Pauline |  |  | 2017-04-27 | N | 00128743
Calendaring : Initial Calendar Build - 00128743 | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline |  |  | 2017-04-19 | N | 00128743
Calendaring : Initial Calendar Build - 00128743 | Make Updates | User | Radenbaugh, Pauline |  |  | NA | Y | 00128743
Calendaring : Initial Calendar Build - 00129427 2 | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  | 2017-07-19 | N | 00129427
Calendaring : Initial Calendar Build - 00131311 | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 00131311
Calendaring : Initial Calendar Build - 147 | Assign to Analyst | User | Radenbaugh, Pauline |  |  | 2017-03-22 | N | 00128322
Calendaring : Initial Calendar Build - 147 | Complete MCA / QCT | User | Radenbaugh, Pauline |  |  | 2017-04-20 | N | 00128322
Calendaring : Initial Calendar Build - 155-ORAL | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 00130803
Calendaring : Initial Calendar Build - 211-HIGGINS | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 00128325
Calendaring : Initial Calendar Build - 225-ROSENBLUM | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 00124224
Calendaring : Initial Calendar Build - 225-ROSENBLUM | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline |  |  | NA | Y | 00124224
Calendaring : Initial Calendar Build - 225-ROSENBLUM | Make Updates | User | Radenbaugh, Pauline |  |  | NA | Y | 00124224
Calendaring : Initial Calendar Build - 235-SUGAR | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 235-SUGAR
Calendaring : Initial Calendar Build - 239-KORLEY | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 00129045
Calendaring : Initial Calendar Build - 239-KORLEY | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline |  |  | NA | Y | 00129045
Calendaring : Initial Calendar Build - 239-KORLEY | Make Updates | User | Radenbaugh, Pauline |  |  | NA | Y | 00129045
Calendaring : Initial Calendar Build - 24-PARIKH | Assign to Analyst | User | Radenbaugh, Pauline |  |  | 2017-04-25 | N | 00128493
Calendaring : Initial Calendar Build - 24-PARIKH | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline |  |  | 2017-04-25 | N | 00128493
Calendaring : Initial Calendar Build - 24-PARIKH | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  | 2017-04-25 | N | 00128493
Calendaring : Initial Calendar Build - 24-PARIKH | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline |  |  | 2017-04-25 | N | 00128493
Calendaring : Initial Calendar Build - 24-PARIKH | Complete MCA / QCT | User | Radenbaugh, Pauline |  |  | 2017-04-25 | N | 00128493
Calendaring : Initial Calendar Build - 24-PARIKH | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline |  |  | 2017-04-25 | N | 00128493
Calendaring : Initial Calendar Build - 24-PARIKH | Feasibility Approval Notice Received | User | Radenbaugh, Pauline |  |  | 2017-04-25 | N | 00128493
Calendaring : Initial Calendar Build - 24-PARIKH | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline |  |  | 2017-04-25 | N | 00128493
Calendaring : Initial Calendar Build - 24-PARIKH | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline |  |  | 2017-04-25 | N | 00128493
Calendaring : Initial Calendar Build - 241-SILVER | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 00132956
Calendaring : Initial Calendar Build - 241-SILVER | Complete Calendar ( ie. Ready for Financials ) | User | Radenbaugh, Pauline |  |  | NA | Y | 00132956
Calendaring : Initial Calendar Build - 241-SILVER | Make Updates | User | Radenbaugh, Pauline |  |  | NA | Y | 00132956
Calendaring : Initial Calendar Build - 244-MODY | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 244-MODY
Calendaring : Initial Calendar Build - 27-WALKOVICH | Attach Build Notes ( as Protocol Doc ) | User | Radenbaugh, Pauline |  |  | 2017-04-20 | N | 00127988
Calendaring : Initial Calendar Build - 27-WALKOVICH | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 00127988
Calendaring : Initial Calendar Build - 27-WALKOVICH | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Radenbaugh, Pauline |  |  | 2017-04-20 | N | 00127988
Calendaring : Initial Calendar Build - 27-WALKOVICH | Nimblify Build is Complete & Ready for Import | User | Radenbaugh, Pauline |  |  | 2017-03-28 | N | 00127988
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 00133341
Calendaring : Initial Calendar Build - 278-CONJEEVARAM | Make Updates | User | Radenbaugh, Pauline |  |  | NA | Y | 00133341
Calendaring : Initial Calendar Build - 287-HUTCHINSON | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 00119926
Calendaring : Initial Calendar Build - 287-HUTCHINSON | Complete MCA / QCT | User | Radenbaugh, Pauline |  |  | NA | Y | 00119926
Calendaring : Initial Calendar Build - 287-HUTCHINSON | Complete SVS & Pricing List ( Built & Coded ) | User | Radenbaugh, Pauline |  |  | NA | Y | 00119926
Calendaring : Initial Calendar Build - 287-HUTCHINSON | Make Updates | User | Radenbaugh, Pauline |  |  | NA | Y | 00119926
Calendaring : Initial Calendar Build - 70-LUGOGO | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 70-LUGOGO
Calendaring : Initial Calendar Build - CIP-1403 | Submit Calendar Build Request and Docs to Nimblify | User | Radenbaugh, Pauline |  |  | 2017-04-21 | N | 00128253
Calendaring : Initial Calendar Build - HUM00091711 | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  |  | N | 00091711
Calendaring : Initial Calendar Build - KCHOU001 | CRAO Approval Issue & Documented | User | Radenbaugh, Pauline |  |  | 2017-06-01 | N | 00130004
Calendaring : Initial Calendar Build - KCHOU001 | Make Updates | User | Radenbaugh, Pauline |  |  | NA | Y | 00130004
Calendaring : Migration - 00087702 | Assign to Analyst | User | Radenbaugh, Pauline |  |  | 2017-04-24 | N | 00087702
Calendaring : Migration - 00087702 | Attach Build Notes and MBECT Calendar Reference ( as Protocol Docs ) | User | Radenbaugh, Pauline |  |  | 2017-04-24 | N | 00087702
Calendaring : Migration - 00087702 | Complete Calendar ( ie. Flag as Ready for Financials ) | User | Radenbaugh, Pauline |  |  | 2017-04-24 | N | 00087702
Calendaring : Migration - 00087702 | Import + Michiganize, including Entry of Care Designations & Comments per Current Approved MBECT Calendar | User | Radenbaugh, Pauline |  |  | 2017-04-24 | N | 00087702
Calendaring : Migration - 00100501 | Assign to Analyst | User | Radenbaugh, Pauline |  |  | 2017-04-21 | N | 00100501
Calendaring : Migration - 00100501 | Attach Build Notes and MBECT Calendar Reference ( as Protocol Docs ) | User | Radenbaugh, Pauline |  |  | 2017-04-21 | N | 00100501
Calendaring : Migration - 00100501 | Complete Calendar ( ie. Flag as Ready for Financials ) | User | Radenbaugh, Pauline |  |  | 2017-04-21 | N | 00100501
Calendaring : Migration - 00100501 | Import + Michiganize, including Entry of Care Designations & Comments per Current Approved MBECT Calendar | User | Radenbaugh, Pauline |  |  | 2017-04-21 | N | 00100501
Calendaring : Migration - 00125493 | Assign to Analyst | User | Radenbaugh, Pauline |  |  | 2017-04-24 | N | 00125493
Calendaring : Specification Update Request(s) - 00127505 | Make Update(s) | User | Radenbaugh, Pauline |  |  | NA | Y | 00127505
Calendaring : Specification Update Request(s) - 00127505 | Re-Complete Calendar | User | Radenbaugh, Pauline |  |  | NA | Y | 00127505
Calendaring : Specification Update Request(s) - 00128322 | Assign to Analyst | User | Radenbaugh, Pauline |  |  | NA | Y | 00128322
Calendaring : Specification Update Request(s) - 00128322 | Make Update(s) | User | Radenbaugh, Pauline |  |  | NA | Y | 00128322
Calendaring : Specification Update Request(s) - 00128322 | Re-Complete Calendar | User | Radenbaugh, Pauline |  |  | NA | Y | 00128322
Open to Accrual - 00120786 | Adequate Equipment and Supplies Available | User | Sullivan, Elizabeth |  |  | 2017-08-21 | N | 00120786
Open to Accrual - 00120786 | Contract Executed | User | Sullivan, Elizabeth |  |  | 2017-07-07 | N | 00120786
Open to Accrual - 00120786 | FDA Approval | User | Sullivan, Elizabeth |  |  | 2017-07-07 | N | 00120786
Open to Accrual - 00120786 | IRB Approval | User | Sullivan, Elizabeth |  |  | 2017-07-07 | N | 00120786
Open to Accrual - 00120786 | Investigational Drug/Device Supplies Available | User | Sullivan, Elizabeth |  |  | 2017-08-21 | N | 00120786
Open to Accrual - 00120786 | Other Personnel Notified | User | Sullivan, Elizabeth |  |  | 2017-08-21 | N | 00120786
Open to Accrual - 00120786 | Provisions for Support and Services Finalized | User | Sullivan, Elizabeth |  |  | 2017-08-21 | N | 00120786
Open to Accrual - 00120786 | Sponsor/Organizing Group Approval Granted for Initiation of Study | User | Sullivan, Elizabeth |  |  | 2017-08-21 | N | 00120786
Open to Accrual - 00120786 | Study Files Established | User | Sullivan, Elizabeth |  |  | 2017-08-21 | N | 00120786
Open to Accrual - 00120786 | Study Team Roles/Responsibilities Finalized | User | Sullivan, Elizabeth |  |  | 2017-08-21 | N | 00120786
CTSU Pre-Award - 337-MIAN | Request MCRU Budget | User | VanderElzen, Liz |  |  | NA | Y | 337-MIAN
CTSU Pre-Award - 338-MIAN | Request MCRU Budget | User | VanderElzen, Liz |  |  | NA | Y | 00133457
CTSU Pre-Award - 351-HIGGINS | Request MCRU Budget | User | VanderElzen, Liz |  |  | NA | Y | 00134870
CTSU Pre-Award v2 - 435-MOROI | Budget Negotiations | User | VanderElzen, Liz |  |  | NA | Y | 435-MOROI
CTSU Pre-Award v2 - 435-MOROI | PAF routed | User | VanderElzen, Liz |  |  | NA | Y | 435-MOROI
Pre-Award Financial - 00108880 | Budget Negotiations | User | VanderElzen, Liz |  |  | NA | Y | 00108880
Pre-Award Financial - 00108880 | Initiate Post-Award Task List | User | VanderElzen, Liz |  |  |  | N | 00108880
Pre-Award Financial - 00108880 | Internal Budget Finished | User | VanderElzen, Liz |  |  | NA | Y | 00108880
Pre-Award Financial - 00108880 | PI approved Budget | User | VanderElzen, Liz |  |  | NA | Y | 00108880
Pre-Award Financial - 00126010 | Initiate Post-Award Task List | User | VanderElzen, Liz |  |  |  | N | 00126010
Pre-Award Financial - 00126010 | Request MCRU Budget | User | VanderElzen, Liz |  |  | NA | Y | 00126010
Pre-Award Financial - 00128173 | Budget Negotiations | User | VanderElzen, Liz |  |  | NA | Y | 00128173
Pre-Award Financial - 00128173 | Internal Budget Finished | User | VanderElzen, Liz |  |  | NA | Y | 00128173
Pre-Award Financial - 00128173 | PI approved Budget | User | VanderElzen, Liz |  |  | NA | Y | 00128173
Pre-Award Financial - 11-HIGGINS | Request MCRU Budget | User | VanderElzen, Liz |  |  | NA | Y | 00134884
Pre-Award Financial - 112-FLAHERTY | Request MCRU Budget | User | VanderElzen, Liz |  |  | NA | Y | 112-FLAHERTY
Pre-Award Financial - 179-LUGOGO | Request MCRU Budget | User | VanderElzen, Liz |  |  | NA | Y | 179-LUGOGO
Pre-Award Financial - 235-SUGAR | Request MCRU Budget | User | VanderElzen, Liz |  |  | NA | Y | 235-SUGAR
Pre-Award Financial - 235-SUGAR | Request Research Pharmacy Budget | User | VanderElzen, Liz |  |  | NA | Y | 235-SUGAR
Pre-Award Financial - 251-COMER | Request MCRU Budget | User | VanderElzen, Liz |  |  | NA | Y | 00134232
Pre-Award Financial - 282-POP-BUSUI | Request MCRU Budget | User | VanderElzen, Liz |  |  | NA | Y | 00133290
Pre-Award Financial - 46-HIGGINS | Planning Meeting Completed | User | VanderElzen, Liz |  |  | NA | Y | 46-HIGGINS
Pre-Award Financial - 46-HIGGINS | Request MCRU Budget | User | VanderElzen, Liz |  |  | NA | Y | 46-HIGGINS
Pre-Award Financial - 49-MARTINEZ | Request MCRU Budget | User | VanderElzen, Liz |  |  | NA | Y | 00132020
Pre-Award Financial - 70-LUGOGO | Request MCRU Budget | User | VanderElzen, Liz |  |  | NA | Y | 70-LUGOGO
Open to Accrual - 00124839 | Sponsor/Organizing Group Approval Granted for Initiation of Study | User | White, Kelsey |  |  | 2017-08-04 | N | 00124839
CTSU Post-Award - 00066077 | Comments | User | Yunk, Jason |  |  |  | N | 00066077
CTSU Post-Award - 00089260 | Comments | User | Yunk, Jason |  |  |  | N | 00089260
CTSU Post-Award - 00101092 | Comments | User | Yunk, Jason |  |  |  | N | 00101092
CTSU Post-Award - 00101426 | Comments | User | Yunk, Jason |  |  |  | N | 00101426
CTSU Post-Award - 00107927 | Comments | User | Yunk, Jason |  |  |  | N | 00107927
CTSU Post-Award - 00107954 | Comments | User | Yunk, Jason |  |  |  | N | 00107954
CTSU Post-Award - 00113496 | Comments | User | Yunk, Jason |  |  |  | N | 00113496
CTSU Post-Award - 00114593 | Comments | User | Yunk, Jason |  |  |  | N | 00114593
CTSU Post-Award - 00118570 | Comments | User | Yunk, Jason |  |  |  | N | 00118570
CTSU Post-Award - 00119399 | Comments | User | Yunk, Jason |  |  |  | N | 00119399
CTSU Post-Award - 00123231 | Comments | User | Yunk, Jason |  |  |  | N | 00123231
CTSU Post-Award - 00123861 | Comments | User | Yunk, Jason |  |  |  | N | 00123861
CTSU Post-Award - 00125425 | Comments | User | Yunk, Jason |  |  |  | N | 00125425
CTSU Post-Award - 00125566 | Comments | User | Yunk, Jason |  |  |  | N | 00125566
CTSU Post-Award - 00125786 | Comments | User | Yunk, Jason |  |  |  | N | 00125786
CTSU Post-Award - 00125794 | Comments | User | Yunk, Jason |  |  |  | N | 00125794
CTSU Post-Award - 00127537 | Comments | User | Yunk, Jason |  |  |  | N | 00127537
CTSU Post-Award - 00129716 | Comments | User | Yunk, Jason |  |  |  | N | 00129716
CTSU Post-Award - 00129820 | Comments | User | Yunk, Jason |  |  |  | N | 00129820
CTSU Post-Award - 00129851 | Comments | User | Yunk, Jason |  |  |  | N | 00129851
CTSU Pre-Award - 309-MOROI | OnCore Budget Build | User | Yunk, Jason |  |  | NA | Y | 309-MOROI
CTSU Pre-Award - 331-FLAHERTY | OnCore Budget Build | User | Yunk, Jason |  |  | NA | Y | 331-FLAHERTY
CTSU Pre-Award - 346-BAPTIST | OnCore Budget Build | User | Yunk, Jason |  |  |  | N | 346-BAPTIST
CTSU Pre-Award - 347-HIGGINS | OnCore Budget Build | User | Yunk, Jason |  |  | NA | Y | 347-HIGGINS
CTSU Pre-Award - 348-CHEY | OnCore Budget Build | User | Yunk, Jason |  |  |  | N | 348-CHEY
CTSU Pre-Award v2 - 397-HODISH | OnCore Budget Build | User | Yunk, Jason |  |  | NA | Y | 397-HODISH
Calendar & Budget Retrofit - 00108880 | Questions | User | Yunk, Jason |  |  | NA | Y | 00108880
Calendar & Budget Retrofit - 00124920 | Questions | User | Yunk, Jason |  |  | NA | Y | 00124920
Calendar & Budget Retrofit - 00125022 | Questions | User | Yunk, Jason |  |  | NA | Y | 00125022
Calendar & Budget Retrofit - 00125425 | Questions | User | Yunk, Jason |  |  | NA | Y | 00125425
Calendar & Budget Retrofit - 00125566 | Questions | User | Yunk, Jason |  |  | NA | Y | 00125566
Calendar & Budget Retrofit - 00126010 | Questions | User | Yunk, Jason |  |  | NA | Y | 00126010
Calendar & Budget Retrofit - 00127136 | Questions | User | Yunk, Jason |  |  | NA | Y | 00127136
Calendar & Budget Retrofit - 00128743 | Questions | User | Yunk, Jason |  |  | NA | Y | 00128743
Calendar & Budget Retrofit - 00129652 | Questions | User | Yunk, Jason |  |  | NA | Y | 00129652
Calendar & Budget Retrofit - 00129716 | Questions | User | Yunk, Jason |  |  | NA | Y | 00129716
Calendar & Budget Retrofit - 00129820 | Questions | User | Yunk, Jason |  |  | NA | Y | 00129820
Calendar & Budget Retrofit - 00130575 | Questions | User | Yunk, Jason |  |  | NA | Y | 00130575
Calendar & Budget Retrofit - 00131329 | Questions | User | Yunk, Jason |  |  | NA | Y | 00131329
Calendar & Budget Retrofit - 00131837 | Questions | User | Yunk, Jason |  |  | NA | Y | 00131837
Calendar & Budget Retrofit - 00131953 | Questions | User | Yunk, Jason |  |  | NA | Y | 00131953
Calendar & Budget Retrofit - 00133290 | Questions | User | Yunk, Jason |  |  | NA | Y | 00133290
Calendar & Budget Retrofit - PLT-INF24-001 | Questions | User | Yunk, Jason |  |  | NA | Y | 00135388
Calendaring : Amendment Checklist & Process - 00123231 | Acknowledge | User | Yunk, Jason |  |  | NA | Y | 00123231
Calendaring : Amendment Checklist & Process - 00123231 | Provide PI-Determined Care Designations ( +/- Feedback ) | User | Yunk, Jason |  |  | NA | Y | 00123231
Calendaring : Specification Update Request(s) - 00127505 | ** Request(s) to Add Unscheduled Procedure(s) | User | Yunk, Jason |  |  | NA | Y | 00127505
Calendaring : Specification Update Request(s) - 00127505 | Acknowledge | User | Yunk, Jason |  |  | NA | Y | 00127505
Calendaring : Specification Update Request(s) - 00127505 | Submit Update Request(s) | User | Yunk, Jason |  |  | NA | Y | 00127505
Pre-Award Financial - 44-MCUNE | OnCore Budget Build | User | Yunk, Jason |  |  |  | N | 44-MCUNE
Calendar Build - 8-AARONSON | ‘Build Notes’ documentation ( w. CRAO comments, as needed ) attached ( as protocol doc ) +/- other supplemental documentation | User | Zahs, Brian |  |  | NA | Y | 00132110
Calendaring : Amendment Checklist & Process - 00132251 | ** Footnote Edits | User | Zahs, Brian |  |  | NA | Y | 00132251
Calendaring : Initial Calendar Build - 00120786 | Complete MCA / QCT | User | Zahs, Brian |  |  | NA | Y | 00120786
Calendaring : Initial Calendar Build - 00120786 | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian |  |  | NA | Y | 00120786
Calendaring : Initial Calendar Build - 00123069 | Assign to Analyst | User | Zahs, Brian |  |  | 2017-04-20 | N | 00123069
Calendaring : Initial Calendar Build - 00126215 | Assign to Analyst | User | Zahs, Brian |  |  | 2017-04-24 | N | 00126215
Calendaring : Initial Calendar Build - 00130757 | Assign to Analyst | User | Zahs, Brian |  |  | NA | Y | 00130757
Calendaring : Initial Calendar Build - 00130757 | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian |  |  | NA | Y | 00130757
Calendaring : Initial Calendar Build - 00130757 | Complete MCA / QCT | User | Zahs, Brian |  |  | NA | Y | 00130757
Calendaring : Initial Calendar Build - 00130757 | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian |  |  | NA | Y | 00130757
Calendaring : Initial Calendar Build - 00130757 | Nimblify Build is Complete & Ready for Import | User | Zahs, Brian |  |  | NA | Y | 00130757
Calendaring : Initial Calendar Build - 00132700 | CRAO Approval Issue & Documented | User | Zahs, Brian |  |  |  | N | 00132700
Calendaring : Initial Calendar Build - 132040 | CRAO Approval Issue & Documented | User | Zahs, Brian |  |  |  | N | 00132040
Calendaring : Initial Calendar Build - 227-STEIGERWALT 3 | Assign to Analyst | User | Zahs, Brian |  |  | 2017-08-10 | N | 227-STEIGERWALT
Calendaring : Initial Calendar Build - 227-STEIGERWALT 3 | Attach Build Notes ( as Protocol Doc ) | User | Zahs, Brian |  |  |  | N | 227-STEIGERWALT
Calendaring : Initial Calendar Build - 227-STEIGERWALT 3 | CRAO Approval Issue & Documented | User | Zahs, Brian |  |  |  | N | 227-STEIGERWALT
Calendaring : Initial Calendar Build - 227-STEIGERWALT 3 | Complete MCA / QCT | User | Zahs, Brian |  |  |  | N | 227-STEIGERWALT
Calendaring : Initial Calendar Build - 227-STEIGERWALT 3 | Nimblify Build is Complete & Ready for Import | User | Zahs, Brian |  |  |  | N | 227-STEIGERWALT
Calendaring : Initial Calendar Build - 230-ROGERS | Complete SVS & Pricing List ( Built & Coded ) | User | Zahs, Brian |  |  | NA | Y | 00130272
Calendaring : Initial Calendar Build - 230-ROGERS | Import + Michiganize & Export Billing Grid for Determining Care Designations | User | Zahs, Brian |  |  | NA | Y | 00130272
Calendaring : Initial Calendar Build - 230-ROGERS | Make Updates | User | Zahs, Brian |  |  | NA | Y | 00130272
Calendaring : Initial Calendar Build - 232-GIPSON | CRAO Approval Issue & Documented | User | Zahs, Brian |  |  |  | N | 232-GIPSON
Calendaring : Initial Calendar Build - 251-COMER | CRAO Approval Issue & Documented | User | Zahs, Brian |  |  |  | N | 00134232
Calendaring : Initial Calendar Build - 282-POP-BUSUI | CRAO Approval Issue & Documented | User | Zahs, Brian |  |  |  | N | 00133290
Calendaring : Initial Calendar Build - 327-HIGGINS | CRAO Approval Issue & Documented | User | Zahs, Brian |  |  |  | N | 327-HIGGINS
Calendaring : Initial Calendar Build - 416-MAO-DRAAYER | CRAO Approval Issue & Documented | User | Zahs, Brian |  |  |  | N | 416-MAO-DRAAYER
Calendaring : Initial Calendar Build - 46-HIGGINS | CRAO Approval Issue & Documented | User | Zahs, Brian |  |  |  | N | 46-HIGGINS
Calendaring : Initial Calendar Build - 71-RICE | CRAO Approval Issue & Documented | User | Zahs, Brian |  |  |  | N | 00134857
Calendaring : Initial Calendar Build - 93-FREEHILL | CRAO Approval Issue & Documented | User | Zahs, Brian |  |  |  | N | 00129863
Calendaring : Specification Update Request(s) - 00128531 | Assign to Analyst | User | Zahs, Brian |  |  | NA | Y | 00128531
Calendaring : Amendment Checklist & Process - HUM00129276 | ** Other | User | van Dijk, Tim |  |  | NA | Y | 00129276
Calendaring : Amendment Checklist & Process - HUM00129276 | ** Visit Tolerance Edits | User | van Dijk, Tim |  |  | NA | Y | 00129276
Calendaring : Initial Calendar Build - 00126135 | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00126135
Calendaring : Initial Calendar Build - 00129709 | Make Updates | User | van Dijk, Tim |  |  | NA | Y | 00129709
Calendaring : Initial Calendar Build - 00130793 | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00130793
Calendaring : Initial Calendar Build - 00133153 | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00133153
Calendaring : Initial Calendar Build - 00134884 | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00134884
Calendaring : Initial Calendar Build - 112-FLAHERTY | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 112-FLAHERTY
Calendaring : Initial Calendar Build - 170-SCHIOPU | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00134035
Calendaring : Initial Calendar Build - 173-WICKMAN | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00133542
Calendaring : Initial Calendar Build - 175-ORAL | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 175-ORAL
Calendaring : Initial Calendar Build - 179-LUGOGO | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 179-LUGOGO
Calendaring : Initial Calendar Build - 190-SCHIOPU | Assign to Analyst | User | van Dijk, Tim |  |  | 2017-06-30 | N | 00134443
Calendaring : Initial Calendar Build - 190-SCHIOPU | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00134443
Calendaring : Initial Calendar Build - 216-MODY | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00134866
Calendaring : Initial Calendar Build - 260-MODY | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00134979
Calendaring : Initial Calendar Build - 268-NEUMAR | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 268-NEUMAR
Calendaring : Initial Calendar Build - 294-ARNEDT | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  | 2017-07-18 | N | 00124702
Calendaring : Initial Calendar Build - 294-ARNEDT | Complete SVS & Pricing List ( Built & Coded ) | User | van Dijk, Tim |  |  | NA | Y | 00124702
Calendaring : Initial Calendar Build - 325-AUCHUS | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00131840
Calendaring : Initial Calendar Build - 326-HIGGINS | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 326-HIGGINS
Calendaring : Initial Calendar Build - 337-MIAN | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 337-MIAN
Calendaring : Initial Calendar Build - 338-MIAN | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00133457
Calendaring : Initial Calendar Build - 341-STOFFEL | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00134997
Calendaring : Initial Calendar Build - 403-HIGGINS | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00134895
Calendaring : Initial Calendar Build - 404-HIGGINS | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00134896
Calendaring : Initial Calendar Build - 409-NASR | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 409-NASR
Calendaring : Initial Calendar Build - 49-MARTINEZ | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00132020
Calendaring : Initial Calendar Build - SLS-III | CRAO Approval Issue & Documented | User | van Dijk, Tim |  |  |  | N | 00131953
Amendment Checklist & Process - 113141 AME per Ginger | ** Footnote Edits |  |  |  |  | NA | Y | 00113141
Amendment Checklist & Process - 113141 AME per Ginger | ** Items/Services : Addition or Removal of Procedures / Events |  |  |  |  | NA | Y | 00113141
Amendment Checklist & Process - 113141 AME per Ginger | ** Other |  |  |  |  | NA | Y | 00113141
Amendment Checklist & Process - 113141 AME per Ginger | ** Structural Specification Edits : Arms / Segments / Logic / etc. |  |  |  |  | NA | Y | 00113141
Amendment Checklist & Process - 113141 AME per Ginger | ** Visit Tolerance Edits |  |  |  |  | NA | Y | 00113141
Amendment Checklist & Process - 113141 AME per Ginger | ** Visits : Addition or Removal of Time Points |  |  |  |  | NA | Y | 00113141
Amendment Checklist & Process - 113141 AME per Ginger | Update RSH Source in MBECT |  |  |  |  | NA | Y | 00113141
BC : Initial Build - PLT-INF24-001 | Assign to Analyst |  |  |  |  | NA | Y | 00135388
Cal Update : h.121246 (add unsched) | ** Footnote Request(s) | [5 empty] | N | 00121246
Cal Update : h.121246 (add unsched) | ** Other Request(s) | [5 empty] | N | 00121246
Cal Update : h.121246 (add unsched) | ** Request for Clarification | [5 empty] | N | 00121246
Cal Update : h.121246 (add unsched) | ** Request to Rename for Clarity | [5 empty] | N | 00121246
Cal Update : h.121246 (add unsched) | ** Structural Edits | [5 empty] | N | 00121246
Cal Update : h.121246 (add unsched) | Assign to Analyst |  |  |  |  | NA | Y | 00121246
Calendar Build - 00121967 | *** N/A for Studies Approved by CRAO in eRRM *** QCT Checklist : completed in OnCore |  |  |  |  | NA | Y | 00121967
Calendar Build - 00121967 | *** N/A for Studies Approved with fully approved MBECT BC *** MBECT SVS ( MBECT Single-Visit-Shell ) : built & coded |  |  |  |  | NA | Y | 00121967
Calendar Build - 00122489 | MBECT SVS ( MBECT Single-Visit-Shell ) : built & coded ( N/A for Studies with Full MBECT BC Built ) |  |  |  |  | NA | Y | 00122489
Calendar Build - 00122489 | QCT Checklist : completed in OnCore ( N/A for Studies Fully Reviewed / Approved in eRRM ) |  |  |  |  | NA | Y | 00122489
Calendar Build - 00124859 | * N/A for MANUAL ENTRY STUDIES W. FULL MBECT BC * // MBECT SVS ( MBECT Single-Visit-Shell ) : built & coded |  |  |  |  | NA | Y | 00124859
Calendar Build - 00124859 | Calendar Build Request sent to Nimblify |  |  |  |  | NA | Y | 00124859
Calendar Build - 00124859 | Feedback incorporated / resolved |  |  |  |  | NA | Y | 00124859
Calendar Build - 00124859 | QCT Checklist : completed in OnCore |  |  |  |  | NA | Y | 00124859
Calendar Build - 1-THOMAS | Calendar Build Request sent to Nimblify |  |  |  |  | NA | Y | 00125306
Calendar Build - 1-THOMAS | MBECT SVS ( MBECT Single-Visit-Shell ) : built & coded |  |  |  |  | NA | Y | 00125306
Calendar Build - 1-THOMAS | QCT Checklist : completed in OnCore |  |  |  |  | NA | Y | 00125306
Calendar Build - 1-THOMAS | Specification has been Imported / Michiganized and is ready for Finance / Study team review, feedback and determination of care designations |  |  |  |  | NA | Y | 00125306
Calendar Build - 50-HUMMEL | CRAO Approval issued / documented | [5 empty] | N | 00129162
Calendar Build - 50-HUMMEL | MBECT SVS ( MBECT Single-Visit-Shell ) : built & coded |  |  |  |  | NA | Y | 00129162
Calendar Build - 50-HUMMEL | QCT Checklist : completed in OnCore |  |  |  |  | NA | Y | 00129162
Calendar Build - 52-AARONSON | CRAO Approval issued / documented | [5 empty] | N | 00128761
Calendar Build - 52-AARONSON | Feedback incorporated / resolved |  |  |  |  | NA | Y | 00128761
Calendaring : Initial Build - 00126224 | Assign to Analyst |  |  |  |  | NA | Y | 00126224
Calendaring : Initial Build - 00126224 | Complete MCA / QCT | [5 empty] | N | 00126224
Calendaring : Specification Update Request(s) - Removing Pregnancy Test | Re-Complete Calendar |  |  |  |  | NA | Y | 00066077
Calendaring : Updates ( per Archie, 4.21 ) // h. 122152 | ** Footnote Request(s) |  |  |  |  | NA | Y | 00122152
Calendaring : Updates ( per Archie, 4.21 ) // h. 122152 | ** Request to Rename for Clarity |  |  |  |  | NA | Y | 00122152
Calendaring : Updates ( per Archie, 4.21 ) // h. 122152 | ** Request(s) to Add Unscheduled Procedure(s) |  |  |  |  | NA | Y | 00122152
Calendaring : Updates ( per Archie, 4.21 ) // h. 122152 | ** Structural Edits |  |  |  |  | NA | Y | 00122152
Calendaring : Updates ( per Archie, 4.21 ) // h. 122153 | ** Footnote Request(s) |  |  |  |  | NA | Y | 00122153
Calendaring : Updates ( per Archie, 4.21 ) // h. 122153 | ** Request to Rename for Clarity |  |  |  |  | NA | Y | 00122153
Calendaring : Updates ( per Archie, 4.21 ) // h. 122153 | ** Request(s) to Add Unscheduled Procedure(s) |  |  |  |  | NA | Y | 00122153
Calendaring : Updates ( per Archie, 4.21 ) // h. 122153 | ** Structural Edits |  |  |  |  | NA | Y | 00122153
Update Requests : 120231 (5.15.17) | ** Footnote Request(s) |  |  |  |  | NA | Y | 00120231
Update Requests : 120231 (5.15.17) | ** Request for Clarification |  |  |  |  | NA | Y | 00120231
Update Requests : 120231 (5.15.17) | ** Request to Rename for Clarity |  |  |  |  | NA | Y | 00120231
Update Requests : 120231 (5.15.17) | ** Request(s) to Add Unscheduled Procedure(s) |  |  |  |  | NA | Y | 00120231
Update Requests : 120231 (5.15.17) | ** Structural Edits |  |  |  |  | NA | Y | 00120231
Report Date: | 2017-08-31 07:30 | [6 empty] | Page 1 of | 1

## Pivot Table
Task List | (Multiple Items)
Product of Completed Date | Column Labels
Row Labels | Intake Form Completed | UFA Completed | Sponsor Reach out | Feasibility w/Documents received | Feasibility approved/CRAO Notified | Planning Meeting Request Sent | Request MCRU Budget | Request Research Pharmacy Budget | Planning Meeting Scheduled | Planning Meeting Completed | Created CTRF & "Notify ORSP" | PI approved Budget | Budget Negotiations | Billing Calendar Received | Internal Budget Finished | Final Budget | Care Designations completed | Calendar Released | IRB Application Submitted | PAF routed | OnCore Budget Build | PAN Released | PI Signoff in OnCore | Open to Accrual | Initiate Post-Award Task List | Initial Post-Award Task List
00091711
00108880 | 2017-04-14 | 0 | 0 | 2017-04-28 | 2017-04-28 | 2017-05-05 | 0 | 0 |  | 2017-05-11 | 2017-06-30 | 0 | 0 | 2017-05-16 | 0 |  | 2017-08-09
00111295 | 2017-05-25 | 2017-05-26 | 2017-06-01
00118070 | 2017-02-13 | 0 | 0 | 0 | 2017-03-24 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2017-06-09 |  | 0 | 2017-06-09 | 2017-05-11
00121967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2017-04-28 |  | 0 | 2017-04-28 | 2017-02-22 | 2016-12-08 | 2016-12-08
00122254 | 2017-02-23 | 0 | 0 | 2017-03-01 | 2017-03-02 | 2017-02-23 | 0 | 0 |  | 2017-03-16 | 2017-03-08 | 2017-05-02 | 2017-05-10 | 2017-04-13 | 2017-04-26 | 2017-07-06 | 2017-05-23 | 2017-07-26 |  | 2017-07-10 | 2017-07-18
00123237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
00123861 | 2017-01-17 | 0 | 0 | 2017-01-19 | 2017-01-19 | 2017-01-26 | 0 | 0 |  | 2017-02-23 | 2017-01-27 | 2017-03-01 | 2017-03-02 | 2017-02-23 | 2017-03-01 | 2017-03-13 | 2017-02-01 | 2017-04-25 |  | 2017-03-24 | 2017-04-25 | 2017-04-07 | 2017-05-19 | 2017-05-19
00124712 | 2017-02-02 | 0 | 0 | 2017-02-06 | 2017-02-07 | 2017-02-07 | 0 | 2017-02-07 |  | 2017-02-23 | 0 | 0 | 0 | 0 | 2017-02-22 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
00124920 | 2017-02-02 | 0 | 0 | 2017-02-07 | 2017-02-07 | 2017-02-13 | 0 | 0 |  | 2017-02-14 | 2017-02-10 | 2017-02-21 | 2017-02-21 | 2017-03-15 | 2017-02-17 | 2017-02-21 | 2017-02-01 | 2017-06-26 | 2017-01-23 | 2017-02-27 | 2017-06-01 | 2017-08-01 |  |  | 2017-08-01
00125022 | 0 | 0 | 0 | 2017-02-21 | 2017-02-21 | 2017-03-03 | 0 | 0 |  | 2017-03-20 | 2017-02-23 | 2017-03-30 | 2017-04-05 | 2017-04-26 | 2017-03-29 | 2017-07-09 | 2017-06-07 | 2017-08-23 |  |  | 2017-08-23
00125425 | 2017-02-07 | 0 | 0 | 2017-02-14 | 2017-02-14 | 2017-02-21 | 0 | 0 |  | 2017-03-08 | 2017-01-24 | 2017-03-29 | 2017-03-30 | 2017-03-15 | 2017-03-23 | 2017-04-18 | 2017-03-15 | 2017-06-13 | 2017-01-25 | 2017-05-03 | 2017-06-05 | 2017-06-13 | 2017-07-14 | 2017-07-14 | 2017-07-06
00125566 | 2017-02-08 | 0 | 0 | 2017-02-23 | 2017-02-23 | 0 | 0 | 0 |  | 0 | 2016-12-19 | 2017-02-07 | 2017-02-13 | 0 | 0 | 2017-02-21 | 2017-03-29 | 2017-06-21 | 2017-02-10 | 2017-02-26 | 2017-06-07 | 2017-06-29 | 2017-07-03 | 2017-07-28 | 2017-07-06
00125786 | 2017-02-01 | 0 | 0 | 2017-02-03 | 2017-02-07 | 0 | 0 | 0 |  | 0 | 2017-01-30 | 2017-02-21 | 2017-03-30 | 2017-03-15 | 2017-02-17 | 2017-04-20 | 2017-02-01 | 2017-06-13 | 2017-02-13 | 2017-04-28 | 2017-06-05 | 2017-07-06 | 2017-06-13 | 2017-07-09 | 2017-07-06
00125794 | 2017-02-09 | 0 | 0 | 2017-02-23 | 2017-02-23 | 2017-03-02 | 0 | 0 |  | 2017-03-27 | 2017-01-26 | 2017-04-12 | 2017-04-12 | 2017-04-06 | 2017-04-11 | 2017-05-05 | 2017-05-12 | 2017-06-26 | 2017-03-10 | 2017-05-12 | 2017-06-06 | 2017-06-27 | 2017-06-26 | 2017-06-27 | 2017-07-06
00126010 | 2017-05-19 | 0 | 0 | 2017-05-24 | 2017-06-06 | 2017-06-06 | 0 | 0 |  | 2017-06-07 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-14 | 2017-06-08 | 2017-06-08 | 2017-08-01 | 2017-08-22 | 2017-06-05 | 2017-06-08 | 2017-07-13
00126215 | 2017-02-09 | 0 | 0 | 2017-02-22 | 2017-02-22 | 2017-03-02 | 0 | 0 |  | 2017-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
00126224 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
00127136 | 2017-02-08 | 0 | 0 | 2017-02-13 | 2017-02-14 | 2017-02-21 | 0 | 0 |  | 2017-02-24 | 2017-02-21 | 2017-03-10 | 2017-03-10 | 2017-02-23 | 2017-02-21 | 2017-05-22 | 2017-03-28 | 2017-06-26 | 2017-06-19 | 2017-05-22 | 2017-06-12
00127356 | 2017-03-08 | 0 | 0 | 2017-03-13 | 2017-03-13 |  | 0 | 0 |  | 0: 2017-03-29; 0: 2017-04-25; 0: 2017-02-01
00127505 | 2017-02-24 | 0 | 0 | 2017-03-02 | 2017-03-02 | 2017-03-17 | 0 | 0 |  | 2017-04-03 | 2017-03-05 | 2017-04-03 | 2017-04-10 | 2017-03-16 | 2017-04-01 | 2017-07-20 | 2017-05-17 | 2017-08-10 | 2017-04-24 | 2017-07-25 | 2017-08-10 | 2017-08-10 |  |  | 2017-08-10
00127537 | 2017-02-03 | 0 | 0 | 2017-02-23 | 2017-02-23 | 2017-03-01 | 0 | 0 |  | 2017-03-28 | 2017-02-23 | 2017-04-14 | 2017-04-17 | 2017-03-28 | 2017-04-06 | 2017-05-05 | 2017-02-01 | 2017-06-15 | 2017-03-14 | 2017-05-17 | 2017-06-05 | 2017-06-13 | 2016-07-07 | 2017-07-10 | 2017-07-06
00127988 | 0 | 0 | 0 | 0 | 2017-02-28 | 0 |  | 2017-05-11 |  | 0: 2017-05-04; 0: 2017-05-10; 0: 2017-04-20; 0: 2017-05-08
00128157 | 2017-03-09 | 0 | 0 | 2017-04-18 | 2017-04-18 | 2017-05-01 | 0 | 0 |  | 2017-06-05 | 2017-05-04 | 2017-06-29 | 2017-07-10 | 2017-05-03 | 2017-05-22 | 2017-08-24 | 2017-08-25 | 2017-08-30 |  | 2017-08-25 | 2017-08-30
00128173 | 2017-04-14 | 0 | 0 | 2017-04-28 | 2017-04-28 | 2017-05-05 | 0 | 0 |  | 2017-05-11 |  | 0 | 0 | 2017-05-20 | 0 |  | 2017-08-14
00128325 | 2017-05-22 | 0 | 0 | 2017-05-24 | 2017-06-08 | 2017-06-09 | 0 | 0 |  | 2017-06-20 | 0 | 2017-07-12 | 0 | 2017-06-26 | 2017-07-06 | 2017-07-12 | 2017-07-12 |  | 2017-07-07 | 0 |  | 0
00128531 | 2017-02-03 | 0 | 0 | 2017-02-08 | 2017-02-09 | 2017-03-17 | 0 | 0 |  | 2017-04-03 | 2017-03-08 | 2017-04-03 | 2017-04-04 | 2017-03-28 | 2017-04-01 | 2017-04-05 | 2017-06-01 | 2017-08-10 | 2017-03-27 | 2017-04-11 | 2017-07-24
00128743 | 2017-03-22 | 0 | 0 | 2017-04-13 | 2017-04-17 | 2017-04-24 | 0 | 0 |  | 2017-05-01 | 2017-04-17 | 2017-06-16 | 2017-06-16 | 2017-04-27 | 2017-06-16 | 2017-06-16 | 2017-06-13 | 2017-08-10 | 2017-07-05 | 2017-06-30 | 2017-08-21
00129045 | 2017-05-30 | 0 | 0 | 2017-07-20 | 2017-07-21 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2017-08-06 | 0 | 0 | 2017-08-06 |  |  | 0 |  | 0
00129276 | 0 | 0 | 0 | 0 | 2017-05-08 | 2017-05-08 | 0 | 2017-05-08 |  | 0: 2017-05-11; 0: 2017-05-08; 0: 2017-05-18; 0: 2017-05-22
00129427 | 2017-04-19 | 0 | 0 | 2017-04-25 | 2017-04-25 | 2017-05-02 | 2017-05-10 | 2017-05-10 |  | 0: 2017-05-15; 0: 0; 0: 2017-05-01; 0: 2017-05-14; 0: 2017-06-13 | 2017-05-15
00129450 | 2017-05-11 | 2017-05-12 | 0 |  |  | 2017-05-12 | 0 | 0 |  | 0: 2017-05-31; 0: 0
00129652 | 2017-04-12 | 2017-04-12 | 2017-05-18 | 2017-05-26 | 2017-05-26 | 2017-05-30 | 2017-06-30 | 2017-05-31 |  | 2017-06-08 | 2017-05-31 | 2017-06-21 | 2017-06-21 | 2017-06-20 | 2017-06-16 | 2017-07-18 | 2017-06-30 | 2017-08-18 | 2017-06-09 | 2017-07-25 | 2017-08-18
00129716 | 2017-02-17 | 0 | 0 | 2017-03-20 | 2017-03-21 | 2017-03-22 | 0 | 0 |  | 2017-03-29 | 2017-03-27 | 2017-04-19 | 2017-04-21 | 2017-04-10 | 2017-04-06 | 2017-06-01 | 2017-04-13 | 2017-06-27 | 2017-06-12 | 2017-06-05 | 2017-06-26 | 2017-08-01 | 2017-07-17 |  | 2017-08-01
00129820 | 2017-04-12 | 0 | 0 | 2017-04-17 | 2017-04-17 | 2017-04-24 | 0 | 0 |  | 2017-05-02 | 2017-04-17 | 2017-05-02 | 2017-05-03 | 2017-04-25 | 2017-05-02 | 2017-05-08 | 2017-05-02 | 2017-07-06 | 2017-04-19 | 2017-05-09 | 2017-06-06 | 2017-06-30 | 2017-08-08 | 2017-08-08 | 2017-07-06
00129851 | 2017-02-14 | 2017-03-07 | 0 | 2017-03-24 | 2017-03-27 | 2017-03-23 | 0 | 0 |  | 2017-04-03 | 2017-03-29 | 2017-04-05 | 2017-04-11 | 2017-04-18 | 2017-04-05 | 2017-04-16 | 2017-02-01 | 2017-06-01 |  | 2017-04-17 | 2017-06-01 | 2017-06-06 | 2017-06-01 | 2017-06-06
00130575 | 2017-03-08 | 0 | 0 | 2017-03-13 | 2017-03-13 | 2017-03-23 | 0 | 0 |  | 2017-03-30 | 2017-03-20 | 2017-03-30 | 2017-04-10 | 2017-04-17 | 2017-04-10 | 2017-06-16 | 2017-04-25 | 2017-08-18 | 2017-07-27 | 2017-06-27 | 2017-07-27
00130583 | 2017-08-16 | 0 | 0 | [6 empty] | 0: 2017-08-07
00130757 | 2017-04-07 | 2017-04-08 | 2017-04-28 | 2017-05-19 | 2017-05-19 | 2017-05-22 | 0 | 2017-05-22 |  | 2017-05-30 | 2017-06-02 | 2017-06-29 | 2017-06-29 | 2017-06-02 | 2017-06-29 | 2017-07-31 | 2017-06-14 | 2017-08-30 | 2017-06-21 | 2017-08-01 | 2017-08-30
00130793 | 2017-02-21 | 2017-03-23 | 2017-05-15 | 2017-05-17 | 2017-05-19 | 2017-05-26 | 0 | 2017-06-05 |  | 2017-06-13 | 2017-06-02 | 2017-08-25 | 2017-08-28 | 2017-06-09 | 2017-07-24 |  | 2017-07-17
00130803 | 2017-05-04 | 0 | 0 | 0 | 2017-06-22 | 0 | 0 | 0 |  | 0 | 2017-05-30 | 0 | 0 | 2017-07-17 | 0 | 0 |  |  |  | 2017-05-30
00131329 | 2017-05-03 | 0 | 0 | 2017-05-26 | 2017-06-02 | 2017-06-02 | 2017-07-07 | 2017-06-05 |  | 2017-06-15 | 2017-08-07 | 2017-07-24 | 2017-07-25 | 2017-06-22 | 2017-07-07 | 2017-08-07 | 2017-07-05 |  | 2017-06-09
00131580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0: 0; 0: 0; 0: 2017-06-20; 0: 2017-07-11
00131837 | 2017-03-29 | 0 | 0 | 2017-06-01 | 2017-06-05 | 0 | 0 | 0 |  | 0 | 0 | 2017-05-19 | 2017-05-24 | 2017-06-21 | 2017-05-19 | 2017-06-12 | 2017-08-14 | 2017-08-18 | 2017-06-07 | 2017-06-12 | 2017-08-17
00131840 | 2017-06-30 | 0 | 0 | 2017-08-09 | 2017-08-18 | 2017-08-24 |  | 0 |  | 0: 0
00131953 | 2017-01-20 | 2017-03-16 | 2017-01-22 | 2017-01-22 | 2017-01-22 | 2017-01-26 | 0 | 0 |  | 2017-02-06 | 2017-07-11 | 2017-03-20 | 2017-03-26 | 2017-02-23 | 2017-03-20 | 2017-04-17 | 2017-06-30 | 2017-08-18 | 2017-07-06 | 2017-07-12 | 2017-08-18
00132020 | 2017-03-09 | 2017-03-09 | 2017-03-30 | 2017-06-05 | 2017-06-06 | 2017-06-06 | 0 | 2017-06-06 |  | 2017-06-26 | 2017-06-06 | 2017-08-04 | 2017-08-04 | 2017-06-20 | 2017-08-03 |  | 2017-08-03
00132110
00132173 | 2017-05-18 | 2017-06-07 | 2017-06-08 | 2017-08-11 | 2017-08-18 | 2017-08-11 | 0 | 2017-08-14 |  | 0: 2017-08-29; 0: 2017-08-23
00132200 | 2017-06-04 | 0 | 0 | 2017-06-20 | 2017-06-22 | 0 | 0 | 2017-06-30 |  | 0 | 0 | 2017-08-01 | 2017-08-02 | 2017-07-18 | 2017-07-07 | 2017-08-10 | 2017-07-25 |  | 2017-06-16 | 2017-08-17
00132700 | 2017-04-07 | 2017-04-07 | 0 | 2017-07-14 | 2017-08-01 | 2017-08-01 | 0 | 2017-08-04 |  | 2017-08-07 | 2017-08-01 | 2017-08-25 | 2017-08-25 | 2017-08-10 | 2017-08-24 |  | 2017-08-17 |  | 2017-08-02
00132705 | [7 empty] | 0 | [16 empty] | 0
00132956 | 2017-02-23 | 0 | 0
00133054 | 2017-07-14 | 0 | 0 | 2017-07-21 | 2017-07-21 | 2017-07-27 | 0 | 2017-08-08 |  | 2017-08-11 | 2017-07-27 | 2017-08-23 | 2017-08-30 | 2017-08-15 | 2017-08-21 |  | 2017-08-24
00133153 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-07-22 | 2017-07-25 | 2017-07-25 | 0 | 2017-06-01 |  | 2017-07-27 | 2017-07-25 | 2017-08-07 | 2017-08-08 | 2017-08-02 | 2017-08-08 | 2017-08-17 | 2017-08-08 |  | 2017-07-27 | 2017-08-21
00133286 | 2017-03-14 | 2017-03-14 | 0 | 2017-06-09 | 2017-06-12 | 2017-07-10 | 0 | 2017-06-15 |  | 2017-07-18 | 2017-06-19 | 2017-08-12 | 2017-08-14 | 2017-07-05 | 2017-08-04 |  | 2017-08-08
00133290 | 2017-06-16 | 0 | 0 | 2017-06-18 | 2017-06-22 | 2017-06-19 | 0 | 0 |  | 2017-06-26 | 2017-06-28 | 2017-06-29 | 2017-06-29 | 2017-07-25 | 2017-06-26 | 2017-07-25 | 2017-08-03 | 2017-08-18 | 2017-07-20 | 2017-07-26 | 2017-08-18
00133341 | 2017-06-15 | 0 | 2017-06-15 | 2017-06-27 | 2017-07-03 | 2017-07-06 | 0 | 2017-07-10 |  | 2017-07-27 | 2017-07-10 | 2017-08-09 | 2017-08-14 | 2017-07-17 | 2017-08-08 | 2017-08-21 | 2017-08-08 |  |  | 2017-08-21
00133457 | 2017-07-06 | 0 | 0 | 2017-07-27 | 2017-08-01 | 2017-08-02 | 0 | 0 |  | 2017-08-14 | 2017-07-13 | 2017-08-28 | 2017-08-29 | 2017-08-07 | 2017-08-28 |  | 2017-08-28
00133613 | 2017-05-02 | 0 | 0 | 2017-08-17 | 2017-08-18
00133684 | 2017-07-06 | 2017-08-25 | 0 | 2016-07-07 | 2017-07-13 | 2017-07-13 | 0 | 2017-08-09 |  | 2017-07-24 | 2017-07-18 | 2017-08-25 | 2017-08-28 | 2017-07-20 | 2017-08-21 |  | 2017-08-14
00134035 | 2017-05-09 | 2017-05-09 | 2017-05-18 | 2017-06-01 | 2017-06-02 | 2017-06-02 | 0 | 2017-06-05 |  | 2017-06-15 | 2017-06-07 | 2017-07-27 | 2017-07-27 | 2017-06-09 | 2017-07-12 | 2017-08-25 | 2017-06-26 |  | 2017-08-01
00134232 | 2017-06-05 | 2017-06-29 | 0 | 2017-07-24 | 2017-07-27 | 2017-07-27 | 0 | 0 |  | 2017-08-09 | 2017-08-01 | 2017-08-11 | 2017-08-15 | 2017-08-02 | 2017-08-10 |  | 2017-08-11
00134236 | 2017-02-10 | 0 | 0 | 2017-07-13 | 2017-07-20 | 2017-07-13 | 0 | 2017-07-31 |  | 2017-07-17 | 2017-08-02 | 2017-08-03 | 2017-08-03 | 2017-08-09 | 2017-07-21 | 2017-08-14 | 2017-08-24 |  | 2017-08-02 | 2017-08-17
00134443 | 2017-05-16 | 2017-05-16 | 2017-05-26 | 2017-06-29 | 2017-06-29 | 2017-07-06 | 0 | 2017-07-05 |  | 2017-07-17 | 2017-07-06 | 2017-08-08 | 2017-08-09 | 2017-07-07 | 2017-08-03 |  | 2017-07-25
00134444 | 2017-04-19 | 0 | 2017-04-21 | 2017-07-24 | 2017-07-27 | 2017-07-27 | 0 | 2017-06-05 |  | 2017-08-08 | 2017-08-07 | 2017-08-16 | 2017-08-17 | 2017-08-21 | 2017-08-14 |  | 2017-08-23
00134459 | 2017-08-01 | 0 | 0
00134857 | 2017-03-27 | 0 | 0 | 2017-05-10 | 2017-05-10 | 2017-05-07 | 0 | 0 |  | 0: 2017-06-12; 0: 2017-03-31; 0: 2017-05-19; 0: 2017-08-14; 0: 2017-07-19
00134870 | 2017-07-14 | 0 | 0 | 2017-07-21 | 2017-07-21 | 2017-07-27 | 0 | 2017-08-22 |  | 2017-08-11 | 2017-08-22 | 2017-08-24 | 2017-08-30 | 2017-07-28 | 2017-08-17 |  | 2017-08-11
00134884 | 2017-02-03 | 2017-04-25 | 2017-02-07 | 2017-08-17 | 2017-08-17 | 2017-08-18 | 0 | 2017-08-28 |  | 0: 2017-08-30; 0: 2017-08-21; 0: 2017-08-24
00134895 | 2017-08-08 | 0 | 0 | 2017-08-17 | 2017-08-17 | 2017-08-18 |  |  |  | 0: 2017-08-30
00134896 | 2017-08-08 | 0 | 0 | 2017-08-17 | 2017-08-17 | 2017-08-18 |  |  |  | 0: 2017-08-30
00134997 | 2017-07-10 | 0 | 0 | 2017-07-17 | 2017-07-19 | 2017-07-20 | 0 | 2017-07-31 |  | 2017-08-01 | 2017-07-14 | 2017-08-21 | 2017-08-21 | 2017-08-11 | 2017-08-07 | 2017-08-21 | 2017-08-15 |  | 2017-08-23 | 2017-08-22
00135072 | 2017-08-17 | 0 | 0
00135388 | 2017-01-24 | 0 | 0 | 2017-02-01 | 2017-02-01 | 2017-02-07 | 0 | 0 |  | 2017-02-23 | 2017-02-10 | 2017-05-17 | 2017-05-18 | 2017-05-22 | 2017-04-24 | 2017-07-05 | 2017-02-01 | 2017-08-18 |  | 2017-07-20 | 2017-08-18
10-JAYASUNDERA | 2017-02-03 | 0
111-HIGGINS | 2017-04-20 | 2017-04-20 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
112-FLAHERTY | 2017-04-20 | 2017-06-30 | 2017-07-06 | 2017-07-07 | 2017-07-13 | 2017-07-27 | 0 | 2017-07-19 |  | 0: 2017-08-02; 0: 2017-08-03; 0: 2017-08-23; 0: 2017-07-20; 0: 2017-07-28
12-HIGGINS | 2017-02-03 | 2017-02-03 | 2017-02-07
131-LUGOGO | 2017-04-28 | 2017-05-01 | 2017-05-30 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
142-FLAHERTY | 2017-05-03 | 2017-05-09
179-LUGOGO | 2017-04-28 | 2017-05-03 | 0 | 2017-07-17 | 2017-07-21 | 2017-07-21 | 0 | 2017-07-24 |  | 0: 2017-08-11; 0: 2017-07-24; 0: 2017-08-11; 0: 2017-08-24
187-MCLAUGHLIN
188-RUBENSTEIN | 2017-05-15 | 2017-05-15 | 2017-06-01
192-ALAM | 2017-05-15
194-MCLAUGHLIN | 2017-05-18 | 2017-06-06
198-LUCKRITZ | 2017-05-18 | 2017-05-19 |  | 2017-08-24 | 2017-08-25 | 2017-08-25 |  | 0 |  | 0: 2017-08-30; 0: 2017-08-25
201-MCCUNE | 2017-05-18 | 2017-06-15 | 2017-06-15 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
205-HIGGINS | 2017-05-19 | 2017-06-13 | 2017-06-14 | 2017-08-21 | 2017-08-25 | 2017-08-28
227-STEIGERWALT | 0 | 2017-02-06 | 0 | 2017-06-22 | 2017-08-09 |  |  | 2017-08-17
234-MCLAUGHLIN | 2017-05-25 | 2017-06-06 | 2017-06-07
235-SUGAR | 2017-05-26 | 0 | 0 | 2017-06-09 | 2017-06-09 | 2017-06-16 | 0 | 0 |  | 0: 2017-06-30; 0: 2017-06-23; 0: 2017-08-09
238-GUNNERSON | 2017-05-30 | 2017-07-11 | 2017-08-15
242-AS-SANIE | 2017-05-31 | 2017-07-18 | 2017-07-18
246-AS-SANIE | 2017-06-02
255-LOK | 2017-06-07 | 2017-07-11 | 2017-07-11
258-SHEEHAN | 2017-06-08 | 2017-06-14 | 2017-06-29
261-LUGOGO | 2017-06-08 | 2017-07-14 | 2017-07-14
263-DELMONTE | 2017-06-09 | 2017-06-13 | 2017-06-14
268-NEUMAR
298-SCHIOPU | 2017-06-21 | 2017-07-10 | 2017-07-10
2-MARSH | 2017-01-30 | 2017-01-30
305-PELOSI | 2017-06-22 | 2017-01-23 | 0
309-MOROI | 2017-06-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2017-07-20 | 0 | 0 | 2017-07-20 | 2017-08-03 | 0 | 0 | 0 | 2017-08-03 | 0 | 0 | 0 | 0 | 0
30-FLAHERTY | 2017-02-14 | 2017-02-21 | 2017-02-22
313-CONJEEVARAM | 2017-06-26 | 2017-08-24 | 2017-08-24
314-PARK | 2017-06-28 | 2017-04-19 | 2017-07-18
323-BOLLING | 2017-06-29 | 2017-08-21 | 2017-08-22
326-HIGGINS | 2017-07-03 | 0 | 0 | 2017-08-21 | 2017-08-25 | 2017-08-28
327-HIGGINS | 2017-07-03 | 0 | 0 | 2017-08-21 | 2017-08-25 | 2017-08-28
331-FLAHERTY | 2017-07-05 | 2017-08-07 | 2017-08-07 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332-BELLOLI | 2017-07-05 | 2017-07-19 | 2017-07-20 | 2017-08-28 | 2017-08-29 | 2017-08-29
337-MIAN | 2017-07-06 | 0 | 0 | 2017-07-27 | 2017-08-01 | 2017-08-02 | 0 | 0 |  | 0: 2017-08-14; 0: 2017-07-13; 0: 2017-08-28; 0: 2017-08-29; 0: 2017-08-09; 0: 2017-08-28; 0: 2017-08-28
342-HUMES | 2017-07-10 | 0 | 0
346-BAPTIST | 2017-07-12 | 0 | 0
347-HIGGINS | 2017-07-12 | 2017-07-26 | 2017-07-26 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348-CHEY | 2017-07-13
34-MARSH | 2017-02-17 | 2017-05-08 | 2017-05-08
354-PAGANI | 2017-07-16 | 2017-08-02 | 2017-08-03
359-SMITH | 2017-07-18 | 2017-08-02 | 2017-08-02
361-HASAN | 2017-07-19 |  | 2017-07-21
363-PARK | 2017-07-21 | 2017-08-04
364-KHAJA | 2017-07-24 | 0 | 0
370-LOK | 2017-07-25 | 2017-08-01 | 2017-08-02
371-LOK | 2017-07-25 | 2017-08-02 | 2017-08-02
375-JAMERSON | 2017-07-26 | 2017-08-01 | 2017-08-02 | 2017-08-25
37-SILVER | 2017-02-23 | 0 | 0
380-LOK | 2017-07-31
381-HIGGINS | 2017-07-31 | 2017-08-04 | 2017-08-07
385-MCLAUGHLIN | 2017-08-01 |  | 2017-08-03
390-DAY | 2017-08-03 | 0 | 0
393-HYZY | 2017-08-07
396-SCHIOPU | 2017-08-07 | 2017-08-14 | 2017-08-14
397-HODISH | 2017-08-07 | 0 | 2017-08-07 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409-NASR | 0 | 0 | 0 | 0 | 2017-08-11 | 2017-08-20 |  |  |  | 0: 2017-08-15
410-PAULUS | 2017-08-09 | 0 | 2017-08-17
412-NASR | 2017-08-10 | 2017-08-11
415-ROMANO | 2017-08-11 | 0 | 0 | 2017-07-12 |  |  |  | 0
427-KOSCHMANN | 2017-08-16
430-HIGGINS | 2017-08-18
432-JAYASUNDERA | 2017-08-18
435-MOROI | 2017-08-21 | 0 | [5 empty] | 0 |  | 0: 0; 0: 0; 0: 0
439-KHANNA | 2017-08-23
440-LOK | 2017-08-23
447-RAO | 2017-08-28 | 0 | 0
44-MCUNE | 2017-02-28 | 2017-03-13 | 2017-07-13
46-HIGGINS | 2017-03-06 | 0 | 0 | 2017-06-09 | 2017-06-12 | 0 | 0 | 2017-07-13 |  | 0: 0; 0: 2017-06-30; 0: 2017-07-23; 0: 2017-07-24; 0: 2017-07-23; 0: 2017-08-25
69-KHANNA | 2017-03-23 | 0 |  |  |  | 0 | 0 | 0 |  | 0: 0; 0: 0; 0: 0; 0: 2017-03-28; 0: 0; 0: 0; 0: 2017-02-13
70-LUGOGO | 2017-03-27 | 2017-03-27 | 0 | 2017-05-26 | 2017-06-05 | 2017-06-05 | 0 | 2017-06-09 |  | 0: 2017-06-13; 0: 2017-06-07; 0: 2017-07-27; 0: 2017-07-27; 0: 2017-06-21; 0: 2017-07-06; 0: 2017-08-03
77-CONJEEVARAM | 2017-03-30 | 0 | 0 |  |  | 2017-04-18
81-HIGGINS | 2017-04-03
82-BOLLING | 2017-04-04 | 2017-04-18 | 2017-05-23
91-ELSE | 2017-04-11 | 2017-06-26 | 0
92-AUCHUS | 2017-04-11 | 2017-04-16
9-JAYASUNDERA | 2017-02-03 | 2017-01-20 | 2017-03-27
FONTANA-3 | 2017-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
MENEES-1 | 2017-01-30
SCHIOPU-1 | 2017-03-03

## UFA Completed Pivot Table
Count of NA | Column Labels
Row Labels | N | Y | Grand Total | N/A
UFA Completed | 84 | 76 | 160
00108880 |  | 1 | 1
00122254 |  | 1 | 1
00123861 |  | 1 | 1
00124712 |  | 1 | 1
00124920 |  | 1 | 1
00125022 |  | 1 | 1
00125425 |  | 1 | 1
00125566 |  | 1 | 1
00125786 |  | 1 | 1
00125794 |  | 1 | 1
00126010 |  | 1 | 1
00126215 |  | 1 | 1
00127136 |  | 1 | 1
00127356 |  | 1 | 1
00127505 |  | 1 | 1
00127537 |  | 1 | 1
00128157 |  | 1 | 1
00128173 |  | 1 | 1
00128325 |  | 1 | 1
00128531 |  | 1 | 1
00128743 |  | 1 | 1
00129427 |  | 1 | 1
00129450 | 1 |  | 1
00129652 | 1 |  | 1
00129716 |  | 1 | 1
00129820 |  | 1 | 1
00129851 | 1 |  | 1
00130575 |  | 1 | 1
00130757 | 1 |  | 1
00130793 | 1 |  | 1
00130803 |  | 1 | 1
00131329 |  | 1 | 1
00131837 |  | 1 | 1
00131953 | 1 |  | 1
00132020 | 1 |  | 1
00132200 |  | 1 | 1
10-JAYASUNDERA |  | 1 | 1
111-HIGGINS | 1 |  | 1
112-FLAHERTY | 1 |  | 1
12-HIGGINS | 1 |  | 1
131-LUGOGO | 1 |  | 1
142-FLAHERTY | 1 |  | 1
179-LUGOGO | 1 |  | 1
188-RUBENSTEIN | 1 |  | 1
201-MCCUNE | 1 |  | 1
205-HIGGINS | 1 |  | 1
235-SUGAR |  | 1 | 1
242-AS-SANIE | 1 |  | 1
246-AS-SANIE | 1 |  | 1
255-LOK | 1 |  | 1
261-LUGOGO | 1 |  | 1
263-DELMONTE | 1 |  | 1
298-SCHIOPU | 1 |  | 1
2-MARSH | 1 |  | 1
309-MOROI |  | 1 | 1
30-FLAHERTY | 1 |  | 1
313-CONJEEVARAM | 1 |  | 1
326-HIGGINS |  | 1 | 1
327-HIGGINS |  | 1 | 1
331-FLAHERTY | 1 |  | 1
332-BELLOLI | 1 |  | 1
337-MIAN |  | 1 | 1
34-MARSH | 1 |  | 1
44-MCUNE | 2 |  | 2
46-HIGGINS |  | 1 | 1
69-KHANNA |  | 1 | 1
70-LUGOGO | 1 |  | 1
77-CONJEEVARAM |  | 1 | 1
81-HIGGINS | 1 |  | 1
91-ELSE | 1 |  | 1
92-AUCHUS | 1 |  | 1
9-JAYASUNDERA | 1 |  | 1
FONTANA-3 |  | 1 | 1
MENEES-1 | 1 |  | 1
SCHIOPU-1 | 1 |  | 1
00133153 | 1 |  | 1
00132700 | 1 |  | 1
00133341 |  | 1 | 1
346-BAPTIST |  | 1 | 1
347-HIGGINS | 1 |  | 1
348-CHEY | 2 |  | 2
359-SMITH | 1 |  | 1
00133684 | 1 |  | 1
00133286 | 1 |  | 1
00134035 | 1 |  | 1
00133290 |  | 1 | 1
00133054 |  | 1 | 1
370-LOK | 1 |  | 1
371-LOK | 1 |  | 1
00134236 |  | 1 | 1
380-LOK | 1 |  | 1
381-HIGGINS | 1 |  | 1
00134444 |  | 1 | 1
00134232 | 1 |  | 1
00131840 |  | 1 | 1
396-SCHIOPU | 1 |  | 1
397-HODISH |  | 1 | 1
00127988 |  | 1 | 1
00129276 |  | 1 | 1
00131580 |  | 1 | 1
00091711 | 1 |  | 1
00132173 | 1 |  | 1
00133457 |  | 1 | 1
00134884 | 1 |  | 1
00133613 |  | 1 | 1
00134443 | 1 |  | 1
00134870 |  | 1 | 1
00134895 |  | 1 | 1
00134896 |  | 1 | 1
410-PAULUS |  | 1 | 1
00126224 |  | 1 | 1
00135072 |  | 1 | 1
430-HIGGINS | 1 |  | 1
432-JAYASUNDERA | 1 |  | 1
435-MOROI |  | 1 | 1
00111295 | 1 |  | 1
439-KHANNA | 1 |  | 1
440-LOK | 1 |  | 1
305-PELOSI | 1 |  | 1
00135388 |  | 1 | 1
227-STEIGERWALT | 1 |  | 1
00118070 |  | 1 | 1
37-SILVER |  | 1 | 1
00132956 |  | 1 | 1
00134857 |  | 1 | 1
82-BOLLING | 1 |  | 1
314-PARK | 1 |  | 1
192-ALAM | 1 |  | 1
194-MCLAUGHLIN | 1 |  | 1
198-LUCKRITZ | 1 |  | 1
234-MCLAUGHLIN | 1 |  | 1
00129045 |  | 1 | 1
268-NEUMAR | 1 |  | 1
323-BOLLING | 1 |  | 1
00132110 | 1 |  | 1
00134997 |  | 1 | 1
342-HUMES |  | 1 | 1
415-ROMANO |  | 1 | 1
354-PAGANI | 1 |  | 1
361-HASAN | 1 |  | 1
363-PARK | 1 |  | 1
364-KHAJA |  | 1 | 1
375-JAMERSON | 1 |  | 1
385-MCLAUGHLIN | 1 |  | 1
390-DAY |  | 1 | 1
393-HYZY | 1 |  | 1
00130583 |  | 1 | 1
409-NASR |  | 1 | 1
00132705 | 1 |  | 1
447-RAO |  | 1 | 1
00134459 |  | 1 | 1
412-NASR | 1 |  | 1
427-KOSCHMANN | 1 |  | 1
00121967 |  | 1 | 1
00123237 |  | 1 | 1
187-MCLAUGHLIN | 1 |  | 1
238-GUNNERSON | 1 |  | 1
258-SHEEHAN | 1 |  | 1
Grand Total | 84 | 76 | 160

## Sheet1
Row Labels | Department | Title | PI | Status | Intake Form Completed | UFA Completed | Sponsor Reach out | Feasibility w/Documents received | Feasibility approved/CRAO Notified | Feasibility Documents received to feasibility approval | Planning Meeting Request Sent | Request MCRU Budget | Request Research Pharmacy Budget | Planning Meeting Scheduled | Planning Meeting Completed | Time from Feasibility to Planning Meeting | Created CTRF & "Notify ORSP" | Billing Calendar Received | Care Designations completed | Internal Budget Finished | PI approved Budget | Time from Planning Meeting to PI approved Budget | Budget Negotiations | Final Budget | PI approved Budget to Final Budget | Calendar Released | IRB Application Submitted | Feasibility Approved to IRB Submission | PAF routed | OnCore Budget Build | PAN Released | PI Signoff in OnCore | PAF Routed to PAN released | Open to Accrual | Feasibility Approval to Open to Accrual
00108880 | Ophthalmology & Visual Sciences | An Open-label, Multi-Centre, Phase I/II Dose Escalation Trial of an Adeno-Associated Virus Vector (AAV2/5-OPTIRPE65) for Gene Therapy of Adults and Children with Retinal Dystrophy associated with Defects in RPE65 (LCA2) | Besirli, Cagri | PRMC APPROVAL | 2017-04-14 | NA | NA | 2017-04-28 | 2017-04-28 | 0 | 2017-05-05 | NA | NA |  | 2017-05-11 | 13 | 2017-06-30 | 2017-05-16 | 2017-08-09 | NA | NA |  | NA
00122254 | Internal Medicine | A Phase 1, First-in-Human Single Center Study in Healthy Volunteers to Assess the Gluten-Degradation Activity of Kuma062 | Turgeon, Danielle | PRMC APPROVAL | 2017-02-23 | NA | NA | 2017-03-01 | 2017-03-02 | 1 | 2017-02-23 | NA | NA |  | 2017-03-16 | 14 | 2017-03-08 | 2017-04-13 | 2017-05-23 | 2017-04-26 | 2017-05-02 | 47 | 2017-05-10 | 2017-07-06 | 65 | 2017-07-26 |  |  | 2017-07-10 | 2017-07-18
00125022 | Internal Medicine | A multi-centre, randomized, double-blind (sponsor open), placebocontrolled, repeat-dose, proof of mechanism study to evaluate the safety, tolerability, pharmacokinetics, pharmacodynamics and explore efficacy of GSK2330811 in participants with diffuse cutaneous systemic sclerosis. | Nagaraja, Vivek | PRMC APPROVAL | NA | NA | NA | 2017-02-21 | 2017-02-21 | 0 | 2017-03-03 | NA | NA |  | 2017-03-20 | 27 | 2017-02-23 | 2017-04-26 | 2017-06-07 | 2017-03-29 | 2017-03-30 | 10 | 2017-04-05 | 2017-07-09 | 101 | 2017-08-23 |  |  |  | 2017-08-23
00127136 | Internal Medicine | Prominent: Pemafibrate to Reduce Cardiovascular Outcomes by Reducing Triglycerides in Patients with Diabetes. | Busui, Rodica | PRMC APPROVAL | 2017-02-08 | NA | NA | 2017-02-13 | 2017-02-14 | 1 | 2017-02-21 | NA | NA |  | 2017-02-24 | 10 | 2017-02-21 | 2017-02-23 | 2017-03-28 | 2017-02-21 | 2017-03-10 | 14 | 2017-03-10 | 2017-05-22 | 73 | 2017-06-26 | 2017-06-19 | 125 | 2017-05-22 | 2017-06-12
00127356 | Internal Medicine | A Phase 2b/3, Multi-center, Randomized, Double-Blind, Parallel-Group, Placebo-Controlled, Multi-Dose Study to Evaluate the Safety and Efficacy of Two Dose Strengths of SYN-010 Compared with Placebo in Adult Subjects with Irritable Bowel Syndrome with Constipation (IBS-C) | Chey, William | PRMC APPROVAL | 2017-03-08 | NA | NA | 2017-03-13 | 2017-03-13 | 0 |  | NA | NA |  |  |  | 2017-03-29 | 2017-04-25 | 2017-02-01
00127505 | Internal Medicine | Phase 3, long-term active treatment extension study of Mongersen (GED-0301) in subjects with Crohn's disease | Higgins, Peter | PRMC APPROVAL | 2017-02-24 | NA | NA | 2017-03-02 | 2017-03-02 | 0 | 2017-03-17 | NA | NA |  | 2017-04-03 | 32 | 2017-03-05 | 2017-03-16 | 2017-05-17 | 2017-04-01 | 2017-04-03 | 0 | 2017-04-10 | 2017-07-20 | 108 | 2017-08-10 | 2017-04-24 | 53 | 2017-07-25 | 2017-08-10 | 2017-08-10 |  | 16
00128157 | Internal Medicine | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Induction Study of the Efficacy and Safety of Risankizumab in Subjects with Moderately to Severely Active Crohn's Disease | Higgins, Peter | PRMC APPROVAL | 2017-03-09 | NA | NA | 2017-04-18 | 2017-04-18 | 0 | 2017-05-01 | NA | NA |  | 2017-06-05 | 48 | 2017-05-04 | 2017-05-03 | 2017-08-25 | 2017-05-22 | 2017-06-29 | 24 | 2017-07-10 | 2017-08-24 | 56 | 2017-08-30 |  |  | 2017-08-25 | 2017-08-30
00128173 | Ophthalmology & Visual Sciences | An open label, multi-centre, Phase I/II dose escalation trial of an adeno-associated virus vector (AAV2/8- hCARp.hCNGB3) for gene therapy of adults and children with achromatopsia owing to defects in CNGB3 | Besirli, Cagri | PRMC APPROVAL | 2017-04-14 | NA | NA | 2017-04-28 | 2017-04-28 | 0 | 2017-05-05 | NA | NA |  | 2017-05-11 | 13 |  | 2017-05-20 | 2017-08-14 | NA | NA |  | NA
00129652 | Internal Medicine | A Phase 2, Multiple-Dose, Dose-Escalation Study to Evaluate the Safety and Efficacy of SPR001 in Adults with Classic Congenital Adrenal Hyperplasia (CAH) | Auchus, Richard | PRMC APPROVAL | 2017-04-12 | 2017-04-12 | 2017-05-18 | 2017-05-26 | 2017-05-26 | 0 | 2017-05-30 | 2017-06-30 | 2017-05-31 |  | 2017-06-08 | 13 | 2017-05-31 | 2017-06-20 | 2017-06-30 | 2017-06-16 | 2017-06-21 | 13 | 2017-06-21 | 2017-07-18 | 27 | 2017-08-18 | 2017-06-09 | 14 | 2017-07-25 | 2017-08-18
00130575 | Internal Medicine | Open-label Rollover Study of Cenicriviroc for the Treatment of Liver Fibrosis in Adult Subjects with Nonalcoholic Steatohepatitis (NASH) | Conjeevaram, Hari | PRMC APPROVAL | 2017-03-08 | NA | NA | 2017-03-13 | 2017-03-13 | 0 | 2017-03-23 | NA | NA |  | 2017-03-30 | 17 | 2017-03-20 | 2017-04-17 | 2017-04-25 | 2017-04-10 | 2017-03-30 | 0 | 2017-04-10 | 2017-06-16 | 78 | 2017-08-18 | 2017-07-27 | 136 | 2017-06-27 | 2017-07-27
00130793 | Internal Medicine | An Open Label Phase II Multiple Dose Safety, Pharmacokinetic and Pharmacodynamics Study of SEL-212 Followed by Open Label Administration of SEL-037 in Subjects with Symptomatic Gout and Elevated Blood Uric Acid | Khanna, Puja | PRMC APPROVAL | 2017-02-21 | 2017-03-23 | 2017-05-15 | 2017-05-17 | 2017-05-19 | 2 | 2017-05-26 | NA | 2017-06-05 |  | 2017-06-13 | 25 | 2017-06-02 | 2017-06-09 | 2017-07-17 | 2017-07-24 | 2017-08-25 | 73 | 2017-08-28
00130803 | Internal Medicine | An Investigator Initiated IND Open-Label, Randomized Study of Gemcabene in Adults with Familial Partial Lipodystrophy (FPL) | Oral, Elif | PRMC APPROVAL | 2017-05-04 | NA | NA | NA | 2017-06-22 |  | NA | NA | NA |  | NA |  | 2017-05-30 | 2017-07-17 |  | NA | NA |  | NA | NA |  |  |  |  | 2017-05-30
00131837 | Internal Medicine | Evaluation of tofacitinib in early diffuse cutaneous systemic sclerosis (dcSSc): A phase I/II two center safety and tolerability study | Khanna, Dinesh | PRMC APPROVAL | 2017-03-29 | NA | NA | 2017-06-01 | 2017-06-05 | 4 | NA | NA | NA |  | NA |  | NA | 2017-06-21 | 2017-08-14 | 2017-05-19 | 2017-05-19 |  | 2017-05-24 | 2017-06-12 | 24 | 2017-08-18 | 2017-06-07 | 2 | 2017-06-12 | 2017-08-17
00131840 | Internal Medicine | A Phase 1-2 Multi-Center Study to Assess the Efficacy and Safety of Abiraterone Acetate as Adjunctive Therapy in Pre-Pubescent Children with Classic 21-Hydroxylase Deficiency | Auchus, Richard | PRMC APPROVAL | 2017-06-30 | NA | NA | 2017-08-09 | 2017-08-18 | 9 | 2017-08-24 |  | NA |  |  |  | NA
00132020 | Internal Medicine | A randomized, double-blind, Sponsor open, placebo-controlled, 52 week study evaluation the effect of danirixin (GSK1325756) on lung function and health related quality of life in participants with mild to moderate Chronic Obstructive Pulmonary Disease (COPD). | Lugogo, Njira | PRMC APPROVAL | 2017-03-09 | 2017-03-09 | 2017-03-30 | 2017-06-05 | 2017-06-06 | 1 | 2017-06-06 | NA | 2017-06-06 |  | 2017-06-26 | 20 | 2017-06-06 | 2017-06-20 | 2017-08-03 | 2017-08-03 | 2017-08-04 | 39 | 2017-08-04
00132173 | Internal Medicine | A double-blind, placebo-controlled, randomized withdrawal following open-label therapy study to assess the safety and efficacy of levoketoconazole (3S, 4R-ketoconazole) in the treatment of endogenous Cushings syndrome (LOGICS  LevOketoconazole to fill a Gap in CS). | Else, Tobias | PRMC APPROVAL | 2017-05-18 | 2017-06-07 | 2017-06-08 | 2017-08-11 | 2017-08-18 | 7 | 2017-08-11 | NA | 2017-08-14 |  | 2017-08-29 | 11 | 2017-08-23
00132200 | Internal Medicine | Evaluation of Brentuximab Vedotin for Diffuse Cutaneous Systemic Sclerosis: A Phase 1/2 Multicenter Randomized, Double Blinded, Safety Study | Khanna, Dinesh | PRMC APPROVAL | 2017-06-04 | NA | NA | 2017-06-20 | 2017-06-22 | 2 | NA | NA | 2017-06-30 |  | NA |  | NA | 2017-07-18 | 2017-07-25 | 2017-07-07 | 2017-08-01 |  | 2017-08-02 | 2017-08-10 | 9 |  | 2017-06-16 | -6 | 2017-08-17
00132700 | Internal Medicine | A Phase 2, Open-Label, Multiple-Dose Study to Evaluate the Safety, Tolerability, Pharmacokinetics, and Pharmacodynamics of NBI-74788 in Adult Subjects with Congenital Adrenal Hyperplasia | Auchus, Richard | PRMC APPROVAL | 2017-04-07 | 2017-04-07 | NA | 2017-07-14 | 2017-08-01 | 18 | 2017-08-01 | NA | 2017-08-04 |  | 2017-08-07 | 6 | 2017-08-01 | 2017-08-10 | 2017-08-17 | 2017-08-24 | 2017-08-25 | 18 | 2017-08-25 |  |  |  | 2017-08-02 | 1
00133054 | Internal Medicine | ECOSPOR III: A Phase 2 Multicenter, Randomized, Double-Blind, Placebo-Controlled, Parallel-Group Study to Evaluate the Safety, Tolerability, and Efficacy of SER-109 vs. Placebo to Reduce Recurrence of Clostridium Difficile Infection (CDI) in Adults Who Have Received Antibacterial Drug Treatment for Recurrent CDI (RCDI) | Higgins, Peter | PRMC APPROVAL | 2017-07-14 | NA | NA | 2017-07-21 | 2017-07-21 | 0 | 2017-07-27 | NA | 2017-08-08 |  | 2017-08-11 | 21 | 2017-07-27 | 2017-08-15 | 2017-08-24 | 2017-08-21 | 2017-08-23 | 12 | 2017-08-30
00133153 | Internal Medicine | A Single Arm, Open Label, Multicenter Study to Evaluate the Efficacy and Safety of Glecaprevir(GLE)/Pibrentasvir(PIB) in Treatment Naïve Adults with Chronic Hepatitis C Virus (HCV) Genotypes 1  6 Infection and Aspartate aminotransferase to Platelet Ratio Index (APRI) &#8804; 1 | Conjeevaram, Hari | PRMC APPROVAL | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-07-22 | 2017-07-25 | 3 | 2017-07-25 | NA | 2017-06-01 |  | 2017-07-27 | 2 | 2017-07-25 | 2017-08-02 | 2017-08-08 | 2017-08-08 | 2017-08-07 | 11 | 2017-08-08 | 2017-08-17 | 10 |  | 2017-07-27 | 2 | 2017-08-21
00133286 | Internal Medicine | A Phase 2, Randomized, Double-Blind, Multicenter Study Evaluating the Safety and Efficacy of Filgotinib and GS-9876 in Subjects with Lupus Membranous Nephropathy (LMN) | Rao, Panduranga | PRMC APPROVAL | 2017-03-14 | 2017-03-14 | NA | 2017-06-09 | 2017-06-12 | 3 | 2017-07-10 | NA | 2017-06-15 |  | 2017-07-18 | 36 | 2017-06-19 | 2017-07-05 | 2017-08-08 | 2017-08-04 | 2017-08-12 | 25 | 2017-08-14
00133290 | Internal Medicine | Multi-center, Randomized, Parallel, Adaptive, Controlled Trial in Adult and Pediatric Patients with Type 1 Diabetes Using Hybrid Closed Loop System and Control (CSII, MDI and SAP) at Home | Busui, Rodica | PRMC APPROVAL | 2017-06-16 | NA | NA | 2017-06-18 | 2017-06-22 | 4 | 2017-06-19 | NA | NA |  | 2017-06-26 | 4 | 2017-06-28 | 2017-07-25 | 2017-08-03 | 2017-06-26 | 2017-06-29 | 3 | 2017-06-29 | 2017-07-25 | 26 | 2017-08-18 | 2017-07-20 | 28 | 2017-07-26 | 2017-08-18
00133341 | Internal Medicine | A Phase 2A, Randomized, Double-Blind, Placebo-Controlled, Dose-Ranging, Parallel Group Study to Evaluate Safety, Tolerability, and Pharmacodynamics of PF-05221304 Administered Daily for 16-Weeks to Adult Subjects with Nonalcoholic Fatty Liver Disease | Conjeevaram, Hari | PRMC APPROVAL | 2017-06-15 | NA | 2017-06-15 | 2017-06-27 | 2017-07-03 | 6 | 2017-07-06 | NA | 2017-07-10 |  | 2017-07-27 | 24 | 2017-07-10 | 2017-07-17 | 2017-08-08 | 2017-08-08 | 2017-08-09 | 13 | 2017-08-14 | 2017-08-21 | 12 |  |  |  | 2017-08-21
00133457 | Ophthalmology & Visual Sciences | A Phase 3, Multi-center, Randomized, Double-Masked Study to Evaluate the Clinical Efficacy and Safety of SHP640 (PVP-Iodine 0.6% and Dexamethasone 0.1%) Ophthalmic Suspension Compared to Placebo in the Treatment of Bacterial Conjunctivitis | Mian, Shahzad | PRMC APPROVAL | 2017-07-06 | NA | NA | 2017-07-27 | 2017-08-01 | 5 | 2017-08-02 | NA | NA |  | 2017-08-14 | 13 | 2017-07-13 | 2017-08-07 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 14 | 2017-08-29
00133613 | Surgery | Clinical Trial for Surgery of the Ulnar Nerve (SUN) at the Elbow | Chung, Kevin | PRMC APPROVAL | 2017-05-02 | NA | NA | 2017-08-17 | 2017-08-18 | 1
00133684 | Internal Medicine | A Phase 4, Randomized, Double-Blind, Multicenter, Placebo-Controlled Study to Evaluate the Safety and Efficacyof Lesinurad 200 mg in Combination With a Xanthine OxidaseInhibitor (XOI), Compared With an XOI Alone, in Subjects With Gout and Estimated Creatinine Clearance 30 to <60 mL/min Who Have Not Achieved Target Serum Uric Acid Levels on an XOI Alone | Khanna, Puja | PRMC APPROVAL | 2017-07-06 | 2017-08-25 | NA | 2017-07-07 | 2017-07-13 | 6 | 2017-07-13 | NA | 2017-08-09 |  | 2017-07-24 | 11 | 2017-07-18 | 2017-07-20 | 2017-08-14 | 2017-08-21 | 2017-08-25 | 32 | 2017-08-28
00134035 | Internal Medicine | Belimumab for Maintenance Therapy in Idiopathic Inflammatory Myositis | Schiopu, Elena | PRMC APPROVAL | 2017-05-09 | 2017-05-09 | 2017-05-18 | 2017-06-01 | 2017-06-02 | 1 | 2017-06-02 | NA | 2017-06-05 |  | 2017-06-15 | 13 | 2017-06-07 | 2017-06-09 | 2017-06-26 | 2017-07-12 | 2017-07-27 | 42 | 2017-07-27 | 2017-08-25 | 29 |  | 2017-08-01 | 60
00134232 | Ophthalmology & Visual Sciences | A Phase III Multicenter Randomized, Sham Controlled, Study to Determine the Safety and Efficacy of Renexus® in Macular Telangiectasia type 2 | Comer, Grant | PRMC APPROVAL | 2017-06-05 | 2017-06-29 | NA | 2017-07-24 | 2017-07-27 | 3 | 2017-07-27 | NA | NA |  | 2017-08-09 | 13 | 2017-08-01 | 2017-08-02 | 2017-08-11 | 2017-08-10 | 2017-08-11 | 2 | 2017-08-15
00134236 | Internal Medicine | A Phase 3, Randomized, Double-Blind, Study Comparing ABT-494 to Placebo and to Adalimumab in Subjects with Active Psoriatic Arthritis Who Have a History of Inadequate Response to at Least One Non-Biologic Disease Modifying Anti-Rheumatic Drug (DMARD)  SELECT  PsA 1 | Schiopu, Elena | PRMC APPROVAL | 2017-02-10 | NA | NA | 2017-07-13 | 2017-07-20 | 7 | 2017-07-13 | NA | 2017-07-31 |  | 2017-07-17 | -3 | 2017-08-02 | 2017-08-09 | 2017-08-24 | 2017-07-21 | 2017-08-03 | 17 | 2017-08-03 | 2017-08-14 | 11 |  | 2017-08-02 | 13 | 2017-08-17
00134443 | Internal Medicine | A Phase 3, Randomized, Double-Blind Clinical Trial to Evaluate the Efficacy and Safety of Abatacept SC with Standard Treatment Compared to Standard Treatment Alone in Improving Disease Activity in Adults with Active Idiopathic Inflammatory Myopathy (IIM) | Schiopu, Elena | PRMC APPROVAL | 2017-05-16 | 2017-05-16 | 2017-05-26 | 2017-06-29 | 2017-06-29 | 0 | 2017-07-06 | NA | 2017-07-05 |  | 2017-07-17 | 18 | 2017-07-06 | 2017-07-07 | 2017-07-25 | 2017-08-03 | 2017-08-08 | 22 | 2017-08-09
00134444 | Internal Medicine | A Phase 3, Multicenter, Randomized, Double-blind, Placebo-controlled Study Evaluating the Efficacy and Safety of Guselkumab Administered Subcutaneously in Subjects with Active Psoriatic Arthritis including those Previously Treated with Biologic Anti-TNF&#945; Agent(s) | Schiopu, Elena | PRMC APPROVAL | 2017-04-19 | NA | 2017-04-21 | 2017-07-24 | 2017-07-27 | 3 | 2017-07-27 | NA | 2017-06-05 |  | 2017-08-08 | 12 | 2017-08-07 | 2017-08-21 | 2017-08-23 | 2017-08-14 | 2017-08-16 | 8 | 2017-08-17
00134857 | Internal Medicine | Multicenter, prospective, randomized study comparing the PillCam® Crohns capsule endoscopy to Ileocolonoscopy (IC) plus MRE [Magnetic Resonance Enterography] for detection of active CD in the small bowel and colon in subjects with known CD and mucosal disease (the BLINK study) Clinical Investigation Plan (Protocol), incorporated herein by reference. | Rice, Michael | PRMC APPROVAL | 2017-03-27 | NA | NA | 2017-05-10 | 2017-05-10 | 0 | 2017-05-07 | NA | NA |  | 2017-06-12 | 33 | 2017-03-31 | 2017-05-19 | 2017-07-19 | 2017-08-14
00134870 | Internal Medicine | ECOSPOR IV: An Open-Label Extension of Study SERES-012 Evaluating SER-109 in Adult Subjects with Recurrent Clostridium difficile Infection (RCDI) | Higgins, Peter | PRMC APPROVAL | 2017-07-14 | NA | NA | 2017-07-21 | 2017-07-21 | 0 | 2017-07-27 | NA | 2017-08-22 |  | 2017-08-11 | 21 | 2017-08-22 | 2017-07-28 | 2017-08-11 | 2017-08-17 | 2017-08-24 | 13 | 2017-08-30
00134884 | Internal Medicine | A Phase 3 Randomized, Double-blind, Placebo-controlled, Parallel-group Efficacy and Safety Study of SHP647 as Induction Therapy in Subjects with Moderate to Severe Ulcerative Colitis (FIGARO UC 302) | Higgins, Peter | PRMC APPROVAL | 2017-02-03 | 2017-04-25 | 2017-02-07 | 2017-08-17 | 2017-08-17 | 0 | 2017-08-18 | NA | 2017-08-28 |  | 2017-08-30 | 13 | 2017-08-21 | 2017-08-24
00134895 | Internal Medicine | A Phase 3 Randomized, Double-blind, Placebo-controlled, Parallel-group Efficacy and Safety Study of SHP647 as Maintenance Therapy in Subjects With Moderate to Severe Ulcerative Colitis (FIGARO UC 303) | Higgins, Peter | PRMC APPROVAL | 2017-08-08 | NA | NA | 2017-08-17 | 2017-08-17 | 0 | 2017-08-18 |  |  |  | 2017-08-30 | 13
00134896 | Internal Medicine | A Phase 3 Long-term Safety Extension Study of SHP647 in Subjects with Moderate to Severe Ulcerative Colitis (AIDA) | Higgins, Peter | PRMC APPROVAL | 2017-08-08 | NA | NA | 2017-08-17 | 2017-08-17 | 0 | 2017-08-18 |  |  |  | 2017-08-30 | 13
00134997 | Urology | A phase III, multicentre, randomised, double blind, parallel group, placebo controlled study to assess the efficacy and safety of one or more intradetrusor treatments of 600 or 800 units of Dysport® for the treatment of urinary incontinence in subjects with neurogenic detrusor overactivity due to spinal cord injury or multiple sclerosis. | Stoffel, John | PRMC APPROVAL | 2017-07-10 | NA | NA | 2017-07-17 | 2017-07-19 | 2 | 2017-07-20 | NA | 2017-07-31 |  | 2017-08-01 | 13 | 2017-07-14 | 2017-08-11 | 2017-08-15 | 2017-08-07 | 2017-08-21 | 20 | 2017-08-21 | 2017-08-21 | 0 |  | 2017-08-23 | 35 | 2017-08-22
00135388 | Internal Medicine | An Antibody Guided Dietary Restriction Trial Using Biomerica InFoods® 24G Test in patients with a previous diagnosis of Irritable Bowel Syndrome (IBS) | Chey, William | PRMC APPROVAL | 2017-01-24 | NA | NA | 2017-02-01 | 2017-02-01 | 0 | 2017-02-07 | NA | NA |  | 2017-02-23 | 22 | 2017-02-10 | 2017-05-22 | 2017-02-01 | 2017-04-24 | 2017-05-17 | 83 | 2017-05-18 | 2017-07-05 | 49 | 2017-08-18 |  |  | 2017-07-20 | 2017-08-18
112-FLAHERTY | Internal Medicine | A Phase II open label study of GBT440 to evaluate the effect on hypoxemia in subjects with Idiopathic Pulmonary Fibrosis (IPF) who are using supplemental oxygen at rest (ZEPHYR) | Flaherty, Kevin | PRMC APPROVAL | 2017-04-20 | 2017-06-30 | 2017-07-06 | 2017-07-07 | 2017-07-13 | 6 | 2017-07-27 | NA | 2017-07-19 |  | 2017-08-02 | 20 |  | 2017-07-20 |  | 2017-07-28 | 2017-08-03 | 1 | 2017-08-23
179-LUGOGO | Internal Medicine | A randomized, double-blind, parallel group, multicenter, stratified study evaluating the efficacy and safety of repeat doses of GSK3772847 compared with placebo in participants with severe asthma. | HUANG, YVONNE | PRMC APPROVAL | 2017-04-28 | 2017-05-03 | NA | 2017-07-17 | 2017-07-21 | 4 | 2017-07-21 | NA | 2017-07-24 |  | 2017-08-11 | 21 | 2017-07-24 | 2017-08-11 | 2017-08-24
205-HIGGINS | Internal Medicine | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Induction Study of the Efficacy and Safety of Upadacitinib (ABT-494) in Subjects with Moderately to Severely Active Crohns Disease who have Inadequately Responded to or are Intolerant to Biologic Therapy | Higgins, Peter | PRMC APPROVAL | 2017-05-19 | 2017-06-13 | 2017-06-14 | 2017-08-21 | 2017-08-25 | 4 | 2017-08-28
235-SUGAR | Ophthalmology & Visual Sciences | A Randomized Multicenter Double-Masked Placebo-Controlled Parallel Phase I/II Study to Determine the Safety and Exploratory Efficacy of Topical Fibrinogen-Depleted Human Platelet Lysate in Subjects with Dry Eye Secondary to Graft vs. Host Disease | Sugar, Alan | PRMC APPROVAL | 2017-05-26 | NA | NA | 2017-06-09 | 2017-06-09 | 0 | 2017-06-16 | NA | NA |  | 2017-06-30 | 21 |  | 2017-06-23 | 2017-08-09
326-HIGGINS | Internal Medicine | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Induction Study of the Efficacy and Safety of Upadacitinib (ABT-494) in Subjects with Moderately to Severely Active Crohns Disease who have Inadequately Responded to or are Intolerant to Conventional Therapies but have not Failed Biologic Therapy | Higgins, Peter | PRMC APPROVAL | 2017-07-03 | NA | NA | 2017-08-21 | 2017-08-25 | 4 | 2017-08-28
327-HIGGINS | Internal Medicine | A Multicenter, Randomized, Double Blind, Placebo Controlled Maintenance and Long Term Extension Study of the Efficacy and Safety of Upadacitinib (ABT 494) in Subjects with Crohns Disease who Completed the M14-431 or M14-433 Studies | Higgins, Peter | PRMC APPROVAL | 2017-07-03 | NA | NA | 2017-08-21 | 2017-08-25 | 4 | 2017-08-28
332-BELLOLI | Internal Medicine | A RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED CLINICAL STUDY TO ASSESS THE SAFETY AND EFFICACY OF PULSED, INHALED NITRIC OXIDE (iNO) IN SUBJECTS WITH PULMONARY HYPERTENSION ASSOCIATED WITH PULMONARY FIBROSIS ON LONG TERM OXYGEN THERAPY (PART 1 AND PART 2) | Belloli, Elizabeth | PRMC APPROVAL | 2017-07-05 | 2017-07-19 | 2017-07-20 | 2017-08-28 | 2017-08-29 | 1 | 2017-08-29
337-MIAN | Ophthalmology & Visual Sciences | A Phase 3, Multi-center, Randomized, Double-Masked Study to Evaluate the Clinical Efficacy and Safety of SHP640 (PVP-Iodine 0.6% and Dexamethasone 0.1%) Ophthalmic Suspension Compared to PVP-Iodine and Placebo in the Treatment of Adenoviral Conjunctivitis | Mian, Shahzad | PRMC APPROVAL | 2017-07-06 | NA | NA | 2017-07-27 | 2017-08-01 | 5 | 2017-08-02 | NA | NA |  | 2017-08-14 | 13 | 2017-07-13 | 2017-08-09 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 14 | 2017-08-29
46-HIGGINS | Internal Medicine | A Multicenter, Randomized, Double-Blind, Placebo-Controlled 52-Week Maintenance and an Open-Label Extension Study of the Efficacy and Safety of Risankizumab in Subjects with Crohn's Disease Who Responded to Induction Treatment in M16-006 or M15-991 | Higgins, Peter | PRMC APPROVAL | 2017-03-06 | NA | NA | 2017-06-09 | 2017-06-12 | 3 | NA | NA | 2017-07-13 |  | NA |  | 2017-06-30 | 2017-07-24 | 2017-08-25 | 2017-07-23 | 2017-07-23
70-LUGOGO | Internal Medicine | A Multicenter, Randomized, Double-blind, Parallel Group, Placebo-controlled, Phase 3b Study to Evaluate the Safety and Efficacy of Benralizumab 30 mg sc in Patients with Severe Asthma Uncontrolled on Standard of Care Treatment | Lugogo, Njira | PRMC APPROVAL | 2017-03-27 | 2017-03-27 | NA | 2017-05-26 | 2017-06-05 | 10 | 2017-06-05 | NA | 2017-06-09 |  | 2017-06-13 | 8 | 2017-06-07 | 2017-06-21 | 2017-08-03 | 2017-07-06 | 2017-07-27 | 44 | 2017-07-27
00124920 | Internal Medicine | A Multicenter Open-label Extension Study to Assess the Safety and Tolerability of LYC-30937-EC in Subjects with Active Ulcerative Colitis | Stidham, Ryan | PI SIGNOFF | Lycera Corporation | NA | NA | 2017-02-07 | 2017-02-07 | 0 | 2017-02-13 | NA | NA |  | 2017-02-14 | 7 | 2017-02-10 | 2017-03-15 | 2017-02-01 | 2017-02-17 | 2017-02-21 | 7 | 2017-02-21 | 2017-02-21 | 0 | 2017-06-26 | 2017-01-23 | -15 | 2017-02-27 | 2017-06-01 | 2017-08-01 |  | 155
00129716 | Internal Medicine | A Randomized, Double-Blind, Placebo-Controlled, Phase 2 Study of Safety, Tolerability and Efficacy of Pirfenidone in Patients with Rheumatoid Arthritis Interstitial Lung Disease | Flaherty, Kevin | PI SIGNOFF | 2017-02-17 | NA | NA | 2017-03-20 | 2017-03-21 | 1 | 2017-03-22 | NA | NA |  | 2017-03-29 | 8 | 2017-03-27 | 2017-04-10 | 2017-04-13 | 2017-04-06 | 2017-04-19 | 21 | 2017-04-21 | 2017-06-01 | 43 | 2017-06-27 | 2017-06-12 | 83 | 2017-06-05 | 2017-06-26 | 2017-08-01 | 2017-07-17 | 57
00123861 | Internal Medicine | A prospective, multicenter, randomized, double-blind, Sham-controlled study to assess the efficacy and safety of the Vibrant capsule administered 5 times per week; Protocol number: 240CLD | Chey, William | OPEN TO ACCRUAL | 2017-01-17 | NA | NA | 2017-01-19 | 2017-01-19 | 0 | 2017-01-26 | NA | NA |  | 2017-02-23 | 35 | 2017-01-27 | 2017-02-23 | 2017-02-01 | 2017-03-01 | 2017-03-01 | 6 | 2017-03-02 | 2017-03-13 | 12 | 2017-04-25 |  |  | 2017-03-24 | 2017-04-25 | 2017-04-07 | 2017-05-19 | 14 | 2017-05-19 | 120
00125425 | Ophthalmology & Visual Sciences | A Multicenter, Open-Label Extension Study to Evaluate the Long-Term Safety and Tolerability of Lampalizumab in Patients with Geographic Atrophy Secondary to Age-Related Macular Degeneration Who Have Completed A Roche-Sponsored Study. | Johnson, Mark | OPEN TO ACCRUAL | 2017-02-07 | NA | NA | 2017-02-14 | 2017-02-14 | 0 | 2017-02-21 | NA | NA |  | 2017-03-08 | 22 | 2017-01-24 | 2017-03-15 | 2017-03-15 | 2017-03-23 | 2017-03-29 | 21 | 2017-03-30 | 2017-04-18 | 20 | 2017-06-13 | 2017-01-25 | -20 | 2017-05-03 | 2017-06-05 | 2017-06-13 | 2017-07-14 | 41 | 2017-07-14 | 150
00125566 | Internal Medicine | Protocol I6T-MC-AMAG A Phase 2, Multicenter, Randomized, Parallel-Arm, Placebo-Controlled Study of LY3074828 in Subjects with Active Crohns Disease (SERENITY) | Higgins, Peter | OPEN TO ACCRUAL | 2017-02-08 | NA | NA | 2017-02-23 | 2017-02-23 | 0 | NA | NA | NA |  | NA |  | 2016-12-19 | NA | 2017-03-29 | NA | 2017-02-07 |  | 2017-02-13 | 2017-02-21 | 14 | 2017-06-21 | 2017-02-10 | -13 | 2017-02-26 | 2017-06-07 | 2017-06-29 | 2017-07-03 | 123 | 2017-07-28 | 155
00125786 | Ophthalmology & Visual Sciences | Extension Study of NT-501 Ciliary Neurotrophic Factor (CNTF) Implant for Macular Telangiectasia (MacTel) | Comer, Grant | OPEN TO ACCRUAL | 2017-02-01 | NA | NA | 2017-02-03 | 2017-02-07 | 4 | NA | NA | NA |  | NA |  | 2017-01-30 | 2017-03-15 | 2017-02-01 | 2017-02-17 | 2017-02-21 |  | 2017-03-30 | 2017-04-20 | 58 | 2017-06-13 | 2017-02-13 | 6 | 2017-04-28 | 2017-06-05 | 2017-07-06 | 2017-06-13 | 69 | 2017-07-09 | 152
00125794 | Ophthalmology & Visual Sciences | A Prospective, Multicenter Clinical Trial of the Implantable Miniature Telescope in Pseudophakic Eyes with Central Vision Impairment Associated with End-Stage Macular Degeneration | Mian, Shahzad | OPEN TO ACCRUAL | 2017-02-09 | NA | NA | 2017-02-23 | 2017-02-23 | 0 | 2017-03-02 | NA | NA |  | 2017-03-27 | 32 | 2017-01-26 | 2017-04-06 | 2017-05-12 | 2017-04-11 | 2017-04-12 | 16 | 2017-04-12 | 2017-05-05 | 23 | 2017-06-26 | 2017-03-10 | 15 | 2017-05-12 | 2017-06-06 | 2017-06-27 | 2017-06-26 | 46 | 2017-06-27 | 124
00127537 | Ophthalmology & Visual Sciences | A Phase 2a Multicenter, Randomized, Masked Study Evaluating the Pharmacodynamics of Emixustat Hydrochloride in Subjects with Macular Atrophy Secondary to Stargardt Disease | Jayasundera, Kanishka | OPEN TO ACCRUAL | 2017-02-03 | NA | NA | 2017-02-23 | 2017-02-23 | 0 | 2017-03-01 | NA | NA |  | 2017-03-28 | 33 | 2017-02-23 | 2017-03-28 | 2017-02-01 | 2017-04-06 | 2017-04-14 | 17 | 2017-04-17 | 2017-05-05 | 21 | 2017-06-15 | 2017-03-14 | 19 | 2017-05-17 | 2017-06-05 | 2017-06-13 | 2016-07-07 | 27 | 2017-07-10 | 137
00129820 | Ophthalmology & Visual Sciences | RAINBOW extension study: an extension study to evaluate the long term efficacy and safety of RAnibizumab compared with laser therapy for the treatment of INfants BOrn prematurely With retinopathy of prematurity | Besirli, Cagri | OPEN TO ACCRUAL | 2017-04-12 | NA | NA | 2017-04-17 | 2017-04-17 | 0 | 2017-04-24 | NA | NA |  | 2017-05-02 | 15 | 2017-04-17 | 2017-04-25 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 0 | 2017-05-03 | 2017-05-08 | 6 | 2017-07-06 | 2017-04-19 | 2 | 2017-05-09 | 2017-06-06 | 2017-06-30 | 2017-08-08 | 52 | 2017-08-08 | 113
00129851 | Internal Medicine | A Phase 3b, Multi-Center, Randomized, Open-Label, Pragmatic Study of Glecaprevir/Pibrentasvir (G/P) +/- Ribavirin for GT1 Subjects with Chronic Hepatitis C Previously Treated with an NS5A Inhibitor + Sofosbuvir Therapy | Lok, Anna | OPEN TO ACCRUAL | 2017-02-14 | 2017-03-07 | NA | 2017-03-24 | 2017-03-27 | 3 | 2017-03-23 | NA | NA |  | 2017-04-03 | 7 | 2017-03-29 | 2017-04-18 | 2017-02-01 | 2017-04-05 | 2017-04-05 | 2 | 2017-04-11 | 2017-04-16 | 11 | 2017-06-01 |  |  | 2017-04-17 | 2017-06-01 | 2017-06-06 | 2017-06-01 | 50 | 2017-06-06 | 71
00129450 | Otolaryngology | A prospective, multicenter, randomized controlled study of sinus balloon catheter dilation versus functional endoscopic sinus surgery for treatment of chronic rhinosinusitis | Hoff, Paul | NEW | 2017-05-11 | 2017-05-12 | NA |  |  |  | 2017-05-12 | NA | NA |  | 2017-05-31 |  | NA
00131953 | Internal Medicine | Scleroderma Lung Study III (SLS III): Combining the anti-fibrotic effects of pirfenidone (PFD) with mycophenolate (MMF) for treating scleroderma-related interstitial lung disease | Nagaraja, Vivek | NEW | 2017-01-20 | 2017-03-16 | 2017-01-22 | 2017-01-22 | 2017-01-22 | 0 | 2017-01-26 | NA | NA |  | 2017-02-06 | 15 | 2017-07-11 | 2017-02-23 | 2017-06-30 | 2017-03-20 | 2017-03-20 | 42 | 2017-03-26 | 2017-04-17 | 28 | 2017-08-18 | 2017-07-06 | 165 | 2017-07-12 | 2017-08-18
00135072 | Internal Medicine | Interventional Radiology vs. ERC for Perihilar Biliary Tumors: The INTERCPT Trial A Multicenter Randomized Trial of Percutaneous Transhepatic Biliary Drainage vs. Endoscopic Retrograde Cholangiography for Decompression of Suspected Malignant Biliary Hilar Obstruction | Law, Ryan | NEW | 2017-08-17 | NA | NA
10-JAYASUNDERA | Ophthalmology & Visual Sciences | ALK001-P1002 | Jayasundera, Kanishka | NEW | 2017-02-03 | NA
12-HIGGINS | Internal Medicine | Shire CD | Higgins, Peter | NEW | 2017-02-03 | 2017-02-03 | 2017-02-07
142-FLAHERTY | Internal Medicine | Efficacy and safety of SAR156597 in the treatment of Idiopathic Pulmonary Fibrosis (IPF): A randomized, double-blind, placebo-controlled, 52-week study | Flaherty, Kevin | NEW | 2017-05-03 | 2017-05-09
188-RUBENSTEIN | Internal Medicine | Ironwood GERD | Rubenstein, Joel | NEW | 2017-05-15 | 2017-05-15 | 2017-06-01
242-AS-SANIE | Obstetrics/Gynecology | A Phase 3b Study to Evaluate the Long-Term Efficacy and Safety of Elagolix in Combination with Estradiol/Norethindrone Acetate for the Management of Heavy Menstrual Bleeding Associated with Uterine Fibroids in Premenopausal Women | As-Sanie, Sawsan | NEW | 2017-05-31 | 2017-07-18 | 2017-07-18
246-AS-SANIE | Obstetrics/Gynecology |  | As-Sanie, Sawsan | NEW | 2017-06-02
255-LOK | Internal Medicine | HPB2001/2002 | Lok, Anna | NEW | 2017-06-07 | 2017-07-11 | 2017-07-11
261-LUGOGO | Internal Medicine | A 17-Week Randomized, Open-Label Pragmatic Trial of CareTRx to Evaluate Adherence to Inhalation Treatment in Asthma Patients | Lugogo, Njira | NEW | 2017-06-08 | 2017-07-14 | 2017-07-14
263-DELMONTE | Ophthalmology & Visual Sciences | Luminopia VR Device Amblyopia Study | Delmonte, Monte | NEW | 2017-06-09 | 2017-06-13 | 2017-06-14
298-SCHIOPU | Internal Medicine | IgG4 Related Disease-Xencor | Schiopu, Elena | NEW | 2017-06-21 | 2017-07-10 | 2017-07-10
2-MARSH | Obstetrics/Gynecology | Bayer Vilaprisan | Marsh, Erica | NEW | 2017-01-30 | 2017-01-30
309-MOROI | Ophthalmology & Visual Sciences | Aqueous humor dynamics of latanoprostene bunod | Moroi, Sayoko | NEW | 2017-06-23 | NA | NA | NA | NA |  | NA | NA | NA |  | NA |  | NA | NA | NA | 2017-07-20 | 2017-07-20 |  | NA | 2017-08-03 | 14 | NA | NA |  | 2017-08-03 | NA | NA | NA |  | NA
30-FLAHERTY | Internal Medicine | CC-04 IPF Chronic Cough study | Flaherty, Kevin | NEW | 2017-02-14 | 2017-02-21 | 2017-02-22
313-CONJEEVARAM | Internal Medicine | A 52-week double-blind, randomized, placebo-controlled study to assess the efficacy and safety of the dual GLP-1/glucagon agonist SAR425899 for the treatment of non-alcoholic steatohepatitis (NASH) in non-diabetic and type 2 diabetes patients | Conjeevaram, Hari | NEW | 2017-06-26 | 2017-08-24 | 2017-08-24
346-BAPTIST | Internal Medicine | A 12-week, multicenter, randomized, double-blind, placebocontrolled study to assess the efficacy and safety of QAW039 when added to standard-of-care asthma therapy in patients with uncontrolled asthma | Baptist, Alan | NEW | 2017-07-12 | NA | NA
348-CHEY | Internal Medicine | PRA/Nestec NSTOMEG3-OMEGP3 | Chey, William | NEW | 2017-07-13
359-SMITH | Ophthalmology & Visual Sciences | A Phase 3, Randomized, Double-Masked, Placebo-Controlled, Parallel-Group, Multicenter Study Evaluating Teprotumumab (HZN-001) Treatment in Subjects with Active Thyroid Eye Disease (OPTIC Trial) | Smith, Terry | NEW | 2017-07-18 | 2017-08-02 | 2017-08-02
370-LOK | Internal Medicine | SAFETY AND EFFICACY OF BMS-986036 IN ADULTS WITH NONALCOHOLIC STEATOHEPATITIS (NASH) AND STAGE 3 (F3) BRIDGING FIBROSIS | Lok, Anna | NEW | 2017-07-25 | 2017-08-01 | 2017-08-02
371-LOK | Internal Medicine | SAFETY AND EFFICACY OF BMS-986036 IN ADULTS WITH NONALCOHOLIC STEATOHEPATITIS (NASH) AND STAGE 4 (F4C) COMPENSATED CIRRHOSIS | Lok, Anna | NEW | 2017-07-25 | 2017-08-02 | 2017-08-02
380-LOK | Internal Medicine | Janssen 64294178HPC3005 | Lok, Anna | NEW | 2017-07-31
381-HIGGINS | Internal Medicine | BMS Compound 986166 | Higgins, Peter | NEW | 2017-07-31 | 2017-08-04 | 2017-08-07
396-SCHIOPU | Internal Medicine | Genentech WA40144 RA Study | Schiopu, Elena | NEW | 2017-08-07 | 2017-08-14 | 2017-08-14
410-PAULUS | Ophthalmology & Visual Sciences | Evaluation of novel fluorescent agent MB-102 for ocular angiography | Paulus, Yannis | NEW | 2017-08-09 | NA | 2017-08-17
430-HIGGINS | Internal Medicine | Takeda EVOLVE | Higgins, Peter | NEW | 2017-08-18
432-JAYASUNDERA | Internal Medicine | ReNeuron Retinal Progenitor Cells | Jayasundera, Kanishka | NEW | 2017-08-18
435-MOROI | Ophthalmology & Visual Sciences | Aqueous Humor Dynamic Components that Determine Intraocular Pressure Variance | Moroi, Sayoko | NEW | 2017-08-21 | NA | [6 empty] | NA |  |  |  | NA | [5 empty] | NA | [5 empty] | NA
439-KHANNA | Internal Medicine | Boehringer Ingelheim 1199.225 (SENSCIS extension) | Khanna, Dinesh | NEW | 2017-08-23
440-LOK | Internal Medicine | BMS IM025-006 | Lok, Anna | NEW | 2017-08-23
447-RAO | Ophthalmology & Visual Sciences | Phase1 Clinical Study of RPESC-derived RPE Transplantation as Therapy for Non-exudative Age-related Macular Degeneration | Rao, Rajesh | NEW | 2017-08-28 | NA | NA
44-MCUNE | Internal Medicine | Baricitinib in SLE | McCune, William | NEW | 2017-02-28 | 2017-03-13 | 2017-07-13
69-KHANNA | Internal Medicine | RECIPE | Khanna, Puja | NEW | 2017-03-23 | NA |  |  |  |  | NA | NA | NA |  | NA |  | NA |  |  | NA | NA |  | 2017-03-28 | NA |  |  |  |  | 2017-02-13
77-CONJEEVARAM | Internal Medicine | Increlex in NASH | Conjeevaram, Hari | NEW | 2017-03-30 | NA | NA |  |  |  | 2017-04-18
81-HIGGINS | Internal Medicine | A Phase 3, Randomized, Double-blind, Placebo- and Active-controlled, Parallel-group, Multicenter Protocol to Evaluate the Safety and Efficacy of Guselkumab Induction and Maintenance Therapy in Subjects with Moderately to Severely Active Crohn's Disease | Higgins, Peter | NEW | 2017-04-03
91-ELSE | Internal Medicine | Adrenal insufficiency | Else, Tobias | NEW | 2017-04-11 | 2017-06-26 | NA
92-AUCHUS | Internal Medicine | Mifepristone prior to surgery | Auchus, Richard | NEW | 2017-04-11 | 2017-04-16
9-JAYASUNDERA | Ophthalmology & Visual Sciences | Treatment of the ultra-orphan disease MERTK Rod Cone Dystrophy | Jayasundera, Kanishka | NEW | 2017-02-03 | 2017-01-20 | 2017-03-27
MENEES-1 | Internal Medicine | ColonaryConepts | Menees, Stacy | NEW | 2017-01-30
SCHIOPU-1 | Internal Medicine | CT-P13 biosimilar IV/SQ | Schiopu, Elena | NEW | 2017-03-03
00126010 | Internal Medicine | A Phase III, multi-center, randomized, double-blind, 48 week study with an initial 12 week placebo-controlled period to evaluate the safety and efficacy of osilodrostat in patients with Cushings disease | Turcu, Adina | IRB INITIAL APPROVAL | 2017-05-19 | NA | NA | 2017-05-24 | 2017-06-06 | 13 | 2017-06-06 | NA | NA |  | 2017-06-07 | 1 | 2017-06-08 | 2017-06-14 | 2017-08-01 | 2017-06-08 | 2017-06-08 | 1 | 2017-06-08 | 2017-06-08 | 0 | 2017-08-22 | 2017-06-05 | -1 | 2017-06-08 | 2017-07-13
00128325 | Internal Medicine | A Mixed Methods Pilot Study of a Low-Carbohydrate Diabetes Prevention Program Among Individuals with Prediabetes | Griauzde, Dina | IRB INITIAL APPROVAL | 2017-05-22 | NA | NA | 2017-05-24 | 2017-06-08 | 15 | 2017-06-09 | NA | NA |  | 2017-06-20 | 12 | NA | 2017-06-26 | 2017-07-12 | 2017-07-06 | 2017-07-12 | 22 | NA | 2017-07-12 | 0 |  | 2017-07-07 | 29 | NA |  | NA
00128531 | Internal Medicine | Open Label, Randomized, Multicenter, Comparative Effectiveness Trial of Specific Carbohydrate and Mediterranean Diets to Induce Remission in Patients with Crohns Disease | Higgins, Peter | IRB INITIAL APPROVAL | 2017-02-03 | NA | NA | 2017-02-08 | 2017-02-09 | 1 | 2017-03-17 | NA | NA |  | 2017-04-03 | 53 | 2017-03-08 | 2017-03-28 | 2017-06-01 | 2017-04-01 | 2017-04-03 | 0 | 2017-04-04 | 2017-04-05 | 2 | 2017-08-10 | 2017-03-27 | 46 | 2017-04-11 | 2017-07-24
00128743 | Ophthalmology & Visual Sciences | A multi-center, randomized, double-masked, placebo-controlled clinical trial of suppressive valacyclovir for one year in immunocompetent study participants with an episode of dendriform epithelial keratitis, stromal keratitis, endothelial keratitis, and/or iritis due to Herpes Zoster Ophthalmicus (HZO) in the year prior to enrollment. | Mian, Shahzad | IRB INITIAL APPROVAL | 2017-03-22 | NA | NA | 2017-04-13 | 2017-04-17 | 4 | 2017-04-24 | NA | NA |  | 2017-05-01 | 14 | 2017-04-17 | 2017-04-27 | 2017-06-13 | 2017-06-16 | 2017-06-16 | 46 | 2017-06-16 | 2017-06-16 | 0 | 2017-08-10 | 2017-07-05 | 79 | 2017-06-30 | 2017-08-21
00129427 | Internal Medicine | A Longitudinal Study to Identify IBS Phenotypes Using Fecal Microbiota and Hydrogen Breath Testing | Lee, Allen | IRB INITIAL APPROVAL | 2017-04-19 | NA | NA | 2017-04-25 | 2017-04-25 | 0 | 2017-05-02 | 2017-05-10 | 2017-05-10 |  | 2017-05-15 | 20 | NA | 2017-05-01 | 2017-06-13 | 2017-05-14 | [6 empty] | 2017-05-15 | 20
00130757 | Internal Medicine | An Open-Label Extension Study of Volanesorsen Administered Subcutaneously to Patients with Familial Chylomicronemia Syndrome (FCS) | Oral, Elif | IRB INITIAL APPROVAL | 2017-04-07 | 2017-04-08 | 2017-04-28 | 2017-05-19 | 2017-05-19 | 0 | 2017-05-22 | NA | 2017-05-22 |  | 2017-05-30 | 11 | 2017-06-02 | 2017-06-02 | 2017-06-14 | 2017-06-29 | 2017-06-29 | 30 | 2017-06-29 | 2017-07-31 | 32 | 2017-08-30 | 2017-06-21 | 33 | 2017-08-01 | 2017-08-30
00131329 | Internal Medicine | A Phase 3, Multicenter, Randomized, Double-blind, Placebo-controlled Study Evaluating the Efficacy and Safety of Guselkumab Administered Subcutaneously in Subjects with Active Psoriatic Arthritis | Schiopu, Elena | IRB INITIAL APPROVAL | 2017-05-03 | NA | NA | 2017-05-26 | 2017-06-02 | 7 | 2017-06-02 | 2017-07-07 | 2017-06-05 |  | 2017-06-15 | 13 | 2017-08-07 | 2017-06-22 | 2017-07-05 | 2017-07-07 | 2017-07-24 | 39 | 2017-07-25 | 2017-08-07 | 14 |  | 2017-06-09 | 7
00124712 | Internal Medicine | A Phase IV, Randomized, Multi-Center, Open-Label, Prospective, Crossover Study to Evaluate Patient Preference of Movantik versus Polyethylene Glycol 3350 (PEG 3350) for Opioid-Induced Constipation (OIC) Treatment | Chey, William | ABANDONED | 2017-02-02 | NA | NA | 2017-02-06 | 2017-02-07 | 1 | 2017-02-07 | NA | 2017-02-07 |  | 2017-02-23 | 16 | NA | NA | NA | 2017-02-22 | NA |  | NA | NA |  | NA |  |  | NA | NA | NA | NA |  | NA
00126215 | Ophthalmology & Visual Sciences | A Phase 3, Multi-Center, Randomized, Double Masked, Placebo Controlled Clinical Study to Assess the Safety and Efficacy of 0.1% RGN-259 Ophthalmic Solution for the Treatment of Neurotrophic Keratopathy (SEER-1) | Mian, Shahzad | ABANDONED | 2017-02-09 | NA | NA | 2017-02-22 | 2017-02-22 | 0 | 2017-03-02 | NA | NA |  | 2017-03-27 | 33 | NA | NA | NA | NA | NA |  | NA | NA |  | NA |  |  | NA | NA | NA | NA |  | NA
111-HIGGINS | Internal Medicine | A Randomized, Double-Blind, Placebo-Controlled Study of the Safety and Efficacy of BMS-986165 in Participants with Moderate to Severe Crohn's Disease (CD) | Higgins, Peter | ABANDONED | 2017-04-20 | 2017-04-20 | NA | NA | NA |  | NA | NA | NA |  | NA |  | NA | NA | NA | NA | NA |  | NA | NA |  | NA |  |  | NA | NA | NA | NA |  | NA
131-LUGOGO | Internal Medicine | A Multinational, Single Arm, Observational Study to Evaluate the Real-world Effectiveness and Pattern of Use of Mepolizumab in Patients with Severe Eosinophilic Asthma (204710). | HUANG, YVONNE | ABANDONED | 2017-04-28 | 2017-05-01 | 2017-05-30 | NA | NA |  | NA | NA | NA |  | NA |  | NA | NA | NA | NA | NA |  | NA | NA |  | NA |  |  | NA | NA | NA | NA |  | NA
201-MCCUNE | Internal Medicine | A Phase 2 Randomized, Double-Blind, Placebo-Controlled Study to Evaluate Efficacy and Safety of BMS-986165 in Subjects with Systemic Lupus Erythematosus | McCune, William | ABANDONED | 2017-05-18 | 2017-06-15 | 2017-06-15 | NA | NA |  | NA | NA | NA |  | NA |  | NA | NA | NA | NA | NA |  | NA | NA |  | NA | NA |  | NA | NA | NA | NA
331-FLAHERTY | Internal Medicine | Novartis IPF | Flaherty, Kevin | ABANDONED | 2017-07-05 | 2017-08-07 | 2017-08-07 | NA | NA |  | NA | NA | NA |  | NA |  | NA | NA | NA | NA | NA |  | NA | NA |  | NA | NA |  | NA | NA | NA | NA |  | NA
347-HIGGINS | Internal Medicine | Protocol GA39925 | Higgins, Peter | ABANDONED | 2017-07-12 | 2017-07-26 | 2017-07-26 | NA | NA |  | NA | NA | NA |  | NA |  | NA | NA | NA | NA | NA |  | NA | NA |  | NA | NA |  | NA | NA | NA | NA |  | NA
397-HODISH | Internal Medicine | The SCORED Trial | Hodish, Israel | ABANDONED | 2017-08-07 | NA | 2017-08-07 | NA | NA |  | NA |  | NA |  | NA |  | NA | NA | NA | NA | NA |  | NA | NA |  | NA | NA |  | NA | NA | NA | NA |  | NA
[10 empty] | 2.6716 | [5 empty] | 17.6545 | [5 empty] | 20.5581 |  |  | 28.7059 |  |  | 32.7857 |  |  |  |  | 59.0909 |  | 127.75
Formulas:
PI approved Budget to Final Budget = DAYS([Final Budget],[PI approved Budget])
Feasibility Approved to IRB Submission = DAYS([IRB Application Submitted],[Feasibility approved/CRAO Notified])
PAF Routed to PAN released = DAYS([PAN Released],[PAF routed])
Feasibility Approval to Open to Accrual = DAYS([Open to Accrual],[Feasibility approved/CRAO Notified])